## Fix list
Contract | Line(s) | What | Baseplan says | Site / P&L says (truth) | Change | $ effect on Baseplan | Who
1000047 | 1 | Branch | Scrim 50m roll: STPS-CON | the items it serves are KINP in the P&L | Code KINP-CON |  | Baseplan
1000048 | 1 | Branch | Scrim 50m roll: STPS-CON | the items it serves are KINP in the P&L | Code KINP-CON |  | Baseplan
1000048 | 2 | Branch | Scrim 50m Roll: STPS-CON | the items it serves are KINP in the P&L | Code KINP-CON |  | Baseplan
1000048 | 3 | Branch | Transport Charge for 10x rolls: STPS-FRI | the items it serves are KINP in the P&L | Code KINP-FRI |  | Baseplan
9961265 | 13 | Branch | VMS10 120T Variable Message Board Senior Premiair: KINP-SUB | the P&L carries every VMS board on STPS, the Premiair rehire boards with them | Code STPS-SUB and book the Premiair cost to STPS (or keep the sub-hire branch and the P&L moves instead) |  | Decision
9961265 | 15 | Branch | VMS11 467T Variable Message Board - Premiair: KINP-SUB | the P&L carries every VMS board on STPS, the Premiair rehire boards with them | Code STPS-SUB and book the Premiair cost to STPS (or keep the sub-hire branch and the P&L moves instead) |  | Decision
9961265 | 24 | Branch | VMS18 472T Variable Message Board Senior Premiair: KINP-SUB | the P&L carries every VMS board on STPS, the Premiair rehire boards with them | Code STPS-SUB and book the Premiair cost to STPS (or keep the sub-hire branch and the P&L moves instead) |  | Decision
9961265 | 25 | Branch | VMS19 487T Variable Message Board Senior Premiair: KINP-SUB | the P&L carries every VMS board on STPS, the Premiair rehire boards with them | Code STPS-SUB and book the Premiair cost to STPS (or keep the sub-hire branch and the P&L moves instead) |  | Decision
9961265 | 26 | Branch | VMS20 475T Variable Message Board Senior Premiair: KINP-SUB | the P&L carries every VMS board on STPS, the Premiair rehire boards with them | Code STPS-SUB and book the Premiair cost to STPS (or keep the sub-hire branch and the P&L moves instead) |  | Decision
9961265 | 28 | Branch | VMS21 Variable Message Board Senior Premiair: KINP-SUB | the P&L carries every VMS board on STPS, the Premiair rehire boards with them | Code STPS-SUB and book the Premiair cost to STPS (or keep the sub-hire branch and the P&L moves instead) |  | Decision
9961265 | 29 | Branch | VMS22 445T Variable Message Board Senior Premiair: KINP-SUB | the P&L carries every VMS board on STPS, the Premiair rehire boards with them | Code STPS-SUB and book the Premiair cost to STPS (or keep the sub-hire branch and the P&L moves instead) |  | Decision
9961265 | 30 | Branch | VMS23 453T Variable Message Board Senior Premiair: KINP-SUB | the P&L carries every VMS board on STPS, the Premiair rehire boards with them | Code STPS-SUB and book the Premiair cost to STPS (or keep the sub-hire branch and the P&L moves instead) |  | Decision
9961265 | 31 | Branch | VMS24 450T Variable Message Board Senior: NVAC-SUB | the P&L carries every VMS board on STPS, the Premiair rehire boards with them | Code STPS-SUB and book the Premiair cost to STPS (or keep the sub-hire branch and the P&L moves instead) |  | Decision
9974042 | 2 | Branch | Container - Refrigerated 6.0M x 2.4M: STPS-SUB | T0266 is on KINP in the P&L (the sheet notes the sub-hire account on the coded branch) | Code KINP-SUB and book the supplier cost there too (or keep the code and the P&L moves) |  | Decision
9994954 | 10 | Branch | GN26 Generator - 200kVA (Diesel): KINP-HIR | GN? is on NVAC in the P&L | Code NVAC-HIR |  | Baseplan
9994954 | 11 | Branch | GN27 Generator - 200kVA (Diesel): KINP-HIR | GN? is on NVAC in the P&L | Code NVAC-HIR |  | Baseplan
9994954 | 12 | Branch | Cable - 120mm2 Single Double Insulated: KINP-HIR | the cable goes with GN26/27, on NVAC in the P&L | Code NVAC-HIR |  | Baseplan
9994954 | 13 | Branch | Labour Charge Sync Generators: KINP-INS | generator work is NVAC in the P&L | Code NVAC-INS |  | Baseplan
9994954 | 14 | Branch | Transport Charge Generators: KINP-FRI | generator work is NVAC in the P&L | Code NVAC-FRI |  | Baseplan
9994954 | 25 | Branch | Labour Charge Event Gen Tech: KINP-INS | Gen Tech — entertainment is NVAC in the P&L (the responsible branch for the role) | Code NVAC-INS |  | Baseplan
9997710 | 2 | Branch | Shade Cloth: STPS-CON | the items it serves are KINP in the P&L | Code KINP-CON |  | Baseplan
our record | T0085 | Branch | T0085 is tagged NVAC on our record | its contract line 9987005/1 and the P&L hire for it are MEAD | Put T0085 on MEAD (Costs labour ticks follow the reference) |  | Our record
our record | T0109 | Branch | T0109 is tagged NVAC on our record | its contract line 9987005/7 and the P&L hire for it are MEAD | Put T0109 on MEAD (Costs labour ticks follow the reference) |  | Our record
- | - | Missing line | no line for Fence team | Fence team: 213 h x $91.14 = $19,412.82 (C004 scope, 3.15 Security & Demarcation Fencing) | Add the event labour line on STPS-INS | 19412.82 | Baseplan
9968955 | new | Missing line | no water on any contract | the P&L charges water at what Event Portables charge us: Water Truck $6,800.00; Water Truck - Pre fill $2,800.00; Water delivery $2,250.00; 3000 Ltr Free Drinking Water Tank $2,100.00 | Add the water lines ($13,950.00) on KINP | 13950 | Baseplan
9973977 | new | Missing line | no cleaning line for the WCTV block (T0243) | the P&L charges its sewer-connect clean every race night: 3 x $260.25 | Add Cleaning & Restock Sewer Connect 3 x $260.25 on KINP-CLE | 780.75 | Baseplan
9990776 | new | Missing line | no line for fence blocks | 216 on the signed dockets at $3.02 | Add 216 at $3.02 | 652.32 | Baseplan
9990776 | new | Missing line | no line for fencing labour (h) | 8.5 on the signed dockets at $142.00 | Add 8.5 at $142.00 | 1207 | Baseplan
9961265 | 44 | Hours | Event Labour Charge: 65 h | the scope has 65.3333 h (VMS board movements) | Quantity 65.3333 h | 30.38 | Baseplan
9961976 | 56 | Hours | Labour Charge Event Gen Tech: 31.55 h | the scope has 27.25 h (Gen Tech) | Quantity 27.25 h | -645.47 | Baseplan
9968862 | 141 | Hours | Labour Charge Project Manager Event: 15.22 h | keyed as hours:minutes (15 h 22 min); the scope has 15.375 h | Quantity 15.375 h | 23.27 | Baseplan
9968955 | 164 | Hours | Labour Charge Project Manager 50%: 15.22 h | keyed as hours:minutes (15 h 22 min); the scope has 15.375 h | Quantity 15.375 h | 23.27 | Baseplan
9968955 | 165 | Hours | Labour Charge Event Toilet: 27.15 h | keyed as hours:minutes (27 h 15 min); the scope has 27.25 h | Quantity 27.25 h | 9.11 | Baseplan
9961976 | 1 | Rate | LT01 MOLENDINAR Lighting Tower LED Metro: $643.30 | a light tower is charged for the three event days at the card ($64.33 a day = $192.99), never its days on site (branch rule) | Rate $192.99 | -450.31 | Baseplan
9961976 | 2 | Rate | LT02 MOLENDINAR Lighting Tower LED Metro: $643.30 | a light tower is charged for the three event days at the card ($64.33 a day = $192.99), never its days on site (branch rule) | Rate $192.99 | -450.31 | Baseplan
9961976 | 3 | Rate | LT03 MOLENDINAR Lighting Tower LED 76500: $643.30 | a light tower is charged for the three event days at the card ($64.33 a day = $192.99), never its days on site (branch rule) | Rate $192.99 | -450.31 | Baseplan
9961976 | 4 | Rate | LT04 MOLENDINAR Lighting Tower LED Metro: $643.30 | a light tower is charged for the three event days at the card ($64.33 a day = $192.99), never its days on site (branch rule) | Rate $192.99 | -450.31 | Baseplan
9961976 | 5 | Rate | LT09 Lighting Tower LED 76500lm Hybrid: $643.30 | a light tower is charged for the three event days at the card ($64.33 a day = $192.99), never its days on site (branch rule) | Rate $192.99 | -450.31 | Baseplan
9961976 | 6 | Rate | GN20-S01-Generator 365kVA Diesel: $6,260.40 | the P&L charges $6,840.83 (Street Rate Card 2026 · Generator 315 kVA · next size down from 350 kVA · published Standby Rate before 23 Oct, from the day it turned up Wed 30 Sep) | Rate $6,840.83 | 580.43 | Baseplan
9961976 | 7 | Rate | GN19-Generator - Diesel - 80kVA DEL AS 6: $1,254.50 | the P&L charges $965.01 (Street Rate Card 2026 · Generator 60 kVA · published Standby Rate before 23 Oct, from the day it turned up Mon 19 Oct) | Rate $965.01 | -289.49 | Baseplan
9961976 | 9 | Rate | GN23-Generator - Sync - Hardwire Only 15: $2,412.54 | the P&L charges $3,886.83 (Street Rate Card 2026 · Generator 150 kVA · published Standby Rate before 23 Oct, from the day it turned up Wed 30 Sep) | Rate $3,886.83 | 1474.29 | Baseplan
9961976 | 10 | Rate | GN03-Generator - 30kVA (Diesel): $1,132.28 | the P&L charges $1,981.47 (Street Rate Card 2026 · Generator 30 kVA · published Standby Rate before 23 Oct, from the day it turned up Thu 01 Oct) | Rate $1,981.47 | 849.19 | Baseplan
9961976 | 11 | Rate | GN18-Generator - 60kVA (Diesel): $2,187.36 | the P&L charges $2,005.07 (Street Rate Card 2026 · Generator 50 kVA · published Standby Rate before 23 Oct, from the day it turned up Wed 07 Oct) | Rate $2,005.07 | -182.29 | Baseplan
9961976 | 14 | Rate | GN04-Generator - 30kVA (Diesel): $919.97 | the P&L charges $707.67 (Street Rate Card 2026 · Generator 30 kVA · published Standby Rate before 23 Oct, from the day it turned up -) | Rate $707.67 | -212.3 | Baseplan
9961976 | 15 | Rate | G10- Generator - 60kVA (Diesel): $1,142.96 | the P&L charges $611.16 (Street Rate Card 2026 · Generator 20 kVA · published Standby Rate before 23 Oct, from the day it turned up -) | Rate $611.16 | -531.8 | Baseplan
9961976 | 16 | Rate | GN01-Generator - 60kVA (Diesel): $1,544.00 | the P&L charges $2,991.52 (Street Rate Card 2026 · Generator 60 kVA · published Standby Rate before 23 Oct, from the day it turned up Mon 28 Sep) | Rate $2,991.52 | 1447.52 | Baseplan
9961976 | 18 | Rate | GN25-Generator - 20kVA (Diesel): $855.63 | the P&L charges $611.16 (Street Rate Card 2026 · Generator 20 kVA · published Standby Rate before 23 Oct, from the day it turned up Mon 19 Oct) | Rate $611.16 | -244.47 | Baseplan
9961976 | 19 | Rate | LT05/06-Lighting Tower POD Metro: $385.98 | a light tower is charged for the three event days at the card ($64.33 a day = $192.99), never its days on site (branch rule) | Rate $192.99 | -192.99 | Baseplan
9961976 | 20 | Rate | LT05/06-Lighting Tower POD Metro: $385.98 | a light tower is charged for the three event days at the card ($64.33 a day = $192.99), never its days on site (branch rule) | Rate $192.99 | -192.99 | Baseplan
9961976 | 21, 25, 26, 27, 31, 34, 35 | Rate | Coates forklifts at $0 (COATES Forklift 3.0t Contain, COATES Forklift Rough Terrai, COATES Forklift Rough Terrai, ...) | the P&L charges them from the card: $28,671.82 of NVAC revenue | Andrew to say: Coates own (no charge, the P&L comes down) or charged to the V8s (rates on the lines) | 28671.82 | Decision
9961976 | 38 | Rate | GN21-Generator - 60kVA (Diesel): $868.50 | the P&L charges $2,798.52 (Street Rate Card 2026 · Generator 60 kVA · published Standby Rate before 23 Oct, from the day it turned up Wed 30 Sep) | Rate $2,798.52 | 1930.02 | Baseplan
9961976 | 44 | Rate | GN13 Generator - 60kVA (Diesel) DEL AS 4: $1,406.72 | the P&L charges $1,494.68 (Street Rate Card 2026 · Generator 45 kVA · published Standby Rate before 23 Oct, from the day it turned up -) | Rate $1,494.68 | 87.96 | Baseplan
9961976 | 48 | Rate | GN06 Generator - 60kVA (Diesel): $1,168.72 | the P&L charges $1,275.95 (Street Rate Card 2026 · Generator 50 kVA · published Standby Rate before 23 Oct, from the day it turned up -) | Rate $1,275.95 | 107.23 | Baseplan
9961976 | 49 | Rate | GN24-Generator - 60kVA (Diesel) - Traile: $984.33 | the P&L charges $965.01 (Street Rate Card 2026 · Generator 60 kVA · published Standby Rate before 23 Oct, from the day it turned up -) | Rate $965.01 | -19.32 | Baseplan
9990776 | 8 | Rate | Barrier - Crowd Control Flat Feet: $7.51 | the card rate the P&L charges is $9.65 | Rate $9.65 | 578.1 | Baseplan
9994954 | 10 | Rate | GN26 Generator - 200kVA (Diesel): $2,005.08 | the P&L charges $3,098.74 (Street Rate Card 2026 · Generator 200 kVA · published Standby Rate before 23 Oct, from the day it turned up Mon 12 Oct) | Rate $3,098.74 | 1093.66 | Baseplan
9994954 | 11 | Rate | GN27 Generator - 200kVA (Diesel): $2,551.92 | the P&L charges $3,098.74 (Street Rate Card 2026 · Generator 200 kVA · published Standby Rate before 23 Oct, from the day it turned up Mon 12 Oct) | Rate $3,098.74 | 546.82 | Baseplan
9968862 / 9968955 | 140 / 163 | Amount | ACCOM / MEALS 50% x 2 = $27,700.00 | the C004 scope (row 68) charges $19,101.60 for accommodation and travel, half each on buildings and toilets | Andrew to say which figure stands | -8598.4 | Decision
9961976 | 52 | Quantity | Labour Charge Generator: 1 x $333.12 | 2 on site (GN20-A, GN23) | Quantity 2 | 333.12 | Baseplan
9961976 | 53 | Quantity | Transport Charge: 6 x $309.00 | 10 on site (GN03, GN04, GN10, GN25 x 2 legs) | Quantity 10 | 1236 | Baseplan
9961976 | 54 | Quantity | Transport Charge: 16 x $463.50 | 14 on site (GN01, GN06, GN13, GN18, GN19, GN21, GN24 x 2 legs) | Quantity 14 | -927 | Baseplan
9961976 | 55 | Quantity | Transport Charge: 2 x $600.00 | 4 on site (GN20-A, GN23 x 2 legs) | Quantity 4 | 1200 | Baseplan
9968955 | 84, 140 | Quantity | WC67 FWF: 3 on hire | WC67 has 4 FWF on site (arrived Thu 01 Oct) | Add 1 FWF (hire line) |  | Baseplan
9972648/9990776 | - | Quantity | WB07: 0 barriers | WB07: 17 on site | Match the quantity to the site count (barriers are charged from when they go in) |  | Baseplan
9972648/9990776 | 4 | Quantity | WB05: 12 barriers | WB05: 13 on site | Match the quantity to the site count (barriers are charged from when they go in) |  | Baseplan
9972648/9990776 | 5 | Quantity | WB04: 13 barriers | WB04: 14 on site | Match the quantity to the site count (barriers are charged from when they go in) |  | Baseplan
9990776 | 2 | Quantity | Ped Gates: 32 | 22 on the signed dockets (to 25 Oct) | Quantity 22 | -361.8 | Baseplan
9990776 | 3, 5 | Quantity | 1.8 m security fence 8778 m + with hoarding 110 m | 9325 m of fence with no scrim on the signed dockets (their 13302.5 m of clean less the 3977.5 m under the scrim, charged once) | Quantity 9215 m on line 3 (keep the 110 m with hoarding on line 5 if it is in the dockets' clean metres) | 7061.92 | Baseplan
9990776 | 4 | Quantity | Fence Relocation: 1520 | 137.5 on the signed dockets (to 25 Oct); demob relocation still to come | Quantity 137.5 to date | -11958.62 | Baseplan
9990776 | 6 | Quantity | 1.8m Fence w/Scrim: 2775 | 3977.5 m of fence with scrim on the signed dockets (to 25 Oct) | Quantity 3977.5 | 19432.4 | Baseplan
9990776 | 7 | Quantity | Barrier - Crowd Control: 2350 | 2195 on the signed dockets (to 25 Oct) | Quantity 2195 | -1164.05 | Baseplan
9990776 | 8 | Quantity | Barrier - Crowd Control Flat Feet: 220 | 270 on the signed dockets (to 25 Oct) | Quantity 270 | 375.5 | Baseplan
9990776 | 9 | Quantity | Demarcation CCB: 4603 | 5062.5 on the signed dockets (to 25 Oct) | Quantity 5062.5 | 6010.26 | Baseplan
9990776 | 10 | Quantity | Shade Cloth: 2775 | 3977.5 m of fence with scrim on the signed dockets (to 25 Oct) | Quantity 3977.5 | 11267.43 | Baseplan
our P&L | servicing | Quantity | the P&L charges WC31's two 16-pan blocks as sewer-connect cleans (2 x 3 x $260.25 = $1,561.50) | they are pumped out every night (servicing tracker), as Baseplan line 142 charges them (2 x 3 x $624.60 = $3,747.60) | Count the 16-pans with the tank pump-outs on Costs (P&L +$2,186.10) |  | Our record
9968955 | 154 | Remove | PG29 Toilet FWF at $90.07 | PG29 is on its own hire schedule (held out of every charge, Andrew 23 Oct) | Take the line off this contract | -90.07 | Baseplan
1000052 | 1 | Not on site | P68 Hydration Station (MISCITEMS) Delivered | no unit on the record carries this number or label | Say what it is, or close the line |  | Ask Andrew
9961976 | 48 | Not on site | GN06 Generator - 60kVA (Diesel) Off Rent | GN06 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 105 | Not on site | P25 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated Off Rent | P25 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 107 | Not on site | P25 Refrigerator - Large Off Rent | P25 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 108 | Not on site | P67 Commentary Booth 6.0M x 3.0M Off Rent | P67 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 110 | Not on site | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated Off Rent | P65 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 112 | Not on site | P65 Refrigerator - Large Off Rent | P65 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 113 | Not on site | P66 Portable Building Shell 6.0M x 3.0M Off Rent | P66 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 115 | Not on site | P66 Refrigerator - Large Off Rent | P66 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 116 | Not on site | P60 Ticket Office 4.8Mx2.4M Off Rent | P60 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 118 | Not on site | P62 Commentary Booth 6.0M x 3.0M Off Rent | P62 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 120 | Not on site | P62 Refrigerator - Large Off Rent | P62 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968862 | 121 | Not on site | P63 Portable Building Shell 6.0M x 3.0M Off Rent | P63 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 85 | Not on site | WC70 Toilet Portable - Fresh Water Flush Delivered | WC70 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 100 | Not on site | WC34 Toilet Portable - Fresh Water Flush Delivered | WC34 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 101 | Not on site | WC33 Toilet Portable - Fresh Water Flush Delivered | WC33 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 106 | Not on site | WC59 FWF Toilet Delivered | WC59 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 107 | Not on site | WC57 FWF Toilet Delivered | WC57 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 108 | Not on site | WC49 FWF Toilet Delivered | WC49 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 109 | Not on site | WC48 FWF Toilet Delivered | WC48 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 112 | Not on site | WC54 FWF Toilet Delivered | WC54 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 113 | Not on site | WC56 FWF Toilet Delivered | WC56 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 115 | Not on site | WC45 Toilet Portable - Fresh Water Flush Delivered | WC45 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 116 | Not on site | WC47 Toilet Portable - Fresh Water Flush Delivered | WC47 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 118 | Not on site | WC25 Toilet Portable - Fresh Water Flush Delivered | WC25 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 119 | Not on site | WC23 Toilet Portable - Fresh Water Flush Delivered | WC23 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 120 | Not on site | WC26 Toilet Portable - Fresh Water Flush Delivered | WC26 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 121 | Not on site | WC24 Toilet Portable - Fresh Water Flush Delivered | WC24 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 122 | Not on site | WC13 Toilet Portable - Fresh Water Flush Delivered | WC13 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 123 | Not on site | WC28 Toilet Portable - Fresh Water Flush Delivered | WC28 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 124 | Not on site | WC29 Toilet Portable - Fresh Water Flush Delivered | WC29 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 125 | Not on site | WC30 Toilet Portable - Fresh Water Flush Delivered | WC30 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 126 | Not on site | WC35 Toilet Portable - Fresh Water Flush Delivered | WC35 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 127 | Not on site | WC46 Toilet Portable - Fresh Water Flush Delivered | WC46 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 128 | Not on site | WC55 Toilet Portable - Fresh Water Flush Delivered | WC55 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 129 | Not on site | WC62 Toilet Portable - Fresh Water Flush Delivered | WC62 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 130 | Not on site | WC65 Toilet Portable - Fresh Water Flush Delivered | WC65 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 153 | Not on site | PG05 FWF Toilet Delivered | PG05 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 154 | Not on site | PG29 Toilet FWF Delivered | PG29 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9968955 | 156 | Not on site | WC53 FWF Toilet Delivered | WC53 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9992300 | 5 | Not on site | Knuckle Boom 61ft (18.6M) - Diesel Off Rent | EQ0002 is not on site on the record | Check: delivered or not? |  | Ask Andrew
9961265 | 34 | Start date | VMS14 Variable Message Board Junior: start Mon 19 Oct | on site Fri 16 Oct (recorded on site (load T0158)) | Start Fri 16 Oct (VMS is charged from when it goes in) | -160.83 | Baseplan
9961265 | 35 | Start date | VMS15 Variable Message Board Senior: start Mon 19 Oct | on site Fri 16 Oct (recorded on site (load T0158)) | Start Fri 16 Oct (VMS is charged from when it goes in) | -160.83 | Baseplan
9961265 | 37 | Start date | VMS16 Variable Message Board Senior: start Mon 19 Oct | on site Fri 16 Oct (recorded on site (load T0158)) | Start Fri 16 Oct (VMS is charged from when it goes in) | -160.83 | Baseplan
9961265 | 39 | Start date | VMS17 Variable Message Board Senior: start Mon 19 Oct | on site Fri 16 Oct (recorded on site (load T0158)) | Start Fri 16 Oct (VMS is charged from when it goes in) | -160.83 | Baseplan
9972648 | 2 | Start date | WB03 Barrier - Crash Rated Water filled - Armorzon: start Fri 18 Sep | WB03 first on site Wed 23 Sep | Start Wed 23 Sep (charged from when it goes in) |  | Baseplan
9987005 | 1 | Start date | Supply Forklift 5.0t Diesel: start Mon 05 Oct | T0085 first on site Mon 28 Sep (machines changed on some plant references: confirm this unit's day) | Start Mon 28 Sep (charged from when it goes in) |  | Ask Andrew
9987005 | 2 | Start date | Supply Telehandler Fork Extension 1800mm: start Mon 05 Oct | EQ0005 first on site Fri 23 Oct (machines changed on some plant references: confirm this unit's day) | Start Fri 23 Oct (charged from when it goes in) |  | Ask Andrew
9987005 | 7 | Start date | Forklift Rough Terrain 2.5t 4WD Diesel: start Tue 13 Oct | T0109 first on site Mon 28 Sep (machines changed on some plant references: confirm this unit's day) | Start Mon 28 Sep (charged from when it goes in) |  | Ask Andrew
9992300 | 4 | Start date | Scissor Lift With Operator Protection 43ft (13.0M): start Mon 19 Oct | EQ0001 first on site Thu 22 Oct (machines changed on some plant references: confirm this unit's day) | Start Thu 22 Oct (charged from when it goes in) |  | Ask Andrew

## Every line
Contract | Line | Status | Item | Description | Qty | Rate 1 | Price | Sales code | P&L branch | Start | Term | Reference on site | Turned up | Checks
9987005 | 1 | Delivered | 1272166 | Supply Forklift 5.0t Diesel | 1 | 150 | 0 | MEAD-HIR | MEAD | 2026-10-05 |  | T0085 | 2026-09-28 | starts Mon 05 Oct, turned up Mon 28 Sep (+7 days)
9987005 | 2 | Delivered | 1262224 | Supply Telehandler Fork Extension 1800mm | 1 | 20 | 0 | MEAD-HIR | MEAD | 2026-10-05 |  | EQ0005 | 2026-10-23 | starts Mon 05 Oct, turned up Fri 23 Oct (-18 days)
9987005 | 3 | Pending | TRANSPORT | Transport Charge | 4 |  | 500 | MEAD-FRI | MEAD | 2026-10-05
9987005 | 7 | Delivered | 1281615 | Forklift Rough Terrain 2.5t 4WD Diesel | 1 | 185.4 | 0 | MEAD-HIR | MEAD | 2026-10-13 |  | T0109 | 2026-09-28 | starts Tue 13 Oct, turned up Mon 28 Sep (+15 days)
9987005 | 8 | Delivered | 1065384 | Laserplane | 1 | 0 | 0 | MEAD-HIR | MEAD | 2026-10-16 |  | EQ0006 | 2026-10-25 | starts Fri 16 Oct, turned up Sun 25 Oct (-9 days)
9973977 | 1 | Delivered | 1311144 | WCTV Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 2476.85 | 0 | KINP-HIR | KINP | 2026-09-14 |  | T0243
9973977 | 2 | Delivered | LABOUR | Install & Demob | 1 |  | 707.88 | KINP-INS | KINP | 2026-10-19
9973977 | 3 | Delivered | TRANSPORT | Transport Charge | 2 |  | 500 | KINP-FRI | KINP | 2026-10-19
9968955 | 1 | Delivered | 1097377 | WC05 Toilet Block 6.0M x 3.0M | 1 | 3227.41 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC05 | 2026-09-14
9968955 | 3 | Delivered | 1328978 | WC05 Sewage Holding Tank 6.0M x 2.4M | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC05 | 2026-09-14
9968955 | 4 | Delivered | 1211961 | WC12 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC12 | 2026-09-14
9968955 | 5 | Delivered | 1200601 | WC12 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC12 | 2026-09-14
9968955 | 6 | Delivered | 1211969 | WC11 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC11 | 2026-09-14
9968955 | 7 | Delivered | 1211977 | WC21 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC21 | 2026-09-14
9968955 | 8 | Delivered | 1211964 | WC21 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC21 | 2026-09-14
9968955 | 10 | Delivered | 1322587 | WC16 Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 2476.85 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC16 | 2026-09-14
9968955 | 11 | Delivered | 1322588 | WC16 Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 2476.85 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC16 | 2026-09-14
9968955 | 12 | Delivered | 1288823 | WC100 Toilet Portable - With Trailer | 1 | 237.71 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC100 | 2026-09-14
9968955 | 13 | Delivered | 1248439 | WC100 Toilet Portable - With Trailer | 1 | 237.71 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC100 | 2026-09-14
9968955 | 14 | Delivered | 1002747 | WC21 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC21 | 2026-09-14
9968955 | 15 | Delivered | 1195658 | WC06 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC06 | 2026-09-23 | starts Mon 14 Sep, turned up Wed 23 Sep (-9 days)
9968955 | 16 | Delivered | 1211971 | WC21 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC21 | 2026-09-14
9968955 | 17 | Delivered | 1002565 | WC12 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC12 | 2026-09-14
9968955 | 18 | Delivered | 1212172 | WC21 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC21 | 2026-09-14
9968955 | 19 | Delivered | 1103497 | WC21 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC21 | 2026-09-14
9968955 | 20 | Delivered | 1327224 | WC17 Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 2476.85 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC17 | 2026-09-15 | starts Mon 14 Sep, turned up Tue 15 Sep (-1 days)
9968955 | 21 | Delivered | 1327223 | WC17 Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 2476.85 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC17 | 2026-09-15 | starts Mon 14 Sep, turned up Tue 15 Sep (-1 days)
9968955 | 22 | Delivered | 1211974 | WC50 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC50 | 2026-09-23 | starts Mon 14 Sep, turned up Wed 23 Sep (-9 days)
9968955 | 23 | Delivered | 1211976 | WC11 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC11 | 2026-09-14
9968955 | 24 | Delivered | 1002566 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 25 | Delivered | 1317640 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 26 | Delivered | 1211959 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 27 | Delivered | 1317649 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 28 | Delivered | 1317647 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 29 | Delivered | 1317626 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 30 | Delivered | 1317652 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 31 | Delivered | 1317648 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 32 | Delivered | 1212552 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 33 | Delivered | 1200595 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 34 | Delivered | 1181004 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 35 | Delivered | 1002538 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 36 | Delivered | 1317658 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 37 | Delivered | 1317632 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 38 | Delivered | 1317643 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 39 | Delivered | 1317641 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 40 | Delivered | 1002715 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 41 | Delivered | 1083300 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 42 | Delivered | 1192643 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 43 | Delivered | 1002651 | WC07 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC07 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 44 | Delivered | 1212502 | WC04 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC04 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 45 | Delivered | 1058086 | WC02 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC02 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968955 | 46 | Delivered | 1211958 | WC01 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC01 | 2026-09-28 | starts Mon 14 Sep, turned up Mon 28 Sep (-14 days)
9968955 | 47 | Delivered | 1327228 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 3227.41 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC20 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968955 | 48 | Delivered | 1327225 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 3227.41 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC20 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968955 | 49 | Delivered | 1311341 | WC20 Sewage Holding Tank 6.0M x 2.4M | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC20 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968955 | 50 | Delivered | 1328982 | WC20 Sewage Holding Tank 6.0M x 2.4M | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC20 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968955 | 51 | Delivered | 1296899 | Wc86 Toilet - Disabled Access | 1 | 337.75 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC86 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968955 | 52 | Delivered | 1119484 | WC27 Toilet Block 6.0M x 3.0M | 1 | 3227.41 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC27 | 2026-09-25 | starts Mon 14 Sep, turned up Fri 25 Sep (-11 days)
9968955 | 54 | Delivered | 1328979 | WC27 Sewage Holding Tank 6.0M x 2.4M | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC27 | 2026-09-25 | starts Mon 14 Sep, turned up Fri 25 Sep (-11 days)
9968955 | 55 | Delivered | 1327226 | WC15 Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 2476.85 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC15 | 2026-09-25 | starts Mon 14 Sep, turned up Fri 25 Sep (-11 days)
9968955 | 56 | Delivered | 1303835 | WC15 Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 2476.85 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC15 | 2026-09-25 | starts Mon 14 Sep, turned up Fri 25 Sep (-11 days)
9968955 | 57 | Delivered | 1317644 | WC01 Toilet - Accessible | 1 | 337.75 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC01 | 2026-09-28 | starts Mon 14 Sep, turned up Mon 28 Sep (-14 days)
9968955 | 58 | Delivered | 1212523 | WC06 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC06 | 2026-09-23 | starts Mon 14 Sep, turned up Wed 23 Sep (-9 days)
9968955 | 59 | Delivered | miscitems | WC41 Toilet Portable - Fresh Water Flush | 10 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC41 | 2026-09-28 | starts Mon 14 Sep, turned up Mon 28 Sep (-14 days)
9968955 | 69 | Delivered | 1211967 | WC01 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC01 | 2026-09-28 | starts Mon 14 Sep, turned up Mon 28 Sep (-14 days)
9968955 | 70 | Delivered | miscitem | WC43 Toilet Portable - Fresh Water Flush | 10 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC43 | 2026-09-28 | starts Mon 14 Sep, turned up Mon 28 Sep (-14 days)
9968955 | 80 | Delivered | miscitem | WC44 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC44 | 2026-10-01 | starts Mon 14 Sep, turned up Thu 01 Oct (-17 days)
9968955 | 81 | Delivered | miscitem | WC44 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC44 | 2026-10-01 | starts Mon 14 Sep, turned up Thu 01 Oct (-17 days)
9968955 | 84 | Delivered | miscitems | WC67 Toilet Portable - Fresh Water Flush | 2 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC67 | 2026-10-01 | starts Mon 14 Sep, turned up Thu 01 Oct (-17 days)
9968955 | 85 | Delivered | miscitems | WC70 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC70 |  | not on site on the record
9968955 | 86 | Delivered | miscitems | WC71 Toilet Portable - Fresh Water Flush | 8 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC71 | 2026-10-01 | starts Mon 14 Sep, turned up Thu 01 Oct (-17 days)
9968955 | 87 | Delivered | miscitems | WC69 Toilet Portable - Fresh Water Flush | 12 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC69 | 2026-10-12 | starts Mon 14 Sep, turned up Mon 12 Oct (-28 days)
9968955 | 88 | Delivered | MISCITEM | WC38 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC38 | 2026-10-13 | starts Mon 14 Sep, turned up Tue 13 Oct (-29 days)
9968955 | 89 | Delivered | MISCITEM | WC39 Toilet Portable - Fresh Water Flush | 2 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC39 | 2026-10-13 | starts Mon 14 Sep, turned up Tue 13 Oct (-29 days)
9968955 | 90 | Delivered | MISCITEM | WC40 Toilet Portable - Fresh Water Flush | 5 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC40 | 2026-10-13 | starts Mon 14 Sep, turned up Tue 13 Oct (-29 days)
9968955 | 91 | Delivered | 1087500 | WC60 Toilet Block 6.0M x 3.0M | 1 | 3227.41 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC60 | 2026-10-01 | starts Mon 14 Sep, turned up Thu 01 Oct (-17 days)
9968955 | 93 | Delivered | 1119489 | WC60 Toilet Block 6.0M x 3.0M | 1 | 3227.41 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC60 | 2026-10-01 | starts Mon 14 Sep, turned up Thu 01 Oct (-17 days)
9968955 | 94 | Delivered | 1328980 | WC60 Sewage Holding Tank 6.0M x 2.4M | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC60 | 2026-10-01 | starts Mon 14 Sep, turned up Thu 01 Oct (-17 days)
9968955 | 95 | Delivered | 1328981 | WC60 Sewage Holding Tank 6.0M x 2.4M | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC60 | 2026-10-01 | starts Mon 14 Sep, turned up Thu 01 Oct (-17 days)
9968955 | 96 | Delivered | MISCITEM | WC61 Toilet Portable - Fresh Water Flush | 8 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC61 | 2026-10-12 | starts Mon 14 Sep, turned up Mon 12 Oct (-28 days)
9968955 | 97 | Delivered | 1317645 | WC31 Toilet - Accessible | 1 | 337.75 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC31 | 2026-09-25 | starts Mon 14 Sep, turned up Fri 25 Sep (-11 days)
9968955 | 98 | Delivered | MISCITEM | WC31 16 Pan Block | 2 | 2852.13 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC31 | 2026-09-25 | starts Mon 14 Sep, turned up Fri 25 Sep (-11 days)
9968955 | 100 | Delivered | MISCITEM | WC34 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC34 |  | not on site on the record
9968955 | 101 | Delivered | MISCITEM | WC33 Toilet Portable - Fresh Water Flush | 17 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC33 |  | not on site on the record
9968955 | 106 | Delivered | MISCITEM | WC59 FWF Toilet | 7 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC59 |  | not on site on the record
9968955 | 107 | Delivered | MISCITEM | WC57 FWF Toilet | 2 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC57 |  | not on site on the record
9968955 | 108 | Delivered | MISCITEM | WC49 FWF Toilet | 3 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC49 |  | not on site on the record
9968955 | 109 | Delivered | MISCITEM | WC48 FWF Toilet | 4 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC48 |  | not on site on the record
9968955 | 110 | Delivered | MISCITEM | WC51 FWF Toilet | 6 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC51 | 2026-10-15 | starts Mon 14 Sep, turned up Thu 15 Oct (-31 days)
9968955 | 111 | Off Rent | 1197174 | WC51 Toilet - Accessible | 1 | 337.75 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-26 | WC51 | 2026-10-15 | starts Mon 14 Sep, turned up Thu 15 Oct (-31 days)
9968955 | 112 | Delivered | MISCITEM | WC54 FWF Toilet | 6 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC54 |  | not on site on the record
9968955 | 113 | Delivered | MISCITEM | WC56 FWF Toilet | 12 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC56 |  | not on site on the record
9968955 | 115 | Delivered | MISCITEM | WC45 Toilet Portable - Fresh Water Flush | 8 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC45 |  | not on site on the record
9968955 | 116 | Delivered | MISCITEM | WC47 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC47 |  | not on site on the record
9968955 | 117 | Delivered | MISCITEM | WC19 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC19 | 2026-10-16 | starts Mon 14 Sep, turned up Fri 16 Oct (-32 days)
9968955 | 118 | Delivered | MISCITEM | WC25 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC25 |  | not on site on the record
9968955 | 119 | Delivered | MISCITEM | WC23 Toilet Portable - Fresh Water Flush | 5 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC23 |  | not on site on the record
9968955 | 120 | Delivered | MISCITEM | WC26 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC26 |  | not on site on the record
9968955 | 121 | Delivered | MISCITEM | WC24 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC24 |  | not on site on the record
9968955 | 122 | Delivered | MISCITEM | WC13 Toilet Portable - Fresh Water Flush | 2 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC13 |  | not on site on the record
9968955 | 123 | Delivered | MISCITEM | WC28 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC28 |  | not on site on the record
9968955 | 124 | Delivered | MISCITEM | WC29 Toilet Portable - Fresh Water Flush | 7 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC29 |  | not on site on the record
9968955 | 125 | Delivered | MISCITEM | WC30 Toilet Portable - Fresh Water Flush | 8 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC30 |  | not on site on the record
9968955 | 126 | Delivered | MISCITEM | WC35 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC35 |  | not on site on the record
9968955 | 127 | Delivered | MISCITEM | WC46 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC46 |  | not on site on the record
9968955 | 128 | Delivered | MISCITEM | WC55 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC55 |  | not on site on the record
9968955 | 129 | Delivered | MISCITEM | WC62 Toilet Portable - Fresh Water Flush | 2 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC62 |  | not on site on the record
9968955 | 130 | Delivered | MISCITEM | WC65 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC65 |  | not on site on the record
9968955 | 131 | Delivered | MISCITEM | WC68 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC68 | 2026-10-13 | starts Mon 14 Sep, turned up Tue 13 Oct (-29 days)
9968955 | 132 | Delivered | MISCITEM | WC72 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC72 | 2026-10-13 | starts Mon 14 Sep, turned up Tue 13 Oct (-29 days)
9968955 | 133 | Delivered | MISCITEM | WC73 Toilet Portable - Fresh Water Flush | 2 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC73 | 2026-10-13 | starts Mon 14 Sep, turned up Tue 13 Oct (-29 days)
9968955 | 134 | Delivered | MISCITEM | WC85 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC85 | 2026-10-16 | starts Mon 14 Sep, turned up Fri 16 Oct (-32 days)
9968955 | 140 | Delivered | 172824 | WC67 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | WC67 | 2026-10-01 | starts Mon 14 Sep, turned up Thu 01 Oct (-17 days)
9968955 | 141 | Pending | PUMPOUT | Pumpout Service FWF & Accessable | 702 |  | 72.87 | KINP-TOI | KINP | 2026-10-18
9968955 | 142 | Pending | PUMPOUT | Pumpout Service Tank Mounts | 24 |  | 624.6 | KINP-TOI | KINP | 2026-10-18
9968955 | 143 | Pending | CLEAN | Cleaning & Restock Sewer Connect | 24 |  | 260.25 | KINP-CLE | KINP | 2026-10-18
9968955 | 144 | Pending | LABOUR | Install Demob Toilet Blocks | 12 |  | 707.88 | KINP-INS | KINP | 2026-10-18
9968955 | 145 | Pending | LABOUR | Labour Charge Accessable Install & Demob | 8 |  | 88.49 | KINP-INS | KINP | 2026-10-18
9968955 | 146 | Pending | LABOUR | Labour Charge FWF Install & Demob | 434 |  | 36.44 | KINP-INS | KINP | 2026-10-18
9968955 | 147 | Pending | TRANSPORT | Transport Charge Blocks & 16 Pan | 28 |  | 500 | KINP-FRI | KINP | 2026-10-18
9968955 | 148 | Pending | TRANSPORT | Transport Charge Accessable Toilets | 8 |  | 500 | KINP-FRI | KINP | 2026-10-18
9968955 | 149 | Pending | TRANSPORT | Transport Charge FWF | 434 |  | 47.5 | KINP-FRI | KINP | 2026-10-18
9968955 | 150 | Delivered | MISC | Pallets Toilet Consumables Paper | 4 |  | 0 | KINP-MIS | KINP | 2026-10-19
9968955 | 151 | Delivered | MISCITEM | PG01 FWF Toilet | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-22 |  | PG01 | 2026-10-16 | starts Thu 22 Oct, turned up Fri 16 Oct (+6 days)
9968955 | 152 | Delivered | MISCITEM | PG03 FWF Toilet | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-22 |  | PG03 | 2026-10-16 | starts Thu 22 Oct, turned up Fri 16 Oct (+6 days)
9968955 | 153 | Delivered | MISCITEM | PG05 FWF Toilet | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-22 |  | PG05 |  | not on site on the record
9968955 | 154 | Delivered | MISCITEM | PG29 Toilet FWF | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-22 |  | PG29 |  | held out: on its own hire schedule; not on site on the record
9968955 | 155 | Delivered | MISCITEM | WC42 FWF Toilet | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-22 |  | WC42 | 2026-09-28 | starts Thu 22 Oct, turned up Mon 28 Sep (+24 days)
9968955 | 156 | Delivered | MISCITEM | WC53 FWF Toilet | 3 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-22 |  | WC53 |  | not on site on the record
9968955 | 157 | Delivered | MISCITEM | WC81 FWF Toilet | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-22 |  | WC81 | 2026-09-14 | starts Thu 22 Oct, turned up Mon 14 Sep (+38 days)
9968955 | 158 | Delivered | 1211963 | WC12 Toilet Portable - Fresh Water Flush | 1 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-22 |  | WC12 | 2026-09-14 | starts Thu 22 Oct, turned up Mon 14 Sep (+38 days)
9968955 | 160 | Pending | LABOUR | Install Demob 16 Pan | 2 |  | 551.73 | KINP-INS | KINP | 2026-10-22
9968955 | 162 | Pending | TRANSPORT | Transport Charge Waste Tanks | 12 |  | 500 | KINP-FRI | KINP | 2026-10-22
9968955 | 163 | Pending | TRAVEL EXPENSES | ACCOM / ETC 50% | 1 |  | 13850 | KINP-MIS | KINP | 2026-10-25
9968955 | 164 | Pending | LABOUR | Labour Charge Project Manager 50% | 15.22 |  | 150.11 | KINP-INS | KINP | 2026-10-25
9968955 | 165 | Pending | LABOUR | Labour Charge Event Toilet | 27.15 |  | 91.14 | KINP-INS | KINP | 2026-10-25
9968929 | 1 | Delivered | 960639 | Portable Building Shell 4.8M x 3.0M | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | T0021 | 2026-09-16 | starts Mon 14 Sep, turned up Wed 16 Sep (-2 days)
9968929 | 3 | Delivered | 960634 | Portable Building Shell 4.8M x 3.0M | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | T0022 | 2026-09-15 | starts Mon 14 Sep, turned up Tue 15 Sep (-1 days)
9968929 | 5 | Del Req | 1257261 | Shop Front - Shut Down | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | T0023 | 2026-09-15
9968929 | 7 | Delivered | 1211968 | Toilet Portable - Fresh Water Flush | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  | T0024 | 2026-09-26 | held out: on its own hire schedule; starts Mon 14 Sep, turned up Sat 26 Sep (-12 days)
9968929 | 8 | Pending | 1328965 | Spare Air Conditioner - 1hp - 2hp | 1 | 0 | 0 | KINP-HIR | KINP | 2026-10-21 |  |  |  | fit-out item
9968929 | 9 | Pending | 1327125 | Spare Air Conditioner - 1hp - 2hp | 1 | 0 | 0 | KINP-HIR | KINP | 2026-10-21 |  |  |  | fit-out item
9968929 | 10 | Pending | 1326268 | Spare Air Conditioner - 1hp - 2hp | 1 | 0 | 0 | KINP-HIR | KINP | 2026-10-21 |  |  |  | fit-out item
9968929 | 11 | Pending | 1284004 | Spare Refrigerator - Medium | 1 | 0 | 0 | KINP-HIR | KINP | 2026-10-21 |  |  |  | fit-out item
9968929 | 12 | Pending | 1254847 | Spare Refrigerator - Medium | 1 | 0 | 0 | KINP-HIR | KINP | 2026-10-21 |  |  |  | fit-out item
9968862 | 1 | Delivered | 1322583 | P01 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1 | 1951.46 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P01 | 2026-09-14
9968862 | 3 | Delivered | 1328956 | P01 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P01 | 2026-09-14
9968862 | 4 | Delivered | 1327212 | P03 Portable Building Shell 12.0M x 3.0M - Cyclonic Ra | 1 | 1951.46 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P03 | 2026-09-14
9968862 | 6 | Delivered | 1328955 | P03 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P03 | 2026-09-14
9968862 | 7 | Delivered | 1327213 | P04 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1 | 1951.46 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P04 | 2026-09-14
9968862 | 9 | Delivered | 1328954 | P04 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P04 | 2026-09-14
9968862 | 10 | Delivered | 1189422 | P05 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P05 | 2026-09-14
9968862 | 12 | Delivered | CHAIRPADDED | P05 Chair Padded | 4 | 4.05 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P05 | 2026-09-14
9968862 | 13 | Delivered | 1311988 | P05 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P05 | 2026-09-14
9968862 | 14 | Delivered | 1320150 | P05 Microwave Oven | 1 | 50.15 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P05 | 2026-09-14
9968862 | 15 | Delivered | SINK/HANDBASIN | P05 Sink & Cupboard | 1 | 90.68 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P05 | 2026-09-14
9968862 | 16 | Delivered | 1127574 | P05 Auto Boil | 1 | 54.28 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P05 | 2026-09-14
9968862 | 17 | Delivered | 1105057 | CP1 P68 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | CP1 | 2026-09-14
9968862 | 19 | Delivered | CHAIRSSTACKING | CP1 Chairs Stacking | 2 | 2.25 | 0 | KINP-HIR | KINP | 2026-09-14 |  | CP1 | 2026-09-14
9968862 | 20 | Delivered | DESK | CP1 Desk | 1 | 5.85 | 0 | KINP-HIR | KINP | 2026-09-14 |  | CP1 | 2026-09-14
9968862 | 21 | Delivered | 1116687 | CP1 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | CP1 | 2026-09-14
9968862 | 22 | Delivered | 119810 | CP1 Urn | 1 | 51.26 | 0 | KINP-HIR | KINP | 2026-09-14 |  | CP1 | 2026-09-14
9968862 | 23 | Delivered | SINK/HANDBASIN | CP1 Sink & Cupboard | 1 | 90.68 | 0 | KINP-HIR | KINP | 2026-09-14 |  | CP1 | 2026-09-14
9968862 | 24 | Delivered | 453375 | P33 Portable Building Shell 9.6M x 3.0M | 1 | 1576.18 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P33 | 2026-09-14
9968862 | 26 | Delivered | 1328952 | P33 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P33 | 2026-09-14
9968862 | 27 | Delivered | SINK/HANDBASIN | P33 Sink & Cupboard | 1 | 90.68 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P33 | 2026-09-14
9968862 | 28 | Delivered | 1268824 | P09 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P09 | 2026-09-16 | starts Mon 14 Sep, turned up Wed 16 Sep (-2 days)
9968862 | 30 | Delivered | 1328958 | P09 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P09 | 2026-09-16
9968862 | 31 | Delivered | SINK/HANDBASIN | P09 Sink & Cupboard | 1 | 90.68 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P09 | 2026-09-16
9968862 | 32 | Delivered | 1254390 | P09 Auto Boil | 1 | 54.28 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P09 | 2026-09-16
9968862 | 33 | Delivered | 1268887 | P17 Portable Building Shell Cyclone Rated 9.6m x 3m | 1 | 1576.18 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P17 | 2026-09-16 | starts Mon 14 Sep, turned up Wed 16 Sep (-2 days)
9968862 | 34 | Delivered | 1110619 | P19 Portable Building Shell 6.0M x 3.0M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P19 | 2026-09-16 | starts Mon 14 Sep, turned up Wed 16 Sep (-2 days)
9968862 | 36 | Delivered | 1097343 | P18 Portable Building Shell 4.8M x 2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P18 | 2026-09-16 | starts Mon 14 Sep, turned up Wed 16 Sep (-2 days)
9968862 | 38 | Delivered | 1097339 | P20 Portable Building Shell 4.8M x 2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P20 | 2026-09-16 | starts Mon 14 Sep, turned up Wed 16 Sep (-2 days)
9968862 | 44 | Delivered | 105626 | P10 Portable Building Shell 4.8M x 2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P10 | 2026-09-17 | starts Mon 14 Sep, turned up Thu 17 Sep (-3 days)
9968862 | 46 | Delivered | 415576 | P11 Portable Building Shell 4.8M x 2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P11 | 2026-09-17 | starts Mon 14 Sep, turned up Thu 17 Sep (-3 days)
9968862 | 48 | Delivered | 418665 | P12 Portable Building Shell 4.8M x 2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P12 | 2026-09-17 | starts Mon 14 Sep, turned up Thu 17 Sep (-3 days)
9968862 | 50 | Delivered | 1105053 | P37 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P37 | 2026-09-17 | starts Mon 14 Sep, turned up Thu 17 Sep (-3 days)
9968862 | 51 | Delivered | 1097346 | P13 Portable Building Shell 4.8M x 2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P13 | 2026-09-21 | starts Mon 14 Sep, turned up Mon 21 Sep (-7 days)
9968862 | 53 | Delivered | 960599 | P14 Portable Building Shell 4.8M x 2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P14 | 2026-09-21 | starts Mon 14 Sep, turned up Mon 21 Sep (-7 days)
9968862 | 55 | Delivered | 1097345 | P15 Portable Building Shell 4.8M x 2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P15 | 2026-09-21 | starts Mon 14 Sep, turned up Mon 21 Sep (-7 days)
9968862 | 57 | Delivered | 415575 | P16 Portable Building Shell 4.8M x 2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P16 | 2026-09-21 | starts Mon 14 Sep, turned up Mon 21 Sep (-7 days)
9968862 | 59 | Delivered | 1273656 | P58 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P58 | 2026-09-23 | starts Mon 14 Sep, turned up Wed 23 Sep (-9 days)
9968862 | 61 | Delivered | 198481 | P44 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P44 | 2026-09-24 | starts Mon 14 Sep, turned up Thu 24 Sep (-10 days)
9968862 | 63 | Delivered | 1189412 | P41 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P41 | 2026-09-22 | starts Mon 14 Sep, turned up Tue 22 Sep (-8 days)
9968862 | 64 | Delivered | 1087453 | P06 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P06 | 2026-09-28 | starts Mon 14 Sep, turned up Mon 28 Sep (-14 days)
9968862 | 66 | Delivered | 1272749 | P06 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P06 | 2026-09-28
9968862 | 67 | Delivered | SINK&CUPBOARD | P06 Sink & Cupboard | 1 | 90.68 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P06 | 2026-09-28
9968862 | 68 | Delivered | 1173374 | P06 Auto Boil | 1 | 54.28 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P06 | 2026-09-28
9968862 | 69 | Delivered | 1284012 | P06 Microwave Oven | 1 | 50.15 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P06 | 2026-09-28
9968862 | 79 | Delivered | 1327211 | P52 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1 | 1951.46 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P52 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968862 | 81 | Delivered | 1328953 | P52 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P52 | 2026-10-07
9968862 | 85 | Delivered | 1327219 | P54 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P54 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968862 | 87 | Delivered | 172114 | P55 Ticket Office 6.0Mx3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P55 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968862 | 89 | Delivered | 1268865 | P56 Portable Building Shell Cyclone Rated 3.6m x 2.4m | 1 | 975.73 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P56 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968862 | 90 | Delivered | 1268888 | P57 Portable Building Shell Cyclone Rated 9.6m x 3m | 1 | 1576.18 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P57 | 2026-10-07 | starts Mon 14 Sep, turned up Wed 07 Oct (-23 days)
9968862 | 91 | Delivered | 1280688 | P57 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P57 | 2026-10-07
9968862 | 92 | Delivered | 1327220 | P21 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P21 | 2026-09-16 | starts Mon 14 Sep, turned up Wed 16 Sep (-2 days)
9968862 | 93 | Delivered | 1282487 | P36 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P36 | 2026-09-17 | starts Mon 14 Sep, turned up Thu 17 Sep (-3 days)
9968862 | 94 | Delivered | 1322579 | P51 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1 | 1951.46 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P51 | 2026-10-06 | starts Mon 14 Sep, turned up Tue 06 Oct (-22 days)
9968862 | 96 | Delivered | 1328959 | P46 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P46 | 2026-10-06
9968862 | 100 | Delivered | 1327215 | P46 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1 | 1951.46 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P46 | 2026-10-06 | starts Mon 14 Sep, turned up Tue 06 Oct (-22 days)
9968862 | 102 | Delivered | 1328957 | P51 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P51 | 2026-10-06
9968862 | 103 | Off Rent | 107247 | P69 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P69 | 2026-10-12 | starts Mon 14 Sep, turned up Mon 12 Oct (-28 days)
9968862 | 105 | Off Rent | 1189408 | P25 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P25 |  | not on site on the record
9968862 | 107 | Off Rent | 1260174 | P25 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P25 |  | not on site on the record
9968862 | 108 | Off Rent | 421107 | P67 Commentary Booth 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P67 |  | not on site on the record
9968862 | 110 | Off Rent | 1327217 | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P65 |  | not on site on the record
9968862 | 112 | Off Rent | 1283982 | P65 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P65 |  | not on site on the record
9968862 | 113 | Off Rent | 1327222 | P66 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P66 |  | not on site on the record
9968862 | 115 | Off Rent | 1311990 | P66 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P66 |  | not on site on the record
9968862 | 116 | Off Rent | 1015699 | P60 Ticket Office 4.8Mx2.4M | 1 | 1125.84 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P60 |  | not on site on the record
9968862 | 118 | Off Rent | 1189409 | P62 Commentary Booth 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P62 |  | not on site on the record
9968862 | 120 | Off Rent | 1254221 | P62 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P62 |  | not on site on the record
9968862 | 121 | Off Rent | 960719 | P63 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-25 | P63 |  | not on site on the record
9968862 | 123 | Delivered | 1311992 | P26 Refrigerator - Large | 1 | 46.48 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P26 | 2026-10-14
9968862 | 124 | Delivered | 1283996 | P28 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P28 | 2026-10-14
9968862 | 125 | Delivered | CHAIRPADDED | P34 Chair Padded | 2 | 4.05 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P34 | 2026-10-14
9968862 | 126 | Delivered | 421138 | P08 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P08 | 2026-10-06 | starts Mon 14 Sep, turned up Tue 06 Oct (-22 days)
9968862 | 128 | Delivered | 1114312 | P08 Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 |  | P08 | 2026-10-06
9968862 | 131 | Off Rent | 107135 | P45 Portable Building Shell 6.0M x 3.0M | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-26 | P45 | 2026-10-12 | starts Mon 14 Sep, turned up Mon 12 Oct (-28 days)
9968862 | 132 | Off Rent | 1272751 | P46 Refrigerator | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-09-14 | 2026-10-26 | P46 | 2026-10-06
9968862 | 133 | Pending | LABOUR | Install & Demob | 38 |  | 655.83 | KINP-INS | KINP | 2026-10-16
9968862 | 134 | Pending | TRANSPORT | Transport Charge up to 6m Buildings | 66 |  | 500 | KINP-FRI | KINP | 2026-10-16
9968862 | 135 | Pending | TRANSPORT | Transport Charge 9.6m & 12m Building | 18 |  | 800 | KINP-FRI | KINP | 2026-10-16
9968862 | 136 | Delivered | MISC | Site Shift for Supply | 1 |  | 500 | KINP-MIS | KINP | 2026-10-19
9968862 | 137 | Del Req | MISCITEM | Stillage Fire Extinguishers | 1 | 0 | 0 | KINP-HIR | KINP | 2026-09-14 |  |  |  | nothing on the record carries this line
9968862 | 139 | Pending | LABOUR | Install & Demob (no steps) | 4 |  | 499.68 | KINP-INS | KINP | 2026-10-22
9968862 | 140 | Pending | TRAVEL EXPENSES | ACCOM / ETC 50% | 1 |  | 13850 | KINP-MIS | KINP | 2026-10-25
9968862 | 141 | Pending | LABOUR | Labour Charge Project Manager Event | 15.22 |  | 150.11 | KINP-INS | KINP | 2026-10-25
9974042 | 1 | Delivered | 1134386 | Container 3.0M x 2.4M | 1 | 285.6 | 0 | KINP-HIR | KINP | 2026-09-28 |  | T0258 | 2026-10-07 | starts Mon 28 Sep, turned up Wed 07 Oct (-9 days)
9974042 | 2 | Delivered | SUB-2131 | Container - Refrigerated 6.0M x 2.4M | 1 | 1428 | 0 | STPS-SUB | KINP | 2026-09-28 |  | T0266 | 2026-10-13 | starts Mon 28 Sep, turned up Tue 13 Oct (-15 days); sales code STPS-SUB, P&L KINP
9974042 | 3 | Pending | TRANSPORT | Delivery each way per container | 2 |  | 500 | KINP-FRI | KINP | 2026-09-28
9974042 | 4 | Pending | TRANSPORT | Pickup each way per Container | 2 |  | 500 | KINP-FRI | KINP | 2026-09-28
9961976 | 1 | Delivered | 1264929 | LT01 MOLENDINAR Lighting Tower LED Metro | 1 | 643.3 | 0 | NVAC-HIR | NVAC | 2026-09-11 |  | T0002
9961976 | 2 | Delivered | 1314284 | LT02 MOLENDINAR Lighting Tower LED Metro | 1 | 643.3 | 0 | NVAC-HIR | NVAC | 2026-09-11 |  | T0002
9961976 | 3 | Delivered | 1264899 | LT03 MOLENDINAR Lighting Tower LED 76500lm Hybrid | 1 | 643.3 | 0 | NVAC-HIR | NVAC | 2026-09-11 |  | T0002
9961976 | 4 | Delivered | 1188888 | LT04 MOLENDINAR Lighting Tower LED Metro | 1 | 643.3 | 0 | NVAC-HIR | NVAC | 2026-09-11 |  | T0002
9961976 | 5 | Delivered | 1249499 | LT09 Lighting Tower LED 76500lm Hybrid | 1 | 643.3 | 0 | NVAC-HIR | NVAC | 2026-09-11 |  | T0002
9961976 | 6 | Delivered | 1276701 | GN20-S01-Generator 365kVA Diesel | 1 | 6260.4 | 0 | NVAC-HIR | NVAC | 2026-09-30 |  | GN20-A | 2026-09-30
9961976 | 7 | Delivered | 1276416 | GN19-Generator - Diesel - 80kVA DEL AS 60KVA | 1 | 1254.5 | 0 | NVAC-HIR | NVAC | 2026-10-19 |  | GN19 | 2026-10-19
9961976 | 9 | Delivered | 1297157 | GN23-Generator - Sync - Hardwire Only 150kVA Diesel | 1 | 2412.54 | 0 | NVAC-HIR | NVAC | 2026-09-30 |  | GN23 | 2026-09-30
9961976 | 10 | Off Rent | 1320829 | GN03-Generator - 30kVA (Diesel) | 1 | 1132.28 | 0 | NVAC-HIR | NVAC | 2026-10-01 | 2026-10-28 | GN03 | 2026-10-01
9961976 | 11 | Delivered | 1261273 | GN18-Generator - 60kVA (Diesel) | 1 | 2187.36 | 0 | NVAC-HIR | NVAC | 2026-10-07 |  | GN18 | 2026-10-07
9961976 | 14 | Return Pending | 1277400 | GN04-Generator - 30kVA (Diesel) | 1 | 919.97 | 0 | NVAC-HIR | NVAC | 2026-10-19 | 2026-10-26 | GN04 |  | not on site on the record
9961976 | 15 | Returned | 1283681 | G10- Generator - 60kVA (Diesel) | 1 | 1142.96 | 0 | NVAC-HIR | NVAC | 2026-10-19 | 2026-10-25 | GN10 |  | not on site on the record
9961976 | 16 | Delivered | 1276507 | GN01-Generator - 60kVA (Diesel) | 1 | 1544 | 0 | NVAC-HIR | NVAC | 2026-09-28 |  | GN01 | 2026-09-28
9961976 | 18 | Off Rent | 1244536 | GN25-Generator - 20kVA (Diesel) | 1 | 855.63 | 0 | NVAC-HIR | NVAC | 2026-10-19 | 2026-10-26 | GN25 | 2026-10-19
9961976 | 19 | Off Rent | 1224783 | LT05/06-Lighting Tower POD Metro | 1 | 385.98 | 0 | NVAC-HIR | NVAC | 2026-10-20 | 2026-10-26 | LT05 | 2026-10-20
9961976 | 20 | Off Rent | 1224791 | LT05/06-Lighting Tower POD Metro | 1 | 385.98 | 0 | NVAC-HIR | NVAC | 2026-10-20 | 2026-10-26 | LT06 | 2026-10-20
9961976 | 21 | Delivered | 1197839 | COATES Forklift 3.0t Container Diesel | 1 | 0 | 0 | NVAC-HIR | NVAC | 2026-09-11 |  | T0004
9961976 | 25 | Returned | 1247787 | COATES Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD | 1 | 0 | 0 | NVAC-HIR | NVAC | 2026-09-11 | 2026-09-17 | T0005 | 2026-09-14 | starts Fri 11 Sep, turned up Mon 14 Sep (-3 days)
9961976 | 26 | Delivered | 1312577 | COATES Forklift Rough Terrain 4WD With Rotator 2.5t Diesel | 1 | 0 | 0 | NVAC-HIR | NVAC | 2026-09-11 |  | T0005 | 2026-09-14 | starts Fri 11 Sep, turned up Mon 14 Sep (-3 days)
9961976 | 27 | Pending | 1210921 | SUPPLY-Forklift 3.5t Diesel | 1 | 0 | 0 | NVAC-HIR | NVAC | 2026-10-21 |  | EQ0004 | 2026-10-22 | starts Wed 21 Oct, turned up Thu 22 Oct (-1 days)
9961976 | 31 | Delivered | MISCITEM | COATES- 5T FORKLIFT 1.8TYNNES | 1 | 0 | 0 | NVAC-HIR | NVAC | 2026-09-11 |  | FL01 | 2026-09-25 | starts Fri 11 Sep, turned up Fri 25 Sep (-14 days)
9961976 | 34 | Delivered | MISCITEM | AT009 Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD | 1 | 0 | 0 | NVAC-HIR | NVAC | 2026-09-17 |  |  |  | nothing on the record carries this line
9961976 | 35 | Delivered | 1247787 | COATES-Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD | 1 | 0 | 0 | NVAC-HIR | NVAC | 2026-10-19 |  | T0005 | 2026-09-14 | starts Mon 19 Oct, turned up Mon 14 Sep (+35 days)
9961976 | 37 | Delivered | 1302007 | COATES-Forklift Tyne Rotator | 1 | 0 | 0 | NVAC-HIR | NVAC | 2026-10-19 |  |  |  | nothing on the record carries this line
9961976 | 38 | Delivered | 1261284 | GN21-Generator - 60kVA (Diesel) | 1 | 868.5 | 0 | NVAC-HIR | NVAC | 2026-09-30 |  | GN21 | 2026-09-30
9961976 | 41 | Delivered | 1189078 | GN23-Distribution Board Lifeguard 17 | 1 | 0 | 0 | NVAC-HIR | NVAC | 2026-09-30 |  | GN23 | 2026-09-30
9961976 | 44 | Return Pending | 1276503 | GN13 Generator - 60kVA (Diesel) DEL AS 45KVA | 1 | 1406.72 | 0 | NVAC-HIR | NVAC | 2026-10-12 | 2026-10-26 | GN13 |  | not on site on the record
9961976 | 48 | Off Rent | 1320828 | GN06 Generator - 60kVA (Diesel) | 1 | 1168.72 | 0 | NVAC-HIR | NVAC | 2026-10-15 | 2026-10-25 | GN06 |  | not on site on the record
9961976 | 49 | Returned | 1277089 | GN24-Generator - 60kVA (Diesel) - Trailer Mounted | 1 | 984.33 | 0 | NVAC-HIR | NVAC | 2026-10-19 | 2026-10-26 | GN24 |  | not on site on the record
9961976 | 51 | Pending | LABOUR | Labour Charge Generator | 11 |  | 300.22 | NVAC-INS | NVAC | 2026-10-19
9961976 | 52 | Pending | LABOUR | Labour Charge Generator | 1 |  | 333.12 | NVAC-INS | NVAC | 2026-10-19
9961976 | 53 | Pending | TRANSPORT | Transport Charge | 6 |  | 309 | NVAC-FRI | NVAC | 2026-10-19
9961976 | 54 | Pending | TRANSPORT | Transport Charge | 16 |  | 463.5 | NVAC-FRI | NVAC | 2026-10-19
9961976 | 55 | Pending | TRANSPORT | Transport Charge | 2 |  | 600 | NVAC-FRI | NVAC | 2026-10-19
9961976 | 56 | Pending | LABOUR | Labour Charge Event Gen Tech | 31.55 |  | 150.11 | NVAC-INS | NVAC | 2026-10-25
9961976 | 58 | Pending | LABOUR | Labour Charge Light Tower | 7 |  | 182.28 | NVAC-INS | NVAC | 2026-10-27
9961976 | 59 | Pending | TRANSPORT | Transport Charge Light Towers | 14 |  | 154.5 | NVAC-FRI | NVAC | 2026-10-27
9961976 | 60 | Pending | LABOUR | Labour Charge 350KVA | 1 |  | 333.12 | NVAC-INS | NVAC | 2026-10-27
9972648 | 1 | Off Rent | ARMORZONMASHTL2 | WB01 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 12 | 1.18 | 0 | STPS-HIR | STPS | 2026-09-14 | 2026-10-29 | WB01 | 2026-09-14
9972648 | 2 | Off Rent | ARMORZONMASHTL2 | WB03 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 30 | 1.18 | 0 | STPS-HIR | STPS | 2026-09-18 | 2026-10-29 | WB03 | 2026-09-23 | starts Fri 18 Sep, turned up Wed 23 Sep (-5 days)
9972648 | 3 | Off Rent | ARMORZONMASHTL2 | WB02 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 34 | 1.18 | 0 | STPS-HIR | STPS | 2026-09-21 | 2026-09-25 | WB02 | 2026-09-21
9972648 | 4 | Off Rent | ARMORZONMASHTL2 | WB05 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 12 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-16 | 2026-10-27 | WB05 | 2026-10-16
9972648 | 5 | Delivered | ARMORZONMASHTL2 | WB04 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 13 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-16 |  | WB04 | 2026-10-16
9972648 | 6 | Off Rent | ARMORZONMASHTL2 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 60 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-15 | 2026-10-27 | WB06 | 2026-10-15
9972648 | 9 | Delivered | ARMORZONMASHTL2 | WB14 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 2 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-21 |  | WB14 | 2026-10-21
9972648 | 10 | Delivered | ARMORZONMASHTL2 | WB15 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 4 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-21 |  | WB15 | 2026-10-21
9972648 | 11 | Delivered | ARMORZONMASHTL2 | WB16 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 13 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-21 |  | WB16 | 2026-10-21
9972648 | 12 | Off Rent | ARMORZONMASHTL2 | WB17 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 5 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-22 | 2026-10-27 | WB17 | 2026-10-22
9972648 | 13 | Delivered | ARMORZONMASHTL2 | WB18 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 2 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-22 |  | WB18 | 2026-10-22
9972648 | 14 | Pending | ARMORZONMASHTL2 | WB20 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 30 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-26 |  | WB20 |  | not on site on the record
9972648 | 15 | Pending | ARMORZONMASHTL2 | WB19 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 34 | 1.18 | 0 | STPS-HIR | STPS | 2026-11-02 |  | WB19 |  | not on site on the record
9972648 | 16 | Off Rent | ARMORZONMASHTL2 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 60 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-15 | 2026-10-27 | WB06 | 2026-10-15
9972648 | 17 | Off Rent | ARMORZONMASHTL2 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 34 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-15 | 2026-10-27 | WB06 | 2026-10-15
9972648 | 18 | Pending | ARMORZONMASHTL2 | WB22 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 4 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-18 |  |  |  | nothing on the record carries this line
9972648 | 19 | Pending | LABOUR | Labour Charge WFB | 1 |  | 7700 | STPS-INS | STPS | 2026-10-25
9972648 | 20 | Pending | TRANSPORT | Transport Charge WFB | 1 |  | 17900 | STPS-FRI | STPS | 2026-10-25
9972648 | 21 | Delivered | ARMORZONMASHTL2 | WB17 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 1 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-22 |  | WB17 | 2026-10-22
9961265 | 1 | Returned | 1211404 | Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-09-07 | 2026-09-22 | VMS09 | 2026-10-08 | returned Tue 22 Sep
9961265 | 3 | Delivered | 1211370 | Variable Message Board Senior - REED | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-09-07 |  | 1211370 | 2026-09-07
9961265 | 4 | Delivered | 1211354 | Variable Message Board Senior - MARS | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-09-07 |  | 1211354 | 2026-09-07
9961265 | 5 | Delivered | 1182999 | Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-09-07 |  | 1182999 | 2026-09-07
9961265 | 6 | Delivered | 1191877 | Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-09-07 |  | 1191877 | 2026-09-07
9961265 | 7 | Delivered | 1211359 | Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-09-07 |  | 1211359 | 2026-09-07
9961265 | 8 | Delivered | 1211383 | Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-09-07 |  | 1211383 | 2026-09-07
9961265 | 9 | Delivered | 1271129 | Variable Message Board - Colour - Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-09-07 |  | 1271129 | 2026-09-07
9961265 | 12 | Delivered | 1211404 | VMS09 Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-10-08 |  | VMS09 | 2026-10-08
9961265 | 13 | Delivered | sub-17093 | VMS10 120T Variable Message Board Senior Premiair | 1 | 53.61 | 0 | KINP-SUB | STPS | 2026-10-08 |  | VMS10 | 2026-10-08 | sales code KINP-SUB
9961265 | 15 | Off Rent | SUB-17093 | VMS11 467T Variable Message Board - Premiair | 1 | 53.61 | 0 | KINP-SUB | STPS | 2026-10-16 | 2026-10-26 | VMS11 | 2026-10-16 | sales code KINP-SUB
9961265 | 16 | Delivered | 1211646 | VMS12 Variable Message Board Junior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-10-16 |  | VMS12 | 2026-10-16
9961265 | 24 | Delivered | SUB-2631 | VMS18 472T Variable Message Board Senior Premiair | 1 | 53.61 | 0 | KINP-SUB | STPS | 2026-10-19 |  | VMS18 | 2026-10-19 | sales code KINP-SUB
9961265 | 25 | Delivered | SUB-2631 | VMS19 487T Variable Message Board Senior Premiair | 1 | 53.61 | 0 | KINP-SUB | STPS | 2026-10-19 |  | VMS19 | 2026-10-19 | sales code KINP-SUB
9961265 | 26 | Off Rent | SUB-2631 | VMS20 475T Variable Message Board Senior Premiair | 1 | 53.61 | 0 | KINP-SUB | STPS | 2026-10-19 | 2026-10-26 | VMS20 | 2026-10-19 | sales code KINP-SUB
9961265 | 28 | Delivered | SUB-2631 | VMS21 Variable Message Board Senior Premiair | 1 | 53.61 | 0 | KINP-SUB | STPS | 2026-10-22 |  | VMS21 | 2026-10-22 | sales code KINP-SUB
9961265 | 29 | Delivered | SUB-2631 | VMS22 445T Variable Message Board Senior Premiair | 1 | 53.61 | 0 | KINP-SUB | STPS | 2026-10-22 |  | VMS22 | 2026-10-22 | sales code KINP-SUB
9961265 | 30 | Delivered | SUB-2631 | VMS23 453T Variable Message Board Senior Premiair | 1 | 53.61 | 0 | KINP-SUB | STPS | 2026-10-19 |  | VMS23 | 2026-10-19 | sales code KINP-SUB
9961265 | 31 | Delivered | SUB-1101 | VMS24 450T Variable Message Board Senior | 1 | 53.61 | 0 | NVAC-SUB | STPS | 2026-10-22 |  | VMS24 | 2026-10-22 | sales code NVAC-SUB
9961265 | 32 | Delivered | 1191957 | VMS13 Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-10-19 |  | VMS13 | 2026-10-19
9961265 | 34 | Delivered | 1201864 | VMS14 Variable Message Board Junior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-10-19 |  | VMS14 | 2026-10-16 | starts Mon 19 Oct, on site Fri 16 Oct (recorded on site (load T0158))
9961265 | 35 | Delivered | 1211348 | VMS15 Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-10-19 |  | VMS15 | 2026-10-16 | starts Mon 19 Oct, on site Fri 16 Oct (recorded on site (load T0158))
9961265 | 37 | Delivered | 1211376 | VMS16 Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-10-19 |  | VMS16 | 2026-10-16 | starts Mon 19 Oct, on site Fri 16 Oct (recorded on site (load T0158))
9961265 | 39 | Delivered | 1211364 | VMS17 Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-10-19 |  | VMS17 | 2026-10-16 | starts Mon 19 Oct, on site Fri 16 Oct (recorded on site (load T0158))
9961265 | 40 | Pending | LABOUR | Labour Charge | 24 |  | 176.97 | STPS-INS | STPS | 2026-10-19
9961265 | 41 | Pending | TRANSPORT | Transport Charge | 48 |  | 150 | STPS-FRI | STPS | 2026-10-19
9961265 | 42 | Pending | TRANSPORT | Transport Charge Site Shifts | 8 |  | 150 | STPS-FRI | STPS | 2026-10-19
9961265 | 43 | Off Rent | 1211356 | VMS05a Variable Message Board Senior | 1 | 53.61 | 0 | STPS-HIR | STPS | 2026-10-20 | 2026-10-26 | VMS05 | 2026-10-20
9961265 | 44 | Pending | LABOUR | Event Labour Charge | 65 |  | 91.14 | STPS-INS | STPS | 2026-10-25
9973079 | 1 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 20 | 5 | 0 | STPS-HIR | STPS | 2026-09-14 |  |  |  | trakmat: see quantities
9973079 | 3 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 20 | 5.05 | 0 | STPS-HIR | STPS | 2026-10-16 |  |  |  | trakmat: see quantities
9973079 | 4 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 25 | 5.05 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | trakmat: see quantities
9973079 | 5 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 12 | 5.05 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | trakmat: see quantities
9973079 | 6 | Pending | TRANSPORT | Transport Charge | 1 |  | 150 | STPS-FRI | STPS | 2026-10-19
9973079 | 7 | Pending | TRANSPORT | Transport Charge | 1 |  | 275 | STPS-FRI | STPS | 2026-10-19
9973079 | 8 | Pending | TRANSPORT | Transport Charge | 1 |  | 275 | STPS-FRI | STPS | 2026-10-19
9992300 | 1 | Delivered | 1321364 | Forklift Rough Terrain 5.0t 4WD Diesel | 1 | 268.06 | 0 | MEAD-HIR | MEAD | 2026-10-17 |  | FL03 | 2026-10-16 | starts Sat 17 Oct, turned up Fri 16 Oct (+1 days)
9992300 | 2 | Delivered | 1298390 | Forklift Rough Terrain 2.5t 4WD Diesel | 1 | 123.31 | 0 | MEAD-HIR | MEAD | 2026-10-17 |  | FL04 | 2026-10-16 | starts Sat 17 Oct, turned up Fri 16 Oct (+1 days)
9992300 | 3 | Delivered | MISCITEM | Fork Extensions 2.4m | 1 | 24.6 | 0 | MEAD-HIR | MEAD | 2026-10-17 |  | EQ0005 | 2026-10-23 | starts Sat 17 Oct, turned up Fri 23 Oct (-6 days)
9992300 | 4 | Delivered | 1220903 | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | 1 | 209.08 | 0 | MEAD-HIR | MEAD | 2026-10-19 |  | EQ0001 | 2026-10-22 | starts Mon 19 Oct, turned up Thu 22 Oct (-3 days)
9992300 | 5 | Off Rent | 1300290 | Knuckle Boom 61ft (18.6M) - Diesel | 1 | 310.95 | 0 | MEAD-HIR | MEAD | 2026-10-21 | 2026-10-26 | EQ0002 |  | not on site on the record
9992300 | 6 | Delivered | MISCITEM | Trakmat | 1 | 4.83 | 0 | MEAD-HIR | MEAD | 2026-10-17 |  |  |  | trakmat: see quantities
9992300 | 7 | Delivered | TRANSPORT | Transport Charge 5T Forklift | 2 |  | 500 | MEAD-FRI | MEAD | 2026-10-17
9992300 | 8 | Delivered | TRANSPORT | Transport Charge 2.5T Forklift | 2 |  | 500 | MEAD-FRI | MEAD | 2026-10-17
9992300 | 9 | Delivered | TRANSPORT | Transport Charge 43' Scissorlift | 2 |  | 500 | MEAD-FRI | MEAD | 2026-10-17
9992300 | 10 | Delivered | TRANSPORT | Transport Charge 60' Boom | 2 |  | 500 | MEAD-FRI | MEAD | 2026-10-17
9992300 | 11 | Delivered | TRANSPORT | Transport Charge Trakmat | 2 |  | 176.97 | MEAD-FRI | MEAD | 2026-10-17
9992300 | 12 | Return Pending | 1286482 | Straight Boom Lift 60ft - Diesel | 1 | 310.95 | 0 | MEAD-HIR | MEAD | 2026-10-21 | 2026-10-26 | EQ0003 |  | not on site on the record
9992300 | 13 | Delivered | TRANSPORT | Transport Charge 60' Straight | 2 |  | 500 | MEAD-FRI | MEAD | 2026-10-19
9990776 | 1 | Off Rent | ARMORZONMASHTL2 | WB13 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 10 | 1.18 | 0 | STPS-HIR | STPS | 2026-10-19 | 2026-10-26 | WB13 | 2026-10-19
9990776 | 2 | Pending | TEMPFENCEFEETRH | Ped Gates | 32 | 36.18 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | fencing: its own reconciliation (dockets to POs)
9990776 | 3 | Pending | TEMPFENCEFEETRH | 1.8m Security Fence | 8778 | 16.16 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | fencing: its own reconciliation (dockets to POs)
9990776 | 4 | Pending | TEMPFENCEFEETRH | Fence Relocation | 1520 | 8.65 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | fencing: its own reconciliation (dockets to POs)
9990776 | 5 | Pending | TEMPFENCEFEETRH | 1.8m Security Fence w/ Hoarding | 110 | 23.59 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | fencing: its own reconciliation (dockets to POs)
9990776 | 6 | Pending | TEMPFENCEFEETRH | 1.8m Fence w/Scrim | 2775 | 16.16 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | fencing: its own reconciliation (dockets to POs)
9990776 | 7 | Pending | MISCITEM | Barrier - Crowd Control | 2350 | 7.51 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | fencing: its own reconciliation (dockets to POs)
9990776 | 8 | Pending | MISCITEM | Barrier - Crowd Control Flat Feet | 220 | 7.51 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | fencing: its own reconciliation (dockets to POs)
9990776 | 9 | Pending | MISCITEM | Demarcation CCB | 4603 | 13.08 | 0 | STPS-HIR | STPS | 2026-10-19 |  |  |  | fencing: its own reconciliation (dockets to POs)
9990776 | 10 | Pending | SHADECLOTH | Shade Cloth | 2775 |  | 9.37 | STPS-CON | STPS | 2026-10-19
9990776 | 11 | Pending | SHADECLOTH | Weed Mat 50m roll | 40 |  | 79.62 | STPS-CON | STPS | 2026-10-22
9990776 | 12 | Del Req | SHADECLOTH | Weed Mat | 10 |  | 95 | STPS-CON | STPS | 2026-10-22
9990776 | 13 | Pending | TRANSPORT | Transport Charge 10x rolls scrim | 1 |  | 150 | STPS-FRI | STPS | 2026-10-25
9990776 | 14 | Pending | LABOUR | Event Labour Charge | 213 |  | 91.14 | STPS-INS | STPS | 2026-10-25
9994248 | 1 | Pending |  | Temporary Fence 1.8m (per Meter) | 35 | 17.5 | 0 | STPS-HIR | STPS | 2026-10-20 |  |  |  | fencing: its own reconciliation (dockets to POs)
9994248 | 2 | Pending |  | Barrier - Crowd Control (per Meter) | 45 | 14 | 0 | STPS-HIR | STPS | 2026-10-20 |  |  |  | fencing: its own reconciliation (dockets to POs)
9994248 | 3 | Del Req | CHAIRSSTACKING | Chairs Stacking | 24 | 2.2 | 0 | STPS-HIR | STPS | 2026-10-20 |  |  |  | fit-out item
9994248 | 4 | Quoted | DELIVERY | Delivery for Line Item(s) 3,4 19 Oct 2026 | 1 |  | 250 | STPS-FRI | STPS | 2026-10-20
9994248 | 5 | Quoted | PICKUP CHARGE | Pickup | 1 |  | 250 | STPS-FRI | STPS | 2026-10-20
9994996 | 1 | Pending | LABOUR | Labour Charge WFB Install & Removal | 1 |  | 7700 | STPS-INS | STPS | 2026-10-23
9994996 | 2 | Pending | TRANSPORT | Transport Charge WFB Delivery & Removal | 1 |  | 17900 | STPS-FRI | STPS | 2026-10-23
9994954 | 1 | Delivered | 1327218 | P38 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-10-23 |  | P38 | 2026-09-28 | starts Fri 23 Oct, turned up Mon 28 Sep (+25 days)
9994954 | 3 | Delivered | 1327216 | P39 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-10-23 |  | P39 | 2026-09-28 | starts Fri 23 Oct, turned up Mon 28 Sep (+25 days)
9994954 | 4 | Delivered | 1327221 | P42 Portable Building Shell 6.0M x 3.0M - Cyclonic Rat | 1 | 1426.07 | 0 | KINP-HIR | KINP | 2026-10-23 |  | P42 | 2026-09-28 | starts Fri 23 Oct, turned up Mon 28 Sep (+25 days)
9994954 | 5 | Delivered | LABOUR | Install & Demob | 3 |  | 499.68 | KINP-INS | KINP | 2026-10-23
9994954 | 6 | Delivered | TRANSPORT | Transport Charge | 6 |  | 500 | KINP-FRI | KINP | 2026-10-23
9994954 | 7 | Delivered | 1272737 | P38 Refrigerator | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-10-23 |  | P38 | 2026-09-28
9994954 | 8 | Delivered | 1272755 | P39 Refrigerator | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-10-23 |  | P39 | 2026-09-28
9994954 | 9 | Delivered | 1272746 | P42 Refrigerator | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-10-23 |  | P42 | 2026-09-28
9994954 | 10 | Delivered | 1316182 | GN26 Generator - 200kVA (Diesel) | 1 | 2005.08 | 0 | KINP-HIR | NVAC | 2026-10-12 |  | GN? | 2026-10-12 | sales code KINP-HIR, P&L NVAC
9994954 | 11 | Delivered | 1316183 | GN27 Generator - 200kVA (Diesel) | 1 | 2551.92 | 0 | KINP-HIR | NVAC | 2026-10-12 |  | GN? | 2026-10-12 | sales code KINP-HIR, P&L NVAC
9994954 | 12 | Delivered | CABLESSDI120MM | Cable - 120mm2 Single Double Insulated | 2 | 0 | 0 | KINP-HIR | NVAC | 2026-10-23 |  |  |  | generator cable for GN26/27
9994954 | 13 | Delivered | LABOUR | Labour Charge Sync Generators | 12 |  | 150.11 | KINP-INS | NVAC | 2026-10-23
9994954 | 14 | Delivered | TRANSPORT | Transport Charge Generators | 4 |  | 600 | KINP-FRI | NVAC | 2026-10-23
9994954 | 15 | Delivered | 1268858 | WC09 Toilet Block 6.0M x 3.0M - CAT 2 | 1 | 2476.85 | 0 | KINP-HIR | KINP | 2026-10-23 |  | WC09 | 2026-10-08 | starts Fri 23 Oct, turned up Thu 08 Oct (+15 days)
9994954 | 16 | Delivered | 1311146 | WC09 Toilet Block Male Female Cyclone Rated 6m x 3m | 1 | 2476.85 | 0 | KINP-HIR | KINP | 2026-10-23 |  | WC09 | 2026-10-08 | starts Fri 23 Oct, turned up Thu 08 Oct (+15 days)
9994954 | 17 | Delivered | LABOUR | Labour Charge Toilet Block | 2 |  | 707.88 | KINP-INS | KINP | 2026-10-23
9994954 | 18 | Delivered | TRANSPORT | Transport Charge Toilet Block | 4 |  | 500 | KINP-FRI | KINP | 2026-10-23
9994954 | 19 | Delivered | MISCITEM | Pee Panels | 6 | 672.17 | 0 | KINP-HIR | KINP | 2026-10-23 |  | WC09 | 2026-10-08 | starts Fri 23 Oct, turned up Thu 08 Oct (+15 days)
9994954 | 20 | Delivered | LABOUR | Labour Charge Pee Panel | 6 |  | 551.73 | KINP-INS | KINP | 2026-10-23
9994954 | 21 | Delivered | MISCITEM | WC09 FWF Toilet | 10 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-23 |  | WC09 | 2026-10-08 | starts Fri 23 Oct, turned up Thu 08 Oct (+15 days)
9994954 | 22 | Delivered | MISCITEM | WC10 FWF Toilet | 3 | 90.07 | 0 | KINP-HIR | KINP | 2026-10-23 |  | WC10 | 2026-10-13 | starts Fri 23 Oct, turned up Tue 13 Oct (+10 days)
9994954 | 23 | Delivered | LABOUR | Labour Charge FWF | 13 |  | 72.88 | KINP-INS | KINP | 2026-10-23
9994954 | 24 | Delivered | TRANSPORT | Transport Charge FWF | 26 |  | 47.5 | KINP-FRI | KINP | 2026-10-23
9994954 | 25 | Pending | LABOUR | Labour Charge Event Gen Tech | 4.5 |  | 150.11 | KINP-INS | NVAC | 2026-10-25
9994954 | 26 | Pending | LABOUR | Labour Charge Toilet Tech | 4.5 |  | 91.14 | KINP-INS | KINP | 2026-10-25
1000052 | 1 | Delivered | MISCITEMS | P68 Hydration Station | 1 | 77.54 | 0 | KINP-HIR | KINP | 2026-09-14 |  |  |  | nothing on the record carries this line
1000052 | 2 | Delivered | WATER | Water Charges | 1 |  | 450.34 | KINP-CON | KINP | 2026-10-27
1000052 | 3 | Delivered | TRANSPORT | Transport Charge Hydration Station | 2 |  | 443.93 | KINP-FRI | KINP | 2026-10-27
1000052 | 4 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 20 | 4.83 | 0 | KINP-HIR | STPS | 2026-09-15 |  |  |  | trakmat: see quantities
1000052 | 5 | Delivered | TRANSPORT | Transport Charge 20x matts | 1 |  | 150 | KINP-FRI | KINP | 2026-10-27
1000052 | 6 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 20 | 4.83 | 0 | KINP-HIR | STPS | 2026-10-16 |  |  |  | trakmat: see quantities
1000052 | 7 | Delivered | TRANSPORT | Transport Charge 16/10 20x | 1 |  | 275 | KINP-FRI | KINP | 2026-10-27
1000052 | 8 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 37 | 4.83 | 0 | KINP-HIR | STPS | 2026-10-27 |  |  |  | trakmat: see quantities
1000052 | 9 | Delivered | TRANSPORT | Transport Charge 37x 19/10 | 1 |  | 275 | KINP-FRI | KINP | 2026-10-27
1000052 | 10 | Quoted | PICKUP CHARGE | Pickup Charge For Track Mat | 1 |  | 150 | KINP-FRI | KINP | 2026-10-27
1000052 | 11 | Delivered | TRANSPORT | Site Shift Supply Container | 1 |  | 500 | KINP-FRI | KINP | 2026-10-27
1000050 | 1 | Delivered | MISCCONS | Toilet Paper | 55 |  | 84.5 | KINP-CON | KINP | 2026-10-27
1000050 | 2 | Delivered | MISCCONS | Hand Towel | 21 |  | 98.9 | KINP-CON | KINP | 2026-10-27
9997711 | 1 | Delivered | 1129733 | Refrigerator - Large | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-10-20 |  | FR01 | 2026-10-17
9997711 | 2 | Delivered | TRANSPORT | Transport Charge | 2 |  | 97.69 | KINP-FRI | KINP | 2026-10-20
9997711 | 3 | Delivered | 1157786 | Fridge Freezer | 1 | 46.84 | 0 | KINP-HIR | KINP | 2026-10-20 |  | FR02 | 2026-10-17 | starts Tue 20 Oct, turned up Sat 17 Oct (+3 days)
9997710 | 1 | Pending | TEMPFENCEFEETRH | 1.8m Fence | 144 | 0.12 | 0 | STPS-HIR | STPS | 2026-10-17 |  |  |  | fencing: its own reconciliation (dockets to POs)
9997710 | 2 | Pending | SHADECLOTH | Shade Cloth | 144 |  | 9.37 | STPS-CON | KINP | 2026-10-17
1000048 | 1 | Delivered | MISCCONS | Scrim 50m roll | 12 |  | 82.01 | STPS-CON | KINP | 2026-10-23
1000048 | 2 | Delivered | MISCCONS | Scrim 50m Roll | 10 |  | 95 | STPS-CON | KINP | 2026-10-27
1000048 | 3 | Delivered | TRANSPORT | Transport Charge for 10x rolls | 1 |  | 150 | STPS-FRI | KINP | 2026-10-27
1000047 | 1 | Pending | MISCCONS | Scrim 50m roll | 28 |  | 82.01 | STPS-CON | KINP | 2026-10-23

## Toilets by reference
Reference | Kind | On site | Baseplan | Baseplan lines | Turned up | Verdict
PG01 | FWF | 1 | 1 | 9968955/151 | 2026-10-16 | agrees
PG03 | FWF | 1 | 1 | 9968955/152 | 2026-10-16 | agrees
PG05 | FWF | 1 | 1 | 9968955/153 | - | agrees
T0243 | Toilet Block 6m | 1 | 1 | 9973977/1 | - | agrees
WC01 | FWF | 2 | 2 | 9968955/46, 9968955/69 | 2026-09-28 | agrees
WC01 | Accessible Toilet | 1 | 1 | 9968955/57 | 2026-09-28 | agrees
WC02 | FWF | 1 | 1 | 9968955/45 | 2026-09-22 | agrees
WC04 | FWF | 1 | 1 | 9968955/44 | 2026-09-22 | agrees
WC05 | Toilet Block 6m | 1 | 1 | 9968955/1 | 2026-09-14 | agrees
WC05 | Waste tank | 1 | 1 | 9968955/3 | 2026-09-14 | agrees
WC06 | FWF | 2 | 2 | 9968955/15, 9968955/58 | 2026-09-23 | agrees
WC07 | FWF | 20 | 20 | 9968955/24, 9968955/25, 9968955/26, 9968955/27, 9968955/28, 9968955/29, 9968955/30, 9968955/31, 9968955/32, 9968955/33, 9968955/34, 9968955/35, 9968955/36, 9968955/37, 9968955/38, 9968955/39, 9968955/40, 9968955/41, 9968955/42, 9968955/43 | 2026-09-22 | agrees
WC09 | FWF | 10 | 10 | 9994954/21 | 2026-10-08 | agrees
WC09 | Toilet Block 6m | 2 | 2 | 9994954/15, 9994954/16 | 2026-10-08 | agrees
WC09 | Pee Panel | 6 | 6 | 9994954/19 | 2026-10-08 | agrees
WC10 | FWF | 3 | 3 | 9994954/22 | 2026-10-13 | agrees
WC11 | FWF | 2 | 2 | 9968955/6, 9968955/23 | 2026-09-14 | agrees
WC12 | FWF | 4 | 4 | 9968955/4, 9968955/5, 9968955/17, 9968955/158 | 2026-09-14 | agrees
WC13 | FWF | 2 | 2 | 9968955/122 | - | agrees
WC15 | Toilet Block 6m | 2 | 2 | 9968955/55, 9968955/56 | 2026-09-25 | agrees
WC16 | Toilet Block 6m | 2 | 2 | 9968955/10, 9968955/11 | 2026-09-14 | agrees
WC17 | Toilet Block 6m | 2 | 2 | 9968955/20, 9968955/21 | 2026-09-15 | agrees
WC19 | FWF | 1 | 1 | 9968955/117 | 2026-10-16 | agrees
WC20 | Toilet Block 6m | 2 | 2 | 9968955/47, 9968955/48 | 2026-10-07 | agrees
WC20 | Waste tank | 2 | 2 | 9968955/49, 9968955/50 | 2026-10-07 | agrees
WC21 | FWF | 6 | 6 | 9968955/7, 9968955/8, 9968955/14, 9968955/16, 9968955/18, 9968955/19 | 2026-09-14 | agrees
WC23 | FWF | 5 | 5 | 9968955/119 | - | agrees
WC24 | FWF | 1 | 1 | 9968955/121 | - | agrees
WC25 | FWF | 1 | 1 | 9968955/118 | - | agrees
WC26 | FWF | 1 | 1 | 9968955/120 | - | agrees
WC27 | Toilet Block 6m | 1 | 1 | 9968955/52 | 2026-09-25 | agrees
WC27 | Waste tank | 1 | 1 | 9968955/54 | 2026-09-25 | agrees
WC28 | FWF | 1 | 1 | 9968955/123 | - | agrees
WC29 | FWF | 7 | 7 | 9968955/124 | - | agrees
WC30 | FWF | 8 | 8 | 9968955/125 | - | agrees
WC31 | Accessible Toilet | 1 | 1 | 9968955/97 | 2026-09-25 | agrees
WC31 | 16Pan Block | 2 | 2 | 9968955/98 | 2026-09-25 | agrees
WC33 | FWF | 17 | 17 | 9968955/101 | - | agrees
WC34 | FWF | 1 | 1 | 9968955/100 | - | agrees
WC35 | FWF | 1 | 1 | 9968955/126 | - | agrees
WC38 | FWF | 1 | 1 | 9968955/88 | 2026-10-13 | agrees
WC39 | FWF | 2 | 2 | 9968955/89 | 2026-10-13 | agrees
WC40 | FWF | 5 | 5 | 9968955/90 | 2026-10-13 | agrees
WC41 | FWF | 10 | 10 | 9968955/59 | 2026-09-28 | agrees
WC42 | FWF | 1 | 1 | 9968955/155 | 2026-09-28 | agrees
WC43 | FWF | 10 | 10 | 9968955/70 | 2026-09-28 | agrees
WC44 | FWF | 2 | 2 | 9968955/80, 9968955/81 | 2026-10-01 | agrees
WC45 | FWF | 8 | 8 | 9968955/115 | - | agrees
WC46 | FWF | 1 | 1 | 9968955/127 | - | agrees
WC47 | FWF | 1 | 1 | 9968955/116 | - | agrees
WC48 | FWF | 4 | 4 | 9968955/109 | - | agrees
WC49 | FWF | 3 | 3 | 9968955/108 | - | agrees
WC50 | FWF | 1 | 1 | 9968955/22 | 2026-09-23 | agrees
WC51 | FWF | 6 | 6 | 9968955/110 | 2026-10-15 | agrees
WC51 | Accessible Toilet | 1 | 1 | 9968955/111 | 2026-10-15 | agrees
WC53 | FWF | 3 | 3 | 9968955/156 | - | agrees
WC54 | FWF | 6 | 6 | 9968955/112 | - | agrees
WC55 | FWF | 1 | 1 | 9968955/128 | - | agrees
WC56 | FWF | 12 | 12 | 9968955/113 | - | agrees
WC57 | FWF | 2 | 2 | 9968955/107 | - | agrees
WC59 | FWF | 7 | 7 | 9968955/106 | - | agrees
WC60 | Toilet Block 6m | 2 | 2 | 9968955/91, 9968955/93 | 2026-10-01 | agrees
WC60 | Waste tank | 2 | 2 | 9968955/94, 9968955/95 | 2026-10-01 | agrees
WC61 | FWF | 8 | 8 | 9968955/96 | 2026-10-12 | agrees
WC62 | FWF | 2 | 2 | 9968955/129 | - | agrees
WC65 | FWF | 1 | 1 | 9968955/130 | - | agrees
WC67 | FWF | 4 | 3 | 9968955/84, 9968955/140 | 2026-10-01 | Baseplan 3, site 4
WC68 | FWF | 1 | 1 | 9968955/131 | 2026-10-13 | agrees
WC69 | FWF | 12 | 12 | 9968955/87 | 2026-10-12 | agrees
WC70 | FWF | 1 | 1 | 9968955/85 | - | agrees
WC71 | FWF | 8 | 8 | 9968955/86 | 2026-10-01 | agrees
WC72 | FWF | 1 | 1 | 9968955/132 | 2026-10-13 | agrees
WC73 | FWF | 2 | 2 | 9968955/133 | 2026-10-13 | agrees
WC81 | FWF | 1 | 1 | 9968955/157 | 2026-09-14 | agrees
WC85 | FWF | 1 | 1 | 9968955/134 | 2026-10-16 | agrees
WC86 | Accessible Toilet | 1 | 1 | 9968955/51 | 2026-10-07 | agrees
WC100 | FWF Trailer | 2 | 2 | 9968955/12, 9968955/13 | 2026-09-14 | agrees

## Water barriers
Reference | State | Turned up | On site | Baseplan | Baseplan lines | Verdict
WB01 | on site | 2026-09-14 | 12 | 12 | 9972648/1 12 | agrees
WB02 | on site | 2026-09-21 | 34 | 34 | 9972648/3 34 | agrees
WB03 | on site | 2026-09-23 | 30 | 30 | 9972648/2 30 | agrees
WB04 | on site | 2026-10-16 | 14 | 13 | 9972648/5 13 | Baseplan 13, site 14
WB05 | on site | 2026-10-16 | 13 | 12 | 9972648/4 12 | Baseplan 12, site 13
WB06 | on site | 2026-10-15 | 154 | 154 | 9972648/6 60; 9972648/16 60; 9972648/17 34 | agrees
WB07 | on site | 2026-10-21 | 17 | 0 |  | Baseplan 0, site 17
WB13 | on site | 2026-10-19 | 10 | 10 | 9990776/1 10 | agrees
WB14 | on site | 2026-10-21 | 2 | 2 | 9972648/9 2 | agrees
WB15 | on site | 2026-10-21 | 4 | 4 | 9972648/10 4 | agrees
WB16 | on site | 2026-10-21 | 13 | 13 | 9972648/11 13 | agrees
WB17 | on site | 2026-10-22 | 6 | 6 | 9972648/12 5; 9972648/21 1 | agrees
WB18 | on site | 2026-10-22 | 2 | 2 | 9972648/13 2 | agrees
WB19 | not on site | - | 34 | 34 | 9972648/15 34 | agrees
WB20 | not on site | - | 30 | 30 | 9972648/14 30 | agrees

## Charge lines
Contract | Line | Baseplan line | Baseplan qty | Price | Baseplan $ | Our count | Our $ at that price | Our basis (site record / P&L) | Verdict | Sales code | P&L branch
9968955 | 141 | Pumpout Service FWF & Accessable | 702 | 72.87 | 51154.74 | 702 | 51154.74 | 234 FWF and accessible on site (60 references, WC09/WC10 included) x 3 nights | agrees | KINP-TOI | KINP
9968955 | 142 | Pumpout Service Tank Mounts | 24 | 624.6 | 14990.4 | 24 | 14990.4 | 6 waste tanks + 2 sixteen-pan blocks (WC31) x 3 nights; the crews pump the 16-pans out every night (servicing tracker) | agrees with site; the P&L counts only the 6 tanks (18) and the 16-pans as sewer-connect cleans | KINP-TOI | KINP
9968955 | 143 | Cleaning & Restock Sewer Connect | 24 | 260.25 | 6246 | 27 | 7026.75 | 9 sewer-connected blocks: WC15, WC16, WC17 (2 each), WC09 (2, on 9994954) and T0243 WCTV (on 9973977) x 3 nights | Baseplan 24 = 8 blocks; the WCTV block (T0243) has no cleaning line on any contract | KINP-CLE | KINP
9968955 | 144 | Install Demob Toilet Blocks | 12 | 707.88 | 8494.56 | 12 | 8494.56 | 12 toilet blocks on the toilets contract (WC09 is on 9994954, WCTV on 9973977) | agrees | KINP-INS | KINP
9968955 | 160 | Install Demob 16 Pan | 2 | 551.73 | 1103.46 | 2 | 1103.46 | 16-pan blocks (WC31) | agrees | KINP-INS | KINP
9968955 | 145 | Labour Charge Accessable Install & Demob | 8 | 88.49 | 707.92 | 8 | 707.92 | 4 accessible toilets x 2 (install + demob) | agrees | KINP-INS | KINP
9968955 | 146 | Labour Charge FWF Install & Demob | 434 | 36.44 | 15814.96 | 434 | 15814.96 | 217 FWF on the toilets contract (Coates and Event Portables) x 2 | agrees | KINP-INS | KINP
9968955 | 147 | Transport Charge Blocks & 16 Pan | 28 | 500 | 14000 | 28 | 14000 | 14 blocks and 16-pans x 2 legs | agrees | KINP-FRI | KINP
9968955 | 148 | Transport Charge Accessable Toilets | 8 | 500 | 4000 | 8 | 4000 | 4 accessible x 2 legs | agrees | KINP-FRI | KINP
9968955 | 149 | Transport Charge FWF | 434 | 47.5 | 20615 | 434 | 20615 | 217 FWF x 2 legs (Event Portables units included at the Coates rate) | agrees | KINP-FRI | KINP
9968955 | 162 | Transport Charge Waste Tanks | 12 | 500 | 6000 | 12 | 6000 | 6 waste tanks x 2 legs | agrees | KINP-FRI | KINP
9994954 | 17 | Labour Charge Toilet Block | 2 | 707.88 | 1415.76 | 2 | 1415.76 | WC09 two blocks | agrees | KINP-INS | KINP
9994954 | 18 | Transport Charge Toilet Block | 4 | 500 | 2000 | 4 | 2000 | two blocks x 2 legs | agrees | KINP-FRI | KINP
9994954 | 20 | Labour Charge Pee Panel | 6 | 551.73 | 3310.38 | 6 | 3310.38 | six pee panels at WC09 | agrees | KINP-INS | KINP
9994954 | 23 | Labour Charge FWF | 13 | 72.88 | 947.44 | 13 | 947.44 | WC09 10 + WC10 3 FWF (one labour line each) | agrees | KINP-INS | KINP
9994954 | 24 | Transport Charge FWF | 26 | 47.5 | 1235 | 26 | 1235 | 13 FWF x 2 legs | agrees | KINP-FRI | KINP
9994954 | 5 | Install & Demob | 3 | 499.68 | 1499.04 | 3 | 1499.04 | P38, P39, P42 on site since 28 Sep, no steps | agrees | KINP-INS | KINP
9994954 | 6 | Transport Charge | 6 | 500 | 3000 | 6 | 3000 | three buildings x 2 legs | agrees | KINP-FRI | KINP
9994954 | 14 | Transport Charge Generators | 4 | 600 | 2400 | 4 | 2400 | GN26 + GN27 x 2 legs | agrees | KINP-FRI | NVAC
9968862 | 133 | Install & Demob | 38 | 655.83 | 24921.54 | 34 | 22298.22 | 38 buildings charged on site (AA and HRP tracked only; team buildings held out): CP1, P01, P03, P04, P05, P06, P08, P09, P10, P11, P12, P13, P14, P15, P16, P17, P18, P19, P20, P21, P33, P36, P37, P38, P39, P41, P42, P44, P45, P46, P51, P52, P54, P55, P56, P57, P58, P69; steps on all but P06, P38, P39, P42, P60, P62, P63 | Baseplan 38, ours 34 | KINP-INS | KINP
9968862 | 139 | Install & Demob (no steps) | 4 | 499.68 | 1998.72 | 1 | 499.68 | P06, P60, P62, P63 | Baseplan 4, ours 1 | KINP-INS | KINP
9968862 | 134 | Transport Charge up to 6m Buildings | 66 | 500 | 33000 | 52 | 26000 | 26 buildings up to 6 m on this contract x 2 legs | Baseplan 66, ours 52 | KINP-FRI | KINP
9968862 | 135 | Transport Charge 9.6m & 12m Building | 18 | 800 | 14400 | 18 | 14400 | 9 large buildings (P01, P03, P04, P17, P33, P46, P51, P52, P57) x 2 legs | agrees | KINP-FRI | KINP
9961976 | 51 | Labour Charge Generator | 11 | 300.22 | 3302.42 | 11 | 3302.42 | 11 sets up to 60 kVA on site: GN03, GN04, GN10, GN25, GN01, GN06, GN13, GN18, GN19, GN21, GN24 | agrees | NVAC-INS | NVAC
9961976 | 52 | Labour Charge Generator | 1 | 333.12 | 333.12 | 2 | 666.24 | 2 large sets on site: GN20-A, GN23 | Baseplan 1, ours 2 | NVAC-INS | NVAC
9961976 | 53 | Transport Charge | 6 | 309 | 1854 | 10 | 3090 | 4 sets up to 30 kVA (GN03, GN04, GN10, GN25) x 2 legs + 2 for each swap on our record (GN10) | Baseplan 6, ours 10 | NVAC-FRI | NVAC
9961976 | 54 | Transport Charge | 16 | 463.5 | 7416 | 14 | 6489 | 7 sets 45-60 kVA (GN01, GN06, GN13, GN18, GN19, GN21, GN24) x 2 legs | Baseplan 16, ours 14 | NVAC-FRI | NVAC
9961976 | 55 | Transport Charge | 2 | 600 | 1200 | 4 | 2400 | 2 large sets (GN20-A, GN23) x 2 legs | Baseplan 2, ours 4 | NVAC-FRI | NVAC
9961265 | 40 | Labour Charge | 24 | 176.97 | 4247.28 | 24 | 4247.28 | 24 boards | agrees | STPS-INS | STPS
9961265 | 41 | Transport Charge | 48 | 150 | 7200 | 48 | 7200 | 24 boards x 2 legs ($150 a leg is the branch figure; the card says POA) | agrees | STPS-FRI | STPS

## Event labour
Role (C004 scope) | Scope hours | Rate | Scope $ (P&L) | P&L branch | Baseplan hours | Baseplan $ | Baseplan lines
Project Manager | 30.75 | 150.11 | 4615.88 | KINP | 30.44 | 4569.35 | 9968862/141 KINP-INS, 9968955/164 KINP-INS
Gen Tech | 27.25 | 150.11 | 4090.5 | NVAC | 31.55 | 4735.97 | 9961976/56 NVAC-INS
Toilets | 27.25 | 91.14 | 2483.57 | KINP | 27.15 | 2474.45 | 9968955/165 KINP-INS
VMS board movements | 65.3333 | 91.14 | 5954.48 | STPS | 65 | 5924.1 | 9961265/44 STPS-INS
Fence team | 213 | 91.14 | 19412.82 | STPS | 0 | 0 | no line
Gen Tech — entertainment | 4.5 | 150.11 | 675.5 | NVAC | 4.5 | 675.5 | 9994954/25 KINP-INS
Toilets — entertainment | 4.5 | 91.14 | 410.13 | KINP | 4.5 | 410.13 | 9994954/26 KINP-INS
Accommodation, meals, travel |  |  | 19101.6 | KINP |  | 27700 | 9968862/140 + 9968955/163 KINP-MIS

## Fencing (9990776)
Category | Signed dockets (to 25 Oct) | Card rate | P&L $ | Baseplan lines | Baseplan qty | Baseplan rate | Baseplan $
Fence, no scrim (m): line 3 at $16.16 + hoarding line 5 at $23.59 | 9325 | 16.1607 | 150698.53 | 3 + 5 | 8888 | 16.16 | 144447.38
Fence with scrim (m): fence line 6 + shade cloth line 10 | 3977.5 | 25.53 | 101545.58 | 6 + 10 | 2775 | 25.53 | 70845.75
Crowd control barrier (m) | 2195 | 7.51 | 16484.45 | 7 | 2350 | 7.51 | 17648.5
CCB flat feet | 270 | 9.6511 | 2605.8 | 8 | 220 | 7.51 | 1652.2
Demarcation CCB (m) | 5062.5 | 13.08 | 66217.5 | 9 | 4603 | 13.08 | 60207.24
Pedestrian gates | 22 | 36.1839 | 796.05 | 2 | 32 | 36.18 | 1157.76
Fence relocation (m) | 137.5 | 8.652 | 1189.65 | 4 | 1520 | 8.65 | 13148
Fence blocks | 216 | 3.02 | 652.32 | no line | 0
Fencing labour (h) | 8.5 | 142 | 1207 | no line | 0
Total |  |  | 365341.63 |  |  |  | 309106.83

## Generators
Contract | Line | Baseplan line | Asset | Reference | Turned up | Baseplan start | Baseplan rate | P&L charge | P&L basis | Sales code
9961976 | 6 | GN20-S01-Generator 365kVA Diesel | 1276701 | GN20-A | 2026-09-30 | 2026-09-30 | 6260.4 | 6840.83 | Street Rate Card 2026 · Generator 315 kVA · next size down from 350 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 7 | GN19-Generator - Diesel - 80kVA DEL AS 60KVA | 1276416 | GN19 | 2026-10-19 | 2026-10-19 | 1254.5 | 965.01 | Street Rate Card 2026 · Generator 60 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 9 | GN23-Generator - Sync - Hardwire Only 150kVA Diese | 1297157 | GN23 | 2026-09-30 | 2026-09-30 | 2412.54 | 3886.83 | Street Rate Card 2026 · Generator 150 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 10 | GN03-Generator - 30kVA (Diesel) | 1320829 | GN03 | 2026-10-01 | 2026-10-01 | 1132.28 | 1981.47 | Street Rate Card 2026 · Generator 30 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 11 | GN18-Generator - 60kVA (Diesel) | 1261273 | GN18 | 2026-10-07 | 2026-10-07 | 2187.36 | 2005.07 | Street Rate Card 2026 · Generator 50 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 14 | GN04-Generator - 30kVA (Diesel) | 1277400 | GN04 | - | 2026-10-19 | 919.97 | 707.67 | Street Rate Card 2026 · Generator 30 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 15 | G10- Generator - 60kVA (Diesel) | 1283681 | GN10 | - | 2026-10-19 | 1142.96 | 611.16 | Street Rate Card 2026 · Generator 20 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 16 | GN01-Generator - 60kVA (Diesel) | 1276507 | GN01 | 2026-09-28 | 2026-09-28 | 1544 | 2991.52 | Street Rate Card 2026 · Generator 60 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 18 | GN25-Generator - 20kVA (Diesel) | 1244536 | GN25 | 2026-10-19 | 2026-10-19 | 855.63 | 611.16 | Street Rate Card 2026 · Generator 20 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 38 | GN21-Generator - 60kVA (Diesel) | 1261284 | GN21 | 2026-09-30 | 2026-09-30 | 868.5 | 2798.52 | Street Rate Card 2026 · Generator 60 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 44 | GN13 Generator - 60kVA (Diesel) DEL AS 45KVA | 1276503 | GN13 | - | 2026-10-12 | 1406.72 | 1494.68 | Street Rate Card 2026 · Generator 45 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 48 | GN06 Generator - 60kVA (Diesel) | 1320828 | GN06 | - | 2026-10-15 | 1168.72 | 1275.95 | Street Rate Card 2026 · Generator 50 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9961976 | 49 | GN24-Generator - 60kVA (Diesel) - Trailer Mounted | 1277089 | GN24 | - | 2026-10-19 | 984.33 | 965.01 | Street Rate Card 2026 · Generator 60 kVA · published Standby Rate before 23 Oct | NVAC-HIR
9994954 | 10 | GN26 Generator - 200kVA (Diesel) | 1316182 | GN? | 2026-10-12 | 2026-10-12 | 2005.08 | 3098.74 | Street Rate Card 2026 · Generator 200 kVA · published Standby Rate before 23 Oct | KINP-HIR
9994954 | 11 | GN27 Generator - 200kVA (Diesel) | 1316183 | GN? | 2026-10-12 | 2026-10-12 | 2551.92 | 3098.74 | Street Rate Card 2026 · Generator 200 kVA · published Standby Rate before 23 Oct | KINP-HIR

## On site, no line
Reference | Item | Asset no | Turned up | P&L branch
AA | Building 6m | 142514 | 2026-09-17 | KINP
HRP | Building 6m | 1189410 | 2026-09-17 | KINP

## Branch tie-out
Branch | P&L revenue, current record | P&L revenue, job total | Baseplan to move (fixes with a $ figure) | Waiting on a decision | Made up of
KINP | 415919.18 | 415919.18 | 14696.33 | -8598.4 | Baseplan · Hours: $55.65; Baseplan · Missing line: $14,730.75; Baseplan · Remove: $-90.07; Decision · Amount: $-8,598.40
NVAC | 90269.38 | 90269.38 | 5196.57 | 28671.82 | Baseplan · Hours: $-645.47; Baseplan · Quantity: $1,842.12; Baseplan · Rate: $3,999.92; Decision · Rate: $28,671.82
STPS | 470314.64 | 496837.04 | 51900.34 | 0 | Baseplan · Hours: $30.38; Baseplan · Missing line: $21,272.14; Baseplan · Quantity: $30,663.04; Baseplan · Rate: $578.10; Baseplan · Start date: $-643.32
MEAD | 19628.72 | 19628.72 | 0 | 0
All | 996131.92 | 1022654.32 | 71793.24 | 20073.42

## Start dates
Contract | Line | Baseplan line | Baseplan start | Turned up (site) | Days | Charged from when it goes in | Basis
9987005 | 1 | Supply Forklift 5.0t Diesel | Mon 05 Oct | Mon 28 Sep | 7 | yes | T0085 on site on the record
9987005 | 2 | Supply Telehandler Fork Extension 1800mm | Mon 05 Oct | Fri 23 Oct | -18 | yes | EQ0005 on site on the record
9987005 | 7 | Forklift Rough Terrain 2.5t 4WD Diesel | Tue 13 Oct | Mon 28 Sep | 15 | yes | T0109 on site on the record
9987005 | 8 | Laserplane | Fri 16 Oct | Sun 25 Oct | -9 | no - over the event; record only | EQ0006 on site on the record
9968955 | 15 | WC06 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Wed 23 Sep | -9 | no - over the event; record only | WC06 on site on the record
9968955 | 22 | WC50 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Wed 23 Sep | -9 | no - over the event; record only | WC50 on site on the record
9968955 | 24 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 25 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 26 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 27 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 28 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 29 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 30 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 31 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 32 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 33 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 34 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 35 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 36 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 37 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 38 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 39 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 40 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 41 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 42 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 43 | WC07 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC07 on site on the record
9968955 | 44 | WC04 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC04 on site on the record
9968955 | 45 | WC02 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | WC02 on site on the record
9968955 | 46 | WC01 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Mon 28 Sep | -14 | no - over the event; record only | WC01 on site on the record
9968955 | 47 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3 | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | WC20 on site on the record
9968955 | 48 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3 | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | WC20 on site on the record
9968955 | 49 | WC20 Sewage Holding Tank 6.0M x 2.4M | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | WC20 on site on the record
9968955 | 50 | WC20 Sewage Holding Tank 6.0M x 2.4M | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | WC20 on site on the record
9968955 | 51 | Wc86 Toilet - Disabled Access | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | WC86 on site on the record
9968955 | 52 | WC27 Toilet Block 6.0M x 3.0M | Mon 14 Sep | Fri 25 Sep | -11 | no - over the event; record only | WC27 on site on the record
9968955 | 54 | WC27 Sewage Holding Tank 6.0M x 2.4M | Mon 14 Sep | Fri 25 Sep | -11 | no - over the event; record only | WC27 on site on the record
9968955 | 55 | WC15 Toilet Block Male Female Cyclone Rated 6m x 3 | Mon 14 Sep | Fri 25 Sep | -11 | no - over the event; record only | WC15 on site on the record
9968955 | 56 | WC15 Toilet Block Male Female Cyclone Rated 6m x 3 | Mon 14 Sep | Fri 25 Sep | -11 | no - over the event; record only | WC15 on site on the record
9968955 | 57 | WC01 Toilet - Accessible | Mon 14 Sep | Mon 28 Sep | -14 | no - over the event; record only | WC01 on site on the record
9968955 | 58 | WC06 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Wed 23 Sep | -9 | no - over the event; record only | WC06 on site on the record
9968955 | 59 | WC41 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Mon 28 Sep | -14 | no - over the event; record only | WC41 on site on the record
9968955 | 69 | WC01 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Mon 28 Sep | -14 | no - over the event; record only | WC01 on site on the record
9968955 | 70 | WC43 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Mon 28 Sep | -14 | no - over the event; record only | WC43 on site on the record
9968955 | 80 | WC44 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Thu 01 Oct | -17 | no - over the event; record only | WC44 on site on the record
9968955 | 81 | WC44 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Thu 01 Oct | -17 | no - over the event; record only | WC44 on site on the record
9968955 | 84 | WC67 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Thu 01 Oct | -17 | no - over the event; record only | WC67 on site on the record
9968955 | 86 | WC71 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Thu 01 Oct | -17 | no - over the event; record only | WC71 on site on the record
9968955 | 87 | WC69 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Mon 12 Oct | -28 | no - over the event; record only | WC69 on site on the record
9968955 | 88 | WC38 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 13 Oct | -29 | no - over the event; record only | WC38 on site on the record
9968955 | 89 | WC39 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 13 Oct | -29 | no - over the event; record only | WC39 on site on the record
9968955 | 90 | WC40 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 13 Oct | -29 | no - over the event; record only | WC40 on site on the record
9968955 | 91 | WC60 Toilet Block 6.0M x 3.0M | Mon 14 Sep | Thu 01 Oct | -17 | no - over the event; record only | WC60 on site on the record
9968955 | 93 | WC60 Toilet Block 6.0M x 3.0M | Mon 14 Sep | Thu 01 Oct | -17 | no - over the event; record only | WC60 on site on the record
9968955 | 94 | WC60 Sewage Holding Tank 6.0M x 2.4M | Mon 14 Sep | Thu 01 Oct | -17 | no - over the event; record only | WC60 on site on the record
9968955 | 95 | WC60 Sewage Holding Tank 6.0M x 2.4M | Mon 14 Sep | Thu 01 Oct | -17 | no - over the event; record only | WC60 on site on the record
9968955 | 96 | WC61 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Mon 12 Oct | -28 | no - over the event; record only | WC61 on site on the record
9968955 | 97 | WC31 Toilet - Accessible | Mon 14 Sep | Fri 25 Sep | -11 | no - over the event; record only | WC31 on site on the record
9968955 | 98 | WC31 16 Pan Block | Mon 14 Sep | Fri 25 Sep | -11 | no - over the event; record only | WC31 on site on the record
9968955 | 110 | WC51 FWF Toilet | Mon 14 Sep | Thu 15 Oct | -31 | no - over the event; record only | WC51 on site on the record
9968955 | 111 | WC51 Toilet - Accessible | Mon 14 Sep | Thu 15 Oct | -31 | no - over the event; record only | WC51 on site on the record
9968955 | 117 | WC19 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Fri 16 Oct | -32 | no - over the event; record only | WC19 on site on the record
9968955 | 131 | WC68 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 13 Oct | -29 | no - over the event; record only | WC68 on site on the record
9968955 | 132 | WC72 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 13 Oct | -29 | no - over the event; record only | WC72 on site on the record
9968955 | 133 | WC73 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Tue 13 Oct | -29 | no - over the event; record only | WC73 on site on the record
9968955 | 134 | WC85 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Fri 16 Oct | -32 | no - over the event; record only | WC85 on site on the record
9968955 | 140 | WC67 Toilet Portable - Fresh Water Flush | Mon 14 Sep | Thu 01 Oct | -17 | no - over the event; record only | WC67 on site on the record
9968955 | 151 | PG01 FWF Toilet | Thu 22 Oct | Fri 16 Oct | 6 | no - over the event; record only | PG01 on site on the record
9968955 | 152 | PG03 FWF Toilet | Thu 22 Oct | Fri 16 Oct | 6 | no - over the event; record only | PG03 on site on the record
9968955 | 155 | WC42 FWF Toilet | Thu 22 Oct | Mon 28 Sep | 24 | no - over the event; record only | WC42 on site on the record
9968955 | 157 | WC81 FWF Toilet | Thu 22 Oct | Mon 14 Sep | 38 | no - over the event; record only | WC81 on site on the record
9968955 | 158 | WC12 Toilet Portable - Fresh Water Flush | Thu 22 Oct | Mon 14 Sep | 38 | no - over the event; record only | WC12 on site on the record
9968929 | 1 | Portable Building Shell 4.8M x 3.0M | Mon 14 Sep | Wed 16 Sep | -2 | no - over the event; record only | T0021 on site on the record
9968929 | 7 | Toilet Portable - Fresh Water Flush | Mon 14 Sep | Sat 26 Sep | -12 | no - over the event; record only | T0024 on site on the record
9968862 | 28 | P09 Portable Building Shell 6.0M x 3.0M - Cyclonic | Mon 14 Sep | Wed 16 Sep | -2 | no - over the event; record only | P09 on site on the record
9968862 | 33 | P17 Portable Building Shell Cyclone Rated 9.6m x 3 | Mon 14 Sep | Wed 16 Sep | -2 | no - over the event; record only | P17 on site on the record
9968862 | 34 | P19 Portable Building Shell 6.0M x 3.0M | Mon 14 Sep | Wed 16 Sep | -2 | no - over the event; record only | P19 on site on the record
9968862 | 36 | P18 Portable Building Shell 4.8M x 2.4M | Mon 14 Sep | Wed 16 Sep | -2 | no - over the event; record only | P18 on site on the record
9968862 | 38 | P20 Portable Building Shell 4.8M x 2.4M | Mon 14 Sep | Wed 16 Sep | -2 | no - over the event; record only | P20 on site on the record
9968862 | 44 | P10 Portable Building Shell 4.8M x 2.4M | Mon 14 Sep | Thu 17 Sep | -3 | no - over the event; record only | P10 on site on the record
9968862 | 46 | P11 Portable Building Shell 4.8M x 2.4M | Mon 14 Sep | Thu 17 Sep | -3 | no - over the event; record only | P11 on site on the record
9968862 | 48 | P12 Portable Building Shell 4.8M x 2.4M | Mon 14 Sep | Thu 17 Sep | -3 | no - over the event; record only | P12 on site on the record
9968862 | 50 | P37 Portable Building Shell 6.0M x 3.0M | Mon 14 Sep | Thu 17 Sep | -3 | no - over the event; record only | P37 on site on the record
9968862 | 51 | P13 Portable Building Shell 4.8M x 2.4M | Mon 14 Sep | Mon 21 Sep | -7 | no - over the event; record only | P13 on site on the record
9968862 | 53 | P14 Portable Building Shell 4.8M x 2.4M | Mon 14 Sep | Mon 21 Sep | -7 | no - over the event; record only | P14 on site on the record
9968862 | 55 | P15 Portable Building Shell 4.8M x 2.4M | Mon 14 Sep | Mon 21 Sep | -7 | no - over the event; record only | P15 on site on the record
9968862 | 57 | P16 Portable Building Shell 4.8M x 2.4M | Mon 14 Sep | Mon 21 Sep | -7 | no - over the event; record only | P16 on site on the record
9968862 | 59 | P58 Portable Building Shell 6.0M x 3.0M - Cyclonic | Mon 14 Sep | Wed 23 Sep | -9 | no - over the event; record only | P58 on site on the record
9968862 | 61 | P44 Portable Building Shell 6.0M x 3.0M | Mon 14 Sep | Thu 24 Sep | -10 | no - over the event; record only | P44 on site on the record
9968862 | 63 | P41 Portable Building Shell 6.0M x 3.0M | Mon 14 Sep | Tue 22 Sep | -8 | no - over the event; record only | P41 on site on the record
9968862 | 64 | P06 Portable Building Shell 6.0M x 3.0M | Mon 14 Sep | Mon 28 Sep | -14 | no - over the event; record only | P06 on site on the record
9968862 | 79 | P52 Portable Building Shell 12.0M x 3.0M - Cycloni | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | P52 on site on the record
9968862 | 85 | P54 Portable Building Shell 6.0M x 3.0M - Cyclonic | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | P54 on site on the record
9968862 | 87 | P55 Ticket Office 6.0Mx3.0M | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | P55 on site on the record
9968862 | 89 | P56 Portable Building Shell Cyclone Rated 3.6m x 2 | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | P56 on site on the record
9968862 | 90 | P57 Portable Building Shell Cyclone Rated 9.6m x 3 | Mon 14 Sep | Wed 07 Oct | -23 | no - over the event; record only | P57 on site on the record
9968862 | 92 | P21 Portable Building Shell 6.0M x 3.0M - Cyclonic | Mon 14 Sep | Wed 16 Sep | -2 | no - over the event; record only | P21 on site on the record
9968862 | 93 | P36 Portable Building Shell 6.0M x 3.0M | Mon 14 Sep | Thu 17 Sep | -3 | no - over the event; record only | P36 on site on the record
9968862 | 94 | P51 Portable Building Shell 12.0M x 3.0M - Cycloni | Mon 14 Sep | Tue 06 Oct | -22 | no - over the event; record only | P51 on site on the record
9968862 | 100 | P46 Portable Building Shell 12.0M x 3.0M - Cycloni | Mon 14 Sep | Tue 06 Oct | -22 | no - over the event; record only | P46 on site on the record
9968862 | 103 | P69 Portable Building Shell 6.0M x 3.0M | Mon 14 Sep | Mon 12 Oct | -28 | no - over the event; record only | P69 on site on the record
9968862 | 126 | P08 Portable Building Shell 6.0M x 3.0M | Mon 14 Sep | Tue 06 Oct | -22 | no - over the event; record only | P08 on site on the record
9968862 | 131 | P45 Portable Building Shell 6.0M x 3.0M | Mon 14 Sep | Mon 12 Oct | -28 | no - over the event; record only | P45 on site on the record
9974042 | 1 | Container 3.0M x 2.4M | Mon 28 Sep | Wed 07 Oct | -9 | no - over the event; record only | T0258 on site on the record
9974042 | 2 | Container - Refrigerated 6.0M x 2.4M | Mon 28 Sep | Tue 13 Oct | -15 | no - over the event; record only | T0266 on site on the record
9961976 | 25 | COATES Forklift Rough Terrain 2.5t With Switchable | Fri 11 Sep | Mon 14 Sep | -3 | no - over the event; record only | T0005 on site on the record
9961976 | 26 | COATES Forklift Rough Terrain 4WD With Rotator 2.5 | Fri 11 Sep | Mon 14 Sep | -3 | no - over the event; record only | T0005 on site on the record
9961976 | 31 | COATES- 5T FORKLIFT 1.8TYNNES | Fri 11 Sep | Fri 25 Sep | -14 | no - over the event; record only | FL01 on site on the record
9961976 | 35 | COATES-Forklift Rough Terrain 2.5t With Switchable | Mon 19 Oct | Mon 14 Sep | 35 | no - over the event; record only | T0005 on site on the record
9972648 | 2 | WB03 Barrier - Crash Rated Water filled - Armorzon | Fri 18 Sep | Wed 23 Sep | -5 | yes | WB03 on site on the record
9961265 | 34 | VMS14 Variable Message Board Junior | Mon 19 Oct | Fri 16 Oct | 3 | yes | recorded on site (load T0158)
9961265 | 35 | VMS15 Variable Message Board Senior | Mon 19 Oct | Fri 16 Oct | 3 | yes | recorded on site (load T0158)
9961265 | 37 | VMS16 Variable Message Board Senior | Mon 19 Oct | Fri 16 Oct | 3 | yes | recorded on site (load T0158)
9961265 | 39 | VMS17 Variable Message Board Senior | Mon 19 Oct | Fri 16 Oct | 3 | yes | recorded on site (load T0158)
9992300 | 3 | Fork Extensions 2.4m | Sat 17 Oct | Fri 23 Oct | -6 | no - over the event; record only | EQ0005 on site on the record
9992300 | 4 | Scissor Lift With Operator Protection 43ft (13.0M) | Mon 19 Oct | Thu 22 Oct | -3 | yes | EQ0001 on site on the record
9994954 | 1 | P38 Portable Building Shell 6.0M x 3.0M - Cyclonic | Fri 23 Oct | Mon 28 Sep | 25 | no - over the event; record only | P38 on site on the record
9994954 | 3 | P39 Portable Building Shell 6.0M x 3.0M - Cyclonic | Fri 23 Oct | Mon 28 Sep | 25 | no - over the event; record only | P39 on site on the record
9994954 | 4 | P42 Portable Building Shell 6.0M x 3.0M - Cyclonic | Fri 23 Oct | Mon 28 Sep | 25 | no - over the event; record only | P42 on site on the record
9994954 | 15 | WC09 Toilet Block 6.0M x 3.0M - CAT 2 | Fri 23 Oct | Thu 08 Oct | 15 | no - over the event; record only | WC09 on site on the record
9994954 | 16 | WC09 Toilet Block Male Female Cyclone Rated 6m x 3 | Fri 23 Oct | Thu 08 Oct | 15 | no - over the event; record only | WC09 on site on the record
9994954 | 19 | Pee Panels | Fri 23 Oct | Thu 08 Oct | 15 | no - over the event; record only | WC09 on site on the record
9994954 | 21 | WC09 FWF Toilet | Fri 23 Oct | Thu 08 Oct | 15 | no - over the event; record only | WC09 on site on the record
9994954 | 22 | WC10 FWF Toilet | Fri 23 Oct | Tue 13 Oct | 10 | no - over the event; record only | WC10 on site on the record
9997711 | 3 | Fridge Freezer | Tue 20 Oct | Sat 17 Oct | 3 | no - over the event; record only | FR02 on site on the record

## Since 25 Oct
Contract | Line | Change | Description | Detail
1000047 | 1 | added | Scrim 50m roll | Pending ¦ MISCCONS ¦ qty 28 ¦ rate 82.01 ¦ STPS-CON ¦ start 2026-10-23
1000048 | 1 | added | Scrim 50m roll | Delivered ¦ MISCCONS ¦ qty 12 ¦ rate 82.01 ¦ STPS-CON ¦ start 2026-10-23
1000048 | 2 | added | Scrim 50m Roll | Delivered ¦ MISCCONS ¦ qty 10 ¦ rate 95 ¦ STPS-CON ¦ start 2026-10-27
1000048 | 3 | added | Transport Charge for 10x rolls | Delivered ¦ TRANSPORT ¦ qty 1 ¦ rate 150 ¦ STPS-FRI ¦ start 2026-10-27
1000050 | 1 | added | Toilet Paper | Delivered ¦ MISCCONS ¦ qty 55 ¦ rate 84.5 ¦ KINP-CON ¦ start 2026-10-27
1000050 | 2 | added | Hand Towel | Delivered ¦ MISCCONS ¦ qty 21 ¦ rate 98.9 ¦ KINP-CON ¦ start 2026-10-27
1000052 | 1 | added | P68 Hydration Station | Delivered ¦ MISCITEMS ¦ qty 1 ¦ rate 77.54 ¦ KINP-HIR ¦ start 2026-09-14
1000052 | 10 | added | Pickup Charge For Track Mat | Quoted ¦ PICKUP CHARGE ¦ qty 1 ¦ rate 150 ¦ KINP-FRI ¦ start 2026-10-27
1000052 | 11 | added | Site Shift Supply Container | Delivered ¦ TRANSPORT ¦ qty 1 ¦ rate 500 ¦ KINP-FRI ¦ start 2026-10-27
1000052 | 2 | added | Water Charges | Delivered ¦ WATER ¦ qty 1 ¦ rate 450.34 ¦ KINP-CON ¦ start 2026-10-27
1000052 | 3 | added | Transport Charge Hydration Station | Delivered ¦ TRANSPORT ¦ qty 2 ¦ rate 443.93 ¦ KINP-FRI ¦ start 2026-10-27
1000052 | 4 | added | Trakmat - 2.4M x 1.1M - TM4496 | Delivered ¦ TRAKMAT2.4X1.1 ¦ qty 20 ¦ rate 4.83 ¦ KINP-HIR ¦ start 2026-09-15
1000052 | 5 | added | Transport Charge 20x matts | Delivered ¦ TRANSPORT ¦ qty 1 ¦ rate 150 ¦ KINP-FRI ¦ start 2026-10-27
1000052 | 6 | added | Trakmat - 2.4M x 1.1M - TM4496 | Delivered ¦ TRAKMAT2.4X1.1 ¦ qty 20 ¦ rate 4.83 ¦ KINP-HIR ¦ start 2026-10-16
1000052 | 7 | added | Transport Charge 16/10 20x | Delivered ¦ TRANSPORT ¦ qty 1 ¦ rate 275 ¦ KINP-FRI ¦ start 2026-10-27
1000052 | 8 | added | Trakmat - 2.4M x 1.1M - TM4496 | Delivered ¦ TRAKMAT2.4X1.1 ¦ qty 37 ¦ rate 4.83 ¦ KINP-HIR ¦ start 2026-10-27
1000052 | 9 | added | Transport Charge 37x 19/10 | Delivered ¦ TRANSPORT ¦ qty 1 ¦ rate 275 ¦ KINP-FRI ¦ start 2026-10-27
9961976 | 58 | added | Labour Charge Light Tower | Pending ¦ LABOUR ¦ qty 7 ¦ rate 182.28 ¦ NVAC-INS ¦ start 2026-10-27
9961976 | 59 | added | Transport Charge Light Towers | Pending ¦ TRANSPORT ¦ qty 14 ¦ rate 154.5 ¦ NVAC-FRI ¦ start 2026-10-27
9961976 | 60 | added | Labour Charge 350KVA | Pending ¦ LABOUR ¦ qty 1 ¦ rate 333.12 ¦ NVAC-INS ¦ start 2026-10-27
9972648 | 19 | added | Labour Charge WFB | Pending ¦ LABOUR ¦ qty 1 ¦ rate 7700 ¦ STPS-INS ¦ start 2026-10-25
9972648 | 20 | added | Transport Charge WFB | Pending ¦ TRANSPORT ¦ qty 1 ¦ rate 17900 ¦ STPS-FRI ¦ start 2026-10-25
9972648 | 21 | added | WB17 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Delivered ¦ ARMORZONMASHTL2 ¦ qty 1 ¦ rate 1.18 ¦ STPS-HIR ¦ start 2026-10-22
9990776 | 11 | added | Weed Mat 50m roll | Pending ¦ SHADECLOTH ¦ qty 40 ¦ rate 79.62 ¦ STPS-CON ¦ start 2026-10-22
9990776 | 12 | added | Weed Mat | Del Req ¦ SHADECLOTH ¦ qty 10 ¦ rate 95 ¦ STPS-CON ¦ start 2026-10-22
9990776 | 13 | added | Transport Charge 10x rolls scrim | Pending ¦ TRANSPORT ¦ qty 1 ¦ rate 150 ¦ STPS-FRI ¦ start 2026-10-25
9990776 | 14 | added | Event Labour Charge | Pending ¦ LABOUR ¦ qty 213 ¦ rate 91.14 ¦ STPS-INS ¦ start 2026-10-25
9997710 | 1 | added | 1.8m Fence | Pending ¦ TEMPFENCEFEETRH ¦ qty 144 ¦ rate 0.12 ¦ STPS-HIR ¦ start 2026-10-17
9997710 | 2 | added | Shade Cloth | Pending ¦ SHADECLOTH ¦ qty 144 ¦ rate 9.37 ¦ STPS-CON ¦ start 2026-10-17
9997711 | 1 | added | Refrigerator - Large | Delivered ¦ 1129733 ¦ qty 1 ¦ rate 46.84 ¦ KINP-HIR ¦ start 2026-10-20
9997711 | 2 | added | Transport Charge | Delivered ¦ TRANSPORT ¦ qty 2 ¦ rate 97.69 ¦ KINP-FRI ¦ start 2026-10-20
9997711 | 3 | added | Fridge Freezer | Delivered ¦ 1157786 ¦ qty 1 ¦ rate 46.84 ¦ KINP-HIR ¦ start 2026-10-20
9961265 | 15 | changed | VMS11 467T Variable Message Board - Premiair | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Term Time: None -> 14:00:00
9961265 | 26 | changed | VMS20 475T Variable Message Board Senior Premiair | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Term Time: None -> 14:00:00
9961265 | 29 | changed | VMS22 445T Variable Message Board Senior Premiair | Start Date: 2026-10-21T00:00:00 -> 2026-10-22T00:00:00
9961265 | 31 | changed | VMS24 450T Variable Message Board Senior | Start Date: 2026-10-19T00:00:00 -> 2026-10-22T00:00:00
9961265 | 43 | changed | VMS05a Variable Message Board Senior | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Term Time: None -> 14:00:00
9961976 | 1 | changed | LT01 MOLENDINAR Lighting Tower LED Metro | Billed Units: 0 -> 47; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 643.3; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 796.08
9961976 | 10 | changed | GN03-Generator - 30kVA (Diesel) | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-28T00:00:00; Billed Units: 0 -> 27; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 1132.28; Billed To Date: None -> 2026-10-28T00:00:00; Term Time: None -> 07:00:00; Tot(inc.SD,DW&GST): 0 -> 1401.2
9961976 | 11 | changed | GN18-Generator - 60kVA (Diesel) | Billed Units: 0 -> 21; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 2187.36; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 2706.86
9961976 | 14 | changed | GN04-Generator - 30kVA (Diesel) | Status: Off Rent -> Return Pending; Billed Units: 0 -> 7; Billed To Time: None -> 09:00:00; Billed Amount: 0 -> 919.97; Billed To Date: None -> 2026-10-26T00:00:00; Tot(inc.SD,DW&GST): 0 -> 1138.47
9961976 | 15 | changed | G10- Generator - 60kVA (Diesel) | Status: Off Rent -> Returned; Return Number: None -> 21966376; Billed Units: 0 -> 7; Billed To Time: None -> 16:00:00; Billed Amount: 0 -> 1142.96; Billed To Date: None -> 2026-10-25T00:00:00; Tot(inc.SD,DW&GST): 0 -> 1414.41
9961976 | 16 | changed | GN01-Generator - 60kVA (Diesel) | Billed Units: 0 -> 30; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 1544; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 1910.7
9961976 | 18 | changed | GN25-Generator - 20kVA (Diesel) | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Billed Units: 0 -> 7; Billed To Time: None -> 06:00:00; Billed Amount: 0 -> 855.63; Billed To Date: None -> 2026-10-26T00:00:00; Term Time: None -> 06:00:00; Tot(inc.SD,DW&GST): 0 -> 1058.84
9961976 | 19 | changed | LT05/06-Lighting Tower POD Metro | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Billed Units: 0 -> 6; Billed To Time: None -> 06:00:00; Billed Amount: 0 -> 385.98; Billed To Date: None -> 2026-10-26T00:00:00; Term Time: None -> 06:00:00; Tot(inc.SD,DW&GST): 0 -> 477.65
9961976 | 2 | changed | LT02 MOLENDINAR Lighting Tower LED Metro | Billed Units: 0 -> 47; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 643.3; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 796.08
9961976 | 20 | changed | LT05/06-Lighting Tower POD Metro | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Billed Units: 0 -> 6; Billed To Time: None -> 06:00:00; Billed Amount: 0 -> 385.98; Billed To Date: None -> 2026-10-26T00:00:00; Term Time: None -> 06:00:00; Tot(inc.SD,DW&GST): 0 -> 477.65
9961976 | 3 | changed | LT03 MOLENDINAR Lighting Tower LED 76500lm Hybrid | Billed Units: 0 -> 47; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 643.3; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 796.08
9961976 | 38 | changed | GN21-Generator - 60kVA (Diesel) | Billed Units: 0 -> 28; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 868.5; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 1074.77
9961976 | 4 | changed | LT04 MOLENDINAR Lighting Tower LED Metro | Billed Units: 0 -> 47; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 643.3; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 796.08
9961976 | 44 | changed | GN13 Generator - 60kVA (Diesel) DEL AS 45KVA | Status: Delivered -> Return Pending; Term Date: None -> 2026-10-26T00:00:00; Billed Units: 0 -> 14; Billed To Time: None -> 06:00:00; Billed Amount: 0 -> 1406.72; Billed To Date: None -> 2026-10-26T00:00:00; Term Time: None -> 06:00:00; Tot(inc.SD,DW&GST): 0 -> 1740.82
9961976 | 48 | changed | GN06 Generator - 60kVA (Diesel) | Rate 1: 1184.82 -> 1168.72; Billed Units: 0 -> 11; Billed To Time: None -> 16:00:00; Billed Amount: 0 -> 1168.72; Billed To Date: None -> 2026-10-25T00:00:00; Start Date: 2026-10-19T00:00:00 -> 2026-10-15T00:00:00; Tot(inc.SD,DW&GST): 0 -> 1446.29
9961976 | 49 | changed | GN24-Generator - 60kVA (Diesel) - Trailer Mounted | Status: Off Rent -> Returned; Return Number: None -> 21966418; Billed Units: 0 -> 7; Billed To Time: None -> 09:00:00; Billed Amount: 0 -> 984.33; Billed To Date: None -> 2026-10-26T00:00:00; Tot(inc.SD,DW&GST): 0 -> 1218.11
9961976 | 5 | changed | LT09 Lighting Tower LED 76500lm Hybrid | Billed Units: 0 -> 47; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 643.3; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 796.08; Description: MOLENDINAR Lighting Tower LED 76500lm Hybrid -> LT09 Lighting Tower LED 76500lm Hybrid
9961976 | 51 | changed | Labour Charge Generator | Billed Amount: 0 -> 3302.42; Billed To Date: None -> 2026-10-27T00:00:00; Price: 291.48 -> 300.22; Tot(inc.SD,DW&GST): 0 -> 3632.66; Billed To Time: None -> 14:26:00; Description: Labour Charge -> Labour Charge Generator
9961976 | 52 | changed | Labour Charge Generator | Billed Amount: 0 -> 333.12; Billed To Date: None -> 2026-10-27T00:00:00; Tot(inc.SD,DW&GST): 0 -> 366.43; Billed To Time: None -> 14:26:00; Description: Labour Charge -> Labour Charge Generator; Quantity: 2 -> 1
9961976 | 53 | changed | Transport Charge | Billed Amount: 0 -> 1854; Billed To Date: None -> 2026-10-27T00:00:00; Price: 300 -> 309; Tot(inc.SD,DW&GST): 0 -> 2039.4; Billed To Time: None -> 14:26:00; Quantity: 10 -> 6
9961976 | 54 | changed | Transport Charge | Billed Amount: 0 -> 7416; Billed To Date: None -> 2026-10-27T00:00:00; Price: 450 -> 463.5; Tot(inc.SD,DW&GST): 0 -> 8157.6; Billed To Time: None -> 14:26:00; Quantity: 14 -> 16
9961976 | 55 | changed | Transport Charge | Billed Amount: 0 -> 1200; Billed To Date: None -> 2026-10-27T00:00:00; Tot(inc.SD,DW&GST): 0 -> 1320; Billed To Time: None -> 14:26:00
9961976 | 56 | changed | Labour Charge Event Gen Tech | Billed Amount: 0 -> 4735.97; Billed To Date: None -> 2026-10-27T00:00:00; Tot(inc.SD,DW&GST): 0 -> 5209.57; Billed To Time: None -> 14:26:00; Quantity: 27.15 -> 31.55
9961976 | 6 | changed | GN20-S01-Generator 365kVA Diesel | Billed Units: 0 -> 28; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 6260.4; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 7747.25
9961976 | 7 | changed | GN19-Generator - Diesel - 80kVA DEL AS 60KVA | Billed Units: 0 -> 9; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 1254.5; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 1552.44
9961976 | 9 | changed | GN23-Generator - Sync - Hardwire Only 150kVA Diesel | Billed Units: 0 -> 28; Billed To Time: None -> 08:00:00; Billed Amount: 0 -> 2412.54; Billed To Date: None -> 2026-10-28T00:00:00; Tot(inc.SD,DW&GST): 0 -> 2985.52
9968862 | 103 | changed | P69 Portable Building Shell 6.0M x 3.0M | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-25T00:00:00; Term Time: None -> 16:00:00
9968862 | 131 | changed | P45 Portable Building Shell 6.0M x 3.0M | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Term Time: None -> 16:00:00
9968862 | 132 | changed | P46 Refrigerator | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Term Time: None -> 06:00:00
9968862 | 140 | changed | ACCOM / ETC 50% | Description: ACCOM / MEALS / ETC 50% -> ACCOM / ETC 50%
9968955 | 163 | changed | ACCOM / ETC 50% | Description: ACCOM / MEALS / ETC 50% -> ACCOM / ETC 50%
9972648 | 1 | changed | WB01 Barrier - Crash Rated Water filled - Armorzone MASH TL2
9972648 | 11 | changed | WB16 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Expected Offrental Time: 19:00:00 -> 17:00:00
9972648 | 12 | changed | WB17 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Status: Del Req -> Off Rent; Term Date: None -> 2026-10-27T00:00:00; Term Time: None -> 16:00:00; Quantity: 6 -> 5
9972648 | 13 | changed | WB18 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Status: Del Req -> Delivered
9972648 | 16 | changed | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Start Time: 19:00:00 -> 10:00:00; Start Date: 2026-10-16T00:00:00 -> 2026-10-15T00:00:00
9972648 | 17 | changed | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Start Time: 19:00:00 -> 10:00:00; Start Date: 2026-10-16T00:00:00 -> 2026-10-15T00:00:00; Expected Offrental Time: None -> 19:00:00
9972648 | 2 | changed | WB03 Barrier - Crash Rated Water filled - Armorzone MASH TL2
9972648 | 3 | changed | WB02 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Status: Delivered -> Off Rent; Term Date: None -> 2026-09-25T00:00:00; Term Time: None -> 16:00:00; Expected Term Date: 2026-09-27T00:00:00 -> 2026-09-25T00:00:00
9972648 | 4 | changed | WB05 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Start Time: 09:00:00 -> 08:00:00
9972648 | 5 | changed | WB04 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Start Time: 19:00:00 -> 08:00:00; Expected Offrental Time: 19:00:00 -> 09:00:00
9972648 | 6 | changed | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Start Time: 19:00:00 -> 10:00:00; Start Date: 2026-10-16T00:00:00 -> 2026-10-15T00:00:00
9972648 | 9 | changed | WB14 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Expected Term Date: 2026-10-27T00:00:00 -> 2026-10-25T00:00:00; Expected Offrental Time: 07:00:00 -> 19:00:00
9990776 | 1 | changed | WB13 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Term Time: None -> 09:00:00; Expected Offrental Time: 07:00:00 -> 10:00:00
9992300 | 12 | changed | Straight Boom Lift 60ft - Diesel | Status: Delivered -> Return Pending; Term Date: None -> 2026-10-26T00:00:00; Return Number: None -> 21967377; Term Time: None -> 07:00:00
9992300 | 5 | changed | Knuckle Boom 61ft (18.6M) - Diesel | Status: Delivered -> Off Rent; Term Date: None -> 2026-10-26T00:00:00; Term Time: None -> 07:00:00
9994954 | 10 | changed | GN26 Generator - 200kVA (Diesel) | Booked Delivery Date: 2026-10-23T00:00:00 -> 2026-10-12T00:00:00; Start Date: 2026-10-23T00:00:00 -> 2026-10-12T00:00:00
9994954 | 11 | changed | GN27 Generator - 200kVA (Diesel) | Booked Delivery Date: 2026-10-23T00:00:00 -> 2026-10-12T00:00:00; Start Date: 2026-10-23T00:00:00 -> 2026-10-12T00:00:00