## Day by day
Ref | kVA asked | Asset | On site | Standby $/day | Full $/day | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | standby | FULL | FULL | FULL | Standby days | Standby $ | Race days | Race $ | Our total | Baseplan line | Baseplan $ | Difference | Note
[6 empty] | Mon 28 Sep | Tue 29 Sep | Wed 30 Sep | Thu 01 Oct | Fri 02 Oct | Sat 03 Oct | Sun 04 Oct | Mon 05 Oct | Tue 06 Oct | Wed 07 Oct | Thu 08 Oct | Fri 09 Oct | Sat 10 Oct | Sun 11 Oct | Mon 12 Oct | Tue 13 Oct | Wed 14 Oct | Thu 15 Oct | Fri 16 Oct | Sat 17 Oct | Sun 18 Oct | Mon 19 Oct | Tue 20 Oct | Wed 21 Oct | Thu 22 Oct | Fri 23 Oct | Sat 24 Oct | Sun 25 Oct
GN01 | 60 | 1276507 | 28 Sep | 96.5007 | 193.0014 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 193 | 193 | 193 | 25 | 2412.52 | 3 | 579 | 2991.52 | 16 | 1544 | 1447.52
GN03 | 30 | 1320829 | 01 Oct | 70.7672 | 141.5323 |  |  |  | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 70.77 | 141.53 | 141.53 | 141.53 | 22 | 1556.88 | 3 | 424.6 | 1981.47 | 10 | 1132.28 | 849.19
GN04 | 30 | 1277400 | 19 Oct | 70.7672 | 141.5323 | [21 empty] | 70.77 | 70.77 | 70.77 | 70.77 | 141.53 | 141.53 | 141.53 | 4 | 283.07 | 3 | 424.6 | 707.67 | 14 | 919.97 | -212.3
GN06 | 50 | 1320828 | 15 Oct | 91.1395 | 182.2791 | [17 empty] | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 182.28 | 182.28 | 182.28 | 8 | 729.12 | 3 | 546.84 | 1275.95 | 48 | 1184.82 | 91.13 | Baseplan says 60 kVA from 19 Oct; a 50 kVA was asked for, on site 15 Oct
GN10 | 20 | 1283681 | 19 Oct | 61.1171 | 122.2301 | [21 empty] | 61.12 | 61.12 | 61.12 | 61.12 | 122.23 | 122.23 | 122.23 | 4 | 244.47 | 3 | 366.69 | 611.16 | 15 | 1142.96 | -531.8 | Baseplan says 60 kVA; a 20 kVA was asked for
GN13 | 45 | 1276503 | 12 Oct | 87.9229 | 175.8416 | [14 empty] | 87.92 | 87.92 | 87.92 | 87.92 | 87.92 | 87.92 | 87.92 | 87.92 | 87.92 | 87.92 | 87.92 | 175.84 | 175.84 | 175.84 | 11 | 967.15 | 3 | 527.52 | 1494.68 | 44 | 1406.72 | 87.96 | Baseplan says 60 kVA delivered as 45, term 12 Nov; a 45 kVA was asked for, hire ends 25 Oct
GN18 | 50 | 1261273 | 07 Oct | 91.1395 | 182.2791 | [9 empty] | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 91.14 | 182.28 | 182.28 | 182.28 | 16 | 1458.23 | 3 | 546.84 | 2005.07 | 11 | 2187.36 | -182.29 | Baseplan says 60 kVA; a 50 kVA was asked for
GN19 | 60 | 1276416 | 19 Oct | 96.5007 | 193.0014 | [21 empty] | 96.5 | 96.5 | 96.5 | 96.5 | 193 | 193 | 193 | 4 | 386 | 3 | 579 | 965.01 | 7 | 1254.5 | -289.49 | Baseplan says 80 kVA delivered as 60; a 60 kVA was asked for
GN20 | 350 | to be given | 30 Sep | 235.8906 | 471.7812 |  |  | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 235.89 | 471.78 | 471.78 | 471.78 | 23 | 5425.48 | 3 | 1415.34 | 6840.83 | 6 | 6260.4 | 580.43 | Baseplan line 6 is 1276701, a 365 kVA that NEVER CAME TO SITE (Andrew, 22 Oct): close that line and raise the right one for the set that is at GN20. A 350 kVA was asked for, on site 30 Sep, asset number to be given; priced at the card's 315 kVA line (no 350 line)
GN21 | 60 | 1261284 | 30 Sep | 96.5007 | 193.0014 |  |  | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 193 | 193 | 193 | 23 | 2219.52 | 3 | 579 | 2798.52 | 38 | 868.5 | 1930.02
GN23 | 150 | 1297157 | 30 Sep | 134.0288 | 268.0575 |  |  | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 134.03 | 268.06 | 268.06 | 268.06 | 23 | 3082.66 | 3 | 804.17 | 3886.83 | 9 | 2412.54 | 1474.29
GN24 | 60 | 1277089 | 19 Oct | 96.5007 | 193.0014 | [21 empty] | 96.5 | 96.5 | 96.5 | 96.5 | 193 | 193 | 193 | 4 | 386 | 3 | 579 | 965.01 | 49 | 984.33 | -19.32 | trailer-mounted 60 kVA; not yet priced on our page (no rate or date recorded) - priced here at the 60 kVA line
GN25 | 20 | 1244536 | 19 Oct | 61.1171 | 122.2301 | [21 empty] | 61.12 | 61.12 | 61.12 | 61.12 | 122.23 | 122.23 | 122.23 | 4 | 244.47 | 3 | 366.69 | 611.16 | 18 | 855.63 | -244.47
GN26 | 200 | 1316182 | 12 Oct | 182.2791 | 364.5582 | [14 empty] | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 364.56 | 364.56 | 364.56 | 11 | 2005.07 | 3 | 1093.67 | 3098.74 | 42 | 2005.08 | 1093.66 | concert set; on our page only as "GN?" - to be given its own reference
GN27 | 200 | 1316183 | 12 Oct | 182.2791 | 364.5582 | [14 empty] | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 182.28 | 364.56 | 364.56 | 364.56 | 11 | 2005.07 | 3 | 1093.67 | 3098.74 | 43 | 2551.92 | 546.82 | concert set; on our page only as "GN?" - to be given its own reference
TOTAL | [5 empty] | 96.5 | 96.5 | 562.92 | 633.69 | 633.69 | 633.69 | 633.69 | 633.69 | 633.69 | 724.83 | 724.83 | 724.83 | 724.83 | 724.83 | 1177.31 | 1177.31 | 1177.31 | 1268.45 | 1268.45 | 1268.45 | 1268.45 | 1654.45 | 1654.45 | 1654.45 | 1654.45 | 3308.89 | 3308.89 | 3308.89 | 193 | 23405.71 | 45 | 9926.66 | 33332.36 |  | 26711.01 | 6621.35 | 15 sets

## Labour & transport
Ref | kVA | On site | Install (done) | Demob (at demob) | Transport each way | Delivery leg (done) | Pickup leg (at demob) | Hire standby to 22 Oct | Hire race days | Hire total | Set total now (hire + install + delivery) | Set total later (demob + pickup) | Set total | Note
GN01 | 60 | 28 Sep | 145.74 | 145.74 | 450 | 450 | 450 | 2412.52 | 579 | 2991.52 | 3587.26 | 595.74 | 4183
GN03 | 30 | 01 Oct | 145.74 | 145.74 | 300 | 300 | 300 | 1556.88 | 424.6 | 1981.48 | 2427.22 | 445.74 | 2872.96
GN04 | 30 | 19 Oct | 145.74 | 145.74 | 300 | 300 | 300 | 283.07 | 424.6 | 707.67 | 1153.41 | 445.74 | 1599.15
GN06 | 50 | 15 Oct | 145.74 | 145.74 | 450 | 450 | 450 | 729.12 | 546.84 | 1275.96 | 1871.7 | 595.74 | 2467.44 | Baseplan says 60 kVA from 19 Oct; a 50 kVA was asked for, on site 15 Oct
GN10 | 20 | 19 Oct | 145.74 | 145.74 | 300 | 300 | 300 | 244.47 | 366.69 | 611.16 | 1056.9 | 445.74 | 1502.64 | Baseplan says 60 kVA; a 20 kVA was asked for
GN13 | 45 | 12 Oct | 145.74 | 145.74 | 300 | 300 | 300 | 967.15 | 527.52 | 1494.67 | 1940.41 | 445.74 | 2386.15 | Baseplan says 60 kVA delivered as 45, term 12 Nov; a 45 kVA was asked for, hire ends 25 Oct
GN18 | 50 | 07 Oct | 145.74 | 145.74 | 450 | 450 | 450 | 1458.23 | 546.84 | 2005.07 | 2600.81 | 595.74 | 3196.55 | Baseplan says 60 kVA; a 50 kVA was asked for
GN19 | 60 | 19 Oct | 145.74 | 145.74 | 450 | 450 | 450 | 386 | 579 | 965 | 1560.74 | 595.74 | 2156.48 | Baseplan says 80 kVA delivered as 60; a 60 kVA was asked for
GN20 | 350 | 30 Sep | 166.56 | 166.56 | 600 | 600 | 600 | 5425.48 | 1415.34 | 6840.82 | 7607.38 | 766.56 | 8373.94 | 350 kVA: no card line for labour or transport; the 200 kVA figures are used
GN21 | 60 | 30 Sep | 145.74 | 145.74 | 450 | 450 | 450 | 2219.52 | 579 | 2798.52 | 3394.26 | 595.74 | 3990
GN23 | 150 | 30 Sep | 166.56 | 166.56 | 450 | 450 | 450 | 3082.66 | 804.17 | 3886.83 | 4503.39 | 616.56 | 5119.95
GN24 | 60 | 19 Oct | 145.74 | 145.74 | 450 | 450 | 450 | 386 | 579 | 965 | 1560.74 | 595.74 | 2156.48 | trailer-mounted 60 kVA; not yet priced on our page (no rate or date recorded) - priced here at the 60 kVA line
GN25 | 20 | 19 Oct | 145.74 | 145.74 | 300 | 300 | 300 | 244.47 | 366.69 | 611.16 | 1056.9 | 445.74 | 1502.64
GN26 | 200 | 12 Oct | 166.56 | 166.56 | 600 | 600 | 600 | 2005.07 | 1093.67 | 3098.74 | 3865.3 | 766.56 | 4631.86 | concert set; on our page only as "GN?" - to be given its own reference
GN27 | 200 | 12 Oct | 166.56 | 166.56 | 600 | 600 | 600 | 2005.07 | 1093.67 | 3098.74 | 3865.3 | 766.56 | 4631.86 | concert set; on our page only as "GN?" - to be given its own reference
TOTAL | 15 sets |  | 2269.38 | 2269.38 |  | 6450 | 6450 | 23405.71 | 9926.63 | 33332.34 | 42051.72 | 8719.38 | 50771.1
Baseplan 9961976 lines 51-55: labour 11 x $291.48 + 4 x $333.12 = $4,538.76 (install + demob a set, the card's figures, on 15 sets); transport 10 x $300 + 14 x $450 + 6 x $600 = $12,900 (both legs, 15 sets). Both count GN20's 1276701, which never came: labour and transport are 14 sets.

## Rates & basis
kVA | Card line | Full daily rate 2026 | Standby rate 2026
20 | Generator 20 KVA | 122.2301 | 61.1171
30 | Generator 30 KVA | 141.5323 | 70.7672
45 | Generator 45 KVA | 175.8416 | 87.9229
50 | Generator 50 KVA | 182.2791 | 91.1395
60 | Generator 60 KVA | 193.0014 | 96.5007
150 | Generator 150 KVA | 268.0575 | 134.0288
200 | Generator 200 KVA | 364.5582 | 182.2791
350 | Generator 315 KVA (next size down; no 350 line) | 471.7812 | 235.8906
Basis: the 2026 street card, ex GST. Standby rate every day from the day the set lands until 22 Oct; full daily rate on the race days 23, 24 and 25 Oct; no hire charge after 25 Oct. The rate follows the size the customer asked for, not the size sent. On-site dates are the site record. Author: Andrew Fisher, 22 Oct 2026.