## Summary
GC500 2026 · asset and off-hire register
From the live site record, version 10993, as at 26 Oct 2026 07:46 AEST. Every asset on the record, grouped, with where it is, what it is and when it goes off hire.
Group | References | Units | Subhire units | First off-hire (plan) | Last off-hire (plan)
Portable buildings | 52 | 52 | 1 | 2026-10-26 | 2026-11-13
Toilets & amenities | 74 | 271 | 203 | 2026-10-26 | 2026-11-13
Water-filled barriers | 15 | 375 | 0 | 2026-09-27 | 2026-11-06
Variable message signs | 4 | 24 | 6 | 2026-11-12 | 2026-11-13
Generators | 14 | 16 | 0 | 2026-10-26 | 2026-11-13
Lighting towers | 3 | 7 | 0 | 2026-10-26 | 2026-10-26
Access & plant | 10 | 12 | 0 | 2026-10-26 | 2026-11-13
Furniture | 5 | 6 | 0 | 2026-11-10 | 2026-11-11
Ground protection | 2 | 30 | 0 | 2026-10-30 | 2026-11-12
Other | 5 | 5 | 0 | 2026-10-27 | 2026-11-12
Total | 184 | 798 | 210
Inside the buildings: 158 recorded items (contents and fire extinguishers) on 49 buildings.
Advanced Temporary Fencing: 167 dockets and week rows, 25 collections (Subhire sheet).
Off-hire by day (demob plan)
Day | References | Confirmed | Plan | Contract | Proposed
2026-09-27 | 1 | 0 | 1 | 0 | 0
2026-10-19 | 1 | 0 | 1 | 0 | 0
2026-10-25 | 1 | 0 | 1 | 0 | 0
2026-10-26 | 21 | 0 | 6 | 14 | 1
2026-10-27 | 21 | 0 | 18 | 3 | 0
2026-10-28 | 20 | 0 | 3 | 0 | 17
2026-10-29 | 19 | 0 | 4 | 0 | 15
2026-10-30 | 20 | 0 | 5 | 2 | 13
2026-11-02 | 11 | 0 | 0 | 0 | 11
2026-11-03 | 7 | 0 | 0 | 0 | 7
2026-11-04 | 6 | 0 | 0 | 0 | 6
2026-11-05 | 7 | 0 | 0 | 0 | 7
2026-11-06 | 7 | 0 | 1 | 0 | 6
2026-11-09 | 6 | 0 | 0 | 0 | 6
2026-11-10 | 6 | 0 | 0 | 0 | 6
2026-11-11 | 10 | 0 | 0 | 0 | 10
2026-11-12 | 9 | 0 | 5 | 0 | 4
2026-11-13 | 9 | 0 | 4 | 0 | 5
What the columns mean
Off-hire (demob plan) | The site demob plan's day for the reference. Its source says how firm it is:
Confirmed | a person typed the due-out date.
Plan | the schedule has a removal row for it.
Contract | the rental contract's off-hire date.
Proposed | worked out by the demob rule; not on the record until someone confirms it.
Contract off-hire date / time | The rental contract line on the record: the actual off-rent date once there is one, else the expected off-hire date and the time where the contract has one.
Status on site | From the page's "left site" record. Still to leave until a departure is recorded with its date and time.
Pin basis | Master plan position = from the 2 Oct master plan, not a phone pin. Report point only = no drop-off set; the site directs drivers from the pit lane. Andrew's pin = a pin dropped on site.
Map | Opens Google Maps at the latitude and longitude.
↳ Inside | An item the record has inside the building (contents and fire extinguishers), with its asset number where recorded.
Blank | The record does not say. Nothing is filled in by guess.
Gaps on the record today
27 | references with no drop-off position (report point only)
2 | references with no position at all
2 | references not in the demob plan
114 | off-hire days proposed by the demob rule, not yet confirmed
2 | references the record has as not on site
13 | units with no unit number on the record
188 | contract lines with no off-hire time
0 | references with a departure recorded so far

## All assets
GC500 2026 · every asset, grouped · live record as at 26 Oct 2026 07:46 AEST · version 10993
Use the 1 · 2 · 3 buttons on the left to fold: 1 groups, 2 references, 3 every unit and what is inside each building. Blank means the record does not say.
Group | Ref | Description | Item | Qty | Asset / fleet no | Owner | Location | Area | Plan section | Lat | Long | Map | Pin basis | Off-hire (demob plan) | Plan source | Contract off-hire date | Contract off-hire time | Contract · line | Contract status | Status on site | Notes
PORTABLE BUILDINGS |  | 52 references · 52 units
Portable buildings | AA | Active Air Crib Room | Building 6m × 1 | 1 |  | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Portable buildings | AA | Active Air Crib Room | Building 6m | 1 | 142514 | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Portable buildings | AA | Active Air Crib Room | ↳ Inside: Fridge | 1 |  | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | fridge; parsed from the schedule notes column
Portable buildings | AA | Active Air Crib Room | ↳ Inside: Folding table | 1 |  | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 1x fold table; parsed from the schedule notes column
Portable buildings | AA | Active Air Crib Room | ↳ Inside: Stackable chair | 4 |  | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 4x stack chair; parsed from the schedule notes column
Portable buildings | AA | Active Air Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | CP1 | P68 · Signevent Crib Room | Building 6m × 1 | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 17 | Delivered | Still to leave
Portable buildings | CP1 | P68 · Signevent Crib Room | Building 6m | 1 | 1105057 | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 17 | Delivered | Still to leave
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Chair | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Chairs; parsed from the schedule notes column
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Desk | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | parsed from the schedule notes column
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Hydration station | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Hydration Station; parsed from the schedule notes column
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Sink with tap | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Sink with Tap; parsed from the schedule notes column
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Fridge | 1 | 1116687 | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Fridge — Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Urn | 1 | 119810 | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Urn — Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | HRP | Hire Republic Crib Room | Building 6m × 1 | 1 |  | Coates | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 93 | Delivered | Still to leave
Portable buildings | HRP | Hire Republic Crib Room | Building 6m | 1 | 1189410 | Coates | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 93 | Delivered | Still to leave
Portable buildings | HRP | Hire Republic Crib Room | ↳ Inside: Air conditioner | 1 | 1189901 | Coates | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | HRP | Hire Republic Crib Room | ↳ Inside: Air conditioner | 1 | 1127305 | Coates | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | HRP | Hire Republic Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P01 | iEDM Engineering Office | Building 12m × 1 | 1 |  | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 1 | Delivered | Still to leave
Portable buildings | P01 | iEDM Engineering Office | Building 12m | 1 | 1322583 | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 1 | Delivered | Still to leave
Portable buildings | P01 | iEDM Engineering Office | ↳ Inside: Fridge | 1 | 1328956 | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge - Full Sized; parsed from the schedule notes column
Portable buildings | P01 | iEDM Engineering Office | ↳ Inside: Air conditioner | 1 | 1322610 | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P01 | iEDM Engineering Office | ↳ Inside: Air conditioner | 1 | 1322609 | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P01 | iEDM Engineering Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P03 | SCA Event Management Office | Building 12m × 1 | 1 |  | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 4 | Delivered | Still to leave
Portable buildings | P03 | SCA Event Management Office | Building 12m | 1 | 1327212 | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 4 | Delivered | Still to leave
Portable buildings | P03 | SCA Event Management Office | ↳ Inside: Fridge | 1 | 1328955 | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge - Full Sized; parsed from the schedule notes column
Portable buildings | P03 | SCA Event Management Office | ↳ Inside: Air conditioner | 1 | 1327954 | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P03 | SCA Event Management Office | ↳ Inside: Air conditioner | 1 | 1327953 | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P03 | SCA Event Management Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P04 | SCA Sales & Marketing Office | Building 12m × 1 | 1 |  | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 7 | Delivered | Still to leave
Portable buildings | P04 | SCA Sales & Marketing Office | Building 12m | 1 | 1327213 | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 7 | Delivered | Still to leave
Portable buildings | P04 | SCA Sales & Marketing Office | ↳ Inside: Fridge | 1 | 1328954 | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge - Full Sized; parsed from the schedule notes column
Portable buildings | P04 | SCA Sales & Marketing Office | ↳ Inside: Air conditioner | 1 | 1327955 | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P04 | SCA Sales & Marketing Office | ↳ Inside: Air conditioner | 1 | 1327956 | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P04 | SCA Sales & Marketing Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P05 | Event Control Center (ECC) | Building 6m × 1 | 1 |  | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 10 | Delivered | Still to leave
Portable buildings | P05 | Event Control Center (ECC) | Building 6m | 1 | 1189422 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 10 | Delivered | Still to leave
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Chair | 1 |  | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | parsed from the schedule notes column
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Fridge | 1 | 1311988 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge (full sized); parsed from the schedule notes column
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Zip boiler | 1 |  | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Zip Boiler; parsed from the schedule notes column
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Sink with tap | 1 |  | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Sink with Tap; parsed from the schedule notes column
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Microwave | 1 | 1320150 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Microwave — Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Air conditioner | 1 | 1127574 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Air conditioner | 1 | 1189939 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Fire extinguisher | 1 |  | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P06 | Wilclean Crib Room | Building 6m × 1 | 1 |  | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 64 | Delivered | Still to leave
Portable buildings | P06 | Wilclean Crib Room | Building 6m | 1 | 1087453 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 64 | Delivered | Still to leave
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Sink with tap | 1 |  | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Sink w Tap; parsed from the schedule notes column
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Air conditioner | 1 | 1097209 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Fridge | 1 | 1272749 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Microwave | 1 | 1284012 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Zip boiler | 1 | 1173374 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P08 | Security | Building 6m × 1 | 1 |  | Coates | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 126 | Delivered | Still to leave
Portable buildings | P08 | Security | Building 6m | 1 | 421138 | Coates | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 126 | Delivered | Still to leave
Portable buildings | P08 | Security | ↳ Inside: Air conditioner | 1 | 1311986 | Coates | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P08 | Security | ↳ Inside: Fridge | 1 | 1114312 | Coates | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P08 | Security | ↳ Inside: Fire extinguisher | 1 |  | Coates | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P09 | Iedm Safety Office | Building 6m × 1 | 1 |  | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 28 | Delivered | Still to leave
Portable buildings | P09 | Iedm Safety Office | Building 6m | 1 | 1268824 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 28 | Delivered | Still to leave
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Sink with tap | 1 |  | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Sink w Tap; parsed from the schedule notes column
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Air conditioner | 1 | 1270403 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Fridge | 1 | 1328958 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Urn | 1 | 1284061 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Zip boiler | 1 | 1254390 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Zip boiler — Boiling-water unit. Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P10 | Team Office - 888 Racing | Building 4.8m × 1 | 1 |  | Coates | P10 - Team Office - 888 Racing | Island north – by FREIGHT | S02 | -27.9866 | 153.4281 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 44 | Delivered | Still to leave
Portable buildings | P10 | Team Office - 888 Racing | Building 4.8m | 1 | 105626 | Coates | P10 - Team Office - 888 Racing | Island north – by FREIGHT | S02 | -27.9866 | 153.4281 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 44 | Delivered | Still to leave
Portable buildings | P10 | Team Office - 888 Racing | ↳ Inside: Air conditioner | 1 | 238771 | Coates | P10 - Team Office - 888 Racing | Island north – by FREIGHT | S02 | -27.9866 | 153.4281 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P10 | Team Office - 888 Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P10 - Team Office - 888 Racing | Island north – by FREIGHT | S02 | -27.9866 | 153.4281 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P11 | Team Office - DJR | Building 4.8m × 1 | 1 |  | Coates | P11 - Team Office - DJR | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 46 | Delivered | Still to leave
Portable buildings | P11 | Team Office - DJR | Building 4.8m | 1 | 415576 | Coates | P11 - Team Office - DJR | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 46 | Delivered | Still to leave
Portable buildings | P11 | Team Office - DJR | ↳ Inside: Air conditioner | 1 | 112940 | Coates | P11 - Team Office - DJR | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P11 | Team Office - DJR | ↳ Inside: Fire extinguisher | 1 |  | Coates | P11 - Team Office - DJR | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P12 | Team 18 | Building 4.8m × 1 | 1 |  | Coates | P12 - Team 18 | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 48 | Delivered | Still to leave
Portable buildings | P12 | Team 18 | Building 4.8m | 1 | 418665 | Coates | P12 - Team 18 | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 48 | Delivered | Still to leave
Portable buildings | P12 | Team 18 | ↳ Inside: Fire extinguisher | 1 |  | Coates | P12 - Team 18 | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P13 | Team Office - WAU | Building 4.8m × 1 | 1 |  | Coates | P13 - Team Office - WAU | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 51 | Delivered | Still to leave
Portable buildings | P13 | Team Office - WAU | Building 4.8m | 1 | 1097346 | Coates | P13 - Team Office - WAU | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 51 | Delivered | Still to leave
Portable buildings | P13 | Team Office - WAU | ↳ Inside: Air conditioner | 1 | 1190775 | Coates | P13 - Team Office - WAU | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P13 | Team Office - WAU | ↳ Inside: Fire extinguisher | 1 |  | Coates | P13 - Team Office - WAU | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P14 | Team Office - Grove Racing | Building 4.8m × 1 | 1 |  | Coates | P14 - Team Office - Grove Racing | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 53 | Delivered | Still to leave
Portable buildings | P14 | Team Office - Grove Racing | Building 4.8m | 1 | 960599 | Coates | P14 - Team Office - Grove Racing | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 53 | Delivered | Still to leave
Portable buildings | P14 | Team Office - Grove Racing | ↳ Inside: Air conditioner | 1 | 118370 | Coates | P14 - Team Office - Grove Racing | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P14 | Team Office - Grove Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P14 - Team Office - Grove Racing | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P15 | Team Office - Erebus Motorsport | Building 4.8m × 1 | 1 |  | Coates | P15 - Team Office - Erebus Motorsport | Island north – by FREIGHT | S02 | -27.9869 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 55 | Delivered | Still to leave
Portable buildings | P15 | Team Office - Erebus Motorsport | Building 4.8m | 1 | 1097345 | Coates | P15 - Team Office - Erebus Motorsport | Island north – by FREIGHT | S02 | -27.9869 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 55 | Delivered | Still to leave
Portable buildings | P15 | Team Office - Erebus Motorsport | ↳ Inside: Fire extinguisher | 1 |  | Coates | P15 - Team Office - Erebus Motorsport | Island north – by FREIGHT | S02 | -27.9869 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P16 | Team Office - WFL | Building 4.8m × 1 | 1 |  | Coates | P16 - Team Office - WFL | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 57 | Delivered | Still to leave
Portable buildings | P16 | Team Office - WFL | Building 4.8m | 1 | 415575 | Coates | P16 - Team Office - WFL | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 57 | Delivered | Still to leave
Portable buildings | P16 | Team Office - WFL | ↳ Inside: Fire extinguisher | 1 |  | Coates | P16 - Team Office - WFL | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P17 | Team Office BJR | Building 9.6m × 1 | 1 |  | Coates | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 33 | Delivered | Still to leave
Portable buildings | P17 | Team Office BJR | Building 9.6m | 1 | 1268887 | Coates | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 33 | Delivered | Still to leave
Portable buildings | P17 | Team Office BJR | ↳ Inside: Air conditioner | 1 | 1270473 | Coates | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P17 | Team Office BJR | ↳ Inside: Air conditioner | 1 | 1270472 | Coates | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P17 | Team Office BJR | ↳ Inside: Fire extinguisher | 1 |  | Coates | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P18 | Team Office - MSR | Building 4.8m × 1 | 1 |  | Coates | P18 - Team Office - MSR | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4268 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 36 | Delivered | Still to leave
Portable buildings | P18 | Team Office - MSR | Building 4.8m | 1 | 1097343 | Coates | P18 - Team Office - MSR | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4268 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 36 | Delivered | Still to leave
Portable buildings | P18 | Team Office - MSR | ↳ Inside: Fridge | 1 |  | Coates | P18 - Team Office - MSR | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4268 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P18 | Team Office - MSR | ↳ Inside: Fire extinguisher | 1 |  | Coates | P18 - Team Office - MSR | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4268 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P19 | Team Office Premiair Racing | Building 4.8m × 1 | 1 |  | Coates | P19 - Team Office Premiair Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 34 | Delivered | Still to leave
Portable buildings | P19 | Team Office Premiair Racing | Building 4.8m | 1 | 1110619 | Coates | P19 - Team Office Premiair Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 34 | Delivered | Still to leave
Portable buildings | P19 | Team Office Premiair Racing | ↳ Inside: Air conditioner | 1 | 1244101 | Coates | P19 - Team Office Premiair Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P19 | Team Office Premiair Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P19 - Team Office Premiair Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P20 | Team Office Blanchard Racing | Building 4.8m × 1 | 1 |  | Coates | P20 - Team Office Blanchard Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 38 | Delivered | Still to leave
Portable buildings | P20 | Team Office Blanchard Racing | Building 4.8m | 1 | 1097339 | Coates | P20 - Team Office Blanchard Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 38 | Delivered | Still to leave
Portable buildings | P20 | Team Office Blanchard Racing | ↳ Inside: Air conditioner | 1 | 1180683 | Coates | P20 - Team Office Blanchard Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P20 | Team Office Blanchard Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P20 - Team Office Blanchard Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P21 | Team Objective Racing | Building 4.8m × 1 | 1 |  | Coates | P21 - Team Objective Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 92 | Delivered | Still to leave
Portable buildings | P21 | Team Objective Racing | Building 4.8m | 1 | 1327220 | Coates | P21 - Team Objective Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 92 | Delivered | Still to leave
Portable buildings | P21 | Team Objective Racing | ↳ Inside: Air conditioner | 1 | 1327938 | Coates | P21 - Team Objective Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P21 | Team Objective Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P21 - Team Objective Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P25 | Support Category Stewards | Building 4.8m × 1 | 1 |  | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 105 | Delivered | Still to leave
Portable buildings | P25 | Support Category Stewards | Building 4.8m | 1 | 1189408 | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 105 | Delivered | Still to leave
Portable buildings | P25 | Support Category Stewards | ↳ Inside: Air conditioner | 1 | 1189951 | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P25 | Support Category Stewards | ↳ Inside: Air conditioner | 1 | 1189950 | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P25 | Support Category Stewards | ↳ Inside: Fridge | 1 | 1260174 | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P25 | Support Category Stewards | ↳ Inside: Fire extinguisher | 1 |  | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P33 | Race Medical | Building 9.6m × 1 | 1 |  | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 24 | Delivered | Still to leave
Portable buildings | P33 | Race Medical | Building 9.6m | 1 | 453375 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 24 | Delivered | Still to leave
Portable buildings | P33 | Race Medical | ↳ Inside: Sink with tap | 1 |  | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Sink with Tap; parsed from the schedule notes column
Portable buildings | P33 | Race Medical | ↳ Inside: Air conditioner | 1 | 1286611 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P33 | Race Medical | ↳ Inside: Air conditioner | 1 | 1127296 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P33 | Race Medical | ↳ Inside: Fridge | 1 | 1238952 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P33 | Race Medical | ↳ Inside: Zip boiler | 1 | 1066777 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P33 | Race Medical | ↳ Inside: Fire extinguisher | 1 |  | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P36 | Harry the Hirer | Building 6m × 1 | 1 |  | Coates | P36 - Harry the Hirer | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 93 | Delivered | Still to leave
Portable buildings | P36 | Harry the Hirer | Building 6m | 1 | 1282487 | Coates | P36 - Harry the Hirer | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 93 | Delivered | Still to leave
Portable buildings | P36 | Harry the Hirer | ↳ Inside: Air conditioner | 1 | 1283004 | Coates | P36 - Harry the Hirer | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P36 | Harry the Hirer | ↳ Inside: Fire extinguisher | 1 |  | Coates | P36 - Harry the Hirer | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P37 | Oz Wide Audio Crib Room | Building 6m × 1 | 1 |  | Coates | P37 Oz Wide Audio Crib Room | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 50 | Delivered | Still to leave
Portable buildings | P37 | Oz Wide Audio Crib Room | Building 6m | 1 | 1105053 | Coates | P37 Oz Wide Audio Crib Room | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 50 | Delivered | Still to leave
Portable buildings | P37 | Oz Wide Audio Crib Room | ↳ Inside: Air conditioner | 1 | 1198145 | Coates | P37 Oz Wide Audio Crib Room | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P37 | Oz Wide Audio Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | P37 Oz Wide Audio Crib Room | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P38 | Green Room 1 | Building 6m × 1 | 1 |  | Coates | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 70 | Delivered | Still to leave
Portable buildings | P38 | Green Room 1 | Building 6m | 1 | 1327218 | Coates | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 70 | Delivered | Still to leave
Portable buildings | P38 | Green Room 1 | ↳ Inside: Air conditioner | 1 | 1327934 | Coates | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P38 | Green Room 1 | ↳ Inside: Fridge | 1 | 1272755 | Coates | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P38 | Green Room 1 | ↳ Inside: Fire extinguisher | 1 |  | Coates | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P39 | Green Room 2 | Building 6m × 1 | 1 |  | Coates | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 73 | Delivered | Still to leave
Portable buildings | P39 | Green Room 2 | Building 6m | 1 | 1327216 | Coates | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 73 | Delivered | Still to leave
Portable buildings | P39 | Green Room 2 | ↳ Inside: Air conditioner | 1 | 1272737 | Coates | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P39 | Green Room 2 | ↳ Inside: Air conditioner | 1 | 1327936 | Coates | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P39 | Green Room 2 | ↳ Inside: Fire extinguisher | 1 |  | Coates | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P41 | QFES Crib Room | Building 6m × 1 | 1 |  | Coates | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 63 | Delivered | Still to leave
Portable buildings | P41 | QFES Crib Room | Building 6m | 1 | 1189412 | Coates | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 63 | Delivered | Still to leave
Portable buildings | P41 | QFES Crib Room | ↳ Inside: Air conditioner | 1 | 1189899 | Coates | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P41 | QFES Crib Room | ↳ Inside: Air conditioner | 1 | 1189908 | Coates | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P41 | QFES Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P42 | Production | Building 6m × 1 | 1 |  | Coates | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 76 | Delivered | Still to leave
Portable buildings | P42 | Production | Building 6m | 1 | 1327221 | Coates | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 76 | Delivered | Still to leave
Portable buildings | P42 | Production | ↳ Inside: Air conditioner | 1 | 1327939 | Coates | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P42 | Production | ↳ Inside: Fridge | 1 | 1272746 | Coates | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P42 | Production | ↳ Inside: Fire extinguisher | 1 |  | Coates | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P44 | Queensland Ambulance Service | Building 6m × 1 | 1 |  | Coates | P44 - Queensland Ambulance Service | Island west parkland entry – by the merch strip |  | -27.9838 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 61 | Delivered | Still to leave
Portable buildings | P44 | Queensland Ambulance Service | Building 6m | 1 | 198481 | Coates | P44 - Queensland Ambulance Service | Island west parkland entry – by the merch strip |  | -27.9838 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 61 | Delivered | Still to leave
Portable buildings | P44 | Queensland Ambulance Service | ↳ Inside: Fridge | 1 | 1183134 | Coates | P44 - Queensland Ambulance Service | Island west parkland entry – by the merch strip |  | -27.9838 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P44 | Queensland Ambulance Service | ↳ Inside: Fire extinguisher | 1 |  | Coates | P44 - Queensland Ambulance Service | Island west parkland entry – by the merch strip |  | -27.9838 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P45 | St John First Aid | Building 6m × 1 | 1 |  | Coates | P45 St John First Aid | Main Beach seaside – by the supply compound |  | -27.9881 | 153.43 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 131 | Delivered | Still to leave
Portable buildings | P45 | St John First Aid | Building 6m | 1 | 107135 | Coates | P45 St John First Aid | Main Beach seaside – by the supply compound |  | -27.9881 | 153.43 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 131 | Delivered | Still to leave
Portable buildings | P45 | St John First Aid | ↳ Inside: Air conditioner | 1 | 1250796 | Coates | P45 St John First Aid | Main Beach seaside – by the supply compound |  | -27.9881 | 153.43 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P45 | St John First Aid | ↳ Inside: Fire extinguisher | 1 |  | Coates | P45 St John First Aid | Main Beach seaside – by the supply compound |  | -27.9881 | 153.43 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P46 | QPS Command Post | Building 12m × 1 | 1 |  | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 100 | Delivered | Still to leave
Portable buildings | P46 | QPS Command Post | Building 12m | 1 | 1327215 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 100 | Delivered | Still to leave
Portable buildings | P46 | QPS Command Post | ↳ Inside: Air conditioner | 1 | 1327959 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P46 | QPS Command Post | ↳ Inside: Air conditioner | 1 | 1327960 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P46 | QPS Command Post | ↳ Inside: Fridge | 1 | 1318501 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge — Police fridge, from T0265's 14 Oct delivery; added in this page
Portable buildings | P46 | QPS Command Post | ↳ Inside: Fridge | 1 | 1260164 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge — Police fridge, from T0265's 14 Oct delivery; added in this page
Portable buildings | P46 | QPS Command Post | ↳ Inside: Fire extinguisher | 1 |  | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P51 | Security Sign On | Building 12m × 1 | 1 |  | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 94 | Delivered | Still to leave
Portable buildings | P51 | Security Sign On | Building 12m | 1 | 1322579 | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 94 | Delivered | Still to leave
Portable buildings | P51 | Security Sign On | ↳ Inside: Air conditioner | 1 | 1326602 | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P51 | Security Sign On | ↳ Inside: Air conditioner | 1 | 1326601 | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P51 | Security Sign On | ↳ Inside: Fridge | 1 | 1328959 | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P51 | Security Sign On | ↳ Inside: Fire extinguisher | 1 |  | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P52 | Gate 1 Volunteer Check-In | Building 12m × 1 | 1 |  | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 79 | Delivered | Still to leave
Portable buildings | P52 | Gate 1 Volunteer Check-In | Building 12m | 1 | 1327211 | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 79 | Delivered | Still to leave
Portable buildings | P52 | Gate 1 Volunteer Check-In | ↳ Inside: Air conditioner | 1 | 1327951 | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P52 | Gate 1 Volunteer Check-In | ↳ Inside: Air conditioner | 1 | 1327952 | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P52 | Gate 1 Volunteer Check-In | ↳ Inside: Fridge | 1 | 1328953 | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P52 | Gate 1 Volunteer Check-In | ↳ Inside: Fire extinguisher | 1 |  | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P54 | Accred Centre BOH | Building 6m × 1 | 1 |  | Coates | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 85 | Delivered | Still to leave
Portable buildings | P54 | Accred Centre BOH | Building 6m | 1 | 1327219 | Coates | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 85 | Delivered | Still to leave
Portable buildings | P54 | Accred Centre BOH | ↳ Inside: Air conditioner | 1 | 1327937 | Coates | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P54 | Accred Centre BOH | ↳ Inside: Fridge | 1 | 1328957 | Coates | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge — Moved from P46 on 14 Oct 2026; same fridge, not an additional hire.; added in this page
Portable buildings | P54 | Accred Centre BOH | ↳ Inside: Fire extinguisher | 1 |  | Coates | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P55 | Gate 1 Ticket Box | Ticket Box 6m × 1 | 1 |  | Coates | P55 - Gate 1 Ticket Box | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4238 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 87 | Delivered | Still to leave
Portable buildings | P55 | Gate 1 Ticket Box | Ticket Box 6m | 1 | 172114 | Coates | P55 - Gate 1 Ticket Box | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4238 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 87 | Delivered | Still to leave
Portable buildings | P55 | Gate 1 Ticket Box | ↳ Inside: Air conditioner | 1 | 1320175 | Coates | P55 - Gate 1 Ticket Box | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4238 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P55 | Gate 1 Ticket Box | ↳ Inside: Fire extinguisher | 1 |  | Coates | P55 - Gate 1 Ticket Box | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4238 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P56 | Gate 1 Ticket BOH | Building 3.6m × 1 | 1 |  | Coates | P56 - Gate 1 Ticket BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 89 | Delivered | Still to leave
Portable buildings | P56 | Gate 1 Ticket BOH | Building 3.6m | 1 | 1268865 | Coates | P56 - Gate 1 Ticket BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 89 | Delivered | Still to leave
Portable buildings | P56 | Gate 1 Ticket BOH | ↳ Inside: Air conditioner | 1 | 1270437 | Coates | P56 - Gate 1 Ticket BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P56 | Gate 1 Ticket BOH | ↳ Inside: Fire extinguisher | 1 |  | Coates | P56 - Gate 1 Ticket BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P57 | Radio Distribution Office | Building 9.6m × 1 | 1 |  | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 90 | Delivered | Still to leave
Portable buildings | P57 | Radio Distribution Office | Building 9.6m | 1 | 1268888 | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 90 | Delivered | Still to leave
Portable buildings | P57 | Radio Distribution Office | ↳ Inside: Air conditioner | 1 | 1270478 | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P57 | Radio Distribution Office | ↳ Inside: Air conditioner | 1 | 1270479 | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P57 | Radio Distribution Office | ↳ Inside: Fridge | 1 | 1280688 | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P57 | Radio Distribution Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P58 | 1300 Medics | Building 6m × 1 | 1 |  | Coates | P58 - 1300 Medics | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 59 | Delivered | Still to leave
Portable buildings | P58 | 1300 Medics | Building 6m | 1 | 1273656 | Coates | P58 - 1300 Medics | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 59 | Delivered | Still to leave
Portable buildings | P58 | 1300 Medics | ↳ Inside: Fridge | 1 | 1201945 | Coates | P58 - 1300 Medics | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P58 | 1300 Medics | ↳ Inside: Fire extinguisher | 1 |  | Coates | P58 - 1300 Medics | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P60 | Gate 5 Ticket Box | Ticket Box 4.8m × 1 | 1 |  | Coates | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 116 | Delivered | Still to leave
Portable buildings | P60 | Gate 5 Ticket Box | Ticket Box 4.8m | 1 | 1015699 | Coates | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 116 | Delivered | Still to leave
Portable buildings | P60 | Gate 5 Ticket Box | ↳ Inside: Air conditioner | 1 | 1267597 | Coates | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P60 | Gate 5 Ticket Box | ↳ Inside: Swivel chair | 4 |  | Coates | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | 4x Swivel chair; added in this page
Portable buildings | P60 | Gate 5 Ticket Box | ↳ Inside: Fire extinguisher | 1 |  | Coates | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P62 | Gate 5 QFES Office | Building 6m × 1 | 1 |  | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 118 | Delivered | Still to leave
Portable buildings | P62 | Gate 5 QFES Office | Building 6m | 1 | 1189409 | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 118 | Delivered | Still to leave
Portable buildings | P62 | Gate 5 QFES Office | ↳ Inside: Air conditioner | 1 | 1189912 | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P62 | Gate 5 QFES Office | ↳ Inside: Air conditioner | 1 | 1189908 | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P62 | Gate 5 QFES Office | ↳ Inside: Fridge | 1 | 1254221 | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P62 | Gate 5 QFES Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P63 | Gate 5 Volunteer Sign On | Building 6m × 1 | 1 |  | Coates | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 121 | Delivered | Still to leave
Portable buildings | P63 | Gate 5 Volunteer Sign On | Building 6m | 1 | 960719 | Coates | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 121 | Delivered | Still to leave
Portable buildings | P63 | Gate 5 Volunteer Sign On | ↳ Inside: Air conditioner | 1 | 1219157 | Coates | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P63 | Gate 5 Volunteer Sign On | ↳ Inside: Air conditioner | 1 | 1219156 | Coates | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P63 | Gate 5 Volunteer Sign On | ↳ Inside: Fire extinguisher | 1 |  | Coates | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P65 | Support Categories Race Secretary | Building 6m × 1 | 1 |  | Coates | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 110 | Delivered | Still to leave
Portable buildings | P65 | Support Categories Race Secretary | Building 6m | 1 | 1327217 | Coates | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 110 | Delivered | Still to leave
Portable buildings | P65 | Support Categories Race Secretary | ↳ Inside: Air conditioner | 1 | 1327935 | Coates | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P65 | Support Categories Race Secretary | ↳ Inside: Fridge | 1 | 1283982 | Coates | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P65 | Support Categories Race Secretary | ↳ Inside: Fire extinguisher | 1 |  | Coates | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P66 | Support Category Scrutineers | Building 6m × 1 | 1 |  | Coates | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 113 | Delivered | Still to leave
Portable buildings | P66 | Support Category Scrutineers | Building 6m | 1 | 1327222 | Coates | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 113 | Delivered | Still to leave
Portable buildings | P66 | Support Category Scrutineers | ↳ Inside: Air conditioner | 1 | 1372940 | Coates | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P66 | Support Category Scrutineers | ↳ Inside: Fridge | 1 | 131190 | Coates | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P66 | Support Category Scrutineers | ↳ Inside: Fire extinguisher | 1 |  | Coates | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P67 | Gate 6 Security Office | Building 6m × 1 | 1 |  | Coates | P67 - Gate 6 Security Office | Pit lane entry |  | -27.9913 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 108 | Delivered | Still to leave
Portable buildings | P67 | Gate 6 Security Office | Building 6m | 1 | 421107 | Coates | P67 - Gate 6 Security Office | Pit lane entry |  | -27.9913 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 108 | Delivered | Still to leave
Portable buildings | P67 | Gate 6 Security Office | ↳ Inside: Air conditioner | 1 | 1300541 | Coates | P67 - Gate 6 Security Office | Pit lane entry |  | -27.9913 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P67 | Gate 6 Security Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P67 - Gate 6 Security Office | Pit lane entry |  | -27.9913 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P69 | Supply Building | Building 6m × 1 | 1 |  | Coates | P69 - Supply Building | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 103 | Delivered | Still to leave
Portable buildings | P69 | Supply Building | Building 6m | 1 | 107247 | Coates | P69 - Supply Building | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 103 | Delivered | Still to leave
Portable buildings | P69 | Supply Building | ↳ Inside: Air conditioner | 1 | 1245808 | Coates | P69 - Supply Building | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P69 | Supply Building | ↳ Inside: Fire extinguisher | 1 |  | Coates | P69 - Supply Building | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | Building 4.8m × 1 | 1 |  | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 | 09:00 | 9968929 · line 1 | Delivered | Still to leave
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | Building 4.8m | 1 | 960639 | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 | 09:00 | 9968929 · line 1 | Delivered | Still to leave
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | ↳ Inside: Folding table | 3 |  | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 3x Fold Table; parsed from the schedule notes column
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | ↳ Inside: Swivel chair | 3 |  | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 3x swivel chair; parsed from the schedule notes column
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | ↳ Inside: Whiteboard | 1 |  | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | White Board; parsed from the schedule notes column
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | ↳ Inside: Fire extinguisher | 1 |  | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | Building 4.8m × 1 | 1 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 | 09:00 | 9968929 · line 3 | Delivered | Still to leave
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | Building 4.8m | 1 | 960634 | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 | 09:00 | 9968929 · line 3 | Delivered | Still to leave
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Folding table | 3 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 3x fold table; parsed from the schedule notes column
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Sink with tap | 1 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | sink; parsed from the schedule notes column
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Stackable chair | 12 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 12x stack Chair; parsed from the schedule notes column
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Microwave | 1 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | parsed from the schedule notes column
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Fridge | 1 | 1272753 | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Fridge | 1 | 1254399 | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Fire extinguisher | 1 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | T0023 | Event Container · event container from eags | Event Container × 1 | 1 |  | Coates | event container from eags | Island west parkland entry – by the merch strip |  | -27.9833 | 153.4263 | Open map | Phone pin | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 09:00 | 9968929 · line 5 | Del Req | Still to leave
Portable buildings | T0023 | Event Container · event container from eags | Event Container | 1 | 1257261 | Coates | event container from eags | Island west parkland entry – by the merch strip |  | -27.9833 | 153.4263 | Open map | Phone pin | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 09:00 | 9968929 · line 5 | Del Req | Still to leave
Portable buildings | T0258 | 3.0m Cont · Helen Park | 3.0m Cont × 1 | 1 |  | Coates | Helen Park | Pit lane entry | S23 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Proposed (demob rule, not confirmed) | 2026-11-13 | 10:00 | 9974042 · line 1 | Delivered | Still to leave
Portable buildings | T0258 | 3.0m Cont · Helen Park | 3.0m Cont | 1 | 1134386 | Coates | Helen Park | Pit lane entry | S23 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Proposed (demob rule, not confirmed) | 2026-11-13 | 10:00 | 9974042 · line 1 | Delivered | Still to leave
Portable buildings | T0266 | 6.0m Refrigerator Cont · Helen Park | 6.0m Refrigerator Cont × 1 | 1 |  | United Rentals / Royal Wolf (subhire) | Helen Park | Pit lane entry | S23 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9974042 · line 2 | Delivered | Still to leave
Portable buildings | T0266 | 6.0m Refrigerator Cont · Helen Park | 6.0m Refrigerator Cont | 1 | 920584 | United Rentals / Royal Wolf (subhire) | Helen Park | Pit lane entry | S23 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9974042 · line 2 | Delivered | Still to leave
TOILETS & AMENITIES |  | 74 references · 271 units
Toilets & amenities | BJR01 | Brad Jones Racing | FWF × 1 | 1 |  | Event Portables (subhire) | Brad Jones Racing | Median strip meet-up – pit stop, by FOAM |  | -27.9859 | 153.4275 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | BJR01 | Brad Jones Racing | FWF | 1 | 0941 | Event Portables (subhire) | Brad Jones Racing | Median strip meet-up – pit stop, by FOAM |  | -27.9859 | 153.4275 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | PG01 | Toilet (Pit Garage) | FWF × 1 | 1 |  | Event Portables (subhire) | PG01 - Toilet (Pit Garage) | Pit lane entry | S01 | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 151 | Delivered | Still to leave
Toilets & amenities | PG01 | Toilet (Pit Garage) | FWF | 1 | 0285 | Event Portables (subhire) | PG01 - Toilet (Pit Garage) | Pit lane entry | S01 | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 151 | Delivered | Still to leave
Toilets & amenities | PG03 | Toilet (Pit Garage) | FWF × 1 | 1 |  | Event Portables (subhire) | PG03 - Toilet (Pit Garage) | Pit lane entry | S01 | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 152 | Delivered | Still to leave
Toilets & amenities | PG03 | Toilet (Pit Garage) | FWF | 1 | 0100 | Event Portables (subhire) | PG03 - Toilet (Pit Garage) | Pit lane entry | S01 | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 152 | Delivered | Still to leave
Toilets & amenities | PG05 | Toilet (Pit Garage) | FWF × 1 | 1 |  | Event Portables (subhire) | PG05 - Toilet (Pit Garage) | Pit lane entry | S01 | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 153 | Delivered | Still to leave
Toilets & amenities | PG05 | Toilet (Pit Garage) | FWF | 1 | 0438 | Event Portables (subhire) | PG05 - Toilet (Pit Garage) | Pit lane entry | S01 | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 153 | Delivered | Still to leave
Toilets & amenities | PG29 | Toilet (Pit Garage) | FWF × 1 | 1 |  | Event Portables (subhire) | Tickford Racing | Pit lane entry | S01 | -27.9866 | 153.4278 | Open map | Placed on the map | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | PG29 | Toilet (Pit Garage) | FWF | 1 | 0573 | Event Portables (subhire) | Tickford Racing | Pit lane entry | S01 | -27.9866 | 153.4278 | Open map | Placed on the map | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | SVP01 | Shell V-Power | FWF × 1 | 1 |  | Event Portables (subhire) | Shell V-Power | Island north – by FREIGHT |  | -27.9862 | 153.4278 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | SVP01 | Shell V-Power | FWF | 1 | 0939 | Event Portables (subhire) | Shell V-Power | Island north – by FREIGHT |  | -27.9862 | 153.4278 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0024 | FWF | FWF × 2 | 2 |  | Coates, Event Portables (subhire) | FWF | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4266 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968929 · line 7 | Delivered | Still to leave
Toilets & amenities | T0024 | FWF | FWF | 1 | 0164 | Event Portables (subhire) | FWF | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4266 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0024 | FWF | FWF | 1 | 1211968 | Coates | FWF | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4266 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968929 · line 7 | Delivered | Still to leave
Toilets & amenities | T0162 | FWF · Blanchard Race | FWF × 1 | 1 |  | Event Portables (subhire) | Blanchard Race | Median strip meet-up – pit stop, by FOAM |  | -27.9857 | 153.4274 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0162 | FWF · Blanchard Race | FWF | 1 | 0990 | Event Portables (subhire) | Blanchard Race | Median strip meet-up – pit stop, by FOAM |  | -27.9857 | 153.4274 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0176 | FWF × 2 · Redbull | FWF × 2 | 2 |  | Event Portables (subhire) | Redbull | Island north – by FREIGHT |  | -27.9867 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0176 | FWF × 2 · Redbull | FWF | 1 | 0994 | Event Portables (subhire) | Redbull | Island north – by FREIGHT |  | -27.9867 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0176 | FWF × 2 · Redbull | FWF | 1 | 0576 | Event Portables (subhire) | Redbull | Island north – by FREIGHT |  | -27.9867 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0243 | Toilet Block 6m · WC-TV (sewer connect) | Toilet Block 6m × 1 | 1 |  | Coates | WC-TV (sewer connect) | Island north – by FREIGHT | S04 | -27.9875 | 153.4283 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 10:00 | 9973977 · line 1 | Delivered | Still to leave
Toilets & amenities | T0243 | Toilet Block 6m · WC-TV (sewer connect) | Toilet Block 6m | 1 | 1311144 | Coates | WC-TV (sewer connect) | Island north – by FREIGHT | S04 | -27.9875 | 153.4283 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 10:00 | 9973977 · line 1 | Delivered | Still to leave
Toilets & amenities | WC01 | Toilets | Accessible Toilet × 1, FWF × 2 | 3 |  | Coates | WC01 - Toilets | Pit lane entry | S10 | -27.9834 | 153.4253 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) |  |  | 3 lines on 9968955 | Delivered | Still to leave | off-hire dates differ by line (see units)
Toilets & amenities | WC01 | Toilets | Accessible Toilet | 1 | 1317644 | Coates | WC01 - Toilets | Pit lane entry | S10 | -27.9834 | 153.4253 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 57 | Delivered | Still to leave
Toilets & amenities | WC01 | Toilets | FWF | 1 | 1211958 | Coates | WC01 - Toilets | Pit lane entry | S10 | -27.9834 | 153.4253 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 46 | Delivered | Still to leave
Toilets & amenities | WC01 | Toilets | FWF | 1 | 1211967 | Coates | WC01 - Toilets | Pit lane entry | S10 | -27.9834 | 153.4253 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 69 | Delivered | Still to leave
Toilets & amenities | WC02 | Toilet | FWF × 1 | 1 |  | Coates | WC02 - Toilet | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-02 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 45 | Delivered | Still to leave
Toilets & amenities | WC02 | Toilet | FWF | 1 | 1058086 | Coates | WC02 - Toilet | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-02 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 45 | Delivered | Still to leave
Toilets & amenities | WC04 | Toilet - QAS | FWF × 1 | 1 |  | Coates | WC04 - Toilet - QAS | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-02 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 44 | Delivered | Still to leave
Toilets & amenities | WC04 | Toilet - QAS | FWF | 1 | 1212502 | Coates | WC04 - Toilet - QAS | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-02 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 44 | Delivered | Still to leave
Toilets & amenities | WC05 | Event Operations Compound Toilet - Combo Block (Tanked) | Waste tank × 1, Toilet Block 6m × 1 | 2 |  | Coates | WC05 | Island west parkland entry – by the merch strip |  | -27.9836 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  | 2 lines on 9968955 | Delivered | Still to leave | WC05 is one reference the schedule delivers as TWO rows on the same day — a Toilet Block 6m ("Combo - Tanked") and a Waste tank ("waste tank for WC05"). Both are on site,…; off-hire dates differ by line (see units)
Toilets & amenities | WC05 | Event Operations Compound Toilet - Combo Block (Tanked) | Waste tank | 1 | 1328978 | Coates | WC05 | Island west parkland entry – by the merch strip |  | -27.9836 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 3 | Delivered | Still to leave
Toilets & amenities | WC05 | Event Operations Compound Toilet - Combo Block (Tanked) | Toilet Block 6m | 1 | 1097377 | Coates | WC05 | Island west parkland entry – by the merch strip |  | -27.9836 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968955 · line 1 | Delivered | Still to leave
Toilets & amenities | WC06 | Toilets - Race Admin | FWF × 2 | 2 |  | Coates | WC06 - Toilets - Race Admin | Median strip meet-up – pit stop, by FOAM | S11 | -27.9847 | 153.4265 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 2 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC06 | Toilets - Race Admin | FWF | 1 | 1195658 | Coates | WC06 - Toilets - Race Admin | Median strip meet-up – pit stop, by FOAM | S11 | -27.9847 | 153.4265 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 15 | Delivered | Still to leave
Toilets & amenities | WC06 | Toilets - Race Admin | FWF | 1 | 1212523 | Coates | WC06 - Toilets - Race Admin | Median strip meet-up – pit stop, by FOAM | S11 | -27.9847 | 153.4265 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 58 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF × 20 | 20 |  | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 20 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317643 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 38 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1181004 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 34 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1002538 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 35 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1212552 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 32 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1002566 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 24 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1083300 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 41 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1200595 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 33 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1211959 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 26 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1002715 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 40 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1192643 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 42 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1002651 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 43 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317649 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 27 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317658 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 36 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317632 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 37 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317641 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 39 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317640 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 25 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317626 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 29 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317648 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 31 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317652 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 30 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317647 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 28 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF × 10, Pee Panel × 6, Toilet Block 6m × 2 | 18 |  | Coates, Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 2 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0085 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0551 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0450 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0585 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0993 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0553 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0140 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0089 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0584 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0081 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP01 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP04 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP05 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP06 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP02 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP03 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Toilet Block 6m | 1 | 1268858 | Coates | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Toilet Block 6m | 1 | 1311146 | Coates | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 105 | Delivered | Still to leave
Toilets & amenities | WC10 | Toilets | FWF × 3 | 3 |  | Event Portables (subhire) | WC10 - Toilets | Median strip meet-up – pit stop, by FOAM | S01 | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 114 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC10 | Toilets | FWF | 1 | 0488 | Event Portables (subhire) | WC10 - Toilets | Median strip meet-up – pit stop, by FOAM | S01 | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 114 | Pending | Still to leave
Toilets & amenities | WC10 | Toilets | FWF | 1 | 0677 | Event Portables (subhire) | WC10 - Toilets | Median strip meet-up – pit stop, by FOAM | S01 | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 114 | Pending | Still to leave
Toilets & amenities | WC10 | Toilets | FWF | 1 | 0119 | Event Portables (subhire) | WC10 - Toilets | Median strip meet-up – pit stop, by FOAM | S01 | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 114 | Pending | Still to leave
Toilets & amenities | WC100 |  | FWF Trailer × 2 | 2 |  | Coates | 1288823 at The Spit · 1248439 at S18 | Pit lane entry |  |  |  |  | No position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 2 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC100 |  | FWF Trailer | 1 | 1248439 | Coates | 1288823 at The Spit · 1248439 at S18 | Pit lane entry |  |  |  |  | No position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 13 | Delivered | Still to leave
Toilets & amenities | WC100 |  | FWF Trailer | 1 | 1288823 | Coates | 1288823 at The Spit · 1248439 at S18 | Pit lane entry |  |  |  |  | No position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 12 | Delivered | Still to leave
Toilets & amenities | WC11 | Toilets | FWF × 2 | 2 |  | Coates | WC11 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 2 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC11 | Toilets | FWF | 1 | 1211969 | Coates | WC11 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 6 | Delivered | Still to leave
Toilets & amenities | WC11 | Toilets | FWF | 1 | 1211976 | Coates | WC11 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 23 | Delivered | Still to leave
Toilets & amenities | WC12 | Toilets | FWF × 4 | 4 |  | Coates | WC12 - Toilets | Pit lane entry | S01 | -27.9855 | 153.4273 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  | 4 lines on 9968955 | Delivered | Still to leave | off-hire dates differ by line (see units)
Toilets & amenities | WC12 | Toilets | FWF | 1 | 1002565 | Coates | WC12 - Toilets | Pit lane entry | S01 | -27.9855 | 153.4273 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 17 | Delivered | Still to leave
Toilets & amenities | WC12 | Toilets | FWF | 1 | 1200601 | Coates | WC12 - Toilets | Pit lane entry | S01 | -27.9855 | 153.4273 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 5 | Delivered | Still to leave
Toilets & amenities | WC12 | Toilets | FWF | 1 | 1211961 | Coates | WC12 - Toilets | Pit lane entry | S01 | -27.9855 | 153.4273 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 4 | Delivered | Still to leave
Toilets & amenities | WC12 | Toilets | FWF | 1 | 1211963 | Coates | WC12 - Toilets | Pit lane entry | S01 | -27.9855 | 153.4273 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 158 | Delivered | Still to leave
Toilets & amenities | WC13 | Toilets | FWF × 2 | 2 |  | Event Portables (subhire) | WC13 - Toilets | Pit lane entry |  | -27.991 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 122 | Pending | Still to leave
Toilets & amenities | WC13 | Toilets | FWF | 1 | 0036 | Event Portables (subhire) | WC13 - Toilets | Pit lane entry |  | -27.991 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 122 | Pending | Still to leave
Toilets & amenities | WC13 | Toilets | FWF | 1 | 0444 | Event Portables (subhire) | WC13 - Toilets | Pit lane entry |  | -27.991 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 122 | Pending | Still to leave
Toilets & amenities | WC15 | Toilets (Sewer Connect) | Toilet Block 6m × 2 | 2 |  | Coates | WC15 - Toilets (Sewer Connect) | Island north – by FREIGHT | S01 | -27.986 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 2 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC15 | Toilets (Sewer Connect) | Toilet Block 6m | 1 | 1327226 | Coates | WC15 - Toilets (Sewer Connect) | Island north – by FREIGHT | S01 | -27.986 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 55 | Delivered | Still to leave
Toilets & amenities | WC15 | Toilets (Sewer Connect) | Toilet Block 6m | 1 | 1303835 | Coates | WC15 - Toilets (Sewer Connect) | Island north – by FREIGHT | S01 | -27.986 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 56 | Delivered | Still to leave
Toilets & amenities | WC16 | S01 Corporate Toilets - 1x Female, x Male (Sewer) | Toilet Block 6m × 2 | 2 |  | Coates | WC16 - S01 Corporate Toilets - 1x Female, x Male (Sewer) | Pit lane entry | S01 | -27.9859 | 153.4277 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 2 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC16 | S01 Corporate Toilets - 1x Female, x Male (Sewer) | Toilet Block 6m | 1 | 1322587 | Coates | WC16 - S01 Corporate Toilets - 1x Female, x Male (Sewer) | Pit lane entry | S01 | -27.9859 | 153.4277 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 10 | Delivered | Still to leave
Toilets & amenities | WC16 | S01 Corporate Toilets - 1x Female, x Male (Sewer) | Toilet Block 6m | 1 | 1322588 | Coates | WC16 - S01 Corporate Toilets - 1x Female, x Male (Sewer) | Pit lane entry | S01 | -27.9859 | 153.4277 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 11 | Delivered | Still to leave
Toilets & amenities | WC17 | S01 Corporate Toilets | Toilet Block 6m × 2 | 2 |  | Coates | WC17 - S01 Corporate Toilets | Island north – by FREIGHT | S02 | -27.9865 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 2 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC17 | S01 Corporate Toilets | Toilet Block 6m | 1 | 1327224 | Coates | WC17 - S01 Corporate Toilets | Island north – by FREIGHT | S02 | -27.9865 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 20 | Delivered | Still to leave
Toilets & amenities | WC17 | S01 Corporate Toilets | Toilet Block 6m | 1 | 1327223 | Coates | WC17 - S01 Corporate Toilets | Island north – by FREIGHT | S02 | -27.9865 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 21 | Delivered | Still to leave
Toilets & amenities | WC19 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC19 - Toilets | Island north – by FREIGHT | S04 | -27.9882 | 153.4283 | Open map | Master plan position | 2026-11-02 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 117 | Pending | Still to leave
Toilets & amenities | WC19 | Toilets | FWF | 1 | 0435 | Event Portables (subhire) | WC19 - Toilets | Island north – by FREIGHT | S04 | -27.9882 | 153.4283 | Open map | Master plan position | 2026-11-02 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 117 | Pending | Still to leave
Toilets & amenities | WC20 | Toilets (Tank Mounted) | Toilet Block 6m × 2, Waste tank × 2 | 4 |  | Coates | WC20 - Toilets (Tank Mounted) | Island north – by FREIGHT | S04 | -27.9875 | 153.4282 | Open map | Master plan position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 4 lines on 9968955 | Delivered | Still to leave | WC20 — Set 1 number/type transcription correction Source: Andrew’s direct instructions: “1327228 is a toilet”; “1311341 is a waste tank”. Individual source-message timestamps…
Toilets & amenities | WC20 | Toilets (Tank Mounted) | Toilet Block 6m | 1 | 1327228 | Coates | WC20 - Toilets (Tank Mounted) | Island north – by FREIGHT | S04 | -27.9875 | 153.4282 | Open map | Master plan position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 47 | Delivered | Still to leave
Toilets & amenities | WC20 | Toilets (Tank Mounted) | Toilet Block 6m | 1 | 1327225 | Coates | WC20 - Toilets (Tank Mounted) | Island north – by FREIGHT | S04 | -27.9875 | 153.4282 | Open map | Master plan position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 48 | Delivered | Still to leave
Toilets & amenities | WC20 | Toilets (Tank Mounted) | Waste tank | 1 | 1311341 | Coates | WC20 - Toilets (Tank Mounted) | Island north – by FREIGHT | S04 | -27.9875 | 153.4282 | Open map | Master plan position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 49 | Delivered | Still to leave
Toilets & amenities | WC20 | Toilets (Tank Mounted) | Waste tank | 1 | 1328982 | Coates | WC20 - Toilets (Tank Mounted) | Island north – by FREIGHT | S04 | -27.9875 | 153.4282 | Open map | Master plan position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 50 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF × 6 | 6 |  | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 6 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1002747 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 14 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1103497 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 19 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1211964 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 8 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1211971 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 16 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1211977 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 7 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1212172 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 18 | Delivered | Still to leave
Toilets & amenities | WC23 | Toilets | FWF × 5 | 5 |  | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0992 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0968 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0960 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0107 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0969 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC24 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC24 - Toilets | Pit lane entry |  | -27.991 | 153.4297 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 121 | Pending | Still to leave
Toilets & amenities | WC24 | Toilets | FWF | 1 | 0489 | Event Portables (subhire) | WC24 - Toilets | Pit lane entry |  | -27.991 | 153.4297 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 121 | Pending | Still to leave
Toilets & amenities | WC25 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC25 - Toilets | Pit lane entry | S15 | -27.9901 | 153.4288 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 118 | Pending | Still to leave
Toilets & amenities | WC25 | Toilets | FWF | 1 | 0472 | Event Portables (subhire) | WC25 - Toilets | Pit lane entry | S15 | -27.9901 | 153.4288 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 118 | Pending | Still to leave
Toilets & amenities | WC26 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC26 - Toilets | Pit lane entry |  | -27.9888 | 153.4296 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 120 | Pending | Still to leave
Toilets & amenities | WC26 | Toilets | FWF | 1 | 0075 | Event Portables (subhire) | WC26 - Toilets | Pit lane entry |  | -27.9888 | 153.4296 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 120 | Pending | Still to leave
Toilets & amenities | WC27 | Toilet (Tank Mounted) | Toilet Block 6m × 1, Waste tank × 1 | 2 |  | Coates | WC27 - Toilet (Tank Mounted) | Main Beach Pde land side – by T8 / A19 | S08 | -27.9852 | 153.4295 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  | 2 lines on 9968955 | Delivered | Still to leave | off-hire dates differ by line (see units)
Toilets & amenities | WC27 | Toilet (Tank Mounted) | Toilet Block 6m | 1 | 1119484 | Coates | WC27 - Toilet (Tank Mounted) | Main Beach Pde land side – by T8 / A19 | S08 | -27.9852 | 153.4295 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 52 | Delivered | Still to leave
Toilets & amenities | WC27 | Toilet (Tank Mounted) | Waste tank | 1 | 1328979 | Coates | WC27 - Toilet (Tank Mounted) | Main Beach Pde land side – by T8 / A19 | S08 | -27.9852 | 153.4295 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 54 | Delivered | Still to leave
Toilets & amenities | WC28 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC28 - Toilets | Pit lane entry |  | -27.9834 | 153.4292 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 123 | Pending | Still to leave
Toilets & amenities | WC28 | Toilets | FWF | 1 | 0102 | Event Portables (subhire) | WC28 - Toilets | Pit lane entry |  | -27.9834 | 153.4292 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 123 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF × 7 | 7 |  | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0079 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0546 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0707 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0564 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0044 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0441 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0598 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF × 8 | 8 |  | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0428 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0440 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0963 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0681 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0043 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0419 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0545 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0024 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC31 | Toilets | Accessible Toilet × 1, 16Pan Block × 2 | 3 |  | Coates, Event Portables (subhire) | WC31 - Toilets | The Hill – entry point A47 | S25 | -27.9825 | 153.4252 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 97 | Delivered | Still to leave
Toilets & amenities | WC31 | Toilets | Accessible Toilet | 1 | 1317645 | Coates | WC31 - Toilets | The Hill – entry point A47 | S25 | -27.9825 | 153.4252 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 97 | Delivered | Still to leave
Toilets & amenities | WC31 | Toilets | 16Pan Block | 1 | 12 | Event Portables (subhire) | WC31 - Toilets | The Hill – entry point A47 | S25 | -27.9825 | 153.4252 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 97 | Delivered | Still to leave
Toilets & amenities | WC31 | Toilets | 16Pan Block | 1 | 74 | Event Portables (subhire) | WC31 - Toilets | The Hill – entry point A47 | S25 | -27.9825 | 153.4252 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 97 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF × 17 | 17 |  | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0634 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0582 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0548 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0782 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0657 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0912 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0554 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0920 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0971 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0586 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0487 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0790 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0297 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0456 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0012 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0938 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0597 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC34 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC34 - Toilets | The Hill – entry point A47 |  | -27.9823 | 153.4259 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 100 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC34 | Toilets | FWF | 1 | 0526 | Event Portables (subhire) | WC34 - Toilets | The Hill – entry point A47 |  | -27.9823 | 153.4259 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 100 | Pending | Still to leave
Toilets & amenities | WC35 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC35 - Toilets | Pit lane entry |  | -27.9818 | 153.4278 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 126 | Pending | Still to leave
Toilets & amenities | WC35 | Toilets | FWF | 1 | 0284 | Event Portables (subhire) | WC35 - Toilets | Pit lane entry |  | -27.9818 | 153.4278 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 126 | Pending | Still to leave
Toilets & amenities | WC38 | Toilet | FWF × 1 | 1 |  | Event Portables (subhire) | WC38 - Toilet | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 88 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC38 | Toilet | FWF | 1 | 0183 | Event Portables (subhire) | WC38 - Toilet | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 88 | Pending | Still to leave
Toilets & amenities | WC39 | Toilets | FWF × 2 | 2 |  | Event Portables (subhire) | WC39 - Toilets | Commodore Park drop point (red dot) |  | -27.9836 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 89 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC39 | Toilets | FWF | 1 | 0188 | Event Portables (subhire) | WC39 - Toilets | Commodore Park drop point (red dot) |  | -27.9836 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 89 | Pending | Still to leave
Toilets & amenities | WC39 | Toilets | FWF | 1 | 0637 | Event Portables (subhire) | WC39 - Toilets | Commodore Park drop point (red dot) |  | -27.9836 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 89 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF × 5 | 5 |  | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0626 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0541 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0965 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0433 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0648 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC41 | Toilets | FWF × 10 | 10 |  | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0521 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0996 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0191 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0669 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0643 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0517 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0682 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0651 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0065 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0518 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC42 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC42 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9833 | 153.4248 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 155 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC42 | Toilets | FWF | 1 | 0141 | Event Portables (subhire) | WC42 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9833 | 153.4248 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 155 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF × 10 | 10 |  | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0723 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0056 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0161 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0182 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0528 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0696 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0420 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0961 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0646 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0581 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC44 | Toilets | FWF × 2 | 2 |  | Event Portables (subhire) | WC44 - Toilets | Pit lane entry | S05 | -27.989 | 153.4283 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 80 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC44 | Toilets | FWF | 1 | 0146 | Event Portables (subhire) | WC44 - Toilets | Pit lane entry | S05 | -27.989 | 153.4283 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 80 | Delivered | Still to leave
Toilets & amenities | WC44 | Toilets | FWF | 1 | 0037 | Event Portables (subhire) | WC44 - Toilets | Pit lane entry | S05 | -27.989 | 153.4283 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 80 | Delivered | Still to leave
Toilets & amenities | WC45 | Toilets | FWF × 8 | 8 |  | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0542 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0086 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0947 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0544 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0632 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0562 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0549 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0673 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC46 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC46 - Toilets | Pit lane entry |  | -27.9922 | 153.4294 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 127 | Pending | Still to leave
Toilets & amenities | WC46 | Toilets | FWF | 1 | 0525 | Event Portables (subhire) | WC46 - Toilets | Pit lane entry |  | -27.9922 | 153.4294 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 127 | Pending | Still to leave
Toilets & amenities | WC47 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC47 - Toilets | Pit lane entry | S15 | -27.9902 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 116 | Pending | Still to leave
Toilets & amenities | WC47 | Toilets | FWF | 1 | 0949 | Event Portables (subhire) | WC47 - Toilets | Pit lane entry | S15 | -27.9902 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 116 | Pending | Still to leave
Toilets & amenities | WC48 | Toilets | FWF × 4 | 4 |  | Event Portables (subhire) | WC48 - Toilets | Pit lane entry |  | -27.9937 | 153.4305 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 109 | Pending | Still to leave
Toilets & amenities | WC48 | Toilets | FWF | 1 | 0050 | Event Portables (subhire) | WC48 - Toilets | Pit lane entry |  | -27.9937 | 153.4305 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 109 | Pending | Still to leave
Toilets & amenities | WC48 | Toilets | FWF | 1 | 0471 | Event Portables (subhire) | WC48 - Toilets | Pit lane entry |  | -27.9937 | 153.4305 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 109 | Pending | Still to leave
Toilets & amenities | WC48 | Toilets | FWF | 1 | 0289 | Event Portables (subhire) | WC48 - Toilets | Pit lane entry |  | -27.9937 | 153.4305 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 109 | Pending | Still to leave
Toilets & amenities | WC48 | Toilets | FWF | 1 | 0486 | Event Portables (subhire) | WC48 - Toilets | Pit lane entry |  | -27.9937 | 153.4305 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 109 | Pending | Still to leave
Toilets & amenities | WC49 | Toilets | FWF × 3 | 3 |  | Event Portables (subhire) | WC49 - Toilets | Pit lane entry |  | -27.9938 | 153.4306 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 108 | Pending | Still to leave
Toilets & amenities | WC49 | Toilets | FWF | 1 | 0919 | Event Portables (subhire) | WC49 - Toilets | Pit lane entry |  | -27.9938 | 153.4306 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 108 | Pending | Still to leave
Toilets & amenities | WC49 | Toilets | FWF | 1 | 0907 | Event Portables (subhire) | WC49 - Toilets | Pit lane entry |  | -27.9938 | 153.4306 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 108 | Pending | Still to leave
Toilets & amenities | WC49 | Toilets | FWF | 1 | 0084 | Event Portables (subhire) | WC49 - Toilets | Pit lane entry |  | -27.9938 | 153.4306 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 108 | Pending | Still to leave
Toilets & amenities | WC50 | Toilet | FWF × 1 | 1 |  | Coates | WC50 - Toilet | Pit lane entry | S18 | -27.9898 | 153.4298 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 22 | Delivered | Still to leave
Toilets & amenities | WC50 | Toilet | FWF | 1 | 1211974 | Coates | WC50 - Toilet | Pit lane entry | S18 | -27.9898 | 153.4298 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 22 | Delivered | Still to leave
Toilets & amenities | WC51 | Toilets | Accessible Toilet × 1, FWF × 6 | 7 |  | Coates, Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | Accessible Toilet | 1 | 1197174 | Coates | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0991 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0167 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0653 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0136 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0453 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0028 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC53 | Toilets | FWF × 3 | 3 |  | Event Portables (subhire) | WC53 - Toilets | Pit lane entry |  | -27.9927 | 153.4303 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 156 | Delivered | Still to leave
Toilets & amenities | WC53 | Toilets | FWF | 1 | 0952 | Event Portables (subhire) | WC53 - Toilets | Pit lane entry |  | -27.9927 | 153.4303 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 156 | Delivered | Still to leave
Toilets & amenities | WC53 | Toilets | FWF | 1 | 0951 | Event Portables (subhire) | WC53 - Toilets | Pit lane entry |  | -27.9927 | 153.4303 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 156 | Delivered | Still to leave
Toilets & amenities | WC53 | Toilets | FWF | 1 | 0074 | Event Portables (subhire) | WC53 - Toilets | Pit lane entry |  | -27.9927 | 153.4303 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 156 | Delivered | Still to leave
Toilets & amenities | WC54 | Toilets | FWF × 6 | 6 |  | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0186 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0619 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0071 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0295 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0007 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0087 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC55 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC55 - Toilets | Pit lane entry |  | -27.9912 | 153.4298 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 128 | Pending | Still to leave
Toilets & amenities | WC55 | Toilets | FWF | 1 | 0650 | Event Portables (subhire) | WC55 - Toilets | Pit lane entry |  | -27.9912 | 153.4298 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 128 | Pending | Still to leave
Toilets & amenities | WC56 | Toilets | FWF × 12 | 12 |  | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0721 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0491 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0190 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0294 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0970 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0974 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0004 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0003 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0445 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0088 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0442 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0009 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC57 | Toilets | FWF × 2 | 2 |  | Event Portables (subhire) | WC57 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 107 | Pending | Still to leave
Toilets & amenities | WC57 | Toilets | FWF | 1 | 0915 | Event Portables (subhire) | WC57 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 107 | Pending | Still to leave
Toilets & amenities | WC57 | Toilets | FWF | 1 | 0008 | Event Portables (subhire) | WC57 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 107 | Pending | Still to leave
Toilets & amenities | WC59 | Toilets | FWF × 7 | 7 |  | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0492 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0935 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0497 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0633 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0064 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0066 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0533 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC60 | Toilets (Tank Mounted) | Toilet Block 6m × 2, Waste tank × 2 | 4 |  | Coates | WC60 - Toilets (Tank Mounted) | Seaside north – between S21 and S22 | S21 | -27.9853 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 4 lines on 9968955 | Delivered | Still to leave
Toilets & amenities | WC60 | Toilets (Tank Mounted) | Toilet Block 6m | 1 | 1087500 | Coates | WC60 - Toilets (Tank Mounted) | Seaside north – between S21 and S22 | S21 | -27.9853 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 91 | Delivered | Still to leave
Toilets & amenities | WC60 | Toilets (Tank Mounted) | Toilet Block 6m | 1 | 1119489 | Coates | WC60 - Toilets (Tank Mounted) | Seaside north – between S21 and S22 | S21 | -27.9853 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 93 | Delivered | Still to leave
Toilets & amenities | WC60 | Toilets (Tank Mounted) | Waste tank | 1 | 1328980 | Coates | WC60 - Toilets (Tank Mounted) | Seaside north – between S21 and S22 | S21 | -27.9853 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 94 | Delivered | Still to leave
Toilets & amenities | WC60 | Toilets (Tank Mounted) | Waste tank | 1 | 1328981 | Coates | WC60 - Toilets (Tank Mounted) | Seaside north – between S21 and S22 | S21 | -27.9853 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 95 | Delivered | Still to leave
Toilets & amenities | WC61 | Toilets | FWF × 8 | 8 |  | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0645 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0105 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0945 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0977 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0547 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0290 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0038 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0015 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC62 | Toilets | FWF × 2 | 2 |  | Event Portables (subhire) | WC62 - Toilets | Pit lane entry |  | -27.9817 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 129 | Pending | Still to leave
Toilets & amenities | WC62 | Toilets | FWF | 1 | 0976 | Event Portables (subhire) | WC62 - Toilets | Pit lane entry |  | -27.9817 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 129 | Pending | Still to leave
Toilets & amenities | WC62 | Toilets | FWF | 1 | 0103 | Event Portables (subhire) | WC62 - Toilets | Pit lane entry |  | -27.9817 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 129 | Pending | Still to leave
Toilets & amenities | WC65 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC65 - Toilets | The Hill – entry point A47 |  | -27.9815 | 153.4264 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 130 | Pending | Still to leave
Toilets & amenities | WC65 | Toilets | FWF | 1 | 0033 | Event Portables (subhire) | WC65 - Toilets | The Hill – entry point A47 |  | -27.9815 | 153.4264 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 130 | Pending | Still to leave
Toilets & amenities | WC67 | Toilets | FWF × 4 | 4 |  | Coates, Event Portables (subhire) | WC67 - Toilets | Helen Park drop point (red dot) | S23 | -27.9814 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 140 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC67 | Toilets | FWF | 1 | 0793 | Event Portables (subhire) | WC67 - Toilets | Helen Park drop point (red dot) | S23 | -27.9814 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 84 | Delivered | Still to leave
Toilets & amenities | WC67 | Toilets | FWF | 1 | 0769 | Event Portables (subhire) | WC67 - Toilets | Helen Park drop point (red dot) | S23 | -27.9814 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 84 | Delivered | Still to leave
Toilets & amenities | WC67 | Toilets | FWF | 1 | 172824 | Coates | WC67 - Toilets | Helen Park drop point (red dot) | S23 | -27.9814 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 140 | Delivered | Still to leave
Toilets & amenities | WC67 | Toilets | FWF | 1 | 0714 | Event Portables (subhire) | WC67 - Toilets | Helen Park drop point (red dot) | S23 | -27.9814 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 84 | Delivered | Still to leave
Toilets & amenities | WC68 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC68 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4244 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 131 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC68 | Toilets | FWF | 1 | 0426 | Event Portables (subhire) | WC68 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4244 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 131 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF × 12 | 12 |  | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0152 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0078 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0010 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0070 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0958 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0647 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0622 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0123 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0432 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0692 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0679 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0592 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC70 | Toilet | FWF × 1 | 1 |  | Event Portables (subhire) | WC70 - Toilet | Helen Park drop point (red dot) | S23 | -27.9817 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 85 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC70 | Toilet | FWF | 1 | 0423 | Event Portables (subhire) | WC70 - Toilet | Helen Park drop point (red dot) | S23 | -27.9817 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 85 | Pending | Still to leave
Toilets & amenities | WC71 | Toilets | FWF × 8 | 8 |  | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0280 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0116 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0279 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0293 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0531 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0644 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0552 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0490 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC72 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | WC72 - Toilets | Helen Park drop point (red dot) | S23 | -27.9821 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 132 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC72 | Toilets | FWF | 1 | 0699 | Event Portables (subhire) | WC72 - Toilets | Helen Park drop point (red dot) | S23 | -27.9821 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 132 | Pending | Still to leave
Toilets & amenities | WC73 | Toilets | FWF × 2 | 2 |  | Event Portables (subhire) | WC73 - Toilets | Island north – by FREIGHT | S02 | -27.987 | 153.4281 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 133 | Pending | Still to leave | subhire: Event Portables
Toilets & amenities | WC73 | Toilets | FWF | 1 | 0765 | Event Portables (subhire) | WC73 - Toilets | Island north – by FREIGHT | S02 | -27.987 | 153.4281 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 133 | Pending | Still to leave
Toilets & amenities | WC73 | Toilets | FWF | 1 | 0192 | Event Portables (subhire) | WC73 - Toilets | Island north – by FREIGHT | S02 | -27.987 | 153.4281 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 133 | Pending | Still to leave
Toilets & amenities | WC81 | Toilet (Cypress) | FWF × 1 | 1 |  | Event Portables (subhire) | WC81 - Toilet (Cypress) | Pit lane entry |  | -27.9975 | 153.4285 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 157 | Delivered | Still to leave | subhire: Event Portables
Toilets & amenities | WC81 | Toilet (Cypress) | FWF | 1 | 0124 | Event Portables (subhire) | WC81 - Toilet (Cypress) | Pit lane entry |  | -27.9975 | 153.4285 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 157 | Delivered | Still to leave
Toilets & amenities | WC85 | Toilets | FWF × 1 | 1 |  | Event Portables (subhire) | Coates compound | Pit lane entry |  | -27.9386 | 153.4265 | Open map | Andrew’s pin | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 134 | Pending | Still to leave
Toilets & amenities | WC85 | Toilets | FWF | 1 | 0135 | Event Portables (subhire) | Coates compound | Pit lane entry |  | -27.9386 | 153.4265 | Open map | Andrew’s pin | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 134 | Pending | Still to leave
Toilets & amenities | WC86 | Toilet | Accessible Toilet × 1 | 1 |  | Coates | WC86 - Toilet | Island north – by FREIGHT | S04 | -27.9877 | 153.4282 | Open map | Master plan position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 51 | Delivered | Still to leave
Toilets & amenities | WC86 | Toilet | Accessible Toilet | 1 | 1296899 | Coates | WC86 - Toilet | Island north – by FREIGHT | S04 | -27.9877 | 153.4282 | Open map | Master plan position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 51 | Delivered | Still to leave
WATER-FILLED BARRIERS |  | 15 references · 375 units
Water-filled barriers | WB01 | Gold Coast Highway (Near PB3 DR - On GCHWY at the Tedder Avenue intersection) | TL2 × 12 | 12 |  | Coates | WB01 Gold Coast Highway (Near PB3 DR - On GCHWY at the Tedder Avenue intersection) | Pit lane entry |  | -27.9821 | 153.4239 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:30 | 9972648 · line 1 | Delivered | Still to leave
Water-filled barriers | WB01 | Gold Coast Highway (Near PB3 DR - On GCHWY at the Tedder Avenue intersection) | TL2 × 12 | 12 |  | Coates | WB01 Gold Coast Highway (Near PB3 DR - On GCHWY at the Tedder Avenue intersection) | Pit lane entry |  | -27.9821 | 153.4239 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:30 | 9972648 · line 1 | Delivered | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB02 | S08 - Pedestrian Pathway along Main Beach Parade | TL2 × 34 | 34 |  | Coates | WB02 S08 - Pedestrian Pathway along Main Beach Parade | Pit lane entry | S08 | -27.9851 | 153.4297 | Open map | From the description | 2026-09-27 | Plan (schedule removal row) | 2026-09-27 | 17:00 | 9972648 · line 3 | Delivered | Still to leave
Water-filled barriers | WB02 | S08 - Pedestrian Pathway along Main Beach Parade | TL2 × 34 | 34 |  | Coates | WB02 S08 - Pedestrian Pathway along Main Beach Parade | Pit lane entry | S08 | -27.9851 | 153.4297 | Open map | From the description | 2026-09-27 | Plan (schedule removal row) | 2026-09-27 | 17:00 | 9972648 · line 3 | Delivered | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB03 | Gold Coast Highway (Turn 2) - Concrete small blocks | TL2 × 30 | 30 |  | Coates | WB03 Gold Coast Highway (Turn 2) - Concrete small blocks | Pit lane entry | S15 | -27.9901 | 153.4286 | Open map | From the description | 2026-10-19 | Plan (schedule removal row) | 2026-10-19 | 22:00 | 9972648 · line 2 | Delivered | Still to leave
Water-filled barriers | WB03 | Gold Coast Highway (Turn 2) - Concrete small blocks | TL2 × 30 | 30 |  | Coates | WB03 Gold Coast Highway (Turn 2) - Concrete small blocks | Pit lane entry | S15 | -27.9901 | 153.4286 | Open map | From the description | 2026-10-19 | Plan (schedule removal row) | 2026-10-19 | 22:00 | 9972648 · line 2 | Delivered | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB04 | Helen Park - HVM | TL2 × 14 | 14 |  | Coates | WB04 Helen Park - HVM | Pit lane entry | S23 | -27.9812 | 153.4238 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 09:00 | 9972648 · line 4 | Del Req | Still to leave
Water-filled barriers | WB04 | Helen Park - HVM | TL2 × 14 | 14 |  | Coates | WB04 Helen Park - HVM | Pit lane entry | S23 | -27.9812 | 153.4238 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 09:00 | 9972648 · line 4 | Del Req | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB05 | Gold Coast Highway (Main Beach Light Rail) | TL2 × 13 | 13 |  | Coates | WB05 Gold Coast Highway (Main Beach Light Rail) | Pit lane entry |  | -27.9821 | 153.4235 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:00 | 9972648 · line 5 | Del Req | Still to leave
Water-filled barriers | WB05 | Gold Coast Highway (Main Beach Light Rail) | TL2 × 13 | 13 |  | Coates | WB05 Gold Coast Highway (Main Beach Light Rail) | Pit lane entry |  | -27.9821 | 153.4235 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:00 | 9972648 · line 5 | Del Req | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB06 | Gold Coast Highway Macintosh Park Turning Lane (Grandstand Barriers) | TL2 × 154 | 154 |  | Coates | WB06 Gold Coast Highway Macintosh Park Turning Lane (Grandstand Barriers) | Pit lane entry |  | -27.9859 | 153.4268 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:00 | 9972648 · line 6 | Delivered | Still to leave
Water-filled barriers | WB06 | Gold Coast Highway Macintosh Park Turning Lane (Grandstand Barriers) | TL2 × 154 | 154 |  | Coates | WB06 Gold Coast Highway Macintosh Park Turning Lane (Grandstand Barriers) | Pit lane entry |  | -27.9859 | 153.4268 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:00 | 9972648 · line 6 | Delivered | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB07 | Admiralty Drive Intersection (Through lane removed between centre islands) | TL2 × 17 | 17 |  | Coates | WB07 Admiralty Drive Intersection (Through lane removed between centre islands) | Pit lane entry | S14 | -27.987 | 153.4267 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 09:00 | 9972648 · line 7 | Pending | Still to leave
Water-filled barriers | WB07 | Admiralty Drive Intersection (Through lane removed between centre islands) | TL2 × 17 | 17 |  | Coates | WB07 Admiralty Drive Intersection (Through lane removed between centre islands) | Pit lane entry | S14 | -27.987 | 153.4267 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 09:00 | 9972648 · line 7 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB13 | Fence bracing behind S15 | TL2 × 10 | 10 |  | Coates | WB13 Fence bracing behind S15 | Pit lane entry | S15 | -27.9906 | 153.4285 | Open map | From the description | 2026-10-26 | Plan (schedule removal row) | 2026-10-26 | 10:00 | 9972648 · line 8 | Del Req | Still to leave
Water-filled barriers | WB13 | Fence bracing behind S15 | TL2 × 10 | 10 |  | Coates | WB13 Fence bracing behind S15 | Pit lane entry | S15 | -27.9906 | 153.4285 | Open map | From the description | 2026-10-26 | Plan (schedule removal row) | 2026-10-26 | 10:00 | 9972648 · line 8 | Del Req | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB14 | MP4.0 Turn 4 Drivers Right | TL2 × 2 | 2 |  | Coates | WB14 MP4.0 Turn 4 Drivers Right | Pit lane entry |  | -27.9918 | 153.4295 | Open map | From the description | 2026-10-25 | Plan (schedule removal row) | 2026-10-27 | 07:00 | 9972648 · line 9 | Pending | Still to leave
Water-filled barriers | WB14 | MP4.0 Turn 4 Drivers Right | TL2 × 2 | 2 |  | Coates | WB14 MP4.0 Turn 4 Drivers Right | Pit lane entry |  | -27.9918 | 153.4295 | Open map | From the description | 2026-10-25 | Plan (schedule removal row) | 2026-10-27 | 07:00 | 9972648 · line 9 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB15 | Turn 11 Runoff (Main Beach Parade North) - HVM | TL2 × 4 | 4 |  | Coates | WB15 Turn 11 Runoff (Main Beach Parade North) - HVM | Pit lane entry |  | -27.9817 | 153.4291 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 07:00 | 9972648 · line 10 | Pending | Still to leave
Water-filled barriers | WB15 | Turn 11 Runoff (Main Beach Parade North) - HVM | TL2 × 4 | 4 |  | Coates | WB15 Turn 11 Runoff (Main Beach Parade North) - HVM | Pit lane entry |  | -27.9817 | 153.4291 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 07:00 | 9972648 · line 10 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB16 | Commodore Park (Commodore Drive) | TL2 × 13 | 13 |  | Coates | WB16 Commodore Park (Commodore Drive) | Pit lane entry |  | -27.9831 | 153.424 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:00 | 9972648 · line 11 | Pending | Still to leave
Water-filled barriers | WB16 | Commodore Park (Commodore Drive) | TL2 × 13 | 13 |  | Coates | WB16 Commodore Park (Commodore Drive) | Pit lane entry |  | -27.9831 | 153.424 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:00 | 9972648 · line 11 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB17 | Racing kerbs (T6/7/8/9) | TL2 × 6 | 6 |  | Coates | WB17 Racing kerbs (T6/7/8/9) | Pit lane entry | S20 | -27.9857 | 153.4299 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 17:00 | 9972648 · line 12 | Pending | Still to leave
Water-filled barriers | WB17 | Racing kerbs (T6/7/8/9) | TL2 × 6 | 6 |  | Coates | WB17 Racing kerbs (T6/7/8/9) | Pit lane entry | S20 | -27.9857 | 153.4299 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 17:00 | 9972648 · line 12 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB18 | Racing kerbs (T2) | TL2 × 2 | 2 |  | Coates | WB18 Racing kerbs (T2) | Pit lane entry | S15 | -27.9901 | 153.4286 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 17:00 | 9972648 · line 13 | Pending | Still to leave
Water-filled barriers | WB18 | Racing kerbs (T2) | TL2 × 2 | 2 |  | Coates | WB18 Racing kerbs (T2) | Pit lane entry | S15 | -27.9901 | 153.4286 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 17:00 | 9972648 · line 13 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB19 | S08 - Pedestrian Pathway along Main Beach Parade | TL2 × 34 | 34 |  | Coates | WB19 S08 - Pedestrian Pathway along Main Beach Parade | Pit lane entry | S08 | -27.9851 | 153.4297 | Open map | From the description | 2026-11-06 | Plan (schedule removal row) | 2026-11-06 | 17:00 | 9972648 · line 15 | Pending | Not on site
Water-filled barriers | WB19 | S08 - Pedestrian Pathway along Main Beach Parade | TL2 × 34 | 34 |  | Coates | WB19 S08 - Pedestrian Pathway along Main Beach Parade | Pit lane entry | S08 | -27.9851 | 153.4297 | Open map | From the description | 2026-11-06 | Plan (schedule removal row) | 2026-11-06 | 17:00 | 9972648 · line 15 | Pending | Not on site | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB20 | Gold Coast Highway (Turn 2) | TL2 × 30 | 30 |  | Coates | WB20 Gold Coast Highway (Turn 2) | Pit lane entry | S15 | -27.9901 | 153.4286 | Open map | From the description | 2026-10-29 | Plan (schedule removal row) | 2026-10-29 | 19:00 | 9972648 · line 14 | Pending | Not on site
Water-filled barriers | WB20 | Gold Coast Highway (Turn 2) | TL2 × 30 | 30 |  | Coates | WB20 Gold Coast Highway (Turn 2) | Pit lane entry | S15 | -27.9901 | 153.4286 | Open map | From the description | 2026-10-29 | Plan (schedule removal row) | 2026-10-29 | 19:00 | 9972648 · line 14 | Pending | Not on site | quantity item, code ARMORZONMASHTL2
VARIABLE MESSAGE SIGNS |  | 4 references · 24 units
Variable message signs | T0001 | VMS × 8 | VMS × 8 | 8 |  | Coates | VMS × 8 | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 7 lines on 9961265 | Delivered | Still to leave | VMS board numbering on site — Andrew Fisher, 14 Sep 2026: vms1 1211354 vms2 1211370 vms3 1271129 vms4 1191877 vms5 1211404 vms6 1211359 vms7 1182999 vms8 1211383 All eight…
Variable message signs | T0001 | VMS × 8 | VMS02 · VMS board | 1 | 1211370 | Coates | Position 02a · Confirmed board location (moved from 02: Waterways Drive northbound) |  |  | -27.9833 | 153.4251 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 3 | Delivered | Still to leave | rego ES3206 · positions 02 → 02a
Variable message signs | T0001 | VMS × 8 | VMS01 · VMS board | 1 | 1211354 | Coates | Position 01 · Gold Coast Highway (median strip), south of Queen St intersection |  |  | -27.9737 | 153.4203 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 4 | Delivered | Still to leave | rego EX0017 · positions 01
Variable message signs | T0001 | VMS × 8 | VMS07 · VMS board | 1 | 1182999 | Coates | Position 07 · Main Beach Parade southbound |  |  | -27.9781 | 153.429 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 5 | Delivered | Still to leave | rego 410UFQ · positions 07a → 07
Variable message signs | T0001 | VMS × 8 | VMS04 · VMS board | 1 | 1191877 | Coates | Position 04 · Admiralty Drive eastbound, Gold Coast Highway intersection |  |  | -27.9867 | 153.427 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 6 | Delivered | Still to leave | rego EM6306 · positions 04
Variable message signs | T0001 | VMS × 8 | VMS06 · VMS board | 1 | 1211359 | Coates | Position 06 · Gold Coast Highway northbound at Birt Ave, median strip, 'The Marriott' |  |  | -27.9927 | 153.428 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 7 | Delivered | Still to leave | rego ER9247 · positions 06
Variable message signs | T0001 | VMS × 8 | VMS08 · VMS board | 1 | 1211383 | Coates | Position 08 · Gold Coast Highway northbound, south of Staghorn intersection |  |  | -27.9955 | 153.4277 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 8 | Delivered | Still to leave | rego ER9381 · positions 08
Variable message signs | T0001 | VMS × 8 | VMS03 · VMS board | 1 | 1271129 | Coates | Position 03a · Confirmed board location (moved from 03: Gold Coast Highway (southbound), north of Breaker St intersection) |  |  | -27.9815 | 153.4234 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 9 | Delivered | Still to leave | rego 536UOO · positions 03 → 03a
Variable message signs | T0001 | VMS × 8 | VMS05 · VMS board | 1 | 1211356 | Coates | Position 05a · Confirmed board location |  |  | -27.9826 | 153.4246 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | rego ER9244 · positions 05a
Variable message signs | T0103 | VMS × 2 | VMS × 2 | 2 |  | Coates, Premiair Hire (subhire) | VMS × 2 | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-09-22 |  | 9961265 · line 1 | Returned | Still to leave | off rent 22 Sep 2026 (actual)
Variable message signs | T0103 | VMS × 2 | VMS09 · VMS board | 1 | 1211404 | Coates | Position 05 · Confirmed board location (moved from 09: Gold Coast Highway (northbound), north of T E Peters Dr intersection (southern end of the Convention Centre)) |  |  | -27.9862 | 153.4283 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 |  | 9961265 · line 12 | Delivered | Still to leave | rego TF15JR · positions 09 → 05
Variable message signs | T0103 | VMS × 2 | VMS10 · VMS board | 1 | 120T | Premiair Hire (subhire) | Position 10 · Old Burleigh Rd (northbound), south of Queensland Ave intersection |  |  | -28.0297 | 153.4341 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 |  | 9961265 · line 13 | Delivered | Still to leave | rego V14221 · positions 10
Variable message signs | T0128 | VMS × 2 | VMS × 2 | 2 |  | Coates, Premiair Hire (subhire) | VMS × 2 | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 |  | 9961265 · line 16 | Del Req | Still to leave
Variable message signs | T0128 | VMS × 2 | VMS11 · VMS board | 1 | 467T | Premiair Hire (subhire) | Position 11 · Confirmed board location |  |  | -27.9862 | 153.4283 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 |  | 9961265 · line 15 | Del Req | Still to leave | rego TE97G · positions 11
Variable message signs | T0128 | VMS × 2 | VMS12 · VMS board | 1 | 1211646 | Coates | Position 12 · Macintosh Island Park, co-located with WC16 |  |  | -27.9859 | 153.4277 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 |  | 9961265 · line 16 | Del Req | Still to leave | rego TF59LR · positions 12
Variable message signs | T0158 | VMS × 9 | VMS × 9 | 9 |  | Coates, Premiair Hire (subhire) | VMS × 9 | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 5 lines on 9961265 | Del Req | Still to leave
Variable message signs | T0158 | VMS × 9 | VMS18 · VMS board | 1 | 472T | Premiair Hire (subhire) | Position 18 · Confirmed board location |  |  | -27.9931 | 153.4282 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 | 07:00 | 9961265 · line 24 | Del Req | Still to leave | rego TE58GZ · positions 18
Variable message signs | T0158 | VMS × 9 | VMS19 · VMS board | 1 | 487T | Premiair Hire (subhire) | Position 19 · Confirmed board location |  |  | -27.9851 | 153.4273 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 | 07:00 | 9961265 · line 25 | Del Req | Still to leave | rego TE02H0 · positions 19
Variable message signs | T0158 | VMS × 9 | VMS20 · VMS board | 1 | 475T | Premiair Hire (subhire) | Position 20 · Confirmed board location |  |  | -27.9935 | 153.4305 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 | 07:00 | 9961265 · line 26 | Del Req | Still to leave | rego TE88HN · positions 20
Variable message signs | T0158 | VMS × 9 | VMS23 · VMS board | 1 | 453T | Premiair Hire (subhire) | Position 23 · Gold Coast Highway (north of Sundale Bridge), eastern side of the road, for southbound traffic |  |  | -27.9748 | 153.4207 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 | 07:00 | 9961265 · line 30 | Del Req | Still to leave | rego TF54CQ · positions 23
Variable message signs | T0158 | VMS × 9 | VMS13 · VMS board | 1 | 1191957 | Coates | Position 13 · Confirmed board location |  |  | -27.9818 | 153.4245 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 32 | Del Req | Still to leave | rego EN3803 · positions 13
Variable message signs | T0158 | VMS × 9 | VMS14 · VMS board | 1 | 1201864 | Coates | Position 14 · Confirmed board location |  |  | -27.9826 | 153.4244 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 34 | Del Req | Still to leave | rego TD98VJ · positions 14
Variable message signs | T0158 | VMS × 9 | VMS15 · VMS board | 1 | 1211348 | Coates | Position 15 · Confirmed board location |  |  | -27.9919 | 153.4294 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 35 | Del Req | Still to leave | rego ER9217 · positions 15
Variable message signs | T0158 | VMS × 9 | VMS16 · VMS board | 1 | 1211376 | Coates | Position 16 · Confirmed board location |  |  | -27.9818 | 153.4291 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 37 | Del Req | Still to leave | rego ES3211 · positions 16
Variable message signs | T0158 | VMS × 9 | VMS17 · VMS board | 1 | 1211364 | Coates | Position 17 · Confirmed board location |  |  | -27.9816 | 153.427 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 39 | Del Req | Still to leave | rego ER9410 · positions 17
Variable message signs | — | VMS boards on the VMS register but on no reference · 3 | VMS | 3 | [10 empty] | Not in the demob plan | [5 empty] | on the board register with their positions; no schedule reference carries them
Variable message signs | — | VMS board on the register | VMS21 · VMS board | 1 | 97T | Premiair Hire (subhire) | Position 21 · Confirmed board location |  |  | -27.9951 | 153.4293 | Open map | VMS register board position |  | Not in the demob plan | 2026-10-26 | 07:00 | 9961265 · line 28 | Pending | Still to leave | rego T16922 · positions 21
Variable message signs | — | VMS board on the register | VMS22 · VMS board | 1 | 445T | Premiair Hire (subhire) | Position 22 · Confirmed board location |  |  | -27.9975 | 153.4306 | Open map | VMS register board position |  | Not in the demob plan | 2026-10-28 | 07:00 | 9961265 · line 29 | Pending | Still to leave | rego TE99CL · positions 22
Variable message signs | — | VMS board on the register | VMS24 · VMS board | 1 | 450T | Premiair Hire (subhire) | Position 24 · Confirmed board location |  |  | -27.9927 | 153.4282 | Open map | VMS register board position |  | Not in the demob plan | 2026-10-26 | 15:00 | 9961265 · line 31 | Pending | Still to leave | rego TE94CL · positions 24
GENERATORS |  | 14 references · 16 units
Generators | GN01 | Generator | 60kva × 1 | 1 |  | Coates | GN01 - Generator | Median strip meet-up – pit stop, by FOAM | S13 | -27.986 | 153.427 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 16 | Delivered | Still to leave
Generators | GN01 | Generator | 60kva | 1 | 1276507 | Coates | GN01 - Generator | Median strip meet-up – pit stop, by FOAM | S13 | -27.986 | 153.427 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 16 | Delivered | Still to leave
Generators | GN03 | Generator | 30kva × 1 | 1 |  | Coates | GN03 - Generator | Island north – by FREIGHT | S04 | -27.988 | 153.428 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 10 | Delivered | Still to leave
Generators | GN03 | Generator | 30kva | 1 | 1320829 | Coates | GN03 - Generator | Island north – by FREIGHT | S04 | -27.988 | 153.428 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 10 | Delivered | Still to leave
Generators | GN04 | Generator | 30kva × 1 | 1 |  | Coates | GN04 - Generator | Pit lane entry | S15 | -27.9905 | 153.4283 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 14 | Del Req | Still to leave
Generators | GN04 | Generator | 30kva | 1 | 1277400 | Coates | GN04 - Generator | Pit lane entry | S15 | -27.9905 | 153.4283 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 14 | Del Req | Still to leave
Generators | GN06 | Generator | 50kva × 1 | 1 |  | Coates | GN06 - Generator | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-10-26 |  | 9961976 · line 48 | Del Req | Still to leave
Generators | GN06 | Generator | 50kva | 1 | 1320828 | Coates | GN06 - Generator | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-10-26 |  | 9961976 · line 48 | Del Req | Still to leave
Generators | GN10 | Generator | 20kva × 1 | 1 |  | Coates | GN10 - Generator | Pit lane entry |  | -27.991 | 153.43 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 13 | Pending | Still to leave
Generators | GN10 | Generator | 20kva | 1 | 1283681 | Coates | GN10 - Generator | Pit lane entry |  | -27.991 | 153.43 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 13 | Pending | Still to leave
Generators | GN13 | Generator | 45kva × 1 | 1 |  | Coates | GN13 - Generator | Main Beach seaside – by the supply compound |  | -27.9884 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-12 |  | 9961976 · line 44 | Delivered | Still to leave
Generators | GN13 | Generator | 45kva | 1 | 1276503 | Coates | GN13 - Generator | Main Beach seaside – by the supply compound |  | -27.9884 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-12 |  | 9961976 · line 44 | Delivered | Still to leave
Generators | GN18 | Generator | 50kva × 1 | 1 |  | Coates | GN18 - Generator | Commodore Park drop point (red dot) |  | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) | 2026-10-26 |  | 9961976 · line 11 | Delivered | Still to leave
Generators | GN18 | Generator | 50kva | 1 | 1261273 | Coates | GN18 - Generator | Commodore Park drop point (red dot) |  | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) | 2026-10-26 |  | 9961976 · line 11 | Delivered | Still to leave
Generators | GN19 | Generator | 60kva × 1 | 1 |  | Coates | GN19 - Generator | The Hill – entry point A47 | S25 | -27.9822 | 153.4245 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 7 | Del Req | Still to leave
Generators | GN19 | Generator | 60kva | 1 | 1276416 | Coates | GN19 - Generator | The Hill – entry point A47 | S25 | -27.9822 | 153.4245 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 7 | Del Req | Still to leave
Generators | GN20-A | S01 (GN20) | 350kva × 1 | 1 |  | Coates | S01 (GN20) | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 6 | Delivered | Still to leave | This is GN20 (S01, 350 kVA), deleted on 20 Oct in error. Andrew, 25 Oct: "i made a error the gn20 is here". Rental 9961976, line 6.
Generators | GN20-A | S01 (GN20) | 350kva | 1 | 1276701 | Coates | S01 (GN20) | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 6 | Delivered | Still to leave
Generators | GN21 | Generator | 60kva × 1 | 1 |  | Coates | GN21 - Generator | Median strip meet-up – pit stop, by FOAM | S13 | -27.9854 | 153.4272 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 38 | Delivered | Still to leave
Generators | GN21 | Generator | 60kva | 1 | 1261284 | Coates | GN21 - Generator | Median strip meet-up – pit stop, by FOAM | S13 | -27.9854 | 153.4272 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 38 | Delivered | Still to leave
Generators | GN23 | Generator | 150kva × 1 | 2 |  | Coates | GN23 - Generator | Island north – by FREIGHT | S02 | -27.9863 | 153.4278 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) |  |  | 2 lines on 9961976 | Delivered | Still to leave | off-hire dates differ by line (see units)
Generators | GN23 | Generator | 150kva | 1 | 1297157 | Coates | GN23 - Generator | Island north – by FREIGHT | S02 | -27.9863 | 153.4278 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 9 | Delivered | Still to leave
Generators | GN23 | Generator | Distribution Board Lifeguard 17 | 1 | 1189078 | Coates | GN23 - Generator | Island north – by FREIGHT | S02 | -27.9863 | 153.4278 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 41 | Delivered | Still to leave | unit on the reference outside its schedule lines
Generators | GN24 | Generator | 60kva × 1 | 1 |  | Coates | GN24 - Generator | Island west parkland entry – by the merch strip |  | -27.9833 | 153.4267 | Open map | Master plan position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 |  | 9961976 · line 49 | Del Req | Still to leave
Generators | GN24 | Generator | 60kva | 1 | 1277089 | Coates | GN24 - Generator | Island west parkland entry – by the merch strip |  | -27.9833 | 153.4267 | Open map | Master plan position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 |  | 9961976 · line 49 | Del Req | Still to leave
Generators | GN25 | Generator | 20kva × 1 | 1 |  | Coates | GN25 - Generator | Pit lane entry |  |  |  |  | No position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 18 | Del Req | Still to leave
Generators | GN25 | Generator | 20kva | 1 | 1244536 | Coates | GN25 - Generator | Pit lane entry |  |  |  |  | No position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 18 | Del Req | Still to leave
Generators | GN? | Concert | 200kva & cables × 2 | 2 |  | Coates | Concert generators · Macintosh Island Park · lawn beside the path junction near the peacock enclosure | Median strip meet-up – pit stop, by FOAM | Concert | -27.9846 | 153.4277 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 2 lines on 9961976 | Delivered | Still to leave
Generators | GN? | Concert | 200kva & cables | 1 | 1316182 | Coates | Concert generators · Macintosh Island Park · lawn beside the path junction near the peacock enclosure | Median strip meet-up – pit stop, by FOAM | Concert | -27.9846 | 153.4277 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 42 | Delivered | Still to leave
Generators | GN? | Concert | 200kva & cables | 1 | 1316183 | Coates | Concert generators · Macintosh Island Park · lawn beside the path junction near the peacock enclosure | Median strip meet-up – pit stop, by FOAM | Concert | -27.9846 | 153.4277 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 43 | Delivered | Still to leave
LIGHTING TOWERS |  | 3 references · 7 units
Lighting towers | LT05 | Light Towers | Light Tower × 1 | 1 |  | Coates | LT05/06: Light Towers | Pit lane entry |  | -27.9381 | 153.4263 | Open map | Placed on the map | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 19 | Pending | Still to leave
Lighting towers | LT05 | Light Towers | Light Tower | 1 | 1224783 | Coates | LT05/06: Light Towers | Pit lane entry |  | -27.9381 | 153.4263 | Open map | Placed on the map | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 19 | Pending | Still to leave
Lighting towers | LT06 | Light Towers | Light Tower × 1 | 1 |  | Coates | LT05/06: Light Towers | Pit lane entry |  | -27.9381 | 153.4263 | Open map | Placed on the map | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 20 | Pending | Still to leave
Lighting towers | LT06 | Light Towers | Light Tower | 1 | 1224791 | Coates | LT05/06: Light Towers | Pit lane entry |  | -27.9381 | 153.4263 | Open map | Placed on the map | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 20 | Pending | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower × 5 | 5 |  | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 5 lines on 9961976 | Delivered | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1264929 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 1 | Delivered | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1314284 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 2 | Delivered | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1264899 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 3 | Delivered | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1188888 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 4 | Delivered | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1249499 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 5 | Delivered | Still to leave
ACCESS & PLANT |  | 10 references · 12 units
Access & plant | EQ0001 | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel × 1 | 1 |  | Coates | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9992300 · line 4 | Del Req | Still to leave | Rental 9992300, line 4.
Access & plant | EQ0001 | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | 1 | 1220903 | Coates | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9992300 · line 4 | Del Req | Still to leave
Access & plant | EQ0002 | Knuckle Boom 61ft (18.6M) - Diesel | Knuckle Boom 61ft (18.6M) - Diesel × 1 | 1 |  | Coates | Knuckle Boom 61ft (18.6M) - Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9992300 · line 5 | Pending | Still to leave | Rental 9992300, line 5.
Access & plant | EQ0002 | Knuckle Boom 61ft (18.6M) - Diesel | Knuckle Boom 61ft (18.6M) - Diesel | 1 | 1300290 | Coates | Knuckle Boom 61ft (18.6M) - Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9992300 · line 5 | Pending | Still to leave
Access & plant | EQ0003 | Straight Boom 60ft - Diesel | Straight Boom 60ft - Diesel × 1 | 1 |  | Coates | Straight Boom 60ft - Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-10-27 |  | 9992300 · line 12 | Delivered | Still to leave | Rental 9992300, line 12.
Access & plant | EQ0003 | Straight Boom 60ft - Diesel | Straight Boom 60ft - Diesel | 1 | 1286482 | Coates | Straight Boom 60ft - Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-10-27 |  | 9992300 · line 12 | Delivered | Still to leave
Access & plant | EQ0004 | SUPPLY - Forklift 3.5t Diesel | SUPPLY - Forklift 3.5t Diesel × 1 | 1 |  | Coates | SUPPLY - Forklift 3.5t Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 27 | Pending | Still to leave | Rental 9961976, line 27.
Access & plant | EQ0004 | SUPPLY - Forklift 3.5t Diesel | SUPPLY - Forklift 3.5t Diesel | 1 | 1210921 | Coates | SUPPLY - Forklift 3.5t Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 27 | Pending | Still to leave
Access & plant | EQ0005 | Fork Extensions 2.4m | Fork Extensions 2.4m × 1 | 1 |  | Coates | Fork Extensions 2.4m | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-30 | Contract (rental off-hire date) | 2026-10-28 |  | 9987005 · line 2 | Delivered | Still to leave | Rental 9992300, line 3.
Access & plant | EQ0005 | Fork Extensions 2.4m | Fork Extensions 2.4m | 1 | 1262224 | Coates | Fork Extensions 2.4m | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-30 | Contract (rental off-hire date) | 2026-10-28 |  | 9987005 · line 2 | Delivered | Still to leave
Access & plant | T0003 | Forklift 5T · Phillip Park | Forklift 5T × 1 | 1 |  |  | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave
Access & plant | T0003 | Forklift 5T · Phillip Park | Forklift 5T | 1 |  |  | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | no unit number on the record
Access & plant | T0004 | Forklift 2.5T · Phillip Park | Forklift 2.5T × 1 | 1 |  | Coates | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 21 | Delivered | Still to leave
Access & plant | T0004 | Forklift 2.5T · Phillip Park | Forklift 2.5T | 1 | 1197839 | Coates | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 21 | Delivered | Still to leave
Access & plant | T0005 | Forklift 2.5T RT × 2 · Macintosh | Forklift 2.5T RT × 2 | 3 |  | Coates | Macintosh | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) |  |  | 3 lines on 9961976 | Delivered, Pending, Returned | Still to leave | off-hire dates differ by line (see units)
Access & plant | T0005 | Forklift 2.5T RT × 2 · Macintosh | Forklift 2.5T RT | 1 | 1247787 | Coates | Macintosh | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) | 2026-09-17 |  | 9961976 · line 25 | Returned | Still to leave | off rent 17 Sep 2026 (actual)
Access & plant | T0005 | Forklift 2.5T RT × 2 · Macintosh | Forklift 2.5T RT | 1 | 1312577 | Coates | Macintosh | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 26 | Delivered | Still to leave
Access & plant | T0005 | Forklift 2.5T RT × 2 · Macintosh | COATES - Forklift Tyne Rotator | 1 | 1302007 | Coates | Macintosh | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) | 2026-10-28 | 08:00 | 9961976 · line 37 | Pending | Still to leave | unit on the reference outside its schedule lines
Access & plant | T0085 | 3.5T Forklift Std · Supply | 3.5T Forklift Std × 1 | 1 |  | Coates | Supply | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-30 | Contract (rental off-hire date) | 2026-10-28 |  | 9987005 · line 1 | Delivered | Still to leave
Access & plant | T0085 | 3.5T Forklift Std · Supply | 3.5T Forklift Std | 1 | 1272166 | Coates | Supply | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-30 | Contract (rental off-hire date) | 2026-10-28 |  | 9987005 · line 1 | Delivered | Still to leave
Access & plant | T0109 | 2.5T Forklift STD · Events | 2.5T Forklift STD × 1 | 1 |  | Coates | Events | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-27 | Contract (rental off-hire date) | 2026-10-27 | 07:00 | 9987005 · line 7 | Delivered | Still to leave
Access & plant | T0109 | 2.5T Forklift STD · Events | 2.5T Forklift STD | 1 | 1281615 | Coates | Events | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-27 | Contract (rental off-hire date) | 2026-10-27 | 07:00 | 9987005 · line 7 | Delivered | Still to leave
FURNITURE |  | 5 references · 6 units
Furniture | FR01 | Fridge · TV compound (broadcast) | Fridge × 1 | 1 |  | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-11 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Furniture | FR01 | Fridge · TV compound (broadcast) | Fridge | 1 | 1129733 | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-11 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Furniture | FR02 | Fridge · TV compound (broadcast) | Fridge × 1 | 1 |  | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-11 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Furniture | FR02 | Fridge · TV compound (broadcast) | Fridge | 1 | 1157786 | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-11 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Furniture | P26 | Fridge · Police 2-storey building | Fridge Lge × 1 | 1 |  | Coates | P26 - Fridge Delivery | Median strip meet-up – pit stop, by FOAM | S11 | -27.9847 | 153.4265 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 123 | Pending | Still to leave
Furniture | P26 | Fridge · Police 2-storey building | Fridge Lge | 1 | 1311992 | Coates | P26 - Fridge Delivery | Median strip meet-up – pit stop, by FOAM | S11 | -27.9847 | 153.4265 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 123 | Pending | Still to leave
Furniture | P28 | Fridge · Police 2-storey building | Fridge Lge × 1 | 1 |  | Coates | P28 - Fridge Delivery | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4265 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 124 | Pending | Still to leave
Furniture | P28 | Fridge · Police 2-storey building | Fridge Lge | 1 | 1283996 | Coates | P28 - Fridge Delivery | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4265 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 124 | Pending | Still to leave
Furniture | P34 | Chair Delivery | Pad Chair × 2 | 2 |  |  | P34 - Chair Delivery | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4265 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 125 | Pending | Still to leave
Furniture | P34 | Chair Delivery | Pad Chair × 2 | 2 |  |  | P34 - Chair Delivery | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4265 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 125 | Pending | Still to leave | no unit number on the record
GROUND PROTECTION |  | 2 references · 30 units
Ground protection | T0025 | Trakmat × 20 · Trackmat Delivery - S18 | Trakmat × 20 | 20 |  | Coates | Trackmat Delivery - S18 | Pit lane entry | S18 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Ground protection | T0025 | Trakmat × 20 · Trackmat Delivery - S18 | Trakmat × 20 | 20 |  | Coates | Trackmat Delivery - S18 | Pit lane entry | S18 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | quantity item, code TRAKMAT2.4X1.1
Ground protection | TM01 | Trakmat × 10 · TV compound (broadcast) | Trakmat × 10 | 10 |  |  | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-12 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Ground protection | TM01 | Trakmat × 10 · TV compound (broadcast) | Trakmat × 10 | 10 |  |  | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-12 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | no unit number on the record
OTHER |  | 5 references · 5 units
Other | EQ0006 | Laserplane | Laserplane × 1 | 1 |  | Coates | Laserplane | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-12 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Rental 9987005, line 8.
Other | EQ0006 | Laserplane | Laserplane | 1 | 1065384 | Coates | Laserplane | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-12 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Other | FL01 |  | Forklift 5T × 1 | 1 |  | Coates | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) |  | Not in the demob plan |  |  |  |  | Still to leave | not in the demob plan; From schedule row T0003 (Week 6 'Week 6'!A4:K4): 1 × Forklift 5T — Phillip Park · Long Tines — the row carried no GC500 reference. The rental system has 1 line against this row…
Other | FL01 |  | Forklift 5T | 1 | 50004 | Coates | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) |  | Not in the demob plan |  |  |  |  | Still to leave
Other | FL02 |  | Forklift 2.5T × 1 | 1 |  | Coates | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) |  | Not in the demob plan | 2026-10-26 | 08:00 | 9961976 · line 21 | Delivered | Still to leave | not in the demob plan; From schedule row T0004 (Week 6 'Week 6'!A5:L5): 1 × Forklift 2.5T — Phillip Park — the row carried no GC500 reference. The rental system has 1 line against this row on…
Other | FL02 |  | Forklift 2.5T | 1 | 1197839 | Coates | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) |  | Not in the demob plan | 2026-10-26 | 08:00 | 9961976 · line 21 | Delivered | Still to leave
Other | FL03 | Forklift 5T · TV compound (broadcast) | Forklift 5T × 1 | 1 |  | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-27 | Contract (rental off-hire date) | 2026-10-27 |  | 9992300 · line 1 | Del Req | Still to leave
Other | FL03 | Forklift 5T · TV compound (broadcast) | Forklift 5T | 1 | 1321364 | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-27 | Contract (rental off-hire date) | 2026-10-27 |  | 9992300 · line 1 | Del Req | Still to leave
Other | FL04 | Forklift 2.5T · TV compound (broadcast) | Forklift 2.5T × 1 | 1 |  | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-27 | Contract (rental off-hire date) | 2026-10-27 |  | 9992300 · line 2 | Del Req | Still to leave
Other | FL04 | Forklift 2.5T · TV compound (broadcast) | Forklift 2.5T | 1 | 1298390 | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-27 | Contract (rental off-hire date) | 2026-10-27 |  | 9992300 · line 2 | Del Req | Still to leave

## Buildings
GC500 2026 · buildings and what is inside them · as at 26 Oct 2026 07:46 AEST
Each building, then (folded under it) every item the record has inside it with its asset number. Press 2 on the left to open them all.
Ref | Building | Item | Asset no | Contract description | Contract · line | Location | Area | Plan section | Lat | Long | Map | Pin basis | On site | Levelled | Steps | Fire extinguisher | Things inside | Off-hire (demob plan) | Plan source | Contract off-hire date | Contract off-hire time | Contract status | Status on site | Notes
AA | Active Air Crib Room | Building 6m | 142514 |  |  | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | Yes | Yes | Yes | 1 | 4 | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  | Still to leave
| ↳ Inside AA | Fridge | [14 empty] | 1 | [6 empty] | fridge; parsed from the schedule notes column
| ↳ Inside AA | Folding table | [14 empty] | 1 | [6 empty] | 1x fold table; parsed from the schedule notes column
| ↳ Inside AA | Stackable chair | [14 empty] | 4 | [6 empty] | 4x stack chair; parsed from the schedule notes column
| ↳ Inside AA | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
CP1 | P68 · Signevent Crib Room | Building 6m | 1105057 | CP1 P68 Portable Building Shell 6.0M x 3.0M | 9968862 · line 17 | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | Yes | Yes | Yes | 1 | 7 | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside CP1 | Chair | [14 empty] | 1 | [6 empty] | Chairs; parsed from the schedule notes column
| ↳ Inside CP1 | Desk | [14 empty] | 1 | [6 empty] | parsed from the schedule notes column
| ↳ Inside CP1 | Hydration station | [14 empty] | 1 | [6 empty] | Hydration Station; parsed from the schedule notes column
| ↳ Inside CP1 | Sink with tap | [14 empty] | 1 | [6 empty] | Sink with Tap; parsed from the schedule notes column
| ↳ Inside CP1 | Fridge | 1116687 | [13 empty] | 1 | [6 empty] | Fridge — Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
| ↳ Inside CP1 | Urn | 119810 | [13 empty] | 1 | [6 empty] | Urn — Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
| ↳ Inside CP1 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
HRP | Hire Republic Crib Room | Building 6m | 1189410 | P36 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 93 | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | Yes | Yes | Yes | 1 | 3 | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside HRP | Air conditioner | 1189901 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside HRP | Air conditioner | 1127305 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside HRP | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P01 | iEDM Engineering Office | Building 12m | 1322583 | P01 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 9968862 · line 1 | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | Yes | Yes | Yes | 1 | 4 | 2026-11-13 | Plan (schedule removal row) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P01 | Fridge | 1328956 | [13 empty] | 1 | [6 empty] | Fridge - Full Sized; parsed from the schedule notes column
| ↳ Inside P01 | Air conditioner | 1322610 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P01 | Air conditioner | 1322609 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P01 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P03 | SCA Event Management Office | Building 12m | 1327212 | P03 Portable Building Shell 12.0M x 3.0M - Cyclonic Ra | 9968862 · line 4 | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | Yes | Yes | Yes | 1 | 4 | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P03 | Fridge | 1328955 | [13 empty] | 1 | [6 empty] | Fridge - Full Sized; parsed from the schedule notes column
| ↳ Inside P03 | Air conditioner | 1327954 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P03 | Air conditioner | 1327953 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P03 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P04 | SCA Sales & Marketing Office | Building 12m | 1327213 | P04 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 9968862 · line 7 | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | Yes | Yes | Yes | 1 | 4 | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P04 | Fridge | 1328954 | [13 empty] | 1 | [6 empty] | Fridge - Full Sized; parsed from the schedule notes column
| ↳ Inside P04 | Air conditioner | 1327955 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P04 | Air conditioner | 1327956 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P04 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P05 | Event Control Center (ECC) | Building 6m | 1189422 | P05 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 10 | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | Yes | Yes | Yes | 1 | 8 | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P05 | Chair | [14 empty] | 1 | [6 empty] | parsed from the schedule notes column
| ↳ Inside P05 | Fridge | 1311988 | [13 empty] | 1 | [6 empty] | Fridge (full sized); parsed from the schedule notes column
| ↳ Inside P05 | Zip boiler | [14 empty] | 1 | [6 empty] | Zip Boiler; parsed from the schedule notes column
| ↳ Inside P05 | Sink with tap | [14 empty] | 1 | [6 empty] | Sink with Tap; parsed from the schedule notes column
| ↳ Inside P05 | Microwave | 1320150 | [13 empty] | 1 | [6 empty] | Microwave — Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
| ↳ Inside P05 | Air conditioner | 1127574 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P05 | Air conditioner | 1189939 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P05 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P06 | Wilclean Crib Room | Building 6m | 1087453 | P06 Portable Building Shell 6.0M x 3.0M | 9968862 · line 64 | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | Yes | Yes |  | 1 | 6 | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P06 | Sink with tap | [14 empty] | 1 | [6 empty] | Sink w Tap; parsed from the schedule notes column
| ↳ Inside P06 | Air conditioner | 1097209 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P06 | Fridge | 1272749 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P06 | Microwave | 1284012 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P06 | Zip boiler | 1173374 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P06 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P08 | Security | Building 6m | 421138 | P08 Portable Building Shell 6.0M x 3.0M | 9968862 · line 126 | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | Yes | Yes | Yes | 1 | 3 | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P08 | Air conditioner | 1311986 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P08 | Fridge | 1114312 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P08 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P09 | Iedm Safety Office | Building 6m | 1268824 | P09 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 28 | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | Yes | Yes | Yes | 1 | 6 | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P09 | Sink with tap | [14 empty] | 1 | [6 empty] | Sink w Tap; parsed from the schedule notes column
| ↳ Inside P09 | Air conditioner | 1270403 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P09 | Fridge | 1328958 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P09 | Urn | 1284061 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P09 | Zip boiler | 1254390 | [13 empty] | 1 | [6 empty] | Zip boiler — Boiling-water unit. Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
| ↳ Inside P09 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P10 | Team Office - 888 Racing | Building 4.8m | 105626 | P10 Portable Building Shell 4.8M x 2.4M | 9968862 · line 44 | P10 - Team Office - 888 Racing | Island north – by FREIGHT | S02 | -27.9866 | 153.4281 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P10 | Air conditioner | 238771 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P10 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P11 | Team Office - DJR | Building 4.8m | 415576 | P11 Portable Building Shell 4.8M x 2.4M | 9968862 · line 46 | P11 - Team Office - DJR | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P11 | Air conditioner | 112940 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P11 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P12 | Team 18 | Building 4.8m | 418665 | P12 Portable Building Shell 4.8M x 2.4M | 9968862 · line 48 | P12 - Team 18 | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | Yes | Yes | Yes | 1 | 1 | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P12 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P13 | Team Office - WAU | Building 4.8m | 1097346 | P13 Portable Building Shell 4.8M x 2.4M | 9968862 · line 51 | P13 - Team Office - WAU | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P13 | Air conditioner | 1190775 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P13 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P14 | Team Office - Grove Racing | Building 4.8m | 960599 | P14 Portable Building Shell 4.8M x 2.4M | 9968862 · line 53 | P14 - Team Office - Grove Racing | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P14 | Air conditioner | 118370 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P14 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P15 | Team Office - Erebus Motorsport | Building 4.8m | 1097345 | P15 Portable Building Shell 4.8M x 2.4M | 9968862 · line 55 | P15 - Team Office - Erebus Motorsport | Island north – by FREIGHT | S02 | -27.9869 | 153.4282 | Open map | Master plan position | Yes | Yes | Yes | 1 | 1 | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P15 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P16 | Team Office - WFL | Building 4.8m | 415575 | P16 Portable Building Shell 4.8M x 2.4M | 9968862 · line 57 | P16 - Team Office - WFL | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | Yes | Yes | Yes | 1 | 1 | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P16 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P17 | Team Office BJR | Building 9.6m | 1268887 | P17 Portable Building Shell Cyclone Rated 9.6m x 3m | 9968862 · line 33 | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | Yes | Yes | Yes | 1 | 3 | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P17 | Air conditioner | 1270473 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P17 | Air conditioner | 1270472 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P17 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P18 | Team Office - MSR | Building 4.8m | 1097343 | P18 Portable Building Shell 4.8M x 2.4M | 9968862 · line 36 | P18 - Team Office - MSR | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4268 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P18 | Fridge | [14 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P18 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P19 | Team Office Premiair Racing | Building 4.8m | 1110619 | P19 Portable Building Shell 6.0M x 3.0M | 9968862 · line 34 | P19 - Team Office Premiair Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P19 | Air conditioner | 1244101 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P19 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P20 | Team Office Blanchard Racing | Building 4.8m | 1097339 | P20 Portable Building Shell 4.8M x 2.4M | 9968862 · line 38 | P20 - Team Office Blanchard Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4269 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P20 | Air conditioner | 1180683 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P20 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P21 | Team Objective Racing | Building 4.8m | 1327220 | P21 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 92 | P21 - Team Objective Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P21 | Air conditioner | 1327938 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P21 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P25 | Support Category Stewards | Building 4.8m | 1189408 | P25 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 105 | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | Yes | Yes | Yes | 1 | 4 | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P25 | Air conditioner | 1189951 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P25 | Air conditioner | 1189950 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P25 | Fridge | 1260174 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P25 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P33 | Race Medical | Building 9.6m | 453375 | P33 Portable Building Shell 9.6M x 3.0M | 9968862 · line 24 | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | Yes | Yes | Yes | 1 | 6 | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P33 | Sink with tap | [14 empty] | 1 | [6 empty] | Sink with Tap; parsed from the schedule notes column
| ↳ Inside P33 | Air conditioner | 1286611 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P33 | Air conditioner | 1127296 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P33 | Fridge | 1238952 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P33 | Zip boiler | 1066777 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P33 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P36 | Harry the Hirer | Building 6m | 1282487 | P36 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 93 | P36 - Harry the Hirer | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P36 | Air conditioner | 1283004 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P36 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P37 | Oz Wide Audio Crib Room | Building 6m | 1105053 | P37 Portable Building Shell 6.0M x 3.0M | 9968862 · line 50 | P37 Oz Wide Audio Crib Room | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P37 | Air conditioner | 1198145 | [13 empty] | 1 | [6 empty] | Aircon; recorded on site as a unit
| ↳ Inside P37 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P38 | Green Room 1 | Building 6m | 1327218 | P38 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 70 | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | Yes | Yes |  | 1 | 3 | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P38 | Air conditioner | 1327934 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P38 | Fridge | 1272755 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P38 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P39 | Green Room 2 | Building 6m | 1327216 | P39 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 73 | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | Yes | Yes |  | 1 | 3 | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P39 | Air conditioner | 1272737 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P39 | Air conditioner | 1327936 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P39 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P41 | QFES Crib Room | Building 6m | 1189412 | P41 Portable Building Shell 6.0M x 3.0M | 9968862 · line 63 | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | Yes | Yes | Yes | 1 | 3 | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P41 | Air conditioner | 1189899 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P41 | Air conditioner | 1189908 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P41 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P42 | Production | Building 6m | 1327221 | P42 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 76 | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | Yes | Yes |  | 1 | 3 | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P42 | Air conditioner | 1327939 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P42 | Fridge | 1272746 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P42 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P44 | Queensland Ambulance Service | Building 6m | 198481 | P44 Portable Building Shell 6.0M x 3.0M | 9968862 · line 61 | P44 - Queensland Ambulance Service | Island west parkland entry – by the merch strip |  | -27.9838 | 153.4265 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P44 | Fridge | 1183134 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P44 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P45 | St John First Aid | Building 6m | 107135 | P45 Portable Building Shell 6.0M x 3.0M | 9968862 · line 131 | P45 St John First Aid | Main Beach seaside – by the supply compound |  | -27.9881 | 153.43 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P45 | Air conditioner | 1250796 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P45 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P46 | QPS Command Post | Building 12m | 1327215 | P46 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 9968862 · line 100 | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | Yes | Yes | Yes | 1 | 5 | 2026-10-29 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P46 | Air conditioner | 1327959 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P46 | Air conditioner | 1327960 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P46 | Fridge | 1318501 | [13 empty] | 1 | [6 empty] | Fridge — Police fridge, from T0265's 14 Oct delivery; added in this page
| ↳ Inside P46 | Fridge | 1260164 | [13 empty] | 1 | [6 empty] | Fridge — Police fridge, from T0265's 14 Oct delivery; added in this page
| ↳ Inside P46 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P51 | Security Sign On | Building 12m | 1322579 | P51 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 9968862 · line 94 | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | Yes | Yes | Yes | 1 | 4 | 2026-10-29 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P51 | Air conditioner | 1326602 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P51 | Air conditioner | 1326601 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P51 | Fridge | 1328959 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P51 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P52 | Gate 1 Volunteer Check-In | Building 12m | 1327211 | P52 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 9968862 · line 79 | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | Yes | Yes | Yes | 1 | 4 | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P52 | Air conditioner | 1327951 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P52 | Air conditioner | 1327952 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P52 | Fridge | 1328953 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P52 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P54 | Accred Centre BOH | Building 6m | 1327219 | P54 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 85 | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | Yes | Yes | Yes | 1 | 3 | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P54 | Air conditioner | 1327937 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P54 | Fridge | 1328957 | [13 empty] | 1 | [6 empty] | Fridge — Moved from P46 on 14 Oct 2026; same fridge, not an additional hire.; added in this page
| ↳ Inside P54 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P55 | Gate 1 Ticket Box | Ticket Box 6m | 172114 | P55 Ticket Office 6.0Mx3.0M | 9968862 · line 87 | P55 - Gate 1 Ticket Box | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4238 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P55 | Air conditioner | 1320175 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P55 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P56 | Gate 1 Ticket BOH | Building 3.6m | 1268865 | P56 Portable Building Shell Cyclone Rated 3.6m x 2.4m | 9968862 · line 89 | P56 - Gate 1 Ticket BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P56 | Air conditioner | 1270437 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P56 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P57 | Radio Distribution Office | Building 9.6m | 1268888 | P57 Portable Building Shell Cyclone Rated 9.6m x 3m | 9968862 · line 90 | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | Yes | Yes | Yes | 1 | 4 | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P57 | Air conditioner | 1270478 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P57 | Air conditioner | 1270479 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P57 | Fridge | 1280688 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P57 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P58 | 1300 Medics | Building 6m | 1273656 | P44 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 59 | P58 - 1300 Medics | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | Delivered | Still to leave
| ↳ Inside P58 | Fridge | 1201945 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P58 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P60 | Gate 5 Ticket Box | Ticket Box 4.8m | 1015699 | P60 Ticket Office 4.8Mx2.4M | 9968862 · line 116 | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | Yes | Yes |  | 1 | 3 | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P60 | Air conditioner | 1267597 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P60 | Swivel chair | [14 empty] | 4 | [6 empty] | 4x Swivel chair; added in this page
| ↳ Inside P60 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P62 | Gate 5 QFES Office | Building 6m | 1189409 | P62 Commentary Booth 6.0M x 3.0M | 9968862 · line 118 | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | Yes | Yes |  | 1 | 4 | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P62 | Air conditioner | 1189912 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P62 | Air conditioner | 1189908 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P62 | Fridge | 1254221 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P62 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P63 | Gate 5 Volunteer Sign On | Building 6m | 960719 | P63 Portable Building Shell 6.0M x 3.0M | 9968862 · line 121 | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | Yes | Yes |  | 1 | 3 | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P63 | Air conditioner | 1219157 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P63 | Air conditioner | 1219156 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P63 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P65 | Support Categories Race Secretary | Building 6m | 1327217 | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 9968862 · line 110 | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | Yes | Yes | Yes | 1 | 3 | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P65 | Air conditioner | 1327935 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P65 | Fridge | 1283982 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P65 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P66 | Support Category Scrutineers | Building 6m | 1327222 | P66 Portable Building Shell 6.0M x 3.0M | 9968862 · line 113 | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | Yes | Yes | Yes | 1 | 3 | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P66 | Air conditioner | 1372940 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P66 | Fridge | 131190 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P66 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P67 | Gate 6 Security Office | Building 6m | 421107 | P67 Commentary Booth 6.0M x 3.0M | 9968862 · line 108 | P67 - Gate 6 Security Office | Pit lane entry |  | -27.9913 | 153.4304 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P67 | Air conditioner | 1300541 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P67 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
P69 | Supply Building | Building 6m | 107247 | P69 Portable Building Shell 6.0M x 3.0M | 9968862 · line 103 | P69 - Supply Building | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | Yes | Yes | Yes | 1 | 2 | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | Delivered | Still to leave
| ↳ Inside P69 | Air conditioner | 1245808 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside P69 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
T0021 | Building 4.8m · Office 4.8x3 | Building 4.8m | 960639 | Portable Building Shell 4.8M x 3.0M | 9968929 · line 1 | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | Yes | Yes | Yes | 1 | 4 | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 | 09:00 | Delivered | Still to leave
| ↳ Inside T0021 | Folding table | [14 empty] | 3 | [6 empty] | 3x Fold Table; parsed from the schedule notes column
| ↳ Inside T0021 | Swivel chair | [14 empty] | 3 | [6 empty] | 3x swivel chair; parsed from the schedule notes column
| ↳ Inside T0021 | Whiteboard | [14 empty] | 1 | [6 empty] | White Board; parsed from the schedule notes column
| ↳ Inside T0021 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
T0022 | Building 4.8m · Lunchroom 4.8x3 | Building 4.8m | 960634 | Portable Building Shell 4.8M x 3.0M | 9968929 · line 3 | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | Yes | Yes | Yes | 1 | 7 | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 | 09:00 | Delivered | Still to leave
| ↳ Inside T0022 | Folding table | [14 empty] | 3 | [6 empty] | 3x fold table; parsed from the schedule notes column
| ↳ Inside T0022 | Sink with tap | [14 empty] | 1 | [6 empty] | sink; parsed from the schedule notes column
| ↳ Inside T0022 | Stackable chair | [14 empty] | 12 | [6 empty] | 12x stack Chair; parsed from the schedule notes column
| ↳ Inside T0022 | Microwave | [14 empty] | 1 | [6 empty] | parsed from the schedule notes column
| ↳ Inside T0022 | Fridge | 1272753 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside T0022 | Fridge | 1254399 | [13 empty] | 1 | [6 empty] | added in this page
| ↳ Inside T0022 | Fire extinguisher | [14 empty] | 1 | [6 empty] | ticked on the record
T0023 | Event Container · event container from eags | Event Container | 1257261 | Shop Front - Shut Down | 9968929 · line 5 | event container from eags | Island west parkland entry – by the merch strip |  | -27.9833 | 153.4263 | Open map | Phone pin | Yes | Yes |  |  | 0 | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 09:00 | Del Req | Still to leave
T0258 | 3.0m Cont · Helen Park | 3.0m Cont | 1134386 | Container 3.0M x 2.4M | 9974042 · line 1 | Helen Park | Pit lane entry | S23 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | Yes | Yes |  |  | 0 | 2026-10-26 | Proposed (demob rule, not confirmed) | 2026-11-13 | 10:00 | Delivered | Still to leave
T0266 | 6.0m Refrigerator Cont · Helen Park | 6.0m Refrigerator Cont | 920584 | Container - Refrigerated 6.0M x 2.4M | 9974042 · line 2 | Helen Park | Pit lane entry | S23 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | Yes | Yes |  |  | 0 | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | Delivered | Still to leave | United Rentals / Royal Wolf (subhire)

## Subhire
GC500 2026 · subhire, by supplier · as at 26 Oct 2026 07:46 AEST
Equipment Coates hires in. Advanced Temporary Fencing is listed by docket: what was put in where, and what has been collected.
Supplier | Ref | Description | Item | Qty on site | Unit / fleet numbers | Location | Lat | Long | Map | Pin basis | Off-hire (demob plan) | Plan source | Supplier out date | Contract off-hire date | Contract off-hire time | Contract · line | Status | Notes
EVENT PORTABLES · 203 UNITS ON SITE ACROSS 55 REFERENCES
Event Portables | BJR01 | Brad Jones Racing | FWF | 1 | 0941 | Brad Jones Racing · Andrew’s pin | -27.9859 | 153.4275 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | PG01 | Toilet (Pit Garage) | FWF | 1 | 0285 | Toilet (Pit Garage) · Andrew’s pin | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | PG03 | Toilet (Pit Garage) | FWF | 1 | 0100 | Toilet (Pit Garage) · Andrew’s pin | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | PG05 | Toilet (Pit Garage) | FWF | 1 | 0438 | Toilet (Pit Garage) · Andrew’s pin | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | PG29 | Toilet (Pit Garage) | FWF | 1 | 0573 | Tickford Racing | -27.9866 | 153.4278 | Open map | Map position — check on site | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | SVP01 | Shell V-Power | FWF | 1 | 0939 | Shell V-Power · Andrew’s pin | -27.9862 | 153.4278 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | T0024 | FWF | FWF | 1 | 0164 | Andrew’s pin | -27.9832 | 153.4266 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | 2 of 2 installed · 2 received
Event Portables | T0162 | FWF · Blanchard Race | FWF | 1 | 0990 | Blanchard Race · Andrew’s pin | -27.9857 | 153.4274 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | T0176 | FWF × 2 · Redbull | FWF | 2 | 0994, 0576 | Redbull · Andrew’s pin | -27.9867 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC09 | Toilets | FWF | 10 | 0085, 0551, 0450, 0585, 0993, 0553, 0140, 0089, 0584, 0081 | Macintosh Island · next to TOILETS, NEW | -27.9847 | 153.428 | Open map | Master plan reference position | 2026-11-11 | Proposed (demob rule, not confirmed) |  |  |  |  | 10 of 10 installed · 10 received
Event Portables | WC09 | Toilets | Pee Panel | 6 | PP01, PP04, PP05, PP06, PP02, PP03 | Macintosh Island · next to TOILETS, NEW | -27.9847 | 153.428 | Open map | Master plan reference position | 2026-11-11 | Proposed (demob rule, not confirmed) |  |  |  |  | 6 of 6 installed · 6 received
Event Portables | WC10 | Toilets | FWF | 3 | 0488, 0677, 0119 | Macintosh Island · beside P42 and the 8 m stage, on the lake-side fence | -27.9845 | 153.4277 | Open map | Master plan reference position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC13 | Toilets | FWF | 2 | 0036, 0444 | Higman St · Seacrest frontage · beside WC24 | -27.991 | 153.4295 | Open map | Master plan reference position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC19 | Toilets | FWF | 1 | 0435 | Gold Coast Hwy track-side verge · S04 TV overflow end, near MP0.6 | -27.9882 | 153.4283 | Open map | Master plan reference position | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC23 | Toilets | FWF | 5 | 0992, 0968, 0960, 0107, 0969 | Ferny Ave · food / Bar 15 area · near Equinox | -27.9895 | 153.4292 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC24 | Toilets | FWF | 1 | 0489 | Main Beach Pde / Higman St · EEP4/6 · beside WC13 | -27.991 | 153.4297 | Open map | Master plan reference position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC25 | Toilets | FWF | 1 | 0472 | Ferny Ave · Turn 2/3 approach · near Narrowneck Lodge | -27.9901 | 153.4288 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC26 | Toilets | FWF | 1 | 0075 | Ferny Ave / Main Beach Pde · Narrowneck Court frontage | -27.9888 | 153.4296 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC28 | Toilets | FWF | 1 | 0102 | Cable St / Main Beach Pde · Cable Park corner | -27.9834 | 153.4292 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC29 | Toilets | FWF | 7 | 0079, 0546, 0707, 0564, 0044, 0441, 0598 | Cable Park · waterfront edge at the Cable St bend | -27.9836 | 153.4286 | Open map | Master plan reference position | 2026-10-26 | Plan (schedule removal row) |  |  |  |  | Recorded installed
Event Portables | WC30 | Toilets | FWF | 8 | 0428, 0440, 0963, 0681, 0043, 0419, 0545, 0024 | Pacific St · Contessa frontage, between Breaker St and Cable St | -27.9824 | 153.4278 | Open map | Master plan reference position | 2026-10-26 | Plan (schedule removal row) |  |  |  |  | Recorded installed
Event Portables | WC31 | Toilets | 16Pan Block | 2 | 12, 74 | Andrew’s pin | -27.9825 | 153.4252 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC33 | Toilets | FWF | 17 | 0634, 0582, 0548, 0782, 0657, 0912, 0554, 0920, 0971, 0586, 0487, 0790, 0297, 0456, 0012, 0938, 0597 | Main Beach Pde · S07 (~50 m) | -27.9861 | 153.4295 | Open map | Master plan reference position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC34 | Toilets | FWF | 1 | 0526 | The Hill · Hill Pde · A45 / MP13.3 | -27.9823 | 153.4259 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC35 | Toilets | FWF | 1 | 0284 | Breaker St / Pacific St · beside BFR / PB2, near Gate 8a | -27.9818 | 153.4278 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC38 | Toilet | FWF | 1 | 0183 | Commodore Park · beside P08 / P51 and GEM, near Gate 2 | -27.9836 | 153.4241 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC39 | Toilets | FWF | 2 | 0188, 0637 | Commodore Park · beside OP14 / P46, next to COW / OPT | -27.9836 | 153.424 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC40 | Toilets | FWF | 5 | 0626, 0541, 0965, 0433, 0648 | Gate 2 · Commodore Drive accessible-parking edge | -27.9837 | 153.4245 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC41 | Toilets | FWF | 10 | 0521, 0996, 0191, 0669, 0643, 0517, 0682, 0651, 0065, 0518 | Macintosh Island · S11 (~40 m) | -27.9848 | 153.4261 | Open map | Master plan reference position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC42 | Toilets | FWF | 1 | 0141 | Gate 2 · Commodore Park · S10 (~50 m) · Gate 2 (~45 m) · Commodore (~85 m) | -27.9833 | 153.4248 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC43 | Toilets | FWF | 10 | 0723, 0056, 0161, 0182, 0528, 0696, 0420, 0961, 0646, 0581 | Macintosh Island · S14 (~20 m) · Pit Lane (~50 m) | -27.9864 | 153.4272 | Open map | Master plan reference position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC44 | Toilets | FWF | 2 | 0146, 0037 | Outside the island · other spots · S05 (~30 m) · Gate 3 (~50 m) | -27.989 | 153.4283 | Open map | Master plan reference position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC45 | Toilets | FWF | 8 | 0542, 0086, 0947, 0544, 0632, 0562, 0549, 0673 | Grandstand S15 · Gold Coast Hwy side | -27.9907 | 153.4284 | Open map | Master plan reference position | 2026-10-26 | Plan (schedule removal row) |  |  |  |  | Recorded installed
Event Portables | WC46 | Toilets | FWF | 1 | 0525 | Surfers Paradise Blvd · Turn 4 / A7 · opposite light rail station | -27.9922 | 153.4294 | Open map | Master plan reference position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC47 | Toilets | FWF | 1 | 0949 | Turn 2 · S15 approach · near Ferny Ave | -27.9902 | 153.4284 | Open map | Master plan reference position | 2026-10-26 | Plan (schedule removal row) |  |  |  |  | Recorded installed
Event Portables | WC48 | Toilets | FWF | 4 | 0050, 0471, 0289, 0486 | The Esplanade · Gate 6 area · beside OP54 | -27.9937 | 153.4305 | Open map | Master plan reference position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC49 | Toilets | FWF | 3 | 0919, 0907, 0084 | The Esplanade · Gate 6 compound · between P62 and P63 | -27.9938 | 153.4306 | Open map | Drawing position — check on site | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC51 | Toilets | FWF | 6 | 0991, 0167, 0653, 0136, 0453, 0028 | The Esplanade · scales · Gate 6 area | -27.9929 | 153.4305 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC53 | Toilets | FWF | 3 | 0952, 0951, 0074 | The Esplanade · beside OP20 · OP25 marquee area | -27.9927 | 153.4303 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC54 | Toilets | FWF | 6 | 0186, 0619, 0071, 0295, 0007, 0087 | The Esplanade · support Stewards / Scrutineers · P25/P66 · SLS tower 37 | -27.9916 | 153.4305 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC55 | Toilets | FWF | 1 | 0650 | Turn 5 · Meriton frontage · Higman St / EEP4/6 area | -27.9912 | 153.4298 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC56 | Toilets | FWF | 12 | 0721, 0491, 0190, 0294, 0970, 0974, 0004, 0003, 0445, 0088, 0442, 0009 | Main Beach Pde · next to FOOD — beside OP12 — Main Beach Pde (~50 m) · S18 (~20 m) | -27.9898 | 153.4301 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC57 | Toilets | FWF | 2 | 0915, 0008 | Supply compound · inside fence beside Supply Building P69 · MED/WC59 | -27.9882 | 153.4301 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC59 | Toilets | FWF | 7 | 0492, 0935, 0497, 0633, 0064, 0066, 0533 | Main Beach Pde · next to MED, SUPPLY — beside OP40, P69, WC57 | -27.9882 | 153.4302 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC61 | Toilets | FWF | 8 | 0645, 0105, 0945, 0977, 0547, 0290, 0038, 0015 | Main Beach Pde · S22 (~50 m) | -27.9841 | 153.4298 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC62 | Toilets | FWF | 2 | 0976, 0103 | Turn 11 · Breaker St / Main Beach Pde, beside Ocean Resort | -27.9817 | 153.4292 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC65 | Toilets | FWF | 1 | 0033 | Breaker St · Inlet frontage · near Gate 9 | -27.9815 | 153.4264 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC67 | Toilets | FWF | 3 | 0793, 0769, 0714 | Gate 1 · Tedder Ave / Helen Park · next to SCA, WC-BSF, BSF — beside OP16, P52, P57, WC69 — Breaker St (~45 m) · S23 (~25 m) · Gate 1 (~65 m) · Helen (~40 m) | -27.9814 | 153.4242 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | 4 of 4 installed · 4 received
Event Portables | WC68 | Toilets | FWF | 1 | 0426 | Helen Park · BSF fence at the G10 / Turn 14 end of S23 | -27.9815 | 153.4244 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC69 | Toilets | FWF | 12 | 0152, 0078, 0010, 0070, 0958, 0647, 0622, 0123, 0432, 0692, 0679, 0592 | Helen Park · alongside S23, beside the WC-BSF compound | -27.9815 | 153.4242 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC70 | Toilet | FWF | 1 | 0423 | Helen Park · beside OP83 and Bar 19, alongside S23 | -27.9817 | 153.424 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC71 | Toilets | FWF | 8 | 0280, 0116, 0279, 0293, 0531, 0644, 0552, 0490 | Gate 1 · Tedder Ave / Helen Park · Breaker St (~35 m) · S23 (~75 m) · Gate 1 (~35 m) · Park (~15 m) | -27.9813 | 153.4235 | Open map | Master plan reference position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC72 | Toilets | FWF | 1 | 0699 | Turn 15 · beside HINO / MP15.0, Gold Coast Highway side of The Hill | -27.9821 | 153.424 | Open map | Master plan reference position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC73 | Toilets | FWF | 2 | 0765, 0192 | Macintosh Island team paddock · beside Dunlop / P15 / P16, behind S02 | -27.987 | 153.4281 | Open map | Master plan reference position | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC81 | Toilet (Cypress) | FWF | 1 | 0124 | Toilet (Cypress) · beside P68 — Surfers Paradise Blvd (~50 m) | -27.9975 | 153.4285 | Open map | Master plan reference position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
Event Portables | WC85 | Toilets | FWF | 1 | 0135 | Coates compound · Andrew’s pin | -27.9386 | 153.4265 | Open map | Andrew’s pin | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Recorded installed
PREMIAIR HIRE · 9 VMS BOARDS
Premiair Hire | T0103 | VMS10 · VMS board | VMS | 1 | fleet 120T · rego V14221 | Position 10 · Old Burleigh Rd (northbound), south of Queensland Ave intersection | -28.0297 | 153.4341 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) |  | 2026-10-27 |  | 9961265 · line 13 | Still to leave | positions 10
Premiair Hire | T0128 | VMS11 · VMS board | VMS | 1 | fleet 467T · rego TE97G | Position 11 · Confirmed board location | -27.9862 | 153.4283 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) |  | 2026-10-26 |  | 9961265 · line 15 | Still to leave | positions 11
Premiair Hire | T0158 | VMS18 · VMS board | VMS | 1 | fleet 472T · rego TE58GZ | Position 18 · Confirmed board location | -27.9931 | 153.4282 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) |  | 2026-10-26 | 07:00 | 9961265 · line 24 | Still to leave | positions 18
Premiair Hire | T0158 | VMS19 · VMS board | VMS | 1 | fleet 487T · rego TE02H0 | Position 19 · Confirmed board location | -27.9851 | 153.4273 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) |  | 2026-10-26 | 07:00 | 9961265 · line 25 | Still to leave | positions 19
Premiair Hire | T0158 | VMS20 · VMS board | VMS | 1 | fleet 475T · rego TE88HN | Position 20 · Confirmed board location | -27.9935 | 153.4305 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) |  | 2026-10-26 | 07:00 | 9961265 · line 26 | Still to leave | positions 20
Premiair Hire | — | VMS21 · VMS board | VMS | 1 | fleet 97T · rego T16922 | Position 21 · Confirmed board location | -27.9951 | 153.4293 | Open map | VMS register board position |  | Not in the demob plan |  | 2026-10-26 | 07:00 | 9961265 · line 28 | Still to leave | positions 21
Premiair Hire | — | VMS22 · VMS board | VMS | 1 | fleet 445T · rego TE99CL | Position 22 · Confirmed board location | -27.9975 | 153.4306 | Open map | VMS register board position |  | Not in the demob plan |  | 2026-10-28 | 07:00 | 9961265 · line 29 | Still to leave | positions 22
Premiair Hire | T0158 | VMS23 · VMS board | VMS | 1 | fleet 453T · rego TF54CQ | Position 23 · Gold Coast Highway (north of Sundale Bridge), eastern side of the road, for southbound traffic | -27.9748 | 153.4207 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) |  | 2026-10-26 | 07:00 | 9961265 · line 30 | Still to leave | positions 23
Premiair Hire | — | VMS24 · VMS board | VMS | 1 | fleet 450T · rego TE94CL | Position 24 · Confirmed board location | -27.9927 | 153.4282 | Open map | VMS register board position |  | Not in the demob plan |  | 2026-10-26 | 15:00 | 9961265 · line 31 | Still to leave | positions 24
UNITED RENTALS / ROYAL WOLF · 1 LINE
United Rentals / Royal Wolf | T0266 | 6.0m Refrigerator Cont · Helen Park | 6.0m Refrigerator Cont | 1 | 920584 | Helen Park | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-28 | Proposed (demob rule, not confirmed) |  | 2026-11-13 |  | 9974042 · line 2 | Still to leave
ADVANCED TEMPORARY FENCING · 167 DOCKETS AND WEEK ROWS, 25 COLLECTIONS
Advanced Temporary Fencing | 36501 | Sea World Drive, Main Beach | 247.5 clean m |  |  | Sea World Drive, Main Beach | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Sep 2026 | docket
Advanced Temporary Fencing | 36502 | Phillip Park (Advanced compound) | 257.5 clean m |  |  | Phillip Park (Advanced compound) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 11 Sep 2026 | docket
Advanced Temporary Fencing | 36503 | Sea World Drive, Main Beach | — |  |  | Sea World Drive, Main Beach | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 11 Sep 2026 | docket
Advanced Temporary Fencing | 36504 | Helen Park, BSF compound | 72.5 clean m, 72.5 scrim m |  |  | Helen Park, BSF compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 11 Sep 2026 | docket
Advanced Temporary Fencing | 36511 | Yatala — Morayfield (Phillip Island / Morayfield), region Yatala | 8.5 labour h |  |  | Yatala — Morayfield (Phillip Island / Morayfield), region Yatala | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 12 Sep 2026 | docket
Advanced Temporary Fencing | 36505 | Cypress Carpark | 97.5 clean m |  |  | Cypress Carpark | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Sep 2026 | docket
Advanced Temporary Fencing | 36506 | S18 C.2 construction zone | 132.5 clean m, 10 scrim m |  |  | S18 C.2 construction zone | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Sep 2026 | docket
Advanced Temporary Fencing | 36507 | Admiralty Drive — crossing closure | 7.5 clean m |  |  | Admiralty Drive — crossing closure | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Sep 2026 | docket
Advanced Temporary Fencing | 36508 | P.B03 C.2 | 20 clean m |  |  | P.B03 C.2 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Sep 2026 | docket
Advanced Temporary Fencing | 36509 | Pit Building / Paddock C.2 — perimeter fencing | 577.5 clean m, 2 ped gates |  |  | Pit Building / Paddock C.2 — perimeter fencing | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Sep 2026 | docket
Advanced Temporary Fencing | 36510 | Sea World Drive, Main Beach | 50 relocation |  |  | Sea World Drive, Main Beach | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Sep 2026 | docket
Advanced Temporary Fencing | 36512 | S04 Corporate Facility / TV compound | 172.5 clean m |  |  | S04 Corporate Facility / TV compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Sep 2026 | docket
Advanced Temporary Fencing | 36513 | S07 C-Zone | 127.5 clean m, 12.5 scrim m |  |  | S07 C-Zone | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Sep 2026 | docket
Advanced Temporary Fencing | 36514 | Event Operations — iEDM compound | 147.5 clean m, 70 scrim m, 1 ped gates |  |  | Event Operations — iEDM compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Sep 2026 | docket
Advanced Temporary Fencing | 36515 | S07 — hill protection | 60 CCB event m |  |  | S07 — hill protection | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Sep 2026 | docket
Advanced Temporary Fencing | 36516 | Track storage | 87.5 clean m |  |  | Track storage | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Sep 2026 | docket
Advanced Temporary Fencing | 36517 | S.O.5 C.2 | 67.5 clean m |  |  | S.O.5 C.2 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Sep 2026 | docket
Advanced Temporary Fencing | 36518 | S.O.5 — grandstand, back of house | 35 clean m, 22.5 scrim m |  |  | S.O.5 — grandstand, back of house | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Sep 2026 | docket
Advanced Temporary Fencing | 36519 | Event operations — iEDM compound | 72.5 scrim m |  |  | Event operations — iEDM compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Sep 2026 | docket
Advanced Temporary Fencing | 36520 | Coates compound / ABD compound | 112.5 clean m, 40 scrim m |  |  | Coates compound / ABD compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Sep 2026 | docket
Advanced Temporary Fencing | 36521 | S.O.8 exclusion zone | 27.5 clean m |  |  | S.O.8 exclusion zone | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Sep 2026 | docket
Advanced Temporary Fencing | 36522 | Triangles mound, green bays — Macintosh Island Park | 277.5 CCB event m |  |  | Triangles mound, green bays — Macintosh Island Park | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Sep 2026 | docket
Advanced Temporary Fencing | 36523 | Helen Park — BSF compound | 22.5 scrim m |  |  | Helen Park — BSF compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 17 Sep 2026 | docket
Advanced Temporary Fencing | 36524 | Race admin | 137.5 clean m |  |  | Race admin | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 17 Sep 2026 | docket
Advanced Temporary Fencing | 36525 | S.O.5 C.2 | 60 relocation |  |  | S.O.5 C.2 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 17 Sep 2026 | docket
Advanced Temporary Fencing | 36526 | S.O.5 — retaining wall | 10 clean m |  |  | S.O.5 — retaining wall | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 17 Sep 2026 | docket
Advanced Temporary Fencing | 36528 | S.O.8 exclusion zone | 27.5 relocation |  |  | S.O.8 exclusion zone | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 17 Sep 2026 | docket
Advanced Temporary Fencing | 36529 | P.B.03 | 45 clean m, 10 scrim m |  |  | P.B.03 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 17 Sep 2026 | docket
Advanced Temporary Fencing | 36530 | PB01 works area | 15 clean m, 50 CCB event m |  |  | PB01 works area | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 17 Sep 2026 | docket
Advanced Temporary Fencing | 36531 | Pit building paddock | 105 scrim m |  |  | Pit building paddock | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 17 Sep 2026 | docket
Advanced Temporary Fencing | 36532 | S10 compound | 150 clean m, 132.5 scrim m |  |  | S10 compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 18 Sep 2026 | docket
Advanced Temporary Fencing | 36533 | S10 C.2 | 45 clean m |  |  | S10 C.2 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 18 Sep 2026 | docket
Advanced Temporary Fencing | 36534 | S10 to pit entry | 235 CCB demarcation m |  |  | S10 to pit entry | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 18 Sep 2026 | docket
Advanced Temporary Fencing | 36535 | S10 to pedestrian bridge | 30 CCB demarcation m |  |  | S10 to pedestrian bridge | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 18 Sep 2026 | docket
Advanced Temporary Fencing | 36536 | S08 C.Z. — construction zone | 172.5 clean m |  |  | S08 C.Z. — construction zone | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Sep 2026 | docket
Advanced Temporary Fencing | 36537 | S04 C.Z. — construction zone | 172.5 clean m |  |  | S04 C.Z. — construction zone | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Sep 2026 | docket
Advanced Temporary Fencing | 36538 | S.O.5 grandstand walkway | 32.5 clean m |  |  | S.O.5 grandstand walkway | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Sep 2026 | docket
Advanced Temporary Fencing | 36539 | Cypress Carpark | 40 scrim m |  |  | Cypress Carpark | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Sep 2026 | docket
Advanced Temporary Fencing | 36540 | The Hill | 370 CCB demarcation m |  |  | The Hill | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Sep 2026 | docket
Advanced Temporary Fencing | 36541 | The Hill — green bays | 25 CCB event m |  |  | The Hill — green bays | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Sep 2026 | docket
Advanced Temporary Fencing | 36542 | Viewing mound | 60 CCB demarcation m |  |  | Viewing mound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Sep 2026 | docket
Advanced Temporary Fencing | 36543 | PB02 stair protection | 20 clean m |  |  | PB02 stair protection | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Sep 2026 | docket
Advanced Temporary Fencing | 36544 | K01 kitchen compound fencing | 52.5 clean m, 52.5 scrim m, 1 ped gates |  |  | K01 kitchen compound fencing | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Sep 2026 | docket
Advanced Temporary Fencing | 36545 | Race admin | 10 clean m |  |  | Race admin | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Sep 2026 | docket
Advanced Temporary Fencing | 36546 | S.O.4 C.Z. — construction zone | 22.5 clean m |  |  | S.O.4 C.Z. — construction zone | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Sep 2026 | docket
Advanced Temporary Fencing | 36547 | PB01 footings | 72.5 clean m, 72.5 scrim m |  |  | PB01 footings | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Sep 2026 | docket
Advanced Temporary Fencing | 36548 | PB01 to Kapalua | 475 clean m |  |  | PB01 to Kapalua | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Sep 2026 | docket
Advanced Temporary Fencing | 36549 | PB02 footings — north side | 32.5 clean m |  |  | PB02 footings — north side | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Sep 2026 | docket
Advanced Temporary Fencing | 36550 | Axis — Hill Prd | 62.5 clean m |  |  | Axis — Hill Prd | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 24 Sep 2026 | docket
Advanced Temporary Fencing | 36551 | Breaker St / Serisier Ave — T12 to T14 | 510 CCB demarcation m |  |  | Breaker St / Serisier Ave — T12 to T14 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 24 Sep 2026 | docket
Advanced Temporary Fencing | 36552 | Telstra C.O.W. | 25 clean m |  |  | Telstra C.O.W. | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 24 Sep 2026 | docket
Advanced Temporary Fencing | 36553 | PB01 to Kapalua | 12.5 clean m |  |  | PB01 to Kapalua | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 24 Sep 2026 | docket
Advanced Temporary Fencing | 36554 | Main Beach Rd — supply compound to S22 | 352.5 CCB demarcation m |  |  | Main Beach Rd — supply compound to S22 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 24 Sep 2026 | docket
Advanced Temporary Fencing | 36555 | P.B.02 footings (south) | 30 clean m |  |  | P.B.02 footings (south) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 24 Sep 2026 | docket
Advanced Temporary Fencing | 36556 | Narrow Neck to S.O.8 grandstand | 402.5 CCB demarcation m |  |  | Narrow Neck to S.O.8 grandstand | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 25 Sep 2026 | docket
Advanced Temporary Fencing | 36557 | S.O.8 pedestrian walkway | 100 clean m |  |  | S.O.8 pedestrian walkway | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 25 Sep 2026 | docket
Advanced Temporary Fencing | 36558 | Oceanway C.Z. — concrete barrier infill | 10 clean m |  |  | Oceanway C.Z. — concrete barrier infill | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 25 Sep 2026 | docket
Advanced Temporary Fencing | 36559 | S.08 to Midwater, Castle St | 130 clean m, 202.5 CCB demarcation m |  |  | S.08 to Midwater, Castle St | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 28 Sep 2026 | docket
Advanced Temporary Fencing | 36560 | GC Hwy median strip (north) | 507.5 clean m, 427.5 scrim m, 447.5 CCB demarcation m, 1 ped gates |  |  | GC Hwy median strip (north) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 28 Sep 2026 | docket
Advanced Temporary Fencing | 36561 | Ocean Way carpark and construction zone | 142.5 clean m |  |  | Ocean Way carpark and construction zone | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 28 Sep 2026 | docket
Advanced Temporary Fencing | 36562 | S.01 to Gate 6 (beach run) | 327.5 clean m |  |  | S.01 to Gate 6 (beach run) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 29 Sep 2026 | docket
Advanced Temporary Fencing | 36563 | S18 grandstand to Meriton | 150 CCB demarcation m |  |  | S18 grandstand to Meriton | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 29 Sep 2026 | docket
Advanced Temporary Fencing | 36564 | WC15 - rear fencing (toilets) | 40 clean m, 40 scrim m |  |  | WC15 - rear fencing (toilets) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 29 Sep 2026 | docket
Advanced Temporary Fencing | 36565 | S04 to S05 pedestrian bridge | 25 clean m |  |  | S04 to S05 pedestrian bridge | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 29 Sep 2026 | docket
Advanced Temporary Fencing | 36566 | Rear of pit building / rear of Puppet Theatre | 270 scrim m, 216 blocks |  |  | Rear of pit building / rear of Puppet Theatre | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 30 Sep 2026 | docket
Advanced Temporary Fencing | 36567 | Smoking zones - trackwide | 215 CCB event m |  |  | Smoking zones - trackwide | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 30 Sep 2026 | docket
Advanced Temporary Fencing | 36568 | GC Hwy median strip (south) | 462.5 clean m, 447.5 scrim m, 420 CCB demarcation m |  |  | GC Hwy median strip (south) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 1 Oct 2026 | docket
Advanced Temporary Fencing | 36569 | Event - ELEC | 82.5 clean m, 65 scrim m |  |  | Event - ELEC | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 2 Oct 2026 | docket
Advanced Temporary Fencing | 36570 | Telstra COW | 10 scrim m |  |  | Telstra COW | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 2 Oct 2026 | docket
Advanced Temporary Fencing | 36571 | Triangle to Gate 6 beach run | 337.5 clean m |  |  | Triangle to Gate 6 beach run | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 2 Oct 2026 | docket
Advanced Temporary Fencing | 36572 | S14 construction zone | 15 clean m |  |  | S14 construction zone | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 2 Oct 2026 | docket
Advanced Temporary Fencing | 36573 | Paradise Waters — Gate 2 entry | 97.5 clean m |  |  | Paradise Waters — Gate 2 entry | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 6 Oct 2026 | docket
Advanced Temporary Fencing | 36574 | TV parking | 177.5 clean m, 10 scrim m |  |  | TV parking | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 6 Oct 2026 | docket
Advanced Temporary Fencing | 36575 | S01–S02 — stairs | 135 clean m |  |  | S01–S02 — stairs | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 6 Oct 2026 | docket
Advanced Temporary Fencing | 36576 | S01 — toilet infill | 2.5 clean m, 2.5 scrim m |  |  | S01 — toilet infill | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 6 Oct 2026 | docket
Advanced Temporary Fencing | 36577 | Club 500 storage — perimeter fence | 30 clean m, 25 scrim m |  |  | Club 500 storage — perimeter fence | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 6 Oct 2026 | docket
Advanced Temporary Fencing | 36578 | TV compound perimeter fence | 75 clean m |  |  | TV compound perimeter fence | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 6 Oct 2026 | docket
Advanced Temporary Fencing | 36579 | Commodore Park | 177.5 clean m, 122.5 scrim m, 2 ped gates |  |  | Commodore Park | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 7 Oct 2026 | docket
Advanced Temporary Fencing | 36580 | S17–S20 — walk through (grandstands) | 150 clean m |  |  | S17–S20 — walk through (grandstands) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 7 Oct 2026 | docket
Advanced Temporary Fencing | 36581 | S04 — Corporate | 72.5 scrim m |  |  | S04 — Corporate | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 7 Oct 2026 | docket
Advanced Temporary Fencing | 36582 | Race Admin — double stack — C.2 | 82.5 clean m |  |  | Race Admin — double stack — C.2 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 7 Oct 2026 | docket
Advanced Temporary Fencing | 36583 | Helen Park C.2 + perimeter fence | 215 clean m, 55 scrim m |  |  | Helen Park C.2 + perimeter fence | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 8 Oct 2026 | docket
Advanced Temporary Fencing | 36584 | North S01 — Infill | 7.5 clean m, 7.5 scrim m |  |  | North S01 — Infill | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 8 Oct 2026 | docket
Advanced Temporary Fencing | 36585 | Podium | 45 clean m, 45 scrim m, 1 ped gates |  |  | Podium | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 8 Oct 2026 | docket
Advanced Temporary Fencing | 36586 | Teams Area | 25 clean m, 25 scrim m |  |  | Teams Area | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 8 Oct 2026 | docket
Advanced Temporary Fencing | 36587 | Event Operations — perimeter fence | 30 clean m, 22.5 scrim m |  |  | Event Operations — perimeter fence | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Oct 2026 | docket
Advanced Temporary Fencing | 36588 | Club 500 Toilets | 95 clean m, 62.5 scrim m |  |  | Club 500 Toilets | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Oct 2026 | docket
Advanced Temporary Fencing | 36589 | S04 Corporate Toilets | 15 clean m, 15 scrim m |  |  | S04 Corporate Toilets | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Oct 2026 | docket
Advanced Temporary Fencing | 36590 | Club 500 exclusion zone CZ | 107.5 clean m |  |  | Club 500 exclusion zone CZ | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Oct 2026 | docket
Advanced Temporary Fencing | 36591 | Club 500 Creek Protection | 105 CCB event m, 42 flat feet |  |  | Club 500 Creek Protection | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Oct 2026 | docket
Advanced Temporary Fencing | 36592 | The Hill — Monster CZ | 137.5 clean m |  |  | The Hill — Monster CZ | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Oct 2026 | docket
Advanced Temporary Fencing | 36593 | S21 Grandstand — Walk through | 90 clean m |  |  | S21 Grandstand — Walk through | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Oct 2026 | docket
Advanced Temporary Fencing | 36594 | Smoking Zones — The Hill / Club 500 | 22.5 CCB event m |  |  | Smoking Zones — The Hill / Club 500 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Oct 2026 | docket
Advanced Temporary Fencing | 36595 | Rear of S20 — Shower | 10 CCB event m |  |  | Rear of S20 — Shower | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 9 Oct 2026 | docket
Advanced Temporary Fencing | 36596 | Main Beach Pde - Madison Point to Ferny Ave, Higman St to Equinox, Ferny Ave southern side, Seacrest to Pacific Point | 385 clean m, 287.5 CCB demarcation m, 5 ped gates |  |  | Main Beach Pde - Madison Point to Ferny Ave, Higman St to Equinox, Ferny Ave southern side, Seacrest to Pacific Point | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 12 Oct 2026 | docket
Advanced Temporary Fencing | 36597 | The Spit - McMahon's/HTH Compound | 17.5 scrim m |  |  | The Spit - McMahon's/HTH Compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 12 Oct 2026 | docket
Advanced Temporary Fencing | 36598 | Main Beach Pde - Rhapsody | 7.5 clean m, 7.5 scrim m |  |  | Main Beach Pde - Rhapsody | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 12 Oct 2026 | docket
Advanced Temporary Fencing | 36599 | Supply Compound | 147.5 clean m, 147.5 scrim m |  |  | Supply Compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 12 Oct 2026 | docket
Advanced Temporary Fencing | 36600 | I.E.D.M - Compound | — |  |  | I.E.D.M - Compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 12 Oct 2026 | docket
Advanced Temporary Fencing | 36601 | Commodore Park - Ticket Entry | 25 clean m, 25 scrim m |  |  | Commodore Park - Ticket Entry | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 12 Oct 2026 | docket
Advanced Temporary Fencing | 36602 | COW - OPTUS | 45 clean m, 45 scrim m |  |  | COW - OPTUS | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 12 Oct 2026 | docket
Advanced Temporary Fencing | 36603 | Eastern Residents & Demarc - Cable St to Gate 8A - DL & DR | 537.5 clean m, 52.5 scrim m, 672.5 CCB demarcation m, 4 ped gates |  |  | Eastern Residents & Demarc - Cable St to Gate 8A - DL & DR | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 13 Oct 2026 | docket
Advanced Temporary Fencing | 36604 | Breaker St - T11 - DL | 105 flat feet |  |  | Breaker St - T11 - DL | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 13 Oct 2026 | docket
Advanced Temporary Fencing | 36605 | Aloha Lane to Cronin St (Crest) | 95 clean m |  |  | Aloha Lane to Cronin St (Crest) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 13 Oct 2026 | docket
Advanced Temporary Fencing | 36606 | Fishermans Walk | 10 clean m |  |  | Fishermans Walk | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 13 Oct 2026 | docket
Advanced Temporary Fencing | 36607 | Main Beach Tower | 47.5 clean m |  |  | Main Beach Tower | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Oct 2026 | docket
Advanced Temporary Fencing | 36608 | Ferny Ave to Narrow Neck Court | 117.5 clean m, 192.5 CCB demarcation m |  |  | Ferny Ave to Narrow Neck Court | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Oct 2026 | docket
Advanced Temporary Fencing | 36609 | Esplanade south of Meriton - Porsche Lounge CZ | 420 clean m, 420 scrim m |  |  | Esplanade south of Meriton - Porsche Lounge CZ | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Oct 2026 | docket
Advanced Temporary Fencing | 36610 | G8 & surround | 367.5 clean m, 200 CCB demarcation m, 2 ped gates |  |  | G8 & surround | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 14 Oct 2026 | docket
Advanced Temporary Fencing | 36611 | Surfers Paradise Light Rail | 165 clean m, 30 scrim m, 130 CCB event m |  |  | Surfers Paradise Light Rail | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Oct 2026 | docket
Advanced Temporary Fencing | 36612 | Pacific Ave to Cable St | 315 clean m, 3 ped gates |  |  | Pacific Ave to Cable St | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Oct 2026 | docket
Advanced Temporary Fencing | 36613 | Porsche CZ | 70 CCB event m |  |  | Porsche CZ | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Oct 2026 | docket
Advanced Temporary Fencing | 36614 | S.0.8 B.O.H. | 40 clean m, 85 scrim m |  |  | S.0.8 B.O.H. | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Oct 2026 | docket
Advanced Temporary Fencing | 36615 | Gate 5 Compound | 110 clean m, 40 scrim m |  |  | Gate 5 Compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Oct 2026 | docket
Advanced Temporary Fencing | 36616 | Triangle CZ | 147.5 clean m |  |  | Triangle CZ | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 15 Oct 2026 | docket
Advanced Temporary Fencing | 36617 | Main Beach Light Rail | 155 clean m, 37.5 scrim m |  |  | Main Beach Light Rail | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Oct 2026 | docket
Advanced Temporary Fencing | 36618 | Cypress Carpark | 152.5 clean m |  |  | Cypress Carpark | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Oct 2026 | docket
Advanced Temporary Fencing | 36619 | Focus to Meriton - The Esplanade | 262.5 clean m, 302.5 CCB event m |  |  | Focus to Meriton - The Esplanade | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Oct 2026 | docket
Advanced Temporary Fencing | 36620 | I.E.D.M - Compound | — |  |  | I.E.D.M - Compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Oct 2026 | docket
Advanced Temporary Fencing | 36621 | Monster C.Z. - The Hill | 2.5 clean m |  |  | Monster C.Z. - The Hill | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Oct 2026 | docket
Advanced Temporary Fencing | 36622 | Golden Gate | 130 clean m |  |  | Golden Gate | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 16 Oct 2026 | docket
Advanced Temporary Fencing | 36623 | S15 C2 - hoarding fence and demarcation | 97.5 clean m, 100 CCB demarcation m |  |  | S15 C2 - hoarding fence and demarcation | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 19 Oct 2026 | docket
Advanced Temporary Fencing | 36624 | Admiralty Drive Intersection | 32.5 clean m |  |  | Admiralty Drive Intersection | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 19 Oct 2026 | docket
Advanced Temporary Fencing | 36625 | Gate 1 - S23 Compound | 285 clean m, 285 scrim m |  |  | Gate 1 - S23 Compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 19 Oct 2026 | docket
Advanced Temporary Fencing | 36626 | Seaway Carpark - The Spit and fuel compound | 492.5 clean m |  |  | Seaway Carpark - The Spit and fuel compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 19 Oct 2026 | docket
Advanced Temporary Fencing | 36627 | Track wide (four spots) | 125 CCB event m, 7.5 CCB demarcation m |  |  | Track wide (four spots) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36628 | PB03 - footings | 25 clean m, 25 scrim m |  |  | PB03 - footings | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36629 | PB03 - Gate 1 - Helen Park | 80 scrim m, 237.5 CCB event m, 182.5 CCB demarcation m |  |  | PB03 - Gate 1 - Helen Park | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36630 | Macintosh Island - entry | 30 clean m |  |  | Macintosh Island - entry | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36631 | Podium | 5 clean m, 5 scrim m |  |  | Podium | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36632 | Pit Lane - S01 | — |  |  | Pit Lane - S01 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36633 | Fire hydrant - S01 - toilets | 17.5 clean m |  |  | Fire hydrant - S01 - toilets | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36634 | S07 viewing mound | 12.5 CCB demarcation m |  |  | S07 viewing mound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36635 | Esplanade north to the Triangle | 37.5 CCB event m, 35 flat feet |  |  | Esplanade north to the Triangle | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36636 | Higman St and Rhapsody | 205 CCB demarcation m |  |  | Higman St and Rhapsody | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36637 | Macintosh Island foot bridge | 25 CCB event m |  |  | Macintosh Island foot bridge | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36638 | Pit Building north | 88 flat feet |  |  | Pit Building north | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 20 Oct 2026 | docket
Advanced Temporary Fencing | 36639 | McIntosh Island storage | 15 clean m, 15 scrim m |  |  | McIntosh Island storage | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36640 | D.S - storage | 47.5 clean m |  |  | D.S - storage | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36642 | Gate 6 | 7.5 clean m, 7.5 scrim m |  |  | Gate 6 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36643 | Club 500 | 32.5 clean m, 47.5 scrim m, 20 CCB event m |  |  | Club 500 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36644 | Porsche to Staghorn St (Esplanade) | — |  |  | Porsche to Staghorn St (Esplanade) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36645 | Inlet (Breaker St) | 12.5 CCB demarcation m |  |  | Inlet (Breaker St) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36646 | S08 - TV | 15 clean m |  |  | S08 - TV | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36647 | Club 500 - creek protection | 47.5 CCB event m |  |  | Club 500 - creek protection | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36756 | Meriton | 10 clean m |  |  | Meriton | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36757 | The Spit - Transporter Compound | 70 clean m |  |  | The Spit - Transporter Compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 21 Oct 2026 | docket
Advanced Temporary Fencing | 36648 | Gate 7 | 37.5 clean m |  |  | Gate 7 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36649 | Gate 10 | 40 clean m, 40 scrim m |  |  | Gate 10 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36650 | Malibu - Breaker St | 5 clean m |  |  | Malibu - Breaker St | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36751 | Ocean Ave | 147.5 clean m, 315 CCB event m |  |  | Ocean Ave | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36752 | Staghorn St Entry | 20 clean m |  |  | Staghorn St Entry | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36753 | Gate 9 - Breaker St | 17.5 clean m |  |  | Gate 9 - Breaker St | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36754 | Aloha Lane - Gate 8 | 37.5 clean m |  |  | Aloha Lane - Gate 8 | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36755 | Helipad | 35 clean m, 45 CCB event m |  |  | Helipad | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36758 | T.V - Compound | 30 clean m |  |  | T.V - Compound | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36759 | Rhapsody Sales Office - walk through | 72.5 clean m, 72.5 scrim m |  |  | Rhapsody Sales Office - walk through | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36760 | Macintosh Island - fallen tree | 10 CCB demarcation m |  |  | Macintosh Island - fallen tree | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36761 | Rubbish Compactor (Cleanaway) | 35 clean m, 32.5 scrim m |  |  | Rubbish Compactor (Cleanaway) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36762 | Turn 2-3 - Crash Protection | 20 clean m |  |  | Turn 2-3 - Crash Protection | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36763 | Triangle | — |  |  | Triangle | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36764 | Monster (Energy) | 15 CCB event m |  |  | Monster (Energy) | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 22 Oct 2026 | docket
Advanced Temporary Fencing | 36765 | Gate 5 - Ocean Ave | 5 clean m |  |  | Gate 5 - Ocean Ave | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Oct 2026 | docket
Advanced Temporary Fencing | 36766 | Smoking Zone - Breaker St | 10 CCB event m |  |  | Smoking Zone - Breaker St | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Oct 2026 | docket
Advanced Temporary Fencing | 36767 | Gate 7 - security entry | 7.5 clean m |  |  | Gate 7 - security entry | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Oct 2026 | docket
Advanced Temporary Fencing | 36768 | Club 500 - B.O.H. | 50 CCB event m |  |  | Club 500 - B.O.H. | [5 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Installed 23 Oct 2026 | docket
Advanced Temporary Fencing |  | Week 6 | 232.5 clean m, 3 vehicle gates | [8 empty] | Removal: by Advanced, by the hour; dates not on the record |  |  |  |  | Week 6 | week sheet row
Advanced Temporary Fencing | 28551 | Collected: S.O.8 exclusion zone | 11 mesh panel, 10 base, 10 clamp |  |  | S.O.8 exclusion zone | [10 empty] | Collected 21 Sep 2026 | collection form
Advanced Temporary Fencing | 28552 | Collected: S07 C.Z. | 47 mesh panel, 58 base, 58 clamp, 5 brace |  |  | S07 C.Z. | [10 empty] | Collected 25 Sep 2026 | collection form
Advanced Temporary Fencing | 28553 | Collected: S.O.8 C.Z. | 20 mesh panel, 27 base, 23 clamp |  |  | S.O.8 C.Z. | [10 empty] | Collected 25 Sep 2026 | collection form
Advanced Temporary Fencing | 28554 | Collected: S04 Corporate | 29 base, 29 clamp, 26 mesh panel |  |  | S04 Corporate | [10 empty] | Collected 6 Oct 2026 | collection form
Advanced Temporary Fencing | 28555 | Collected: Race Admin — Double Stack CZ | 3 base, 3 clamp, 3 mesh panel |  |  | Race Admin — Double Stack CZ | [10 empty] | Collected 9 Oct 2026 | collection form
Advanced Temporary Fencing | 28556 | Collected: Pit Lane Storage | 36 base, 38 clamp, 38 mesh panel |  |  | Pit Lane Storage | [10 empty] | Collected 9 Oct 2026 | collection form
Advanced Temporary Fencing | 28557 | Collected: Double Stack CZ | 28 base, 28 clamp, 30 mesh panel, 2 wheels |  |  | Double Stack CZ | [10 empty] | Collected 12 Oct 2026 | collection form
Advanced Temporary Fencing | 28558 | Collected: Pit Lane | 86 base, 84 clamp, 84 mesh panel, 2 wheels |  |  | Pit Lane | [10 empty] | Collected 15 Oct 2026 | collection form
Advanced Temporary Fencing | 28559 | Collected: Porsche Lounge | 10 base, 13 clamp, 12 mesh panel |  |  | Porsche Lounge | [10 empty] | Collected 15 Oct 2026 | collection form
Advanced Temporary Fencing | 28560 | Collected: S18 - Grandstand | 6 base, 5 clamp, 6 mesh panel |  |  | S18 - Grandstand | [10 empty] | Collected 15 Oct 2026 | collection form
Advanced Temporary Fencing | 28561 | Collected: Oceanway C.Z. | 34 base, 34 clamp, 34 mesh panel, 2 wheels |  |  | Oceanway C.Z. | [10 empty] | Collected 19 Oct 2026 | collection form
Advanced Temporary Fencing | 28562 | Collected: Pit Building B.O.H. | 7 cc barrier |  |  | Pit Building B.O.H. | [10 empty] | Collected 20 Oct 2026 | collection form
Advanced Temporary Fencing | 28563 | Collected: S.O.4 – C.Z. | 4 base, 8 clamp, 5 mesh panel, 1 wheels |  |  | S.O.4 – C.Z. | [10 empty] | Collected 20 Oct 2026 | collection form
Advanced Temporary Fencing | 28564 | Collected: Medium strip – North – C.Z. | 4 base, 4 clamp, 5 mesh panel, 1 ped gate |  |  | Medium strip – North – C.Z. | [10 empty] | Collected 20 Oct 2026 | collection form
Advanced Temporary Fencing | 28566 | Collected: Porsche C.Z. | 13 base, 10 clamp, 12 mesh panel, 4 wheels |  |  | Porsche C.Z. | [10 empty] | Collected 21 Oct 2026 | collection form
Advanced Temporary Fencing | 28567 | Collected: Triangle C.Z. | 27 base, 28 clamp, 31 mesh panel, 2 wheels |  |  | Triangle C.Z. | [10 empty] | Collected 21 Oct 2026 | collection form
Advanced Temporary Fencing | 28569 | Collected: S15 - C.Z. | 39 base, 37 clamp, 38 mesh panel, 2 wheels |  |  | S15 - C.Z. | [10 empty] | Collected 21 Oct 2026 | collection form
Advanced Temporary Fencing | 28570 | Collected: Club 500 - creek protection zone | 19 base, 19 flat feet ccb |  |  | Club 500 - creek protection zone | [10 empty] | Collected 21 Oct 2026 | collection form
Advanced Temporary Fencing | 28571 | Collected: The Hill - Monster C.Z. | 53 base, 53 clamp, 59 mesh panel, 2 wheels |  |  | The Hill - Monster C.Z. | [10 empty] | Collected 22 Oct 2026 | collection form
Advanced Temporary Fencing | 28572 | Collected: PB03 | 4 mesh panel |  |  | PB03 | [10 empty] | Collected 22 Oct 2026 | collection form
Advanced Temporary Fencing | 28574 | Collected: Macintosh Island - Pit Building north | 1 cc barrier, 16 flat feet ccb |  |  | Macintosh Island - Pit Building north | [10 empty] | Collected 22 Oct 2026 | collection form
Advanced Temporary Fencing | 28575 | Collected: Macintosh Island | 2 mesh panel |  |  | Macintosh Island | [10 empty] | Collected 22 Oct 2026 | collection form
Advanced Temporary Fencing | 28577 | Collected: S19 | 3 base, 15 cc barrier, 3 clamp, 4 mesh panel |  |  | S19 | [10 empty] | Collected 22 Oct 2026 | collection form
Advanced Temporary Fencing | 28578 | Collected: S21 | 2 base, 22 cc barrier, 6 clamp, 4 mesh panel, 2 wheels |  |  | S21 | [10 empty] | Collected 22 Oct 2026 | collection form
Advanced Temporary Fencing | 28579 | Collected: Monster Energy C.Z. | 1 mesh panel |  |  | Monster Energy C.Z. | [10 empty] | Collected 22 Oct 2026 | collection form

## Flat list
GC500 2026 · one row per unit and per item inside a building · as at 26 Oct 2026 07:46 AEST · filter or sort on any column
Group | Ref | Description | Item | Qty | Asset / fleet no | Owner | Location | Area | Plan section | Lat | Long | Map | Pin basis | Off-hire (demob plan) | Plan source | Contract off-hire date | Contract off-hire time | Contract · line | Contract status | Status on site | Notes
Portable buildings | AA | Active Air Crib Room | Building 6m | 1 | 142514 | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Portable buildings | AA | Active Air Crib Room | ↳ Inside: Fridge | 1 |  | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | fridge; parsed from the schedule notes column
Portable buildings | AA | Active Air Crib Room | ↳ Inside: Folding table | 1 |  | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 1x fold table; parsed from the schedule notes column
Portable buildings | AA | Active Air Crib Room | ↳ Inside: Stackable chair | 4 |  | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 4x stack chair; parsed from the schedule notes column
Portable buildings | AA | Active Air Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | AA - Active Air Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4283 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | CP1 | P68 · Signevent Crib Room | Building 6m | 1 | 1105057 | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 17 | Delivered | Still to leave
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Chair | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Chairs; parsed from the schedule notes column
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Desk | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | parsed from the schedule notes column
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Hydration station | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Hydration Station; parsed from the schedule notes column
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Sink with tap | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Sink with Tap; parsed from the schedule notes column
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Fridge | 1 | 1116687 | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Fridge — Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Urn | 1 | 119810 | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Urn — Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
Portable buildings | CP1 | P68 · Signevent Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | CP1 (P68) - Signevent Crib Room | Pit lane entry |  | -27.9975 | 153.4284 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | HRP | Hire Republic Crib Room | Building 6m | 1 | 1189410 | Coates | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 93 | Delivered | Still to leave
Portable buildings | HRP | Hire Republic Crib Room | ↳ Inside: Air conditioner | 1 | 1189901 | Coates | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | HRP | Hire Republic Crib Room | ↳ Inside: Air conditioner | 1 | 1127305 | Coates | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | HRP | Hire Republic Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | HRP - Hire Republic Crib Room | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P01 | iEDM Engineering Office | Building 12m | 1 | 1322583 | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 1 | Delivered | Still to leave
Portable buildings | P01 | iEDM Engineering Office | ↳ Inside: Fridge | 1 | 1328956 | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge - Full Sized; parsed from the schedule notes column
Portable buildings | P01 | iEDM Engineering Office | ↳ Inside: Air conditioner | 1 | 1322610 | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P01 | iEDM Engineering Office | ↳ Inside: Air conditioner | 1 | 1322609 | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P01 | iEDM Engineering Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P01 - iEDM Engineering Office | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P03 | SCA Event Management Office | Building 12m | 1 | 1327212 | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 4 | Delivered | Still to leave
Portable buildings | P03 | SCA Event Management Office | ↳ Inside: Fridge | 1 | 1328955 | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge - Full Sized; parsed from the schedule notes column
Portable buildings | P03 | SCA Event Management Office | ↳ Inside: Air conditioner | 1 | 1327954 | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P03 | SCA Event Management Office | ↳ Inside: Air conditioner | 1 | 1327953 | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P03 | SCA Event Management Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P03 - SCA Event Management Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4265 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P04 | SCA Sales & Marketing Office | Building 12m | 1 | 1327213 | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 7 | Delivered | Still to leave
Portable buildings | P04 | SCA Sales & Marketing Office | ↳ Inside: Fridge | 1 | 1328954 | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge - Full Sized; parsed from the schedule notes column
Portable buildings | P04 | SCA Sales & Marketing Office | ↳ Inside: Air conditioner | 1 | 1327955 | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P04 | SCA Sales & Marketing Office | ↳ Inside: Air conditioner | 1 | 1327956 | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P04 | SCA Sales & Marketing Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P04 - SCA Sales & Marketing Office | Island west parkland entry – by the merch strip |  | -27.9835 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P05 | Event Control Center (ECC) | Building 6m | 1 | 1189422 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968862 · line 10 | Delivered | Still to leave
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Chair | 1 |  | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | parsed from the schedule notes column
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Fridge | 1 | 1311988 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge (full sized); parsed from the schedule notes column
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Zip boiler | 1 |  | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Zip Boiler; parsed from the schedule notes column
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Sink with tap | 1 |  | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Sink with Tap; parsed from the schedule notes column
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Microwave | 1 | 1320150 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Microwave — Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Air conditioner | 1 | 1127574 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Air conditioner | 1 | 1189939 | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P05 | Event Control Center (ECC) | ↳ Inside: Fire extinguisher | 1 |  | Coates | P05 - Event Control Center (ECC) | Island west parkland entry – by the merch strip |  | -27.9834 | 153.4266 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P06 | Wilclean Crib Room | Building 6m | 1 | 1087453 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 64 | Delivered | Still to leave
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Sink with tap | 1 |  | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Sink w Tap; parsed from the schedule notes column
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Air conditioner | 1 | 1097209 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Fridge | 1 | 1272749 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Microwave | 1 | 1284012 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Zip boiler | 1 | 1173374 | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P06 | Wilclean Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | P06 - Wilclean Crib Room | Median strip meet-up – pit stop, by FOAM |  | -27.9842 | 153.4277 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P08 | Security | Building 6m | 1 | 421138 | Coates | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 126 | Delivered | Still to leave
Portable buildings | P08 | Security | ↳ Inside: Air conditioner | 1 | 1311986 | Coates | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P08 | Security | ↳ Inside: Fridge | 1 | 1114312 | Coates | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P08 | Security | ↳ Inside: Fire extinguisher | 1 |  | Coates | P08 Security | Commodore Park drop point (red dot) |  | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P09 | Iedm Safety Office | Building 6m | 1 | 1268824 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 28 | Delivered | Still to leave
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Sink with tap | 1 |  | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Sink w Tap; parsed from the schedule notes column
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Air conditioner | 1 | 1270403 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Fridge | 1 | 1328958 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Urn | 1 | 1284061 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Zip boiler | 1 | 1254390 | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Zip boiler — Boiling-water unit. Confirmed on site by Andrew Fisher, 25 Oct 2026.; added in this page
Portable buildings | P09 | Iedm Safety Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P09 - Iedm Safety Office | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4267 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P10 | Team Office - 888 Racing | Building 4.8m | 1 | 105626 | Coates | P10 - Team Office - 888 Racing | Island north – by FREIGHT | S02 | -27.9866 | 153.4281 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 44 | Delivered | Still to leave
Portable buildings | P10 | Team Office - 888 Racing | ↳ Inside: Air conditioner | 1 | 238771 | Coates | P10 - Team Office - 888 Racing | Island north – by FREIGHT | S02 | -27.9866 | 153.4281 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P10 | Team Office - 888 Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P10 - Team Office - 888 Racing | Island north – by FREIGHT | S02 | -27.9866 | 153.4281 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P11 | Team Office - DJR | Building 4.8m | 1 | 415576 | Coates | P11 - Team Office - DJR | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 46 | Delivered | Still to leave
Portable buildings | P11 | Team Office - DJR | ↳ Inside: Air conditioner | 1 | 112940 | Coates | P11 - Team Office - DJR | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P11 | Team Office - DJR | ↳ Inside: Fire extinguisher | 1 |  | Coates | P11 - Team Office - DJR | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P12 | Team 18 | Building 4.8m | 1 | 418665 | Coates | P12 - Team 18 | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 48 | Delivered | Still to leave
Portable buildings | P12 | Team 18 | ↳ Inside: Fire extinguisher | 1 |  | Coates | P12 - Team 18 | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P13 | Team Office - WAU | Building 4.8m | 1 | 1097346 | Coates | P13 - Team Office - WAU | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 51 | Delivered | Still to leave
Portable buildings | P13 | Team Office - WAU | ↳ Inside: Air conditioner | 1 | 1190775 | Coates | P13 - Team Office - WAU | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P13 | Team Office - WAU | ↳ Inside: Fire extinguisher | 1 |  | Coates | P13 - Team Office - WAU | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P14 | Team Office - Grove Racing | Building 4.8m | 1 | 960599 | Coates | P14 - Team Office - Grove Racing | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 53 | Delivered | Still to leave
Portable buildings | P14 | Team Office - Grove Racing | ↳ Inside: Air conditioner | 1 | 118370 | Coates | P14 - Team Office - Grove Racing | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P14 | Team Office - Grove Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P14 - Team Office - Grove Racing | Island north – by FREIGHT | S02 | -27.9868 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P15 | Team Office - Erebus Motorsport | Building 4.8m | 1 | 1097345 | Coates | P15 - Team Office - Erebus Motorsport | Island north – by FREIGHT | S02 | -27.9869 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 55 | Delivered | Still to leave
Portable buildings | P15 | Team Office - Erebus Motorsport | ↳ Inside: Fire extinguisher | 1 |  | Coates | P15 - Team Office - Erebus Motorsport | Island north – by FREIGHT | S02 | -27.9869 | 153.4282 | Open map | Master plan position | 2026-11-04 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P16 | Team Office - WFL | Building 4.8m | 1 | 415575 | Coates | P16 - Team Office - WFL | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 57 | Delivered | Still to leave
Portable buildings | P16 | Team Office - WFL | ↳ Inside: Fire extinguisher | 1 |  | Coates | P16 - Team Office - WFL | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P17 | Team Office BJR | Building 9.6m | 1 | 1268887 | Coates | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 33 | Delivered | Still to leave
Portable buildings | P17 | Team Office BJR | ↳ Inside: Air conditioner | 1 | 1270473 | Coates | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P17 | Team Office BJR | ↳ Inside: Air conditioner | 1 | 1270472 | Coates | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P17 | Team Office BJR | ↳ Inside: Fire extinguisher | 1 |  | Coates | P17 - Team Office BJR | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.427 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P18 | Team Office - MSR | Building 4.8m | 1 | 1097343 | Coates | P18 - Team Office - MSR | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4268 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 36 | Delivered | Still to leave
Portable buildings | P18 | Team Office - MSR | ↳ Inside: Fridge | 1 |  | Coates | P18 - Team Office - MSR | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4268 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P18 | Team Office - MSR | ↳ Inside: Fire extinguisher | 1 |  | Coates | P18 - Team Office - MSR | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4268 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P19 | Team Office Premiair Racing | Building 4.8m | 1 | 1110619 | Coates | P19 - Team Office Premiair Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 34 | Delivered | Still to leave
Portable buildings | P19 | Team Office Premiair Racing | ↳ Inside: Air conditioner | 1 | 1244101 | Coates | P19 - Team Office Premiair Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P19 | Team Office Premiair Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P19 - Team Office Premiair Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P20 | Team Office Blanchard Racing | Building 4.8m | 1 | 1097339 | Coates | P20 - Team Office Blanchard Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 38 | Delivered | Still to leave
Portable buildings | P20 | Team Office Blanchard Racing | ↳ Inside: Air conditioner | 1 | 1180683 | Coates | P20 - Team Office Blanchard Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P20 | Team Office Blanchard Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P20 - Team Office Blanchard Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.985 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P21 | Team Objective Racing | Building 4.8m | 1 | 1327220 | Coates | P21 - Team Objective Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 92 | Delivered | Still to leave
Portable buildings | P21 | Team Objective Racing | ↳ Inside: Air conditioner | 1 | 1327938 | Coates | P21 - Team Objective Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P21 | Team Objective Racing | ↳ Inside: Fire extinguisher | 1 |  | Coates | P21 - Team Objective Racing | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P25 | Support Category Stewards | Building 4.8m | 1 | 1189408 | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 105 | Delivered | Still to leave
Portable buildings | P25 | Support Category Stewards | ↳ Inside: Air conditioner | 1 | 1189951 | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P25 | Support Category Stewards | ↳ Inside: Air conditioner | 1 | 1189950 | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P25 | Support Category Stewards | ↳ Inside: Fridge | 1 | 1260174 | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P25 | Support Category Stewards | ↳ Inside: Fire extinguisher | 1 |  | Coates | P25 - Support Category Stewards | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P33 | Race Medical | Building 9.6m | 1 | 453375 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 24 | Delivered | Still to leave
Portable buildings | P33 | Race Medical | ↳ Inside: Sink with tap | 1 |  | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Sink with Tap; parsed from the schedule notes column
Portable buildings | P33 | Race Medical | ↳ Inside: Air conditioner | 1 | 1286611 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P33 | Race Medical | ↳ Inside: Air conditioner | 1 | 1127296 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P33 | Race Medical | ↳ Inside: Fridge | 1 | 1238952 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P33 | Race Medical | ↳ Inside: Zip boiler | 1 | 1066777 | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P33 | Race Medical | ↳ Inside: Fire extinguisher | 1 |  | Coates | P33 - Race Medical | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P36 | Harry the Hirer | Building 6m | 1 | 1282487 | Coates | P36 - Harry the Hirer | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 93 | Delivered | Still to leave
Portable buildings | P36 | Harry the Hirer | ↳ Inside: Air conditioner | 1 | 1283004 | Coates | P36 - Harry the Hirer | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P36 | Harry the Hirer | ↳ Inside: Fire extinguisher | 1 |  | Coates | P36 - Harry the Hirer | Island north – by FREIGHT | S02 | -27.9867 | 153.4282 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P37 | Oz Wide Audio Crib Room | Building 6m | 1 | 1105053 | Coates | P37 Oz Wide Audio Crib Room | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 50 | Delivered | Still to leave
Portable buildings | P37 | Oz Wide Audio Crib Room | ↳ Inside: Air conditioner | 1 | 1198145 | Coates | P37 Oz Wide Audio Crib Room | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | Aircon; recorded on site as a unit
Portable buildings | P37 | Oz Wide Audio Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | P37 Oz Wide Audio Crib Room | Island north – by FREIGHT | S02 | -27.9869 | 153.4283 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P38 | Green Room 1 | Building 6m | 1 | 1327218 | Coates | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 70 | Delivered | Still to leave
Portable buildings | P38 | Green Room 1 | ↳ Inside: Air conditioner | 1 | 1327934 | Coates | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P38 | Green Room 1 | ↳ Inside: Fridge | 1 | 1272755 | Coates | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P38 | Green Room 1 | ↳ Inside: Fire extinguisher | 1 |  | Coates | P38 - Green Room 1 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4276 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P39 | Green Room 2 | Building 6m | 1 | 1327216 | Coates | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 73 | Delivered | Still to leave
Portable buildings | P39 | Green Room 2 | ↳ Inside: Air conditioner | 1 | 1272737 | Coates | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P39 | Green Room 2 | ↳ Inside: Air conditioner | 1 | 1327936 | Coates | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P39 | Green Room 2 | ↳ Inside: Fire extinguisher | 1 |  | Coates | P39 Green Room 2 | Median strip meet-up – pit stop, by FOAM |  | -27.9846 | 153.4275 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P41 | QFES Crib Room | Building 6m | 1 | 1189412 | Coates | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 63 | Delivered | Still to leave
Portable buildings | P41 | QFES Crib Room | ↳ Inside: Air conditioner | 1 | 1189899 | Coates | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P41 | QFES Crib Room | ↳ Inside: Air conditioner | 1 | 1189908 | Coates | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P41 | QFES Crib Room | ↳ Inside: Fire extinguisher | 1 |  | Coates | P41 - QFES Crib Room | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-06 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P42 | Production | Building 6m | 1 | 1327221 | Coates | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 76 | Delivered | Still to leave
Portable buildings | P42 | Production | ↳ Inside: Air conditioner | 1 | 1327939 | Coates | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P42 | Production | ↳ Inside: Fridge | 1 | 1272746 | Coates | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P42 | Production | ↳ Inside: Fire extinguisher | 1 |  | Coates | P42 - Production | Median strip meet-up – pit stop, by FOAM |  | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P44 | Queensland Ambulance Service | Building 6m | 1 | 198481 | Coates | P44 - Queensland Ambulance Service | Island west parkland entry – by the merch strip |  | -27.9838 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 61 | Delivered | Still to leave
Portable buildings | P44 | Queensland Ambulance Service | ↳ Inside: Fridge | 1 | 1183134 | Coates | P44 - Queensland Ambulance Service | Island west parkland entry – by the merch strip |  | -27.9838 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P44 | Queensland Ambulance Service | ↳ Inside: Fire extinguisher | 1 |  | Coates | P44 - Queensland Ambulance Service | Island west parkland entry – by the merch strip |  | -27.9838 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P45 | St John First Aid | Building 6m | 1 | 107135 | Coates | P45 St John First Aid | Main Beach seaside – by the supply compound |  | -27.9881 | 153.43 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 131 | Delivered | Still to leave
Portable buildings | P45 | St John First Aid | ↳ Inside: Air conditioner | 1 | 1250796 | Coates | P45 St John First Aid | Main Beach seaside – by the supply compound |  | -27.9881 | 153.43 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P45 | St John First Aid | ↳ Inside: Fire extinguisher | 1 |  | Coates | P45 St John First Aid | Main Beach seaside – by the supply compound |  | -27.9881 | 153.43 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P46 | QPS Command Post | Building 12m | 1 | 1327215 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 100 | Delivered | Still to leave
Portable buildings | P46 | QPS Command Post | ↳ Inside: Air conditioner | 1 | 1327959 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P46 | QPS Command Post | ↳ Inside: Air conditioner | 1 | 1327960 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P46 | QPS Command Post | ↳ Inside: Fridge | 1 | 1318501 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge — Police fridge, from T0265's 14 Oct delivery; added in this page
Portable buildings | P46 | QPS Command Post | ↳ Inside: Fridge | 1 | 1260164 | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge — Police fridge, from T0265's 14 Oct delivery; added in this page
Portable buildings | P46 | QPS Command Post | ↳ Inside: Fire extinguisher | 1 |  | Coates | P46 - QPS Command Post | Commodore Park drop point (red dot) |  | -27.9835 | 153.424 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P51 | Security Sign On | Building 12m | 1 | 1322579 | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 94 | Delivered | Still to leave
Portable buildings | P51 | Security Sign On | ↳ Inside: Air conditioner | 1 | 1326602 | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P51 | Security Sign On | ↳ Inside: Air conditioner | 1 | 1326601 | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P51 | Security Sign On | ↳ Inside: Fridge | 1 | 1328959 | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P51 | Security Sign On | ↳ Inside: Fire extinguisher | 1 |  | Coates | P51 - Security Sign On | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P52 | Gate 1 Volunteer Check-In | Building 12m | 1 | 1327211 | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 79 | Delivered | Still to leave
Portable buildings | P52 | Gate 1 Volunteer Check-In | ↳ Inside: Air conditioner | 1 | 1327951 | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P52 | Gate 1 Volunteer Check-In | ↳ Inside: Air conditioner | 1 | 1327952 | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P52 | Gate 1 Volunteer Check-In | ↳ Inside: Fridge | 1 | 1328953 | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P52 | Gate 1 Volunteer Check-In | ↳ Inside: Fire extinguisher | 1 |  | Coates | P52 - Gate 1 Volunteer Check-In | Helen Park drop point (red dot) | S23 | -27.9813 | 153.424 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P54 | Accred Centre BOH | Building 6m | 1 | 1327219 | Coates | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 85 | Delivered | Still to leave
Portable buildings | P54 | Accred Centre BOH | ↳ Inside: Air conditioner | 1 | 1327937 | Coates | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P54 | Accred Centre BOH | ↳ Inside: Fridge | 1 | 1328957 | Coates | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | Fridge — Moved from P46 on 14 Oct 2026; same fridge, not an additional hire.; added in this page
Portable buildings | P54 | Accred Centre BOH | ↳ Inside: Fire extinguisher | 1 |  | Coates | P54 - Accred Centre BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P55 | Gate 1 Ticket Box | Ticket Box 6m | 1 | 172114 | Coates | P55 - Gate 1 Ticket Box | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4238 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 87 | Delivered | Still to leave
Portable buildings | P55 | Gate 1 Ticket Box | ↳ Inside: Air conditioner | 1 | 1320175 | Coates | P55 - Gate 1 Ticket Box | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4238 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P55 | Gate 1 Ticket Box | ↳ Inside: Fire extinguisher | 1 |  | Coates | P55 - Gate 1 Ticket Box | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4238 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P56 | Gate 1 Ticket BOH | Building 3.6m | 1 | 1268865 | Coates | P56 - Gate 1 Ticket BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 89 | Delivered | Still to leave
Portable buildings | P56 | Gate 1 Ticket BOH | ↳ Inside: Air conditioner | 1 | 1270437 | Coates | P56 - Gate 1 Ticket BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P56 | Gate 1 Ticket BOH | ↳ Inside: Fire extinguisher | 1 |  | Coates | P56 - Gate 1 Ticket BOH | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4239 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P57 | Radio Distribution Office | Building 9.6m | 1 | 1268888 | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 90 | Delivered | Still to leave
Portable buildings | P57 | Radio Distribution Office | ↳ Inside: Air conditioner | 1 | 1270478 | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P57 | Radio Distribution Office | ↳ Inside: Air conditioner | 1 | 1270479 | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P57 | Radio Distribution Office | ↳ Inside: Fridge | 1 | 1280688 | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P57 | Radio Distribution Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P57 - Radio Distribution Office | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4242 | Open map | Master plan position | 2026-10-30 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P58 | 1300 Medics | Building 6m | 1 | 1273656 | Coates | P58 - 1300 Medics | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968862 · line 59 | Delivered | Still to leave
Portable buildings | P58 | 1300 Medics | ↳ Inside: Fridge | 1 | 1201945 | Coates | P58 - 1300 Medics | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | P58 | 1300 Medics | ↳ Inside: Fire extinguisher | 1 |  | Coates | P58 - 1300 Medics | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P60 | Gate 5 Ticket Box | Ticket Box 4.8m | 1 | 1015699 | Coates | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 116 | Delivered | Still to leave
Portable buildings | P60 | Gate 5 Ticket Box | ↳ Inside: Air conditioner | 1 | 1267597 | Coates | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P60 | Gate 5 Ticket Box | ↳ Inside: Swivel chair | 4 |  | Coates | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | 4x Swivel chair; added in this page
Portable buildings | P60 | Gate 5 Ticket Box | ↳ Inside: Fire extinguisher | 1 |  | Coates | P60 - Gate 5 Ticket Box | Pit lane entry |  | -27.9936 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P62 | Gate 5 QFES Office | Building 6m | 1 | 1189409 | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 118 | Delivered | Still to leave
Portable buildings | P62 | Gate 5 QFES Office | ↳ Inside: Air conditioner | 1 | 1189912 | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P62 | Gate 5 QFES Office | ↳ Inside: Air conditioner | 1 | 1189908 | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P62 | Gate 5 QFES Office | ↳ Inside: Fridge | 1 | 1254221 | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P62 | Gate 5 QFES Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P62 - Gate 5 QFES Office | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P63 | Gate 5 Volunteer Sign On | Building 6m | 1 | 960719 | Coates | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 121 | Delivered | Still to leave
Portable buildings | P63 | Gate 5 Volunteer Sign On | ↳ Inside: Air conditioner | 1 | 1219157 | Coates | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P63 | Gate 5 Volunteer Sign On | ↳ Inside: Air conditioner | 1 | 1219156 | Coates | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P63 | Gate 5 Volunteer Sign On | ↳ Inside: Fire extinguisher | 1 |  | Coates | P63 - Gate 5 Volunteer Sign On | Pit lane entry |  | -27.9939 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P65 | Support Categories Race Secretary | Building 6m | 1 | 1327217 | Coates | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 110 | Delivered | Still to leave
Portable buildings | P65 | Support Categories Race Secretary | ↳ Inside: Air conditioner | 1 | 1327935 | Coates | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P65 | Support Categories Race Secretary | ↳ Inside: Fridge | 1 | 1283982 | Coates | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P65 | Support Categories Race Secretary | ↳ Inside: Fire extinguisher | 1 |  | Coates | P65 - Support Categories Race Secretary | Pit lane entry |  | -27.9914 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P66 | Support Category Scrutineers | Building 6m | 1 | 1327222 | Coates | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 113 | Delivered | Still to leave
Portable buildings | P66 | Support Category Scrutineers | ↳ Inside: Air conditioner | 1 | 1372940 | Coates | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P66 | Support Category Scrutineers | ↳ Inside: Fridge | 1 | 131190 | Coates | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P66 | Support Category Scrutineers | ↳ Inside: Fire extinguisher | 1 |  | Coates | P66 - Support Category Scrutineers | Pit lane entry |  | -27.9915 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P67 | Gate 6 Security Office | Building 6m | 1 | 421107 | Coates | P67 - Gate 6 Security Office | Pit lane entry |  | -27.9913 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 108 | Delivered | Still to leave
Portable buildings | P67 | Gate 6 Security Office | ↳ Inside: Air conditioner | 1 | 1300541 | Coates | P67 - Gate 6 Security Office | Pit lane entry |  | -27.9913 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P67 | Gate 6 Security Office | ↳ Inside: Fire extinguisher | 1 |  | Coates | P67 - Gate 6 Security Office | Pit lane entry |  | -27.9913 | 153.4304 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | P69 | Supply Building | Building 6m | 1 | 107247 | Coates | P69 - Supply Building | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968862 · line 103 | Delivered | Still to leave
Portable buildings | P69 | Supply Building | ↳ Inside: Air conditioner | 1 | 1245808 | Coates | P69 - Supply Building | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) |  |  |  |  | Still to leave | added in this page
Portable buildings | P69 | Supply Building | ↳ Inside: Fire extinguisher | 1 |  | Coates | P69 - Supply Building | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | Building 4.8m | 1 | 960639 | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 | 09:00 | 9968929 · line 1 | Delivered | Still to leave
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | ↳ Inside: Folding table | 3 |  | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 3x Fold Table; parsed from the schedule notes column
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | ↳ Inside: Swivel chair | 3 |  | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 3x swivel chair; parsed from the schedule notes column
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | ↳ Inside: Whiteboard | 1 |  | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | White Board; parsed from the schedule notes column
Portable buildings | T0021 | Building 4.8m · Office 4.8x3 | ↳ Inside: Fire extinguisher | 1 |  | Coates | Office 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9831 | 153.4264 | Open map | Placed on the map | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | Building 4.8m | 1 | 960634 | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 | 09:00 | 9968929 · line 3 | Delivered | Still to leave
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Folding table | 3 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 3x fold table; parsed from the schedule notes column
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Sink with tap | 1 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | sink; parsed from the schedule notes column
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Stackable chair | 12 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | 12x stack Chair; parsed from the schedule notes column
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Microwave | 1 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | parsed from the schedule notes column
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Fridge | 1 | 1272753 | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Fridge | 1 | 1254399 | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | added in this page
Portable buildings | T0022 | Building 4.8m · Lunchroom 4.8x3 | ↳ Inside: Fire extinguisher | 1 |  | Coates | Lunchroom 4.8x3 | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4265 | Open map | Phone pin | 2026-11-10 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | ticked on the record
Portable buildings | T0023 | Event Container · event container from eags | Event Container | 1 | 1257261 | Coates | event container from eags | Island west parkland entry – by the merch strip |  | -27.9833 | 153.4263 | Open map | Phone pin | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 09:00 | 9968929 · line 5 | Del Req | Still to leave
Portable buildings | T0258 | 3.0m Cont · Helen Park | 3.0m Cont | 1 | 1134386 | Coates | Helen Park | Pit lane entry | S23 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Proposed (demob rule, not confirmed) | 2026-11-13 | 10:00 | 9974042 · line 1 | Delivered | Still to leave
Portable buildings | T0266 | 6.0m Refrigerator Cont · Helen Park | 6.0m Refrigerator Cont | 1 | 920584 | United Rentals / Royal Wolf (subhire) | Helen Park | Pit lane entry | S23 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9974042 · line 2 | Delivered | Still to leave
Toilets & amenities | BJR01 | Brad Jones Racing | FWF | 1 | 0941 | Event Portables (subhire) | Brad Jones Racing | Median strip meet-up – pit stop, by FOAM |  | -27.9859 | 153.4275 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | PG01 | Toilet (Pit Garage) | FWF | 1 | 0285 | Event Portables (subhire) | PG01 - Toilet (Pit Garage) | Pit lane entry | S01 | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 151 | Delivered | Still to leave
Toilets & amenities | PG03 | Toilet (Pit Garage) | FWF | 1 | 0100 | Event Portables (subhire) | PG03 - Toilet (Pit Garage) | Pit lane entry | S01 | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 152 | Delivered | Still to leave
Toilets & amenities | PG05 | Toilet (Pit Garage) | FWF | 1 | 0438 | Event Portables (subhire) | PG05 - Toilet (Pit Garage) | Pit lane entry | S01 | -27.9868 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 153 | Delivered | Still to leave
Toilets & amenities | PG29 | Toilet (Pit Garage) | FWF | 1 | 0573 | Event Portables (subhire) | Tickford Racing | Pit lane entry | S01 | -27.9866 | 153.4278 | Open map | Placed on the map | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | SVP01 | Shell V-Power | FWF | 1 | 0939 | Event Portables (subhire) | Shell V-Power | Island north – by FREIGHT |  | -27.9862 | 153.4278 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0024 | FWF | FWF | 1 | 0164 | Event Portables (subhire) | FWF | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4266 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0024 | FWF | FWF | 1 | 1211968 | Coates | FWF | Island west parkland entry – by the merch strip |  | -27.9832 | 153.4266 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968929 · line 7 | Delivered | Still to leave
Toilets & amenities | T0162 | FWF · Blanchard Race | FWF | 1 | 0990 | Event Portables (subhire) | Blanchard Race | Median strip meet-up – pit stop, by FOAM |  | -27.9857 | 153.4274 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0176 | FWF × 2 · Redbull | FWF | 1 | 0994 | Event Portables (subhire) | Redbull | Island north – by FREIGHT |  | -27.9867 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0176 | FWF × 2 · Redbull | FWF | 1 | 0576 | Event Portables (subhire) | Redbull | Island north – by FREIGHT |  | -27.9867 | 153.428 | Open map | Andrew’s pin | 2026-11-02 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Toilets & amenities | T0243 | Toilet Block 6m · WC-TV (sewer connect) | Toilet Block 6m | 1 | 1311144 | Coates | WC-TV (sewer connect) | Island north – by FREIGHT | S04 | -27.9875 | 153.4283 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 10:00 | 9973977 · line 1 | Delivered | Still to leave
Toilets & amenities | WC01 | Toilets | Accessible Toilet | 1 | 1317644 | Coates | WC01 - Toilets | Pit lane entry | S10 | -27.9834 | 153.4253 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 57 | Delivered | Still to leave
Toilets & amenities | WC01 | Toilets | FWF | 1 | 1211958 | Coates | WC01 - Toilets | Pit lane entry | S10 | -27.9834 | 153.4253 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 46 | Delivered | Still to leave
Toilets & amenities | WC01 | Toilets | FWF | 1 | 1211967 | Coates | WC01 - Toilets | Pit lane entry | S10 | -27.9834 | 153.4253 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 69 | Delivered | Still to leave
Toilets & amenities | WC02 | Toilet | FWF | 1 | 1058086 | Coates | WC02 - Toilet | Island west parkland entry – by the merch strip | S10 | -27.9836 | 153.4257 | Open map | Master plan position | 2026-11-02 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 45 | Delivered | Still to leave
Toilets & amenities | WC04 | Toilet - QAS | FWF | 1 | 1212502 | Coates | WC04 - Toilet - QAS | Island west parkland entry – by the merch strip |  | -27.9839 | 153.4265 | Open map | Master plan position | 2026-11-02 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 44 | Delivered | Still to leave
Toilets & amenities | WC05 | Event Operations Compound Toilet - Combo Block (Tanked) | Waste tank | 1 | 1328978 | Coates | WC05 | Island west parkland entry – by the merch strip |  | -27.9836 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 3 | Delivered | Still to leave
Toilets & amenities | WC05 | Event Operations Compound Toilet - Combo Block (Tanked) | Toilet Block 6m | 1 | 1097377 | Coates | WC05 | Island west parkland entry – by the merch strip |  | -27.9836 | 153.4264 | Open map | Master plan position | 2026-11-12 | Plan (schedule removal row) | 2026-11-13 | 07:00 | 9968955 · line 1 | Delivered | Still to leave
Toilets & amenities | WC06 | Toilets - Race Admin | FWF | 1 | 1195658 | Coates | WC06 - Toilets - Race Admin | Median strip meet-up – pit stop, by FOAM | S11 | -27.9847 | 153.4265 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 15 | Delivered | Still to leave
Toilets & amenities | WC06 | Toilets - Race Admin | FWF | 1 | 1212523 | Coates | WC06 - Toilets - Race Admin | Median strip meet-up – pit stop, by FOAM | S11 | -27.9847 | 153.4265 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 58 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317643 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 38 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1181004 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 34 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1002538 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 35 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1212552 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 32 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1002566 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 24 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1083300 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 41 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1200595 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 33 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1211959 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 26 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1002715 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 40 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1192643 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 42 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1002651 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 43 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317649 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 27 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317658 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 36 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317632 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 37 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317641 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 39 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317640 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 25 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317626 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 29 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317648 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 31 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317652 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 30 | Delivered | Still to leave
Toilets & amenities | WC07 | Toilets - Merch Area | FWF | 1 | 1317647 | Coates | WC07 - Toilets - Merch Area | Median strip meet-up – pit stop, by FOAM | S11 | -27.9845 | 153.4269 | Open map | Master plan position | 2026-11-05 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 28 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0085 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0551 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0450 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0585 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0993 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0553 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0140 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0089 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0584 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | FWF | 1 | 0081 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP01 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP04 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP05 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP06 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP02 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Pee Panel | 1 | PP03 | Event Portables (subhire) | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Toilet Block 6m | 1 | 1268858 | Coates | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 103 | Delivered | Still to leave
Toilets & amenities | WC09 | Toilets | Toilet Block 6m | 1 | 1311146 | Coates | WC09 - Toilets | Median strip meet-up – pit stop, by FOAM |  | -27.9847 | 153.428 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 105 | Delivered | Still to leave
Toilets & amenities | WC10 | Toilets | FWF | 1 | 0488 | Event Portables (subhire) | WC10 - Toilets | Median strip meet-up – pit stop, by FOAM | S01 | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 114 | Pending | Still to leave
Toilets & amenities | WC10 | Toilets | FWF | 1 | 0677 | Event Portables (subhire) | WC10 - Toilets | Median strip meet-up – pit stop, by FOAM | S01 | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 114 | Pending | Still to leave
Toilets & amenities | WC10 | Toilets | FWF | 1 | 0119 | Event Portables (subhire) | WC10 - Toilets | Median strip meet-up – pit stop, by FOAM | S01 | -27.9845 | 153.4277 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 114 | Pending | Still to leave
Toilets & amenities | WC100 |  | FWF Trailer | 1 | 1248439 | Coates | 1288823 at The Spit · 1248439 at S18 | Pit lane entry |  |  |  |  | No position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 13 | Delivered | Still to leave
Toilets & amenities | WC100 |  | FWF Trailer | 1 | 1288823 | Coates | 1288823 at The Spit · 1248439 at S18 | Pit lane entry |  |  |  |  | No position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 12 | Delivered | Still to leave
Toilets & amenities | WC11 | Toilets | FWF | 1 | 1211969 | Coates | WC11 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 6 | Delivered | Still to leave
Toilets & amenities | WC11 | Toilets | FWF | 1 | 1211976 | Coates | WC11 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9849 | 153.4266 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 23 | Delivered | Still to leave
Toilets & amenities | WC12 | Toilets | FWF | 1 | 1002565 | Coates | WC12 - Toilets | Pit lane entry | S01 | -27.9855 | 153.4273 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 17 | Delivered | Still to leave
Toilets & amenities | WC12 | Toilets | FWF | 1 | 1200601 | Coates | WC12 - Toilets | Pit lane entry | S01 | -27.9855 | 153.4273 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 5 | Delivered | Still to leave
Toilets & amenities | WC12 | Toilets | FWF | 1 | 1211961 | Coates | WC12 - Toilets | Pit lane entry | S01 | -27.9855 | 153.4273 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 4 | Delivered | Still to leave
Toilets & amenities | WC12 | Toilets | FWF | 1 | 1211963 | Coates | WC12 - Toilets | Pit lane entry | S01 | -27.9855 | 153.4273 | Open map | Master plan position | 2026-11-03 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 158 | Delivered | Still to leave
Toilets & amenities | WC13 | Toilets | FWF | 1 | 0036 | Event Portables (subhire) | WC13 - Toilets | Pit lane entry |  | -27.991 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 122 | Pending | Still to leave
Toilets & amenities | WC13 | Toilets | FWF | 1 | 0444 | Event Portables (subhire) | WC13 - Toilets | Pit lane entry |  | -27.991 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 122 | Pending | Still to leave
Toilets & amenities | WC15 | Toilets (Sewer Connect) | Toilet Block 6m | 1 | 1327226 | Coates | WC15 - Toilets (Sewer Connect) | Island north – by FREIGHT | S01 | -27.986 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 55 | Delivered | Still to leave
Toilets & amenities | WC15 | Toilets (Sewer Connect) | Toilet Block 6m | 1 | 1303835 | Coates | WC15 - Toilets (Sewer Connect) | Island north – by FREIGHT | S01 | -27.986 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 56 | Delivered | Still to leave
Toilets & amenities | WC16 | S01 Corporate Toilets - 1x Female, x Male (Sewer) | Toilet Block 6m | 1 | 1322587 | Coates | WC16 - S01 Corporate Toilets - 1x Female, x Male (Sewer) | Pit lane entry | S01 | -27.9859 | 153.4277 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 10 | Delivered | Still to leave
Toilets & amenities | WC16 | S01 Corporate Toilets - 1x Female, x Male (Sewer) | Toilet Block 6m | 1 | 1322588 | Coates | WC16 - S01 Corporate Toilets - 1x Female, x Male (Sewer) | Pit lane entry | S01 | -27.9859 | 153.4277 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 11 | Delivered | Still to leave
Toilets & amenities | WC17 | S01 Corporate Toilets | Toilet Block 6m | 1 | 1327224 | Coates | WC17 - S01 Corporate Toilets | Island north – by FREIGHT | S02 | -27.9865 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 20 | Delivered | Still to leave
Toilets & amenities | WC17 | S01 Corporate Toilets | Toilet Block 6m | 1 | 1327223 | Coates | WC17 - S01 Corporate Toilets | Island north – by FREIGHT | S02 | -27.9865 | 153.4281 | Open map | Master plan position | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 21 | Delivered | Still to leave
Toilets & amenities | WC19 | Toilets | FWF | 1 | 0435 | Event Portables (subhire) | WC19 - Toilets | Island north – by FREIGHT | S04 | -27.9882 | 153.4283 | Open map | Master plan position | 2026-11-02 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 117 | Pending | Still to leave
Toilets & amenities | WC20 | Toilets (Tank Mounted) | Toilet Block 6m | 1 | 1327228 | Coates | WC20 - Toilets (Tank Mounted) | Island north – by FREIGHT | S04 | -27.9875 | 153.4282 | Open map | Master plan position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 47 | Delivered | Still to leave
Toilets & amenities | WC20 | Toilets (Tank Mounted) | Toilet Block 6m | 1 | 1327225 | Coates | WC20 - Toilets (Tank Mounted) | Island north – by FREIGHT | S04 | -27.9875 | 153.4282 | Open map | Master plan position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 48 | Delivered | Still to leave
Toilets & amenities | WC20 | Toilets (Tank Mounted) | Waste tank | 1 | 1311341 | Coates | WC20 - Toilets (Tank Mounted) | Island north – by FREIGHT | S04 | -27.9875 | 153.4282 | Open map | Master plan position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 49 | Delivered | Still to leave
Toilets & amenities | WC20 | Toilets (Tank Mounted) | Waste tank | 1 | 1328982 | Coates | WC20 - Toilets (Tank Mounted) | Island north – by FREIGHT | S04 | -27.9875 | 153.4282 | Open map | Master plan position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 50 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1002747 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 14 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1103497 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 19 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1211964 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 8 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1211971 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 16 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1211977 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 7 | Delivered | Still to leave
Toilets & amenities | WC21 | Toilets | FWF | 1 | 1212172 | Coates | WC21 - Toilets | Pit lane entry | S05 | -27.9892 | 153.4286 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 18 | Delivered | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0992 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0968 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0960 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0107 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC23 | Toilets | FWF | 1 | 0969 | Event Portables (subhire) | WC23 - Toilets | Pit lane entry | S05 | -27.9895 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 119 | Pending | Still to leave
Toilets & amenities | WC24 | Toilets | FWF | 1 | 0489 | Event Portables (subhire) | WC24 - Toilets | Pit lane entry |  | -27.991 | 153.4297 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 121 | Pending | Still to leave
Toilets & amenities | WC25 | Toilets | FWF | 1 | 0472 | Event Portables (subhire) | WC25 - Toilets | Pit lane entry | S15 | -27.9901 | 153.4288 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 118 | Pending | Still to leave
Toilets & amenities | WC26 | Toilets | FWF | 1 | 0075 | Event Portables (subhire) | WC26 - Toilets | Pit lane entry |  | -27.9888 | 153.4296 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 120 | Pending | Still to leave
Toilets & amenities | WC27 | Toilet (Tank Mounted) | Toilet Block 6m | 1 | 1119484 | Coates | WC27 - Toilet (Tank Mounted) | Main Beach Pde land side – by T8 / A19 | S08 | -27.9852 | 153.4295 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 52 | Delivered | Still to leave
Toilets & amenities | WC27 | Toilet (Tank Mounted) | Waste tank | 1 | 1328979 | Coates | WC27 - Toilet (Tank Mounted) | Main Beach Pde land side – by T8 / A19 | S08 | -27.9852 | 153.4295 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 54 | Delivered | Still to leave
Toilets & amenities | WC28 | Toilets | FWF | 1 | 0102 | Event Portables (subhire) | WC28 - Toilets | Pit lane entry |  | -27.9834 | 153.4292 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 123 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0079 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0546 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0707 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0564 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0044 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0441 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC29 | Toilets | FWF | 1 | 0598 | Event Portables (subhire) | WC29 - Toilets | Pit lane entry |  | -27.9836 | 153.4286 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 124 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0428 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0440 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0963 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0681 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0043 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0419 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0545 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC30 | Toilets | FWF | 1 | 0024 | Event Portables (subhire) | WC30 - Toilets | Pit lane entry |  | -27.9824 | 153.4278 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 125 | Pending | Still to leave
Toilets & amenities | WC31 | Toilets | Accessible Toilet | 1 | 1317645 | Coates | WC31 - Toilets | The Hill – entry point A47 | S25 | -27.9825 | 153.4252 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 97 | Delivered | Still to leave
Toilets & amenities | WC31 | Toilets | 16Pan Block | 1 | 12 | Event Portables (subhire) | WC31 - Toilets | The Hill – entry point A47 | S25 | -27.9825 | 153.4252 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 97 | Delivered | Still to leave
Toilets & amenities | WC31 | Toilets | 16Pan Block | 1 | 74 | Event Portables (subhire) | WC31 - Toilets | The Hill – entry point A47 | S25 | -27.9825 | 153.4252 | Open map | Andrew’s pin | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 97 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0634 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0582 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0548 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0782 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0657 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0912 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0554 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0920 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0971 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0586 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0487 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0790 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0297 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0456 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0012 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0938 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC33 | Toilets | FWF | 1 | 0597 | Event Portables (subhire) | WC33 - Toilets | Main Beach Pde land side – by T8 / A19 | S07 | -27.9861 | 153.4295 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 101 | Delivered | Still to leave
Toilets & amenities | WC34 | Toilets | FWF | 1 | 0526 | Event Portables (subhire) | WC34 - Toilets | The Hill – entry point A47 |  | -27.9823 | 153.4259 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 100 | Pending | Still to leave
Toilets & amenities | WC35 | Toilets | FWF | 1 | 0284 | Event Portables (subhire) | WC35 - Toilets | Pit lane entry |  | -27.9818 | 153.4278 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 126 | Pending | Still to leave
Toilets & amenities | WC38 | Toilet | FWF | 1 | 0183 | Event Portables (subhire) | WC38 - Toilet | Commodore Park drop point (red dot) | S10 | -27.9836 | 153.4241 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 88 | Pending | Still to leave
Toilets & amenities | WC39 | Toilets | FWF | 1 | 0188 | Event Portables (subhire) | WC39 - Toilets | Commodore Park drop point (red dot) |  | -27.9836 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 89 | Pending | Still to leave
Toilets & amenities | WC39 | Toilets | FWF | 1 | 0637 | Event Portables (subhire) | WC39 - Toilets | Commodore Park drop point (red dot) |  | -27.9836 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 89 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0626 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0541 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0965 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0433 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC40 | Toilets | FWF | 1 | 0648 | Event Portables (subhire) | WC40 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9837 | 153.4244 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 90 | Pending | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0521 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0996 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0191 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0669 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0643 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0517 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0682 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0651 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0065 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC41 | Toilets | FWF | 1 | 0518 | Event Portables (subhire) | WC41 - Toilets | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4261 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 59 | Delivered | Still to leave
Toilets & amenities | WC42 | Toilets | FWF | 1 | 0141 | Event Portables (subhire) | WC42 - Toilets | Commodore Park drop point (red dot) | S10 | -27.9833 | 153.4248 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 155 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0723 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0056 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0161 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0182 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0528 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0696 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0420 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0961 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0646 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC43 | Toilets | FWF | 1 | 0581 | Event Portables (subhire) | WC43 - Toilets | Island north – by FREIGHT | S14 | -27.9864 | 153.4272 | Open map | Master plan position | 2026-11-09 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 70 | Delivered | Still to leave
Toilets & amenities | WC44 | Toilets | FWF | 1 | 0146 | Event Portables (subhire) | WC44 - Toilets | Pit lane entry | S05 | -27.989 | 153.4283 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 80 | Delivered | Still to leave
Toilets & amenities | WC44 | Toilets | FWF | 1 | 0037 | Event Portables (subhire) | WC44 - Toilets | Pit lane entry | S05 | -27.989 | 153.4283 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 80 | Delivered | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0542 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0086 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0947 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0544 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0632 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0562 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0549 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC45 | Toilets | FWF | 1 | 0673 | Event Portables (subhire) | WC45 - Toilets | Pit lane entry | S15 | -27.9907 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 115 | Pending | Still to leave
Toilets & amenities | WC46 | Toilets | FWF | 1 | 0525 | Event Portables (subhire) | WC46 - Toilets | Pit lane entry |  | -27.9922 | 153.4294 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 127 | Pending | Still to leave
Toilets & amenities | WC47 | Toilets | FWF | 1 | 0949 | Event Portables (subhire) | WC47 - Toilets | Pit lane entry | S15 | -27.9902 | 153.4284 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 116 | Pending | Still to leave
Toilets & amenities | WC48 | Toilets | FWF | 1 | 0050 | Event Portables (subhire) | WC48 - Toilets | Pit lane entry |  | -27.9937 | 153.4305 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 109 | Pending | Still to leave
Toilets & amenities | WC48 | Toilets | FWF | 1 | 0471 | Event Portables (subhire) | WC48 - Toilets | Pit lane entry |  | -27.9937 | 153.4305 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 109 | Pending | Still to leave
Toilets & amenities | WC48 | Toilets | FWF | 1 | 0289 | Event Portables (subhire) | WC48 - Toilets | Pit lane entry |  | -27.9937 | 153.4305 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 109 | Pending | Still to leave
Toilets & amenities | WC48 | Toilets | FWF | 1 | 0486 | Event Portables (subhire) | WC48 - Toilets | Pit lane entry |  | -27.9937 | 153.4305 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 109 | Pending | Still to leave
Toilets & amenities | WC49 | Toilets | FWF | 1 | 0919 | Event Portables (subhire) | WC49 - Toilets | Pit lane entry |  | -27.9938 | 153.4306 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 108 | Pending | Still to leave
Toilets & amenities | WC49 | Toilets | FWF | 1 | 0907 | Event Portables (subhire) | WC49 - Toilets | Pit lane entry |  | -27.9938 | 153.4306 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 108 | Pending | Still to leave
Toilets & amenities | WC49 | Toilets | FWF | 1 | 0084 | Event Portables (subhire) | WC49 - Toilets | Pit lane entry |  | -27.9938 | 153.4306 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 108 | Pending | Still to leave
Toilets & amenities | WC50 | Toilet | FWF | 1 | 1211974 | Coates | WC50 - Toilet | Pit lane entry | S18 | -27.9898 | 153.4298 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 22 | Delivered | Still to leave
Toilets & amenities | WC51 | Toilets | Accessible Toilet | 1 | 1197174 | Coates | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0991 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0167 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0653 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0136 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0453 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC51 | Toilets | FWF | 1 | 0028 | Event Portables (subhire) | WC51 - Toilets | Pit lane entry |  | -27.9929 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 110 | Pending | Still to leave
Toilets & amenities | WC53 | Toilets | FWF | 1 | 0952 | Event Portables (subhire) | WC53 - Toilets | Pit lane entry |  | -27.9927 | 153.4303 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 156 | Delivered | Still to leave
Toilets & amenities | WC53 | Toilets | FWF | 1 | 0951 | Event Portables (subhire) | WC53 - Toilets | Pit lane entry |  | -27.9927 | 153.4303 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 156 | Delivered | Still to leave
Toilets & amenities | WC53 | Toilets | FWF | 1 | 0074 | Event Portables (subhire) | WC53 - Toilets | Pit lane entry |  | -27.9927 | 153.4303 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 156 | Delivered | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0186 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0619 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0071 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0295 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0007 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC54 | Toilets | FWF | 1 | 0087 | Event Portables (subhire) | WC54 - Toilets | Pit lane entry |  | -27.9916 | 153.4305 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 112 | Pending | Still to leave
Toilets & amenities | WC55 | Toilets | FWF | 1 | 0650 | Event Portables (subhire) | WC55 - Toilets | Pit lane entry |  | -27.9912 | 153.4298 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 128 | Pending | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0721 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0491 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0190 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0294 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0970 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0974 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0004 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0003 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0445 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0088 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0442 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC56 | Toilets | FWF | 1 | 0009 | Event Portables (subhire) | WC56 - Toilets | Pit lane entry | S18 | -27.9898 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 113 | Delivered | Still to leave
Toilets & amenities | WC57 | Toilets | FWF | 1 | 0915 | Event Portables (subhire) | WC57 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 107 | Pending | Still to leave
Toilets & amenities | WC57 | Toilets | FWF | 1 | 0008 | Event Portables (subhire) | WC57 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4301 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 107 | Pending | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0492 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0935 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0497 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0633 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0064 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0066 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC59 | Toilets | FWF | 1 | 0533 | Event Portables (subhire) | WC59 - Toilets | Main Beach seaside – by the supply compound |  | -27.9882 | 153.4302 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 106 | Delivered | Still to leave
Toilets & amenities | WC60 | Toilets (Tank Mounted) | Toilet Block 6m | 1 | 1087500 | Coates | WC60 - Toilets (Tank Mounted) | Seaside north – between S21 and S22 | S21 | -27.9853 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 91 | Delivered | Still to leave
Toilets & amenities | WC60 | Toilets (Tank Mounted) | Toilet Block 6m | 1 | 1119489 | Coates | WC60 - Toilets (Tank Mounted) | Seaside north – between S21 and S22 | S21 | -27.9853 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 93 | Delivered | Still to leave
Toilets & amenities | WC60 | Toilets (Tank Mounted) | Waste tank | 1 | 1328980 | Coates | WC60 - Toilets (Tank Mounted) | Seaside north – between S21 and S22 | S21 | -27.9853 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 94 | Delivered | Still to leave
Toilets & amenities | WC60 | Toilets (Tank Mounted) | Waste tank | 1 | 1328981 | Coates | WC60 - Toilets (Tank Mounted) | Seaside north – between S21 and S22 | S21 | -27.9853 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-13 |  | 9968955 · line 95 | Delivered | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0645 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0105 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0945 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0977 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0547 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0290 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0038 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC61 | Toilets | FWF | 1 | 0015 | Event Portables (subhire) | WC61 - Toilets | Seaside north – between S21 and S22 | S22A | -27.9841 | 153.4298 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 96 | Pending | Still to leave
Toilets & amenities | WC62 | Toilets | FWF | 1 | 0976 | Event Portables (subhire) | WC62 - Toilets | Pit lane entry |  | -27.9817 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 129 | Pending | Still to leave
Toilets & amenities | WC62 | Toilets | FWF | 1 | 0103 | Event Portables (subhire) | WC62 - Toilets | Pit lane entry |  | -27.9817 | 153.4292 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 129 | Pending | Still to leave
Toilets & amenities | WC65 | Toilets | FWF | 1 | 0033 | Event Portables (subhire) | WC65 - Toilets | The Hill – entry point A47 |  | -27.9815 | 153.4264 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 130 | Pending | Still to leave
Toilets & amenities | WC67 | Toilets | FWF | 1 | 0793 | Event Portables (subhire) | WC67 - Toilets | Helen Park drop point (red dot) | S23 | -27.9814 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 84 | Delivered | Still to leave
Toilets & amenities | WC67 | Toilets | FWF | 1 | 0769 | Event Portables (subhire) | WC67 - Toilets | Helen Park drop point (red dot) | S23 | -27.9814 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 84 | Delivered | Still to leave
Toilets & amenities | WC67 | Toilets | FWF | 1 | 172824 | Coates | WC67 - Toilets | Helen Park drop point (red dot) | S23 | -27.9814 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 140 | Delivered | Still to leave
Toilets & amenities | WC67 | Toilets | FWF | 1 | 0714 | Event Portables (subhire) | WC67 - Toilets | Helen Park drop point (red dot) | S23 | -27.9814 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 84 | Delivered | Still to leave
Toilets & amenities | WC68 | Toilets | FWF | 1 | 0426 | Event Portables (subhire) | WC68 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4244 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 131 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0152 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0078 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0010 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0070 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0958 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0647 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0622 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0123 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0432 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0692 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0679 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC69 | Toilets | FWF | 1 | 0592 | Event Portables (subhire) | WC69 - Toilets | Helen Park drop point (red dot) | S23 | -27.9815 | 153.4242 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 87 | Pending | Still to leave
Toilets & amenities | WC70 | Toilet | FWF | 1 | 0423 | Event Portables (subhire) | WC70 - Toilet | Helen Park drop point (red dot) | S23 | -27.9817 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 85 | Pending | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0280 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0116 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0279 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0293 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0531 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0644 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0552 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC71 | Toilets | FWF | 1 | 0490 | Event Portables (subhire) | WC71 - Toilets | Helen Park drop point (red dot) | S23 | -27.9813 | 153.4235 | Open map | Master plan position | 2026-10-29 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 86 | Delivered | Still to leave
Toilets & amenities | WC72 | Toilets | FWF | 1 | 0699 | Event Portables (subhire) | WC72 - Toilets | Helen Park drop point (red dot) | S23 | -27.9821 | 153.424 | Open map | Master plan position | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 132 | Pending | Still to leave
Toilets & amenities | WC73 | Toilets | FWF | 1 | 0765 | Event Portables (subhire) | WC73 - Toilets | Island north – by FREIGHT | S02 | -27.987 | 153.4281 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 133 | Pending | Still to leave
Toilets & amenities | WC73 | Toilets | FWF | 1 | 0192 | Event Portables (subhire) | WC73 - Toilets | Island north – by FREIGHT | S02 | -27.987 | 153.4281 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 133 | Pending | Still to leave
Toilets & amenities | WC81 | Toilet (Cypress) | FWF | 1 | 0124 | Event Portables (subhire) | WC81 - Toilet (Cypress) | Pit lane entry |  | -27.9975 | 153.4285 | Open map | Master plan position | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  | 9968955 · line 157 | Delivered | Still to leave
Toilets & amenities | WC85 | Toilets | FWF | 1 | 0135 | Event Portables (subhire) | Coates compound | Pit lane entry |  | -27.9386 | 153.4265 | Open map | Andrew’s pin | 2026-10-28 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968955 · line 134 | Pending | Still to leave
Toilets & amenities | WC86 | Toilet | Accessible Toilet | 1 | 1296899 | Coates | WC86 - Toilet | Island north – by FREIGHT | S04 | -27.9877 | 153.4282 | Open map | Master plan position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-11-13 | 07:00 | 9968955 · line 51 | Delivered | Still to leave
Water-filled barriers | WB01 | Gold Coast Highway (Near PB3 DR - On GCHWY at the Tedder Avenue intersection) | TL2 × 12 | 12 |  | Coates | WB01 Gold Coast Highway (Near PB3 DR - On GCHWY at the Tedder Avenue intersection) | Pit lane entry |  | -27.9821 | 153.4239 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:30 | 9972648 · line 1 | Delivered | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB02 | S08 - Pedestrian Pathway along Main Beach Parade | TL2 × 34 | 34 |  | Coates | WB02 S08 - Pedestrian Pathway along Main Beach Parade | Pit lane entry | S08 | -27.9851 | 153.4297 | Open map | From the description | 2026-09-27 | Plan (schedule removal row) | 2026-09-27 | 17:00 | 9972648 · line 3 | Delivered | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB03 | Gold Coast Highway (Turn 2) - Concrete small blocks | TL2 × 30 | 30 |  | Coates | WB03 Gold Coast Highway (Turn 2) - Concrete small blocks | Pit lane entry | S15 | -27.9901 | 153.4286 | Open map | From the description | 2026-10-19 | Plan (schedule removal row) | 2026-10-19 | 22:00 | 9972648 · line 2 | Delivered | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB04 | Helen Park - HVM | TL2 × 14 | 14 |  | Coates | WB04 Helen Park - HVM | Pit lane entry | S23 | -27.9812 | 153.4238 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 09:00 | 9972648 · line 4 | Del Req | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB05 | Gold Coast Highway (Main Beach Light Rail) | TL2 × 13 | 13 |  | Coates | WB05 Gold Coast Highway (Main Beach Light Rail) | Pit lane entry |  | -27.9821 | 153.4235 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:00 | 9972648 · line 5 | Del Req | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB06 | Gold Coast Highway Macintosh Park Turning Lane (Grandstand Barriers) | TL2 × 154 | 154 |  | Coates | WB06 Gold Coast Highway Macintosh Park Turning Lane (Grandstand Barriers) | Pit lane entry |  | -27.9859 | 153.4268 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:00 | 9972648 · line 6 | Delivered | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB07 | Admiralty Drive Intersection (Through lane removed between centre islands) | TL2 × 17 | 17 |  | Coates | WB07 Admiralty Drive Intersection (Through lane removed between centre islands) | Pit lane entry | S14 | -27.987 | 153.4267 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 09:00 | 9972648 · line 7 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB13 | Fence bracing behind S15 | TL2 × 10 | 10 |  | Coates | WB13 Fence bracing behind S15 | Pit lane entry | S15 | -27.9906 | 153.4285 | Open map | From the description | 2026-10-26 | Plan (schedule removal row) | 2026-10-26 | 10:00 | 9972648 · line 8 | Del Req | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB14 | MP4.0 Turn 4 Drivers Right | TL2 × 2 | 2 |  | Coates | WB14 MP4.0 Turn 4 Drivers Right | Pit lane entry |  | -27.9918 | 153.4295 | Open map | From the description | 2026-10-25 | Plan (schedule removal row) | 2026-10-27 | 07:00 | 9972648 · line 9 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB15 | Turn 11 Runoff (Main Beach Parade North) - HVM | TL2 × 4 | 4 |  | Coates | WB15 Turn 11 Runoff (Main Beach Parade North) - HVM | Pit lane entry |  | -27.9817 | 153.4291 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 07:00 | 9972648 · line 10 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB16 | Commodore Park (Commodore Drive) | TL2 × 13 | 13 |  | Coates | WB16 Commodore Park (Commodore Drive) | Pit lane entry |  | -27.9831 | 153.424 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 19:00 | 9972648 · line 11 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB17 | Racing kerbs (T6/7/8/9) | TL2 × 6 | 6 |  | Coates | WB17 Racing kerbs (T6/7/8/9) | Pit lane entry | S20 | -27.9857 | 153.4299 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 17:00 | 9972648 · line 12 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB18 | Racing kerbs (T2) | TL2 × 2 | 2 |  | Coates | WB18 Racing kerbs (T2) | Pit lane entry | S15 | -27.9901 | 153.4286 | Open map | From the description | 2026-10-27 | Plan (schedule removal row) | 2026-10-27 | 17:00 | 9972648 · line 13 | Pending | Still to leave | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB19 | S08 - Pedestrian Pathway along Main Beach Parade | TL2 × 34 | 34 |  | Coates | WB19 S08 - Pedestrian Pathway along Main Beach Parade | Pit lane entry | S08 | -27.9851 | 153.4297 | Open map | From the description | 2026-11-06 | Plan (schedule removal row) | 2026-11-06 | 17:00 | 9972648 · line 15 | Pending | Not on site | quantity item, code ARMORZONMASHTL2
Water-filled barriers | WB20 | Gold Coast Highway (Turn 2) | TL2 × 30 | 30 |  | Coates | WB20 Gold Coast Highway (Turn 2) | Pit lane entry | S15 | -27.9901 | 153.4286 | Open map | From the description | 2026-10-29 | Plan (schedule removal row) | 2026-10-29 | 19:00 | 9972648 · line 14 | Pending | Not on site | quantity item, code ARMORZONMASHTL2
Variable message signs | T0001 | VMS × 8 | VMS02 · VMS board | 1 | 1211370 | Coates | Position 02a · Confirmed board location (moved from 02: Waterways Drive northbound) |  |  | -27.9833 | 153.4251 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 3 | Delivered | Still to leave | rego ES3206 · positions 02 → 02a
Variable message signs | T0001 | VMS × 8 | VMS01 · VMS board | 1 | 1211354 | Coates | Position 01 · Gold Coast Highway (median strip), south of Queen St intersection |  |  | -27.9737 | 153.4203 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 4 | Delivered | Still to leave | rego EX0017 · positions 01
Variable message signs | T0001 | VMS × 8 | VMS07 · VMS board | 1 | 1182999 | Coates | Position 07 · Main Beach Parade southbound |  |  | -27.9781 | 153.429 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 5 | Delivered | Still to leave | rego 410UFQ · positions 07a → 07
Variable message signs | T0001 | VMS × 8 | VMS04 · VMS board | 1 | 1191877 | Coates | Position 04 · Admiralty Drive eastbound, Gold Coast Highway intersection |  |  | -27.9867 | 153.427 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 6 | Delivered | Still to leave | rego EM6306 · positions 04
Variable message signs | T0001 | VMS × 8 | VMS06 · VMS board | 1 | 1211359 | Coates | Position 06 · Gold Coast Highway northbound at Birt Ave, median strip, 'The Marriott' |  |  | -27.9927 | 153.428 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 7 | Delivered | Still to leave | rego ER9247 · positions 06
Variable message signs | T0001 | VMS × 8 | VMS08 · VMS board | 1 | 1211383 | Coates | Position 08 · Gold Coast Highway northbound, south of Staghorn intersection |  |  | -27.9955 | 153.4277 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 8 | Delivered | Still to leave | rego ER9381 · positions 08
Variable message signs | T0001 | VMS × 8 | VMS03 · VMS board | 1 | 1271129 | Coates | Position 03a · Confirmed board location (moved from 03: Gold Coast Highway (southbound), north of Breaker St intersection) |  |  | -27.9815 | 153.4234 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9961265 · line 9 | Delivered | Still to leave | rego 536UOO · positions 03 → 03a
Variable message signs | T0001 | VMS × 8 | VMS05 · VMS board | 1 | 1211356 | Coates | Position 05a · Confirmed board location |  |  | -27.9826 | 153.4246 | Open map | VMS register board position | 2026-11-12 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | rego ER9244 · positions 05a
Variable message signs | T0103 | VMS × 2 | VMS09 · VMS board | 1 | 1211404 | Coates | Position 05 · Confirmed board location (moved from 09: Gold Coast Highway (northbound), north of T E Peters Dr intersection (southern end of the Convention Centre)) |  |  | -27.9862 | 153.4283 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 |  | 9961265 · line 12 | Delivered | Still to leave | rego TF15JR · positions 09 → 05
Variable message signs | T0103 | VMS × 2 | VMS10 · VMS board | 1 | 120T | Premiair Hire (subhire) | Position 10 · Old Burleigh Rd (northbound), south of Queensland Ave intersection |  |  | -28.0297 | 153.4341 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 |  | 9961265 · line 13 | Delivered | Still to leave | rego V14221 · positions 10
Variable message signs | T0128 | VMS × 2 | VMS11 · VMS board | 1 | 467T | Premiair Hire (subhire) | Position 11 · Confirmed board location |  |  | -27.9862 | 153.4283 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 |  | 9961265 · line 15 | Del Req | Still to leave | rego TE97G · positions 11
Variable message signs | T0128 | VMS × 2 | VMS12 · VMS board | 1 | 1211646 | Coates | Position 12 · Macintosh Island Park, co-located with WC16 |  |  | -27.9859 | 153.4277 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 |  | 9961265 · line 16 | Del Req | Still to leave | rego TF59LR · positions 12
Variable message signs | T0158 | VMS × 9 | VMS18 · VMS board | 1 | 472T | Premiair Hire (subhire) | Position 18 · Confirmed board location |  |  | -27.9931 | 153.4282 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 | 07:00 | 9961265 · line 24 | Del Req | Still to leave | rego TE58GZ · positions 18
Variable message signs | T0158 | VMS × 9 | VMS19 · VMS board | 1 | 487T | Premiair Hire (subhire) | Position 19 · Confirmed board location |  |  | -27.9851 | 153.4273 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 | 07:00 | 9961265 · line 25 | Del Req | Still to leave | rego TE02H0 · positions 19
Variable message signs | T0158 | VMS × 9 | VMS20 · VMS board | 1 | 475T | Premiair Hire (subhire) | Position 20 · Confirmed board location |  |  | -27.9935 | 153.4305 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 | 07:00 | 9961265 · line 26 | Del Req | Still to leave | rego TE88HN · positions 20
Variable message signs | T0158 | VMS × 9 | VMS23 · VMS board | 1 | 453T | Premiair Hire (subhire) | Position 23 · Gold Coast Highway (north of Sundale Bridge), eastern side of the road, for southbound traffic |  |  | -27.9748 | 153.4207 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 | 07:00 | 9961265 · line 30 | Del Req | Still to leave | rego TF54CQ · positions 23
Variable message signs | T0158 | VMS × 9 | VMS13 · VMS board | 1 | 1191957 | Coates | Position 13 · Confirmed board location |  |  | -27.9818 | 153.4245 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 32 | Del Req | Still to leave | rego EN3803 · positions 13
Variable message signs | T0158 | VMS × 9 | VMS14 · VMS board | 1 | 1201864 | Coates | Position 14 · Confirmed board location |  |  | -27.9826 | 153.4244 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 34 | Del Req | Still to leave | rego TD98VJ · positions 14
Variable message signs | T0158 | VMS × 9 | VMS15 · VMS board | 1 | 1211348 | Coates | Position 15 · Confirmed board location |  |  | -27.9919 | 153.4294 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 35 | Del Req | Still to leave | rego ER9217 · positions 15
Variable message signs | T0158 | VMS × 9 | VMS16 · VMS board | 1 | 1211376 | Coates | Position 16 · Confirmed board location |  |  | -27.9818 | 153.4291 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 37 | Del Req | Still to leave | rego ES3211 · positions 16
Variable message signs | T0158 | VMS × 9 | VMS17 · VMS board | 1 | 1211364 | Coates | Position 17 · Confirmed board location |  |  | -27.9816 | 153.427 | Open map | VMS register board position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-27 | 15:00 | 9961265 · line 39 | Del Req | Still to leave | rego ER9410 · positions 17
Variable message signs | — | VMS board on the register | VMS21 · VMS board | 1 | 97T | Premiair Hire (subhire) | Position 21 · Confirmed board location |  |  | -27.9951 | 153.4293 | Open map | VMS register board position |  | Not in the demob plan | 2026-10-26 | 07:00 | 9961265 · line 28 | Pending | Still to leave | rego T16922 · positions 21
Variable message signs | — | VMS board on the register | VMS22 · VMS board | 1 | 445T | Premiair Hire (subhire) | Position 22 · Confirmed board location |  |  | -27.9975 | 153.4306 | Open map | VMS register board position |  | Not in the demob plan | 2026-10-28 | 07:00 | 9961265 · line 29 | Pending | Still to leave | rego TE99CL · positions 22
Variable message signs | — | VMS board on the register | VMS24 · VMS board | 1 | 450T | Premiair Hire (subhire) | Position 24 · Confirmed board location |  |  | -27.9927 | 153.4282 | Open map | VMS register board position |  | Not in the demob plan | 2026-10-26 | 15:00 | 9961265 · line 31 | Pending | Still to leave | rego TE94CL · positions 24
Generators | GN01 | Generator | 60kva | 1 | 1276507 | Coates | GN01 - Generator | Median strip meet-up – pit stop, by FOAM | S13 | -27.986 | 153.427 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 16 | Delivered | Still to leave
Generators | GN03 | Generator | 30kva | 1 | 1320829 | Coates | GN03 - Generator | Island north – by FREIGHT | S04 | -27.988 | 153.428 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 10 | Delivered | Still to leave
Generators | GN04 | Generator | 30kva | 1 | 1277400 | Coates | GN04 - Generator | Pit lane entry | S15 | -27.9905 | 153.4283 | Open map | Master plan position | 2026-10-26 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 14 | Del Req | Still to leave
Generators | GN06 | Generator | 50kva | 1 | 1320828 | Coates | GN06 - Generator | Pit lane entry |  | -27.9937 | 153.4306 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-10-26 |  | 9961976 · line 48 | Del Req | Still to leave
Generators | GN10 | Generator | 20kva | 1 | 1283681 | Coates | GN10 - Generator | Pit lane entry |  | -27.991 | 153.43 | Open map | Master plan position | 2026-10-27 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 13 | Pending | Still to leave
Generators | GN13 | Generator | 45kva | 1 | 1276503 | Coates | GN13 - Generator | Main Beach seaside – by the supply compound |  | -27.9884 | 153.4301 | Open map | Master plan position | 2026-10-28 | Plan (schedule removal row) | 2026-11-12 |  | 9961976 · line 44 | Delivered | Still to leave
Generators | GN18 | Generator | 50kva | 1 | 1261273 | Coates | GN18 - Generator | Commodore Park drop point (red dot) |  | -27.9836 | 153.4242 | Open map | Master plan position | 2026-10-29 | Plan (schedule removal row) | 2026-10-26 |  | 9961976 · line 11 | Delivered | Still to leave
Generators | GN19 | Generator | 60kva | 1 | 1276416 | Coates | GN19 - Generator | The Hill – entry point A47 | S25 | -27.9822 | 153.4245 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 7 | Del Req | Still to leave
Generators | GN20-A | S01 (GN20) | 350kva | 1 | 1276701 | Coates | S01 (GN20) | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 6 | Delivered | Still to leave
Generators | GN21 | Generator | 60kva | 1 | 1261284 | Coates | GN21 - Generator | Median strip meet-up – pit stop, by FOAM | S13 | -27.9854 | 153.4272 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 38 | Delivered | Still to leave
Generators | GN23 | Generator | 150kva | 1 | 1297157 | Coates | GN23 - Generator | Island north – by FREIGHT | S02 | -27.9863 | 153.4278 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 9 | Delivered | Still to leave
Generators | GN23 | Generator | Distribution Board Lifeguard 17 | 1 | 1189078 | Coates | GN23 - Generator | Island north – by FREIGHT | S02 | -27.9863 | 153.4278 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 41 | Delivered | Still to leave | unit on the reference outside its schedule lines
Generators | GN24 | Generator | 60kva | 1 | 1277089 | Coates | GN24 - Generator | Island west parkland entry – by the merch strip |  | -27.9833 | 153.4267 | Open map | Master plan position | 2026-11-13 | Proposed (demob rule, not confirmed) | 2026-10-26 |  | 9961976 · line 49 | Del Req | Still to leave
Generators | GN25 | Generator | 20kva | 1 | 1244536 | Coates | GN25 - Generator | Pit lane entry |  |  |  |  | No position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 18 | Del Req | Still to leave
Generators | GN? | Concert | 200kva & cables | 1 | 1316182 | Coates | Concert generators · Macintosh Island Park · lawn beside the path junction near the peacock enclosure | Median strip meet-up – pit stop, by FOAM | Concert | -27.9846 | 153.4277 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 42 | Delivered | Still to leave
Generators | GN? | Concert | 200kva & cables | 1 | 1316183 | Coates | Concert generators · Macintosh Island Park · lawn beside the path junction near the peacock enclosure | Median strip meet-up – pit stop, by FOAM | Concert | -27.9846 | 153.4277 | Open map | Master plan position | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 43 | Delivered | Still to leave
Lighting towers | LT05 | Light Towers | Light Tower | 1 | 1224783 | Coates | LT05/06: Light Towers | Pit lane entry |  | -27.9381 | 153.4263 | Open map | Placed on the map | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 19 | Pending | Still to leave
Lighting towers | LT06 | Light Towers | Light Tower | 1 | 1224791 | Coates | LT05/06: Light Towers | Pit lane entry |  | -27.9381 | 153.4263 | Open map | Placed on the map | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9961976 · line 20 | Pending | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1264929 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 1 | Delivered | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1314284 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 2 | Delivered | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1264899 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 3 | Delivered | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1188888 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 4 | Delivered | Still to leave
Lighting towers | T0002 | Light Tower × 5 · Delivery to Molendinar | Light Tower | 1 | 1249499 | Coates | Delivery to Molendinar | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 5 | Delivered | Still to leave
Access & plant | EQ0001 | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | 1 | 1220903 | Coates | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9992300 · line 4 | Del Req | Still to leave
Access & plant | EQ0002 | Knuckle Boom 61ft (18.6M) - Diesel | Knuckle Boom 61ft (18.6M) - Diesel | 1 | 1300290 | Coates | Knuckle Boom 61ft (18.6M) - Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 |  | 9992300 · line 5 | Pending | Still to leave
Access & plant | EQ0003 | Straight Boom 60ft - Diesel | Straight Boom 60ft - Diesel | 1 | 1286482 | Coates | Straight Boom 60ft - Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-11 | Proposed (demob rule, not confirmed) | 2026-10-27 |  | 9992300 · line 12 | Delivered | Still to leave
Access & plant | EQ0004 | SUPPLY - Forklift 3.5t Diesel | SUPPLY - Forklift 3.5t Diesel | 1 | 1210921 | Coates | SUPPLY - Forklift 3.5t Diesel | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-26 | Contract (rental off-hire date) | 2026-10-26 | 08:00 | 9961976 · line 27 | Pending | Still to leave
Access & plant | EQ0005 | Fork Extensions 2.4m | Fork Extensions 2.4m | 1 | 1262224 | Coates | Fork Extensions 2.4m | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-30 | Contract (rental off-hire date) | 2026-10-28 |  | 9987005 · line 2 | Delivered | Still to leave
Access & plant | T0003 | Forklift 5T · Phillip Park | Forklift 5T | 1 |  |  | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) |  |  |  |  | Still to leave | no unit number on the record
Access & plant | T0004 | Forklift 2.5T · Phillip Park | Forklift 2.5T | 1 | 1197839 | Coates | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 21 | Delivered | Still to leave
Access & plant | T0005 | Forklift 2.5T RT × 2 · Macintosh | Forklift 2.5T RT | 1 | 1247787 | Coates | Macintosh | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) | 2026-09-17 |  | 9961976 · line 25 | Returned | Still to leave | off rent 17 Sep 2026 (actual)
Access & plant | T0005 | Forklift 2.5T RT × 2 · Macintosh | Forklift 2.5T RT | 1 | 1312577 | Coates | Macintosh | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) | 2026-10-26 | 08:00 | 9961976 · line 26 | Delivered | Still to leave
Access & plant | T0005 | Forklift 2.5T RT × 2 · Macintosh | COATES - Forklift Tyne Rotator | 1 | 1302007 | Coates | Macintosh | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-13 | Plan (schedule removal row) | 2026-10-28 | 08:00 | 9961976 · line 37 | Pending | Still to leave | unit on the reference outside its schedule lines
Access & plant | T0085 | 3.5T Forklift Std · Supply | 3.5T Forklift Std | 1 | 1272166 | Coates | Supply | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-30 | Contract (rental off-hire date) | 2026-10-28 |  | 9987005 · line 1 | Delivered | Still to leave
Access & plant | T0109 | 2.5T Forklift STD · Events | 2.5T Forklift STD | 1 | 1281615 | Coates | Events | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-27 | Contract (rental off-hire date) | 2026-10-27 | 07:00 | 9987005 · line 7 | Delivered | Still to leave
Furniture | FR01 | Fridge · TV compound (broadcast) | Fridge | 1 | 1129733 | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-11 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Furniture | FR02 | Fridge · TV compound (broadcast) | Fridge | 1 | 1157786 | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-11 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Furniture | P26 | Fridge · Police 2-storey building | Fridge Lge | 1 | 1311992 | Coates | P26 - Fridge Delivery | Median strip meet-up – pit stop, by FOAM | S11 | -27.9847 | 153.4265 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 123 | Pending | Still to leave
Furniture | P28 | Fridge · Police 2-storey building | Fridge Lge | 1 | 1283996 | Coates | P28 - Fridge Delivery | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4265 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 124 | Pending | Still to leave
Furniture | P34 | Chair Delivery | Pad Chair × 2 | 2 |  |  | P34 - Chair Delivery | Median strip meet-up – pit stop, by FOAM | S11 | -27.9848 | 153.4265 | Open map | Master plan position | 2026-11-10 | Proposed (demob rule, not confirmed) | 2026-11-13 |  | 9968862 · line 125 | Pending | Still to leave | no unit number on the record
Ground protection | T0025 | Trakmat × 20 · Trackmat Delivery - S18 | Trakmat × 20 | 20 |  | Coates | Trackmat Delivery - S18 | Pit lane entry | S18 | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-30 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | quantity item, code TRAKMAT2.4X1.1
Ground protection | TM01 | Trakmat × 10 · TV compound (broadcast) | Trakmat × 10 | 10 |  |  | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-12 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave | no unit number on the record
Other | EQ0006 | Laserplane | Laserplane | 1 | 1065384 | Coates | Laserplane | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-11-12 | Proposed (demob rule, not confirmed) |  |  |  |  | Still to leave
Other | FL01 |  | Forklift 5T | 1 | 50004 | Coates | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) |  | Not in the demob plan |  |  |  |  | Still to leave
Other | FL02 |  | Forklift 2.5T | 1 | 1197839 | Coates | Phillip Park | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) |  | Not in the demob plan | 2026-10-26 | 08:00 | 9961976 · line 21 | Delivered | Still to leave
Other | FL03 | Forklift 5T · TV compound (broadcast) | Forklift 5T | 1 | 1321364 | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-27 | Contract (rental off-hire date) | 2026-10-27 |  | 9992300 · line 1 | Del Req | Still to leave
Other | FL04 | Forklift 2.5T · TV compound (broadcast) | Forklift 2.5T | 1 | 1298390 | Coates | TV compound | Pit lane entry |  | -27.9849 | 153.4266 | Open map | Report point only (no drop-off set) | 2026-10-27 | Contract (rental off-hire date) | 2026-10-27 |  | 9992300 · line 2 | Del Req | Still to leave

## Contract lines
GC500 2026 · the rental contract lines on the record · as at 26 Oct 2026 07:46 AEST
Contract | Branch | Line | Description | Item | Asset no | Qty | Status | Start date | Start time | Expected off-hire date | Expected off-hire time | Actual off-rent date | Booked pickup | Subhire supplier code | Matched ref
9961265 | STPS | 1 | Variable Message Board Senior | 1211404 | 1211404 | 1 | Returned | 2026-09-07 | 07:00 | 2026-11-13 |  | 2026-09-22 | 2026-10-12 |  | T0001
9961265 | STPS | 3 | Variable Message Board Senior - REED | 1211370 | 1211370 | 1 | Delivered | 2026-09-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | T0001
9961265 | STPS | 4 | Variable Message Board Senior - MARS | 1211354 | 1211354 | 1 | Delivered | 2026-09-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | T0001
9961265 | STPS | 5 | Variable Message Board Senior | 1182999 | 1182999 | 1 | Delivered | 2026-09-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | T0001
9961265 | STPS | 6 | Variable Message Board Senior | 1191877 | 1191877 | 1 | Delivered | 2026-09-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | T0001
9961265 | STPS | 7 | Variable Message Board Senior | 1211359 | 1211359 | 1 | Delivered | 2026-09-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | T0001
9961265 | STPS | 8 | Variable Message Board Senior | 1211383 | 1211383 | 1 | Delivered | 2026-09-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | T0001
9961265 | STPS | 9 | Variable Message Board - Colour - Senior | 1271129 | 1271129 | 1 | Delivered | 2026-09-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | T0001
9961265 | STPS | 12 | VMS09 Variable Message Board Senior | 1211404 | 1211404 | 1 | Delivered | 2026-09-07 | 07:00 | 2026-10-27 |  |  | 2026-10-27
9961265 | STPS | 13 | VMS10 Variable Message Board Senior Premiair | sub-17093 | sub-17093 | 1 | Delivered | 2026-10-08 | 07:00 | 2026-10-27 |  |  | 2026-10-27 | PRE808 | T0103
9961265 | STPS | 15 | VMS11 Variable Message Board - Premiair | SUB-17093 | SUB-17093 | 1 | Del Req |  | 07:00 | 2026-10-26 |  |  | 2026-10-26 | PRE808
9961265 | STPS | 16 | VMS12 Variable Message Board Junior | 1211646 | 1211646 | 1 | Del Req |  | 07:00 | 2026-10-26 |  |  | 2026-10-26
9961265 | STPS | 24 | VMS18 Variable Message Board Senior Premiair | SUB-2631 | SUB-2631 | 1 | Del Req |  | 07:00 | 2026-10-26 | 07:00 |  | 2026-10-26 | PRE808
9961265 | STPS | 25 | VMS19 Variable Message Board Senior Premiair | SUB-2631 | SUB-2631 | 1 | Del Req |  | 07:00 | 2026-10-26 | 07:00 |  | 2026-10-26 | PRE808
9961265 | STPS | 26 | VMS20 Variable Message Board Senior Premiair | SUB-2631 | SUB-2631 | 1 | Del Req |  | 07:00 | 2026-10-26 | 07:00 |  | 2026-10-26 | PRE808
9961265 | STPS | 28 | VMS21 Variable Message Board Senior Premiair | SUB-2631 | SUB-2631 | 1 | Pending |  | 07:00 | 2026-10-26 | 07:00 |  | 2026-10-26 | PRE808
9961265 | STPS | 29 | VMS22 Variable Message Board Senior Premiair | SUB-2631 | SUB-2631 | 1 | Pending |  | 09:00 | 2026-10-28 | 07:00 |  | 2026-10-28 | PRE808
9961265 | STPS | 30 | VMS23 Variable Message Board Senior Premiair | SUB-2631 | SUB-2631 | 1 | Del Req |  | 09:00 | 2026-10-26 | 07:00 |  | 2026-10-26 | PRE808
9961265 | STPS | 31 | VMS24 Variable Message Board Senior | SUB-1101 | SUB-1101 | 1 | Pending |  | 10:00 | 2026-10-26 | 15:00 |  | 2026-10-26 | PRE808
9961265 | STPS | 32 | VMS13 Variable Message Board Senior | 1191957 | 1191957 | 1 | Del Req |  | 09:00 | 2026-10-27 | 15:00 |  | 2026-10-27
9961265 | STPS | 34 | VMS14 Variable Message Board Junior | 1201864 | 1201864 | 1 | Del Req |  | 09:00 | 2026-10-27 | 15:00 |  | 2026-10-27
9961265 | STPS | 35 | VMS15 Variable Message Board Senior | 1211348 | 1211348 | 1 | Del Req |  | 09:00 | 2026-10-27 | 15:00 |  | 2026-10-27
9961265 | STPS | 37 | VMS16 Variable Message Board Senior | 1211376 | 1211376 | 1 | Del Req |  | 09:00 | 2026-10-27 | 15:00 |  | 2026-10-27
9961265 | STPS | 39 | VMS17 Variable Message Board Senior | 1211364 | 1211364 | 1 | Del Req |  | 09:00 | 2026-10-27 | 15:00 |  | 2026-10-27
9961265 | STPS | 41 | Transport Charge | TRANSPORT | TRANSPORT | 48 | Pending
9961976 | NVAC | 1 | LT01 MOLENDINAR Lighting Tower LED Metro | 1264929 | 1264929 | 1 | Delivered | 2026-09-11 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | T0002
9961976 | NVAC | 2 | LT02 MOLENDINAR Lighting Tower LED Metro | 1314284 | 1314284 | 1 | Delivered | 2026-09-11 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | T0002
9961976 | NVAC | 3 | LT03 MOLENDINAR Lighting Tower LED 76500lm Hybrid | 1264899 | 1264899 | 1 | Delivered | 2026-09-11 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | T0002
9961976 | NVAC | 4 | LT04 MOLENDINAR Lighting Tower LED Metro | 1188888 | 1188888 | 1 | Delivered | 2026-09-11 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | T0002
9961976 | NVAC | 5 | MOLENDINAR Lighting Tower LED 76500lm Hybrid | 1249499 | 1249499 | 1 | Delivered | 2026-09-11 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | T0002
9961976 | NVAC | 6 | GN20-S01-Generator 365kVA Diesel | 1276701 | 1276701 | 1 | Delivered | 2026-09-30 | 08:00 | 2026-10-26 |  |  | 2026-10-26 |  | GN20-A
9961976 | NVAC | 7 | GN19-Generator - Diesel - 80kVA DEL AS 60KVA | 1276416 | 1276416 | 1 | Del Req |  | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | GN19
9961976 | NVAC | 9 | GN23-Generator - Sync - Hardwire Only 150kVA Diesel | 1297157 | 1297157 | 1 | Delivered | 2026-09-30 | 08:00 | 2026-10-26 |  |  | 2026-10-26 |  | GN23
9961976 | NVAC | 10 | GN03-Generator - 30kVA (Diesel) | 1320829 | 1320829 | 1 | Delivered | 2026-10-01 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | GN03
9961976 | NVAC | 11 | GN18-Generator - 60kVA (Diesel) | 1261273 | 1261273 | 1 | Delivered | 2026-10-07 | 08:00 | 2026-10-26 |  |  | 2026-10-26 |  | GN18
9961976 | NVAC | 13 | SPARE-Generator - 60kVA | 1283681 | 1283681 | 1 | Pending |  | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26
9961976 | NVAC | 14 | GN04-Generator - 30kVA (Diesel) | 1277400 | 1277400 | 1 | Del Req |  | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | GN04
9961976 | NVAC | 15 | GN10-Generator - 45kVA (Diesel) |  |  | 1 | Pending |  | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26
9961976 | NVAC | 16 | GN01-Generator - 60kVA (Diesel) | 1276507 | 1276507 | 1 | Delivered | 2026-09-28 | 08:00 | 2026-10-26 |  |  | 2026-10-26 |  | GN01
9961976 | NVAC | 18 | GN25-Generator - 20kVA (Diesel) | 1244536 | 1244536 | 1 | Del Req |  | 08:00 | 2026-10-26 |  |  | 2026-10-26 |  | GN25
9961976 | NVAC | 19 | LT05/06-Lighting Tower POD Metro | 1224783 | 1224783 | 1 | Pending |  | 08:00 | 2026-10-26 |  |  | 2026-10-26 |  | LT05
9961976 | NVAC | 20 | LT05/06-Lighting Tower POD Metro | 1224791 | 1224791 | 1 | Pending |  | 08:00 | 2026-10-26 |  |  | 2026-10-26 |  | LT06
9961976 | NVAC | 21 | COATES Forklift 3.0t Container Diesel | 1197839 | 1197839 | 1 | Delivered | 2026-09-11 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | T0004
9961976 | NVAC | 25 | COATES Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD | 1247787 | 1247787 | 1 | Returned | 2026-09-14 | 08:00 | 2026-10-26 | 08:00 | 2026-09-17 | 2026-09-17 |  | T0005
9961976 | NVAC | 26 | COATES Forklift Rough Terrain 4WD With Rotator 2.5t Diesel | 1312577 | 1312577 | 1 | Delivered | 2026-09-14 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | T0005
9961976 | NVAC | 27 | SUPPLY-Forklift 3.5t Diesel | 1210921 | 1210921 | 1 | Pending |  | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26
9961976 | NVAC | 31 | COATES- 5T FORKLIFT 1.8TYNNES | MISCITEM | MISCITEM | 1 | Delivered | 2026-09-11 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | T0003
9961976 | NVAC | 34 | AT009 Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD | MISCITEM | MISCITEM | 1 | Delivered | 2026-09-17 | 12:00 | 2026-09-18 | 08:00 |  | 2026-09-18
9961976 | NVAC | 35 | COATES-Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD | 1247787 | 1247787 | 1 | Pending |  | 07:00 | 2026-10-28 |  |  | 2026-10-28 |  | T0005
9961976 | NVAC | 37 | COATES-Forklift Tyne Rotator | 1302007 | 1302007 | 1 | Pending |  | 08:00 | 2026-10-28 | 08:00 |  | 2026-10-28
9961976 | NVAC | 38 | GN21-Generator - 60kVA (Diesel) | 1261284 | 1261284 | 1 | Delivered | 2026-09-30 | 08:00 | 2026-10-26 |  |  | 2026-10-26 |  | GN21
9961976 | NVAC | 41 | GN23-Distribution Board Lifeguard 17 | 1189078 | 1189078 | 1 | Delivered | 2026-09-30 | 08:00 | 2026-10-26 | 08:00 |  | 2026-10-26 |  | GN23
9961976 | NVAC | 42 | GN26 CONCERT Generator - 200kVA (Diesel) | 1316182 | 1316182 | 1 | Delivered | 2026-10-12 | 07:00 | 2026-10-26 |  |  | 2026-10-26 |  | GN?
9961976 | NVAC | 43 | GN27 CONCERT-Generator - 200kVA (Diesel) | 1316183 | 1316183 | 1 | Delivered | 2026-10-12 | 07:00 | 2026-10-26 |  |  | 2026-10-26 |  | GN?
9961976 | NVAC | 44 | GN13 Generator - 60kVA (Diesel) DEL AS 45KVA | 1276503 | 1276503 | 1 | Delivered | 2026-10-12 | 10:00 | 2026-11-12 |  |  | 2026-11-12 |  | GN13
9961976 | NVAC | 45 | SPARE-Generator - 60kVA (Diesel) | 1261271 | 1261271 | 1 | Pending |  | 08:00 | 2026-10-26 |  |  | 2026-10-26
9961976 | NVAC | 46 | Cable - Set of 5 to suit 200KVA |  |  | 2 | Delivered | 2026-10-12 | 11:47 | 2026-10-13 |  |  | 2026-10-13
9961976 | NVAC | 47 | Cable - 120mm2 Single Double Insulated | CABLESSDI120MM | CABLESSDI120MM | 10 | Delivered | 2026-10-12 | 11:47 | 2026-10-13 |  |  | 2026-10-13
9961976 | NVAC | 48 | GN06 Generator - 60kVA (Diesel) | 1320828 | 1320828 | 1 | Del Req |  | 08:00 | 2026-10-26 |  |  | 2026-10-26 |  | GN06
9961976 | NVAC | 49 | GN24-Generator - 60kVA (Diesel) - Trailer Mounted | 1277089 | 1277089 | 1 | Del Req |  | 07:00 | 2026-10-26 |  |  | 2026-10-26
9961976 | NVAC | 50 | Delivery for Line Item(s) 7,14 15 Oct 2026 | Delivery | Delivery | 1 | Quoted |  | 08:00
9968862 | KINP | 1 | P01 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1322583 | 1322583 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P01
9968862 | KINP | 3 | P01 Refrigerator - Large | 1328956 | 1328956 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P01
9968862 | KINP | 4 | P03 Portable Building Shell 12.0M x 3.0M - Cyclonic Ra | 1327212 | 1327212 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P03
9968862 | KINP | 6 | P03 Refrigerator - Large | 1328955 | 1328955 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P03
9968862 | KINP | 7 | P04 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1327213 | 1327213 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968862 | KINP | 9 | P04 Refrigerator - Large | 1328954 | 1328954 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P04
9968862 | KINP | 10 | P05 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1189422 | 1189422 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P05
9968862 | KINP | 12 | P05 Chair Padded | CHAIRPADDED | CHAIRPADDED | 4 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P05
9968862 | KINP | 13 | P05 Refrigerator - Large | 1311988 | 1311988 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P05
9968862 | KINP | 14 | P05 Microwave Oven | 1320150 | 1320150 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P05
9968862 | KINP | 15 | P05 Sink & Cupboard | SINK/HANDBASIN | SINK/HANDBASIN | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P05
9968862 | KINP | 16 | P05 Auto Boil | 1127574 | 1127574 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P05
9968862 | KINP | 17 | CP1 P68 Portable Building Shell 6.0M x 3.0M | 1105057 | 1105057 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | CP1
9968862 | KINP | 19 | CP1 Chairs Stacking | CHAIRSSTACKING | CHAIRSSTACKING | 2 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | CP1
9968862 | KINP | 20 | CP1 Desk | DESK | DESK | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | CP1
9968862 | KINP | 21 | CP1 Refrigerator - Large | 1116687 | 1116687 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | CP1
9968862 | KINP | 22 | CP1 Urn | 119810 | 119810 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | CP1
9968862 | KINP | 23 | CP1 Sink & Cupboard | SINK/HANDBASIN | SINK/HANDBASIN | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | CP1
9968862 | KINP | 24 | P33 Portable Building Shell 9.6M x 3.0M | 453375 | 453375 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P33
9968862 | KINP | 26 | P33 Refrigerator - Large | 1328952 | 1328952 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P33
9968862 | KINP | 27 | P33 Sink & Cupboard | SINK/HANDBASIN | SINK/HANDBASIN | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P33
9968862 | KINP | 28 | P09 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1268824 | 1268824 | 1 | Delivered | 2026-09-16 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P09
9968862 | KINP | 30 | P09 Refrigerator - Large | 1328958 | 1328958 | 1 | Delivered | 2026-09-16 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P09
9968862 | KINP | 31 | P09 Sink & Cupboard | SINK/HANDBASIN | SINK/HANDBASIN | 1 | Delivered | 2026-09-16 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P09
9968862 | KINP | 32 | P09 Auto Boil | 1254390 | 1254390 | 1 | Delivered | 2026-09-16 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P09
9968862 | KINP | 33 | P17 Portable Building Shell Cyclone Rated 9.6m x 3m | 1268887 | 1268887 | 1 | Delivered | 2026-09-16 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P17
9968862 | KINP | 34 | P19 Portable Building Shell 6.0M x 3.0M | 1110619 | 1110619 | 1 | Delivered | 2026-09-16 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P19
9968862 | KINP | 36 | P18 Portable Building Shell 4.8M x 2.4M | 1097343 | 1097343 | 1 | Delivered | 2026-09-16 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P18
9968862 | KINP | 38 | P20 Portable Building Shell 4.8M x 2.4M | 1097339 | 1097339 | 1 | Delivered | 2026-09-16 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P20
9968862 | KINP | 44 | P10 Portable Building Shell 4.8M x 2.4M | 105626 | 105626 | 1 | Delivered | 2026-09-17 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P10
9968862 | KINP | 46 | P11 Portable Building Shell 4.8M x 2.4M | 415576 | 415576 | 1 | Delivered | 2026-09-17 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P11
9968862 | KINP | 48 | P12 Portable Building Shell 4.8M x 2.4M | 418665 | 418665 | 1 | Delivered | 2026-09-17 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P12
9968862 | KINP | 50 | P37 Portable Building Shell 6.0M x 3.0M | 1105053 | 1105053 | 1 | Delivered | 2026-09-17 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968862 | KINP | 51 | P13 Portable Building Shell 4.8M x 2.4M | 1097346 | 1097346 | 1 | Delivered | 2026-09-21 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P13
9968862 | KINP | 53 | P14 Portable Building Shell 4.8M x 2.4M | 960599 | 960599 | 1 | Delivered | 2026-09-21 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P14
9968862 | KINP | 55 | P15 Portable Building Shell 4.8M x 2.4M | 1097345 | 1097345 | 1 | Delivered | 2026-09-21 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P15
9968862 | KINP | 57 | P16 Portable Building Shell 4.8M x 2.4M | 415575 | 415575 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P16
9968862 | KINP | 59 | P44 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1273656 | 1273656 | 1 | Delivered | 2026-09-23 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P58
9968862 | KINP | 61 | P44 Portable Building Shell 6.0M x 3.0M | 198481 | 198481 | 1 | Delivered | 2026-09-23 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P44
9968862 | KINP | 63 | P41 Portable Building Shell 6.0M x 3.0M | 1189412 | 1189412 | 1 | Delivered | 2026-09-23 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | P41
9968862 | KINP | 64 | P06 Portable Building Shell 6.0M x 3.0M | 1087453 | 1087453 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P06
9968862 | KINP | 66 | P06 Refrigerator - Large | 1272749 | 1272749 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 67 | P06 Sink & Cupboard | SINK&CUPBOARD | SINK&CUPBOARD | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 68 | P06 Auto Boil | 1173374 | 1173374 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 69 | P06 Microwave Oven | 1284012 | 1284012 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 70 | P38 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1327218 | 1327218 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P38
9968862 | KINP | 72 | P38 Refrigerator - Large | 1272737 | 1272737 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P38
9968862 | KINP | 73 | P39 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1327216 | 1327216 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P39
9968862 | KINP | 75 | P39 Refrigerator - Large | 1272755 | 1272755 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P39
9968862 | KINP | 76 | P42 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1327221 | 1327221 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P42
9968862 | KINP | 78 | P42 Refrigerator - Large | 1272746 | 1272746 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P42
9968862 | KINP | 79 | P52 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1327211 | 1327211 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 81 | P52 Refrigerator - Large | 1328953 | 1328953 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P52
9968862 | KINP | 85 | P54 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1327219 | 1327219 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P54
9968862 | KINP | 87 | P55 Ticket Office 6.0Mx3.0M | 172114 | 172114 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P55
9968862 | KINP | 89 | P56 Portable Building Shell Cyclone Rated 3.6m x 2.4m | 1268865 | 1268865 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P56
9968862 | KINP | 90 | P57 Portable Building Shell Cyclone Rated 9.6m x 3m | 1268888 | 1268888 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P57
9968862 | KINP | 91 | P57 Refrigerator - Large | 1280688 | 1280688 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P57
9968862 | KINP | 92 | P21 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1327220 | 1327220 | 1 | Delivered | 2026-09-16 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P21
9968862 | KINP | 93 | P36 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1189410 | 1189410 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | HRP
9968862 | KINP | 94 | P51 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1322579 | 1322579 | 1 | Delivered | 2026-10-06 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P51
9968862 | KINP | 96 | P46 Refrigerator - Large | 1328959 | 1328959 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 100 | P46 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | 1327215 | 1327215 | 1 | Delivered | 2026-10-06 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P46
9968862 | KINP | 102 | P51 Refrigerator - Large | 1328957 | 1328957 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 103 | P69 Portable Building Shell 6.0M x 3.0M | 107247 | 107247 | 1 | Delivered | 2026-10-12 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P69
9968862 | KINP | 105 | P25 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1189408 | 1189408 | 1 | Delivered | 2026-10-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P25
9968862 | KINP | 107 | P25 Refrigerator - Large | 1260174 | 1260174 | 1 | Delivered | 2026-10-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 108 | P67 Commentary Booth 6.0M x 3.0M | 421107 | 421107 | 1 | Delivered | 2026-10-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 110 | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | 1327217 | 1327217 | 1 | Delivered | 2026-10-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P65
9968862 | KINP | 112 | P65 Refrigerator - Large | 1283982 | 1283982 | 1 | Delivered | 2026-10-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 113 | P66 Portable Building Shell 6.0M x 3.0M | 1327222 | 1327222 | 1 | Delivered | 2026-10-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P66
9968862 | KINP | 115 | P66 Refrigerator - Large | 1311990 | 1311990 | 1 | Delivered | 2026-10-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 116 | P60 Ticket Office 4.8Mx2.4M | 1015699 | 1015699 | 1 | Delivered | 2026-10-15 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P60
9968862 | KINP | 118 | P62 Commentary Booth 6.0M x 3.0M | 1189409 | 1189409 | 1 | Delivered | 2026-10-15 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P62
9968862 | KINP | 120 | P62 Refrigerator - Large | 1254221 | 1254221 | 1 | Delivered | 2026-10-15 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 121 | P63 Portable Building Shell 6.0M x 3.0M | 960719 | 960719 | 1 | Delivered | 2026-10-15 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P63
9968862 | KINP | 123 | P26 Refrigerator - Large |  |  | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 124 | P28 Refrigerator - Large |  |  | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 125 | P34 Chair Padded | CHAIRPADDED | CHAIRPADDED | 2 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 126 | P08 Portable Building Shell 6.0M x 3.0M | 421138 | 421138 | 1 | Delivered | 2026-10-06 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P08
9968862 | KINP | 128 | P08 Refrigerator - Large | 1114312 | 1114312 | 1 | Delivered | 2026-10-06 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P08
9968862 | KINP | 131 | P45 Portable Building Shell 6.0M x 3.0M | 107135 | 107135 | 1 | Delivered | 2026-10-12 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | P45
9968862 | KINP | 132 | P46 Refrigerator | 1272751 | 1272751 | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968862 | KINP | 136 | Site Shift for Supply | MISC | MISC | 1 | Delivered
9968929 | KINP | 1 | Portable Building Shell 4.8M x 3.0M | 960639 | 960639 | 1 | Delivered | 2026-09-15 | 09:00 | 2026-11-13 | 09:00 |  | 2026-11-13 |  | T0021
9968929 | KINP | 3 | Portable Building Shell 4.8M x 3.0M | 960634 | 960634 | 1 | Delivered | 2026-09-15 | 09:00 | 2026-11-13 | 09:00 |  | 2026-11-13 |  | T0022
9968929 | KINP | 5 | Shop Front - Shut Down | 1257261 | 1257261 | 1 | Del Req |  | 09:00 | 2026-11-13 | 09:00 |  | 2026-11-13 |  | T0023
9968929 | KINP | 7 | Toilet Portable - Fresh Water Flush | 1211968 | 1211968 | 1 | Delivered | 2026-09-15 | 09:00 | 2026-11-13 |  |  | 2026-11-13 |  | T0024
9968955 | KINP | 1 | WC05 Toilet Block 6.0M x 3.0M | 1097377 | 1097377 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC05
9968955 | KINP | 3 | WC05 Sewage Holding Tank 6.0M x 2.4M | 1328978 | 1328978 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC05
9968955 | KINP | 4 | WC12 Toilet Portable - Fresh Water Flush | 1211961 | 1211961 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC12
9968955 | KINP | 5 | WC12 Toilet Portable - Fresh Water Flush | 1200601 | 1200601 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC12
9968955 | KINP | 6 | WC11 Toilet Portable - Fresh Water Flush | 1211969 | 1211969 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC11
9968955 | KINP | 7 | WC21 Toilet Portable - Fresh Water Flush | 1211977 | 1211977 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC21
9968955 | KINP | 8 | WC21 Toilet Portable - Fresh Water Flush | 1211964 | 1211964 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC21
9968955 | KINP | 9 | WC21 Toilet Portable - Fresh Water Flush | 1083399 | 1083399 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 10 | WC16 Toilet Block Male Female Cyclone Rated 6m x 3m | 1322587 | 1322587 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC16
9968955 | KINP | 11 | WC16 Toilet Block Male Female Cyclone Rated 6m x 3m | 1322588 | 1322588 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC16
9968955 | KINP | 12 | WC100 Toilet Portable - With Trailer | 1288823 | 1288823 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC100
9968955 | KINP | 13 | WC100 Toilet Portable - With Trailer | 1248439 | 1248439 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC100
9968955 | KINP | 14 | WC21 Toilet Portable - Fresh Water Flush | 1002747 | 1002747 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC21
9968955 | KINP | 15 | WC06 Toilet Portable - Fresh Water Flush | 1195658 | 1195658 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC06
9968955 | KINP | 16 | WC21 Toilet Portable - Fresh Water Flush | 1211971 | 1211971 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC21
9968955 | KINP | 17 | WC12 Toilet Portable - Fresh Water Flush | 1002565 | 1002565 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC12
9968955 | KINP | 18 | WC21 Toilet Portable - Fresh Water Flush | 1212172 | 1212172 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC21
9968955 | KINP | 19 | WC21 Toilet Portable - Fresh Water Flush | 1103497 | 1103497 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC21
9968955 | KINP | 20 | WC17 Toilet Block Male Female Cyclone Rated 6m x 3m | 1327224 | 1327224 | 1 | Delivered | 2026-09-15 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC17
9968955 | KINP | 21 | WC17 Toilet Block Male Female Cyclone Rated 6m x 3m | 1327223 | 1327223 | 1 | Delivered | 2026-09-15 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC17
9968955 | KINP | 22 | WC50 Toilet Portable - Fresh Water Flush | 1211974 | 1211974 | 1 | Delivered | 2026-09-21 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC50
9968955 | KINP | 23 | WC11 Toilet Portable - Fresh Water Flush | 1211976 | 1211976 | 1 | Delivered | 2026-09-21 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC11
9968955 | KINP | 24 | WC07 Toilet Portable - Fresh Water Flush | 1002566 | 1002566 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 25 | WC07 Toilet Portable - Fresh Water Flush | 1317640 | 1317640 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 26 | WC07 Toilet Portable - Fresh Water Flush | 1211959 | 1211959 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 27 | WC07 Toilet Portable - Fresh Water Flush | 1317649 | 1317649 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 28 | WC07 Toilet Portable - Fresh Water Flush | 1317647 | 1317647 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 29 | WC07 Toilet Portable - Fresh Water Flush | 1317626 | 1317626 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 30 | WC07 Toilet Portable - Fresh Water Flush | 1317652 | 1317652 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 31 | WC07 Toilet Portable - Fresh Water Flush | 1317648 | 1317648 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 32 | WC07 Toilet Portable - Fresh Water Flush | 1212552 | 1212552 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 33 | WC07 Toilet Portable - Fresh Water Flush | 1200595 | 1200595 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 34 | WC07 Toilet Portable - Fresh Water Flush | 1181004 | 1181004 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 35 | WC07 Toilet Portable - Fresh Water Flush | 1002538 | 1002538 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 36 | WC07 Toilet Portable - Fresh Water Flush | 1317658 | 1317658 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 37 | WC07 Toilet Portable - Fresh Water Flush | 1317632 | 1317632 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 38 | WC07 Toilet Portable - Fresh Water Flush | 1317643 | 1317643 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 39 | WC07 Toilet Portable - Fresh Water Flush | 1317641 | 1317641 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 40 | WC07 Toilet Portable - Fresh Water Flush | 1002715 | 1002715 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 41 | WC07 Toilet Portable - Fresh Water Flush | 1083300 | 1083300 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 42 | WC07 Toilet Portable - Fresh Water Flush | 1192643 | 1192643 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 43 | WC07 Toilet Portable - Fresh Water Flush | 1002651 | 1002651 | 1 | Delivered | 2026-09-22 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13
9968955 | KINP | 44 | WC04 Toilet Portable - Fresh Water Flush | 1212502 | 1212502 | 1 | Delivered | 2026-09-21 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC04
9968955 | KINP | 45 | WC02 Toilet Portable - Fresh Water Flush | 1058086 | 1058086 | 1 | Delivered | 2026-09-21 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC02
9968955 | KINP | 46 | WC01 Toilet Portable - Fresh Water Flush | 1211958 | 1211958 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC01
9968955 | KINP | 47 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3m | 1327228 | 1327228 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC20
9968955 | KINP | 48 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3m | 1327225 | 1327225 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC20
9968955 | KINP | 49 | WC20 Sewage Holding Tank 6.0M x 2.4M | 1311341 | 1311341 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC20
9968955 | KINP | 50 | WC20 Sewage Holding Tank 6.0M x 2.4M | 1328982 | 1328982 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC20
9968955 | KINP | 51 | Wc86 Toilet - Disabled Access | 1296899 | 1296899 | 1 | Delivered | 2026-10-07 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC86
9968955 | KINP | 52 | WC27 Toilet Block 6.0M x 3.0M | 1119484 | 1119484 | 1 | Delivered | 2026-09-25 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC27
9968955 | KINP | 54 | WC27 Sewage Holding Tank 6.0M x 2.4M | 1328979 | 1328979 | 1 | Delivered | 2026-09-25 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC27
9968955 | KINP | 55 | WC15 Toilet Block Male Female Cyclone Rated 6m x 3m | 1327226 | 1327226 | 1 | Delivered | 2026-09-25 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC15
9968955 | KINP | 56 | WC15 Toilet Block Male Female Cyclone Rated 6m x 3m | 1303835 | 1303835 | 1 | Delivered | 2026-09-25 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | WC15
9968955 | KINP | 57 | WC01 Toilet - Accessible | 1317644 | 1317644 | 1 | Delivered | 2026-09-30 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC01
9968955 | KINP | 58 | WC06 Toilet Portable - Fresh Water Flush | 1212523 | 1212523 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC06
9968955 | KINP | 59 | WC41 Toilet Portable - Fresh Water Flush | miscitems | miscitems | 10 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 69 | WC01 Toilet Portable - Fresh Water Flush | 1211967 | 1211967 | 1 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC01
9968955 | KINP | 70 | WC43 Toilet Portable - Fresh Water Flush | miscitem | miscitem | 10 | Delivered | 2026-09-28 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 80 | WC44 Toilet Portable - Fresh Water Flush | miscitem | miscitem | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 81 | WC44 Toilet Portable - Fresh Water Flush | miscitem | miscitem | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 84 | WC67 Toilet Portable - Fresh Water Flush | miscitems | miscitems | 2 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 85 | WC70 Toilet Portable - Fresh Water Flush |  |  | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 86 | WC71 Toilet Portable - Fresh Water Flush | miscitems | miscitems | 8 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 87 | WC69 Toilet Portable - Fresh Water Flush |  |  | 12 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 88 | WC38 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 89 | WC39 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 2 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 90 | WC40 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 5 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 91 | WC60 Toilet Block 6.0M x 3.0M | 1087500 | 1087500 | 1 | Delivered | 2026-10-01 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC60
9968955 | KINP | 93 | WC60 Toilet Block 6.0M x 3.0M | 1119489 | 1119489 | 1 | Delivered | 2026-10-01 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC60
9968955 | KINP | 94 | WC60 Sewage Holding Tank 6.0M x 2.4M | 1328980 | 1328980 | 1 | Delivered | 2026-10-01 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC60
9968955 | KINP | 95 | WC60 Sewage Holding Tank 6.0M x 2.4M | 1328981 | 1328981 | 1 | Delivered | 2026-10-01 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC60
9968955 | KINP | 96 | WC61 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 8 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 97 | WC31 Toilet - Accessible | 1317645 | 1317645 | 1 | Delivered | 2026-10-08 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC31
9968955 | KINP | 98 | WC31 16 Pan Block | MISCITEM | MISCITEM | 2 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 100 | WC34 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 101 | WC33 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 17 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 102 | WC09 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 10 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 103 | WC09 Toilet Block 6.0M x 3.0M | 1268858 | 1268858 | 1 | Delivered | 2026-10-08 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC09
9968955 | KINP | 105 | WC09 Toilet Block 6.0M x 3.0M | 1311146 | 1311146 | 1 | Delivered | 2026-10-08 | 07:00 | 2026-11-13 |  |  | 2026-11-13 |  | WC09
9968955 | KINP | 106 | WC59 FWF Toilet | MISCITEM | MISCITEM | 7 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 107 | WC57 FWF Toilet | MISCITEM | MISCITEM | 2 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 108 | WC49 FWF Toilet | MISCITEM | MISCITEM | 3 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 109 | WC48 FWF Toilet | MISCITEM | MISCITEM | 4 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 110 | WC51 FWF Toilet | MISCITEM | MISCITEM | 6 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 111 | WC51 Toilet - Accessible |  |  | 1 | Del Req |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 112 | WC54 FWF Toilet | MISCITEM | MISCITEM | 6 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 113 | WC56 FWF Toilet | MISCITEM | MISCITEM | 12 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 114 | WC10 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 3 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 115 | WC45 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 8 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 116 | WC47 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 117 | WC19 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 118 | WC25 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 119 | WC23 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 5 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 120 | WC26 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 121 | WC24 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 122 | WC13 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 2 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 123 | WC28 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 124 | WC29 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 7 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 125 | WC30 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 8 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 126 | WC35 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 127 | WC46 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 128 | WC55 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 129 | WC62 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 2 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 130 | WC65 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 131 | WC68 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 132 | WC72 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 133 | WC73 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 2 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 134 | WC85 Toilet Portable - Fresh Water Flush | MISCITEM | MISCITEM | 1 | Pending |  | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 138 | Steps Toilet Block | STEPSTOILETBLK | STEPSTOILETBLK | 1 | Delivered | 2026-10-01 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 139 | Steps Toilet Block | STEPSTOILETBLK | STEPSTOILETBLK | 1 | Delivered | 2026-10-01 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 140 | WC01 Toilet Portable - Fresh Water Flush | 172824 | 172824 | 1 | Delivered | 2026-09-14 | 07:00 | 2026-11-13 |  |  | 2026-11-13
9968955 | KINP | 151 | PG01 FWF Toilet | MISCITEM | MISCITEM | 1 | Delivered | [7 empty] | PG01
9968955 | KINP | 152 | PG03 FWF Toilet | MISCITEM | MISCITEM | 1 | Delivered | [7 empty] | PG03
9968955 | KINP | 153 | PG05 FWF Toilet | MISCITEM | MISCITEM | 1 | Delivered | [7 empty] | PG05
9968955 | KINP | 155 | WC42 FWF Toilet | MISCITEM | MISCITEM | 1 | Delivered | [7 empty] | WC42
9968955 | KINP | 156 | WC53 FWF Toilet | MISCITEM | MISCITEM | 3 | Delivered | [7 empty] | WC53
9968955 | KINP | 157 | WC81 FWF Toilet | MISCITEM | MISCITEM | 1 | Delivered | [7 empty] | WC81
9968955 | KINP | 158 | WC12 Toilet Portable - Fresh Water Flush | 1211963 | 1211963 | 1 | Delivered | [7 empty] | WC12
9972648 | STPS | 1 | WB01 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 12 | Delivered | 2026-09-14 | 20:00 | 2026-10-27 | 19:30 |  | 2026-10-27 |  | WB01
9972648 | STPS | 2 | WB03 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 30 | Delivered | 2026-09-18 | 20:00 | 2026-10-19 | 22:00 |  | 2026-10-29 |  | WB03
9972648 | STPS | 3 | WB02 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 34 | Delivered | 2026-09-21 | 09:00 | 2026-09-27 | 17:00 |  | 2026-10-27 |  | WB02
9972648 | STPS | 4 | WB04 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 12 | Del Req |  | 09:00 | 2026-10-27 | 09:00 |  | 2026-10-27 |  | WB04
9972648 | STPS | 5 | WB05 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 13 | Del Req |  | 19:00 | 2026-10-27 | 19:00 |  | 2026-10-27 |  | WB05
9972648 | STPS | 6 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 60 | Delivered | 2026-10-15 | 19:00 | 2026-10-27 | 19:00 |  | 2026-10-27 |  | WB06
9972648 | STPS | 7 | WB07 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 17 | Pending |  | 20:00 | 2026-10-27 | 09:00 |  | 2026-10-27 |  | WB07
9972648 | STPS | 8 | WB13 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 10 | Del Req |  | 10:00 | 2026-10-26 | 10:00 |  | 2026-10-26 |  | WB13
9972648 | STPS | 9 | WB14 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 2 | Pending |  | 07:00 | 2026-10-27 | 07:00 |  | 2026-10-27 |  | WB14
9972648 | STPS | 10 | WB15 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 4 | Pending |  | 07:00 | 2026-10-27 | 07:00 |  | 2026-10-27 |  | WB15
9972648 | STPS | 11 | WB16 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 13 | Pending |  | 07:00 | 2026-10-27 | 19:00 |  | 2026-10-27 |  | WB16
9972648 | STPS | 12 | WB17 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 6 | Pending |  | 17:00 | 2026-10-27 | 17:00 |  | 2026-10-27 |  | WB17
9972648 | STPS | 13 | WB18 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 2 | Pending |  | 17:00 | 2026-10-27 | 17:00 |  | 2026-10-27 |  | WB18
9972648 | STPS | 14 | WB20 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 30 | Pending |  | 19:00 | 2026-10-29 | 19:00 |  | 2026-10-29 |  | WB20
9972648 | STPS | 15 | WB19 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 34 | Pending |  | 07:00 | 2026-11-06 | 17:00 |  | 2026-11-06 |  | WB19
9972648 | STPS | 16 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 60 | Delivered | 2026-10-15 | 19:00 | 2026-10-27 |  |  | 2026-10-27 |  | WB06
9972648 | STPS | 17 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | ARMORZONMASHTL2 | ARMORZONMASHTL2 | 34 | Delivered | 2026-10-15 | 19:00 | 2026-10-27 |  |  | 2026-10-27 |  | WB06
9973079 | STPS | 1 | Trakmat - 2.4M x 1.1M - TM4496 | TRAKMAT2.4X1.1 | TRAKMAT2.4X1.1 | 20 | Delivered | 2026-09-15 | 07:00 | 2026-11-13 | 07:00 |  | 2026-11-13 |  | T0025
9973079 | STPS | 2 | Delivery for HA Line Item(s) 1,2 15 Sep 2026 | Delivery | Delivery | 1 | Applied |  | 07:00
9973977 | KINP | 1 | WCTV Toilet Block Male Female Cyclone Rated 6m x 3m | 1311144 | 1311144 | 1 | Delivered | 2026-09-23 | 10:00 | 2026-11-13 | 10:00 |  | 2026-11-13 |  | T0243
9974042 | KINP | 1 | Container 3.0M x 2.4M | 1134386 | 1134386 | 1 | Delivered | 2026-10-07 | 10:00 | 2026-11-13 | 10:00 |  | 2026-11-13 |  | T0258
9974042 | KINP | 2 | Container - Refrigerated 6.0M x 2.4M | SUB-2131 | SUB-2131 | 1 | Delivered | 2026-10-13 | 10:00 | 2026-11-13 |  |  | 2026-11-13 | ROY002
9974042 | KINP | 3 | Delivery each way per container | TRANSPORT | TRANSPORT | 2 | Pending |  | 10:00 | 2026-11-13 | 10:00 |  | 2026-11-13
9974042 | KINP | 4 | Pickup each way per Container | TRANSPORT | TRANSPORT | 2 | Pending |  | 10:00 | 2026-11-13 | 10:00 |  | 2026-11-13
9987005 | MEAD | 1 | Supply Forklift 5.0t Diesel | 1272166 | 1272166 | 1 | Delivered | 2026-10-05 | 10:00 | 2026-10-28 |  |  | 2026-10-30 |  | T0085
9987005 | MEAD | 2 | Supply Telehandler Fork Extension 1800mm | 1262224 | 1262224 | 1 | Delivered | 2026-10-12 | 10:00 | 2026-10-28 |  |  | 2026-10-30
9987005 | MEAD | 3 | Transport Charge | TRANSPORT | TRANSPORT | 2 | Pending |  | 10:00 | 2026-10-30 | 17:00 |  | 2026-10-30
9987005 | MEAD | 7 | Forklift Rough Terrain 2.5t 4WD Diesel | 1281615 | 1281615 | 1 | Delivered | 2026-10-13 | 07:00 | 2026-10-27 | 07:00 |  | 2026-10-27 |  | T0109
9992300 | MEAD | 1 | Forklift Rough Terrain 5.0t 4WD Diesel | 1321364 | 1321364 | 1 | Del Req |  | 08:00 | 2026-10-27 |  |  | 2026-10-27
9992300 | MEAD | 2 | Forklift Rough Terrain 2.5t 4WD Diesel | 1298390 | 1298390 | 1 | Del Req |  | 08:00 | 2026-10-27 |  |  | 2026-10-27
9992300 | MEAD | 3 | Fork Extensions 2.4m | MISCITEM | MISCITEM | 1 | Del Req |  | 08:00 | 2026-10-27 | 14:00 |  | 2026-10-27
9992300 | MEAD | 4 | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | 1220903 | 1220903 | 1 | Del Req |  | 08:00 | 2026-10-26 |  |  | 2026-10-26
9992300 | MEAD | 5 | Knuckle Boom 61ft (18.6M) - Diesel | 1300290 | 1300290 | 1 | Pending |  | 08:00 | 2026-10-26 |  |  | 2026-10-26
9992300 | MEAD | 6 | Trakmat | MISCITEM | MISCITEM | 10 | Del Req |  | 08:00 | 2026-10-27 | 14:00 |  | 2026-10-27
9992300 | MEAD | 7 | Transport Charge 5T Forklift | TRANSPORT | TRANSPORT | 2 | Pending |  | 08:00
9992300 | MEAD | 8 | Transport Charge 2.5T Forklift | TRANSPORT | TRANSPORT | 2 | Pending |  | 08:00
9992300 | MEAD | 9 | Transport Charge 43' Scissorlift | TRANSPORT | TRANSPORT | 2 | Pending |  | 08:00
9992300 | MEAD | 10 | Transport Charge 60' Boom | TRANSPORT | TRANSPORT | 2 | Pending |  | 08:00
9992300 | MEAD | 11 | Transport Charge Trakmat | TRANSPORT | TRANSPORT | 2 | Pending |  | 08:00
9992300 | MEAD | 12 | Straight Boom Lift 60ft - Diesel | 1286482 | 1286482 | 1 | Delivered |  | 08:00 | 2026-10-27 |  |  | 2026-10-27 |  | EQ0003
9992300 | MEAD | 13 | Transport Charge 60' Straight | TRANSPORT | TRANSPORT | 2 | Delivered
9994996 | STPS | 1 | Labour Charge WFB Install & Removal | LABOUR | LABOUR | 1 | Pending
9994996 | STPS | 2 | Transport Charge WFB Delivery & Removal | TRANSPORT | TRANSPORT | 1 | Pending