## Fix list
Contract | Line(s) | Baseplan says | Our record says (truth) | What to do | Who
9968862 | 133 | Install & Demob 45 x $655.83 = $29,512.35 (the whole labour package on every building: install, steps, levelling, cleaning, fire extinguisher, demob) | 47 buildings ticked on the record: install 47, levelling 47, cleaning 47, demob 47, steps 40 (none on P06, P38, P39, P42, P60, P62, P63), fire extinguisher 10. At the card that is $27,805.11 | Charge each line by the building, not a flat package: steps only where fitted, fire extinguisher only where supplied. Difference $1,707.24 over on Baseplan as it stands (and it is on 45 buildings where the record has 47) | Baseplan (branch)
9968862 | 134-135 | Transport 72 x $500 (up to 6 m) + 18 x $800 (9.6/12 m) = $50,400 | Delivery and pickup ticked on the record: 76 legs small buildings, 18 legs large | Small-building legs: Baseplan 72, record 76; large: Baseplan 18, record 18. Align the count to the buildings table | Baseplan (branch)
9968862 | - | no hire line for AA | AA on site with install ticked | Add the hire line (and give us the asset number if we lack it) | Baseplan (branch)
9968862 | 93 | labelled P36 (1189410) | that building is HRP on site | Relabel the line HRP | Baseplan (branch)
9968862 | 64 | P06 asset 1087453 | P06 is 1097453 on site | Correct the asset number on the line (the site number stands) | Baseplan (branch)
9968862 | 93 | P36 asset 1189410 | P36 is 1282487 on site | Correct the asset number on the line (the site number stands) | Baseplan (branch)
9968862 | 59 | labelled P44 (1273656) | that building is P58 on site | Relabel the line P58 | Baseplan (branch)
9968955 | 141 | Pumpout FWF & accessible 678 x $72.87 = $49,405.86 | 231 FWF + 4 accessible on the servicing tracker; x 3 race nights = 705 | Quantity to 705 ($51,373.35); the FWF hire list first (by-ref sheet) | Baseplan (branch)
9968955 | 146, 149 | FWF install/demob 444 x $36.44; FWF transport 444 x $47.5 (both on 222 FWF) | 231 FWF on the tracker | Quantities to 462 once the FWF list is right; confirm whether Event Portables units carry Coates transport | Baseplan (branch) + Ask Andrew
9968955 | - | PG01: 0 FWF | PG01: 1 FWF on the tracker (0 Coates, 1 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | - | PG03: 0 FWF | PG03: 1 FWF on the tracker (0 Coates, 1 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | - | PG05: 0 FWF | PG05: 1 FWF on the tracker (0 Coates, 1 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | - | PG29: 0 FWF | PG29: 1 FWF on the tracker (0 Coates, 1 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | 46, 57, 69, 140 | WC01: 3 FWF | WC01: 2 FWF on the tracker (3 Coates, 0 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | 4, 5, 17 | WC12: 3 FWF | WC12: 4 FWF on the tracker (4 Coates, 0 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | 7, 8, 9, 14, 16, 18, 19 | WC21: 7 FWF | WC21: 6 FWF on the tracker (6 Coates, 0 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | - | WC42: 0 FWF | WC42: 1 FWF on the tracker (0 Coates, 1 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | - | WC53: 0 FWF | WC53: 3 FWF on the tracker (0 Coates, 3 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | 84 | WC67: 2 FWF | WC67: 4 FWF on the tracker (1 Coates, 3 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | - | WC81: 0 FWF | WC81: 1 FWF on the tracker (0 Coates, 1 Event Portables numbers) | Match the FWF hire lines to the units on site | Baseplan (branch)
9968955 | 9 | WC21 Toilet Portable - Fresh Water Flush asset 1083399 Delivered | this asset number is not on our record | Check which unit on site this is; give us the number or close the line | Both
9968955 | 38 | WC07 Toilet Portable - Fresh Water Flush asset 1317643 Delivered | this asset number is not on our record | Check which unit on site this is; give us the number or close the line | Both
9961265 | 28 | VMS21 Premiair, no fleet number | fleet 97T, rego T16922 | Put the fleet number on the line | Baseplan (branch)
9961265 | 32-39 | VMS13-17 start 19 Oct; dockets 26134263 (13/14/15) out 16 Oct and 26134314 (16/17) out 19 Oct | all five came 16 Oct on the record (T0158) | Start VMS13, 14, 15 on 16 Oct (3 days x $53.61 each); confirm 16/17 against the 16 Oct delivery | Baseplan (branch) + Ask Andrew
9961265 | 31 | VMS24 start 19 Oct; docket 26143911 out 22 Oct | VMS24 on site 21 Oct on the record (via Codex); Andrew 22 Oct: today's deliveries were the VMS boards and barriers | Start VMS24 on the delivery day; we correct our record to 22 Oct on Andrew's word | Both
9961265 | 43-44 | VMS05a 1211356, 20-21 Oct, $107.22 + delivery $289.52 (docket 26141143) | 1211356 is not on our record; VMS05 is one of the 7 Sep boards | Say what 1211356 is: a second board at 05a for a day, or a wrong entry | Ask Andrew
9961265 | 40-42 | Labour 24 x $176.97; transport 48 x $150; site shifts 8 x $150 | card: VMS labour 2024 $176.97 a board; VMS transport "POA" on the card; 24 boards; our labour ticks 12 of 24 | Labour count agrees with 24 boards. $150 a leg is Baseplan's figure, not on the card: confirm the transport rate and the 8 site shifts | Ask Andrew
9961265 | 13 | VMS10 120T | our register has no fleet or rego for VMS10 | Fill our register: fleet 120T (rego when read) | Our record
all | see sheet | $256,174.16 on pending charge lines dated 16-23 Oct | $85,572.93 of it is work done at 22 Oct; $170,601.23 is demob, return transport and race-night servicing still to come | Invoice the done part now; the rest when done (servicing from the tracker ticks each night) | Baseplan (branch)

## 9968862 buildings
Ref | Building (record) | Our asset no(s) | Baseplan label | Baseplan line | Baseplan asset | Baseplan hire rate | Light | Complete | Levelled (drawer) | Steps (drawer) | Install tick | Steps tick | Levelling tick | Cleaning tick | Fire ext tick | Demob tick | Our labour at card | Transport legs ticked | Note
AA | Building 6m | 142514 | - | - | - | - | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2 | no 9968862 hire line for this building
CP1 | Building 6m | 1105057 | CP1 | 17 | 1105057 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
HRP | Building 6m | 1189410 | P36 | 93 | 1189410 | 1426.07 |  | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2 | Baseplan labels it P36
P01 | Building 12m | 1322583 | P01 | 1 | 1322583 | 1951.46 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P03 | Building 12m | 1327212 | P03 | 4 | 1327212 | 1951.46 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P04 | Building 12m | 1327213 | P04 | 7 | 1327213 | 1951.46 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P05 | Building 6m | 1189422 | P05 | 10 | 1189422 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P06 | Building 6m | 1097453 | line under this label, other number | 64 | 1087453 | 1426.07 | on site | yes | yes | no | yes |  | yes | yes |  | yes | 447.63 | 2 | Baseplan line carries a different number (1087453)
P08 | Building 6m | 421138 | P08 | 126 | 421138 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2
P09 | Building 6m | 1268824 | P09 | 28 | 1268824 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P10 | Building 4.8m | 105626 | P10 | 44 | 105626 | 1125.84 |  | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P11 | Building 4.8m | 415576 | P11 | 46 | 415576 | 1125.84 |  | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P12 | Building 4.8m | 418665 | P12 | 48 | 418665 | 1125.84 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P13 | Building 4.8m | 1097346 | P13 | 51 | 1097346 | 1125.84 |  | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P14 | Building 4.8m | 960599 | P14 | 53 | 960599 | 1125.84 |  | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P15 | Building 4.8m | 1097345 | P15 | 55 | 1097345 | 1125.84 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P16 | Building 4.8m | 415575 | P16 | 57 | 415575 | 1125.84 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P17 | Building 9.6m | 1268887 | P17 | 33 | 1268887 | 1576.18 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P18 | Building 4.8m | 1097343 | P18 | 36 | 1097343 | 1125.84 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P19 | Building 4.8m | 1110619 | P19 | 34 | 1110619 | 1125.84 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P20 | Building 4.8m | 1097339 | P20 | 38 | 1097339 | 1125.84 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P21 | Building 4.8m | 1327220 | P21 | 92 | 1327220 | 1125.84 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P25 | Building 4.8m | 1189408 | P25 | 105 | 1189408 | 1125.84 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2
P33 | Building 9.6m | 453375 | P33 | 24 | 453375 | 1576.18 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P36 | Building 6m | 1282487 | line under this label, other number | 93 | 1189410 | 1426.07 |  | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2 | Baseplan line carries a different number (1189410)
P37 | Building 6m | 1105053 | P37 | 50 | 1105053 | 1426.07 |  | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P38 | Building 6m | 1327218 | P38 | 70 | 1327218 | 1426.07 | on site | yes | yes | no | yes |  | yes | yes |  | yes | 447.63 | 2
P39 | Building 6m | 1327216 | P39 | 73 | 1327216 | 1426.08 | on site | yes | yes | no | yes |  | yes | yes |  | yes | 447.63 | 2
P41 | Building 6m | 1189412 | P41 | 63 | 1189412 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P42 | Building 6m | 1327221 | P42 | 76 | 1327221 | 1426.07 | on site | yes | yes | no | yes |  | yes | yes |  | yes | 447.63 | 2
P44 | Building 6m | 198481 | P44 | 61 | 198481 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P45 | Building 6m | 107135 | P45 | 131 | 107135 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2
P46 | Building 12m | 1327215 | P46 | 100 | 1327215 | 1951.46 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2
P51 | Building 12m | 1322579 | P51 | 94 | 1322579 | 1951.46 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2
P52 | Building 12m | 1327211 | P52 | 79 | 1327211 | 1951.46 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2
P54 | Building 6m | 1327219 | P54 | 85 | 1327219 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2
P55 | Ticket Box 6m | 172114 | P55 | 87 | 172114 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P56 | Building 3.6m | 1268865 | P56 | 89 | 1268865 | 975.73 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P57 | Building 9.6m | 1268888 | P57 | 90 | 1268888 | 1576.18 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2
P58 | Building 6m | 1273656 | P44 | 59 | 1273656 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2 | Baseplan labels it P44
P60 | Ticket Box 4.8m | 1015699 | P60 | 116 | 1015699 | 1125.84 | on site | yes | yes | no | yes |  | yes | yes |  | yes | 447.63 | 2
P62 | Building 6m | 1189409 | P62 | 118 | 1189409 | 1426.07 | on site | yes | yes | no | yes |  | yes | yes |  | yes | 447.63 | 2
P63 | Building 6m | 960719 | P63 | 121 | 960719 | 1426.07 | on site | yes | yes | no | yes |  | yes | yes |  | yes | 447.63 | 2
P65 | Building 6m | 1327217 | P65 | 110 | 1327217 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P66 | Building 6m | 1327222 | P66 | 113 | 1327222 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2
P67 | Building 6m | 421107 | P67 | 108 | 421107 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes |  | yes | 603.78 | 2
P69 | Building 6m | 107247 | P69 | 103 | 107247 | 1426.07 | on site | yes | yes | yes | yes | yes | yes | yes | yes | yes | 655.83 | 2

## 9968955 toilets by ref
Ref | Servicing area | Baseplan lines | FWF Baseplan | FWF record | Accessible Baseplan | Accessible record | Blocks Baseplan | Blocks record (sewer + tank-mounted) | Tanks Baseplan | Tanks record | 16-pan Baseplan | 16-pan record | Coates numbers on record | Event Portables numbers on record | Difference
PG01 | 1 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | fix: FWF: Baseplan 0, record 1
PG03 | 1 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | fix: FWF: Baseplan 0, record 1
PG05 | 1 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | fix: FWF: Baseplan 0, record 1
PG29 | 1 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | fix: FWF: Baseplan 0, record 1
WC01 | 4 | 46, 57, 69, 140 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | fix: FWF: Baseplan 3, record 2
WC02 | 4 | 45 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
WC04 | 3 | 44 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
WC05 | 3 | 1, 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 0
WC06 | 3 | 15, 58 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
WC07 | 3 | 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40, 41, 42, 43 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0
WC09 | 5 | 102, 103, 105 | 10 | 10 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 10
WC10 | 5 | 114 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
WC11 | 3 | 6, 23 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
WC12 | 1 | 4, 5, 17 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | fix: FWF: Baseplan 3, record 4
WC13 | 9 | 122 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
WC15 | 1 | 55, 56 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 0
WC16 | 1 | 10, 11 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 0
WC17 | 1 | 20, 21 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 0
WC19 | 2 | 117 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC20 | 2 | 47, 48, 49, 50 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 4 | 0
WC21 | 2 | 7, 8, 9, 14, 16, 18, 19 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | fix: FWF: Baseplan 7, record 6
WC23 | 7 | 119 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
WC24 | 9 | 121 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC25 | 8 | 118 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC26 | 7 | 120 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC27 | 6 | 52, 54 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 0
WC28 | 5 | 123 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC29 | 5 | 124 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
WC30 | 11 | 125 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WC31 | 4 | 97, 98 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0
WC33 | 6 | 101 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
WC34 | 4 | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC35 | 11 | 126 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC38 | 4 | 88 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC39 | 4 | 89 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
WC40 | 4 | 90 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
WC41 | 3 | 59 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
WC42 | 4 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | fix: FWF: Baseplan 0, record 1
WC43 | 1 | 70 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
WC44 | 2 | 80, 81 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
WC45 | 8 | 115 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WC46 | 10 | 127 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC47 | 8 | 116 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC48 | 10 | 109 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WC49 | 10 | 108 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
WC50 | 7 | 22 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
WC51 | 10 | 110, 111 | 6 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6
WC53 | 10 |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | fix: FWF: Baseplan 0, record 3
WC54 | 9 | 112 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
WC55 | 9 | 128 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC56 | 7 | 113 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
WC57 | 7 | 107 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
WC59 | 7 | 106 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
WC60 | 6 | 91, 93, 94, 95 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 4 | 0
WC61 | 6 | 96 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WC62 | 11 | 129 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
WC65 | 4 | 130 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC67 | 12 | 84 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | fix: FWF: Baseplan 2, record 4
WC68 | 12 | 131 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC69 | 12 | 87 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
WC70 | 12 | 85 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC71 | 12 | 86 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WC72 | 12 | 132 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC73 | 1 | 133 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
WC81 | 13 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | fix: FWF: Baseplan 0, record 1
WC85 | 14 | 134 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WC86 | 2 | 51 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
WC100 | 0 | 12, 13 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0

## 9968955 service lines
Line | Baseplan line | Baseplan qty | Rate | Baseplan $ | Our basis (record) | Our qty | Our $ at the same rate | Verdict
141 | Pumpout Service FWF & Accessable | 678 | 72.87 | 49405.86 | 231 FWF + 4 accessible on the tracker = 235 units x 3 race nights = 705 | 705 | 51373.35 | Baseplan's 678 is 226 units x 3; its hire list is short the units flagged on the by-ref sheet. Count follows the units on site.
142 | Pumpout Service Tank Mounts | 24 | 624.6 | 14990.4 | 6 tanks + 2 16-pan blocks = 8 x 3 = 24 | 24 | 14990.4 | agrees
143 | Cleaning & Restock Sewer Connect | 24 | 260.25 | 6246 | 8 sewer-connected blocks x 3 = 24 (the 6 tank-mounted blocks are cleaned under line 142) | 24 | 6246 | agrees
144 | Install Demob Toilet Blocks | 16 | 603.78 | 9660.48 | 14 blocks + 2 16-pan = 16 | 16 | 9660.48 | agrees
145 | Labour Charge Accessable Install & Demob | 8 | 88.49 | 707.92 | 4 accessible x 2 (install + demob) | 8 | 707.92 | agrees
146 | Labour Charge FWF Install & Demob | 444 | 36.44 | 16179.36 | 231 FWF x 2 (install + demob) | 462 | 16835.28 | Baseplan on 222 FWF; the tracker has 231
147 | Transport Charge Blocks & 16 Pan | 32 | 500 | 16000 | 16 blocks x 2 legs | 32 | 16000 | agrees
148 | Transport Charge Accessable Toilets | 8 | 500 | 4000 | 4 accessible x 2 legs | 8 | 4000 | agrees
149 | Transport Charge FWF | 444 | 47.5 | 21090 | 231 FWF x 2 legs if every FWF is charged transport (Event Portables units included) | 462 | 21945 | Ask: is transport charged on the Event Portables units at the Coates rate?

## 9961265 VMS boards
Line | Board | Baseplan item | Baseplan fleet | Our fleet | Our rego | Status | Start | Expected term | Term | Dockets | On site (record) | Rate/day | Prebill | Note
1 | Variable Message Board Senior | 1211404 |  |  |  | Returned | 2026-09-07 | 2026-11-13 | 2026-09-22 | 26126700 In 2026-10-12; 26053081 Out 2026-09-07 | 2026-09-07 | 53.61 | 857.76
3 | Variable Message Board Senior | 1211370 |  |  | ES3206 | Delivered | 2026-09-07 | 2026-11-13 |  | 26053094 Out 2026-09-07 | 2026-09-07 | 53.61 | 3591.87
4 | Variable Message Board Senior | 1211354 |  |  | EX0017 | Delivered | 2026-09-07 | 2026-11-13 |  | 26053101 Out 2026-09-07 | 2026-09-07 | 53.61 | 3591.87
5 | Variable Message Board Senior | 1182999 |  |  | 410UFQ | Delivered | 2026-09-07 | 2026-11-13 |  | 26053081 Out 2026-09-07 | 2026-09-07 | 53.61 | 3591.87
6 | Variable Message Board Senior | 1191877 |  |  | EM6306 | Delivered | 2026-09-07 | 2026-11-13 |  | 26053081 Out 2026-09-07 | 2026-09-07 | 53.61 | 3591.87
7 | Variable Message Board Senior | 1211359 |  |  | ER9247 | Delivered | 2026-09-07 | 2026-11-13 |  | 26053086 Out 2026-09-07; 26053086 Out 2026-09-07 | 2026-09-07 | 53.61 | 3591.87
8 | Variable Message Board Senior | 1211383 |  |  | ER9381 | Delivered | 2026-09-07 | 2026-11-13 |  | 26053086 Out 2026-09-07; 26053086 Out 2026-09-07 | 2026-09-07 | 53.61 | 3591.87
9 | Variable Message Board - Colou | 1271129 |  |  | 536UOO | Delivered | 2026-09-07 | 2026-11-13 |  | 26053086 Out 2026-09-07; 26053086 Out 2026-09-07 | 2026-09-07 | 53.61 | 3591.87
12 | VMS09 | 1211404 |  |  | TF15JR | Delivered | 2026-10-08 | 2026-10-27 |  | 26126728 Out 2026-10-12 |  | 53.61 | 1018.59 | start 2026-10-08 but docket out 2026-10-12
13 | VMS10 | SUB-17093 | 120T |  |  | Delivered | 2026-10-08 | 2026-10-27 |  | 26115373 Out 2026-10-08 |  | 53.61 | 1018.59 | our record lacks the fleet number 120T
15 | VMS11 | SUB-17093 | 467T | 467T | TE97G | Delivered | 2026-10-16 | 2026-10-26 |  | 26129008 Out 2026-10-16 |  | 53.61 | 536.1
16 | VMS12 | 1211646 |  |  | TF59LR | Delivered | 2026-10-16 | 2026-10-26 |  | 26129024 Out 2026-10-19 |  | 53.61 | 589.71 | start 2026-10-16 but docket out 2026-10-19
24 | VMS18 | SUB-2631 | 472T | 472T | TE58GZ | Delivered | 2026-10-19 | 2026-10-26 |  | 26133749 Out 2026-10-19 |  | 53.61 | 375.27
25 | VMS19 | SUB-2631 | 487T | 487T | TE02H0 | Delivered | 2026-10-19 | 2026-10-26 |  | 26133749 Out 2026-10-19 |  | 53.61 | 375.27
26 | VMS20 | SUB-2631 | 475T | 475T | TE88HN | Delivered | 2026-10-19 | 2026-10-26 |  | 26133759 Out 2026-10-19 |  | 53.61 | 375.27
28 | VMS21 | SUB-2631 |  | 97T | T16922 | Delivered | 2026-10-22 | 2026-10-26 |  | 26143911 Out 2026-10-22; 26143911 Out 2026-10-22 | 2026-10-22 | 53.61 | 214.44 | fix: add fleet 97T (rego T16922) to the line
29 | VMS22 | SUB-2631 | 445T | 445T | TE99CL | Delivered | 2026-10-21 | 2026-10-28 |  | 26143911 Out 2026-10-22; 26143911 Out 2026-10-22 | 2026-10-21 | 53.61 | 375.27 | start 2026-10-21 but docket out 2026-10-22
30 | VMS23 | SUB-2631 | 453T | 453T | TF54CQ | Delivered | 2026-10-19 | 2026-10-26 |  | 26133759 Out 2026-10-19 |  | 53.61 | 375.27
31 | VMS24 | SUB-1101 | 450T | 450T | TE94CL | Delivered | 2026-10-19 | 2026-10-26 |  | 26143911 Out 2026-10-22; 26143911 Out 2026-10-22 | 2026-10-21 | 53.61 | 428.88 | start 2026-10-19 but docket out 2026-10-22
32 | VMS13 | 1191957 |  |  | EN3803 | Delivered | 2026-10-19 | 2026-10-27 |  | 26134263 Out 2026-10-16 |  | 53.61 | 482.49 | start 2026-10-19 but docket out 2026-10-16
34 | VMS14 | 1201864 |  |  | TD98VJ | Delivered | 2026-10-19 | 2026-10-27 |  | 26134263 Out 2026-10-16 |  | 53.61 | 482.49 | start 2026-10-19 but docket out 2026-10-16
35 | VMS15 | 1211348 |  |  | ER9217 | Delivered | 2026-10-19 | 2026-10-27 |  | 26134263 Out 2026-10-16 |  | 53.61 | 482.49 | start 2026-10-19 but docket out 2026-10-16
37 | VMS16 | 1211376 |  |  | ES3211 | Delivered | 2026-10-19 | 2026-10-27 |  | 26134314 Out 2026-10-19 |  | 53.61 | 482.49
39 | VMS17 | 1211364 |  |  | ER9410 | Delivered | 2026-10-19 | 2026-10-27 |  | 26134314 Out 2026-10-19 |  | 53.61 | 482.49
43 | VMS05a | 1211356 |  |  | ER9244 | Delivered | 2026-10-20 | 2026-10-21 |  | 26141143 Out 2026-10-20 |  | 53.61 | 107.22

## Charged before done
Contract | Line | What | Baseplan $ (prebill) | Done now $ | Not done yet $ | Basis
9968862 | 133 | Install & Demob package | 29512.35 | 22954.05 | 6558.3 | demob $145.74 a building is in the package; no building is demobbed yet
9968862 | 134-135 | Building transport, both legs | 50400 | 25200 | 25200 | half is the return leg; nothing has gone back yet
9968955 | 141 | Pumpout Service FWF & Accessable | 49405.86 | 0 | 49405.86 | services over the three race nights; none done at 22 Oct - the count is the tracker ticks after each night
9968955 | 142 | Pumpout Service Tank Mounts | 14990.4 | 0 | 14990.4 | services over the three race nights; none done at 22 Oct - the count is the tracker ticks after each night
9968955 | 143 | Cleaning & Restock Sewer Connect | 6246 | 0 | 6246 | services over the three race nights; none done at 22 Oct - the count is the tracker ticks after each night
9968955 | 144 | Install Demob Toilet Blocks | 9660.48 | 4830.24 | 4830.24 | install done, demob not
9968955 | 145 | Labour Charge Accessable Install & Demob | 707.92 | 353.96 | 353.96 | install done, demob not
9968955 | 146 | Labour Charge FWF Install & Demob | 16179.36 | 8089.68 | 8089.68 | install done, demob not
9968955 | 147 | Transport Charge Blocks & 16 Pan | 16000 | 8000 | 8000 | delivery leg done, return leg not
9968955 | 148 | Transport Charge Accessable Toilets | 4000 | 2000 | 2000 | delivery leg done, return leg not
9968955 | 149 | Transport Charge FWF | 21090 | 10545 | 10545 | delivery leg done, return leg not
9961265 | 41 | Transport Charge | 7200 | 3600 | 3600 | delivery legs done, return legs not
9994996 | 1 | Labour Charge WFB Install & Removal | 7700 | 0 | 7700 | pending from 2026-10-23; the work is from 23 Oct
9994996 | 2 | Transport Charge WFB Delivery & Removal | 17900 | 0 | 17900 | pending from 2026-10-23; the work is from 23 Oct
9994954 | 2 | Cleaning Fee | 214.3 | 0 | 214.3 | pending from 2026-10-23; the work is from 23 Oct
9994954 | 5 | Install & Demob | 1967.49 | 0 | 1967.49 | pending from 2026-10-23; the work is from 23 Oct
9994954 | 6 | Transport Charge | 3000 | 0 | 3000 | pending from 2026-10-23; the work is from 23 Oct

## Access & plant
Source | Date | What it says
Baseplan 9961976 line 21 | 2026-09-11 | Delivered ¦ 1197839 ¦ COATES Forklift 3.0t Container Diesel ¦ qty 1 ¦ rate 0 ¦ to 2026-10-26 ¦ prebill 0 ¦ refs on record ['FL02', 'T0004']
Baseplan 9961976 line 25 | 2026-09-11 | Returned ¦ 1247787 ¦ COATES Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD ¦ qty 1 ¦ rate 0 ¦ to 2026-10-26 ¦ prebill 0 ¦ refs on record ['T0005']
Baseplan 9961976 line 26 | 2026-09-11 | Delivered ¦ 1312577 ¦ COATES Forklift Rough Terrain 4WD With Rotator 2.5t Diesel ¦ qty 1 ¦ rate 0 ¦ to 2026-10-26 ¦ prebill 0 ¦ refs on record ['T0005']
Baseplan 9961976 line 31 | 2026-09-11 | Delivered ¦ MISCITEM ¦ COATES- 5T FORKLIFT 1.8TYNNES ¦ qty 1 ¦ rate 0 ¦ to 2026-10-26 ¦ prebill 0 ¦ refs on record []
Docket 26056641 (9961976) | 2026-09-11 | Out ¦ MISCITEM ¦ COATES- 5T FORKLIFT 1.8TYNNES ¦ charged 0
Docket 26056701 (9961976) | 2026-09-11 | Out ¦ 1197839 ¦ COATES Forklift 3.0t Container Diesel ¦ charged 0
Record plant line T0003 | 2026-09-11 | Forklift 5T · Phillip Park ¦ assets [] ¦ events [('2026-09-11', 'place', 1, 'Phillip Park'), ('2026-11-13', 'remove', 1, 'Phillip Park')] ¦ rental [('9961976', 31, 'MISCITEM', 'same day and kind')]
Record plant line T0004 | 2026-09-11 | Forklift 2.5T · Phillip Park ¦ assets ['1197839'] ¦ events [('2026-09-11', 'place', 1, 'Phillip Park'), ('2026-11-13', 'remove', 1, 'Phillip Park')] ¦ rental [('9961976', 21, '1197839', 'same asset number')]
Schedule 13 · Week 6 | 2026-09-11 | Access ¦ Forklift 5T ¦ 1 ¦ Phillip Park ¦ Long Tines ¦ Coates B4 LUNCH ¦ rehire qld fork lifts ¦ 26056641 ¦ IRWINS ¦ 1 x Irwins drop deck to collect both
Schedule 13 · Week 6 | 2026-09-11 | Access ¦ Forklift 2.5T ¦ 1 ¦ Phillip Park ¦ Coates B4 LUNCH ¦ 1197839 ¦ 26056701 ¦ IRWINS ¦ 1 x Irwins drop deck to collect both ¦ $646.32+
Docket 26058104 (9961976) | 2026-09-14 | Out ¦ 1247787 ¦ COATES Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD ¦ charged 0
Docket 26058119 (9961976) | 2026-09-14 | Out ¦ 1312577 ¦ COATES Forklift Rough Terrain 4WD With Rotator 2.5t Diesel ¦ charged 0
Record plant line T0005 | 2026-09-14 | Forklift 2.5T RT × 2 · Macintosh ¦ assets ['1247787', '1312577'] ¦ events [('2026-09-14', 'place', 2, 'Macintosh'), ('2026-11-13', 'remove', 2, 'Macintosh')] ¦ rental [('9961976', 25, '1247787', 'same asset number'), ('9961976', 26, '1312577', 'same asset number'), ('9961976', 35, '1247787', 'same asset number')]
Schedule 13 · Week 5 | 2026-09-14 | Access ¦ Forklift 2.5T RT ¦ 2 ¦ Macintosh ¦ Coates ¦ 1247787-1312577 ¦ 26058104(4.1T)-26058119 (5.7T) ¦ 0700 OR 0730 ¦ IRWINS DROP DECK ¦ $646.32+
Baseplan 9961976 line 34 | 2026-09-17 | Delivered ¦ MISCITEM ¦ AT009 Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD ¦ qty 1 ¦ rate 0 ¦ to 2026-09-18 ¦ prebill 0 ¦ refs on record []
Docket 26083924 (9961976) | 2026-09-17 | Out ¦ MISCITEM ¦ AT009 Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD ¦ charged 0
Docket 26083950 (9961976) | 2026-09-18 | In ¦ 1247787 ¦ COATES Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD ¦ charged 0
Baseplan 9987005 line 1 | 2026-10-05 | Delivered ¦ 1272166 ¦ Supply Forklift 5.0t Diesel ¦ qty 1 ¦ rate 150 ¦ to 2026-10-28 ¦ prebill 3600 ¦ refs on record ['T0085']
Baseplan 9987005 line 2 | 2026-10-05 | Delivered ¦ 1262224 ¦ Supply Telehandler Fork Extension 1800mm ¦ qty 1 ¦ rate 20 ¦ to 2026-10-28 ¦ prebill 480 ¦ refs on record []
Baseplan 9987005 line 3 | 2026-10-05 | Pending ¦ TRANSPORT ¦ Transport Charge ¦ qty 4 ¦ rate 500 ¦ to 2026-10-30 ¦ prebill 2000 ¦ refs on record []
Docket 26116726 (9987005) | 2026-10-06 | Out ¦ 1272166 ¦ Supply Forklift 5.0t Diesel ¦ charged 0
Record plant line T0085 | 2026-10-06 | 3.5T Forklift Std · Supply ¦ assets ['1272166'] ¦ events [('2026-10-06', 'place', 1, 'Supply')] ¦ rental [('9987005', 1, '1272166', 'same asset number')]
Schedule 13 · Week 2 | 2026-10-06 | Access ¦ 3.5T Forklift Std ¦ 1 ¦ Supply ¦ 1.8m Extensions ¦ scars ¦ 1210921ex eags -SL 1262224 ex mead ¦ 26109954
Record plant line T0109 | 2026-10-12 | 2.5T Forklift STD · Events ¦ assets ['1214298'] ¦ events [('2026-10-12', 'place', 1, 'Events')] ¦ rental []
Schedule 13 · Week 1 | 2026-10-12 | Access ¦ 2.5T Forklift STD ¦ 1 ¦ Events ¦ scars ¦ 1274555 STRP plus forklift tynes. ¦ 26120976 STRP & 26122181 EAGS ¦ mat ¦ na
Baseplan 9987005 line 7 | 2026-10-13 | Delivered ¦ 1281615 ¦ Forklift Rough Terrain 2.5t 4WD Diesel ¦ qty 1 ¦ rate 185.4 ¦ to 2026-10-27 ¦ prebill 2595.6 ¦ refs on record ['T0109']
Docket 26122181 (9987005) | 2026-10-13 | Out ¦ 1262224 ¦ Supply Telehandler Fork Extension 1800mm ¦ charged 0
Docket 26127228 (9987005) | 2026-10-13 | Out ¦ 1281615 ¦ Forklift Rough Terrain 2.5t 4WD Diesel ¦ charged 0
Schedule 13 · Week 1 | 2026-10-13 | Access ¦ 2.5T Forklift RT ¦ 1 ¦ Events ¦ scars ¦ 1281615 ¦ 26127228 & p/up 26127277 ¦ irwins ¦ $290+
Baseplan 9987005 line 8 | 2026-10-16 | Delivered ¦ 1065384 ¦ Laserplane ¦ qty 1 ¦ rate 0 ¦ to 2026-10-17 ¦ prebill 0 ¦ refs on record []
Docket 26133345 (9992300) | 2026-10-16 | Out ¦ 1321364 ¦ Forklift Rough Terrain 5.0t 4WD Diesel ¦ charged 0
Docket 26133361 (9992300) | 2026-10-16 | Out ¦ MISCITEM ¦ Fork Extensions 2.4m ¦ charged 0
Docket 26133373 (9992300) | 2026-10-16 | Out ¦ 1298390 ¦ Forklift Rough Terrain 2.5t 4WD Diesel ¦ charged 0
Docket 26135873 (9987005) | 2026-10-16 | Out ¦ 1065384 ¦ Laserplane ¦ charged 0
Schedule 13 · Week 1 | 2026-10-16 | Access ¦ 5t RT Forklift ¦ 1 ¦ with slippers ¦ Broadcast ¦ 26133345 ROCL & Slippers 26133361 ¦ sfl ¦ $290+
Schedule 13 · Week 1 | 2026-10-16 | Access ¦ 2.5T RT Forklift ¦ 1 ¦ Broadcast ¦ 26133373 TING ¦ sfl ¦ $290+
Baseplan 9992300 line 1 | 2026-10-17 | Delivered ¦ 1321364 ¦ Forklift Rough Terrain 5.0t 4WD Diesel ¦ qty 1900-01-01T00:00:00 ¦ rate 268.06 ¦ to 2026-10-27 ¦ prebill 2948.66 ¦ refs on record ['FL03']
Baseplan 9992300 line 10 | 2026-10-17 | Pending ¦ TRANSPORT ¦ Transport Charge 60' Boom ¦ qty 2 ¦ rate 500 ¦ to None ¦ prebill 1000 ¦ refs on record []
Baseplan 9992300 line 11 | 2026-10-17 | Delivered ¦ TRANSPORT ¦ Transport Charge Trakmat ¦ qty 2 ¦ rate 176.97 ¦ to None ¦ prebill 353.94 ¦ refs on record []
Baseplan 9992300 line 2 | 2026-10-17 | Delivered ¦ 1298390 ¦ Forklift Rough Terrain 2.5t 4WD Diesel ¦ qty 1900-01-01T00:00:00 ¦ rate 123.31 ¦ to 2026-10-27 ¦ prebill 1356.41 ¦ refs on record ['FL04']
Baseplan 9992300 line 3 | 2026-10-17 | Delivered ¦ MISCITEM ¦ Fork Extensions 2.4m ¦ qty 1900-01-01T00:00:00 ¦ rate 24.6 ¦ to 2026-10-27 ¦ prebill 270.6 ¦ refs on record []
Baseplan 9992300 line 7 | 2026-10-17 | Delivered ¦ TRANSPORT ¦ Transport Charge 5T Forklift ¦ qty 2 ¦ rate 500 ¦ to None ¦ prebill 1000 ¦ refs on record []
Baseplan 9992300 line 8 | 2026-10-17 | Delivered ¦ TRANSPORT ¦ Transport Charge 2.5T Forklift ¦ qty 2 ¦ rate 500 ¦ to None ¦ prebill 1000 ¦ refs on record []
Baseplan 9992300 line 9 | 2026-10-17 | Delivered ¦ TRANSPORT ¦ Transport Charge 43' Scissorlift ¦ qty 2 ¦ rate 500 ¦ to None ¦ prebill 1000 ¦ refs on record []
Baseplan 9961976 line 35 | 2026-10-19 | Delivered ¦ 1247787 ¦ COATES-Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD ¦ qty 1 ¦ rate 0 ¦ to 2026-10-28 ¦ prebill 0 ¦ refs on record ['T0005']
Baseplan 9961976 line 37 | 2026-10-19 | Delivered ¦ 1302007 ¦ COATES-Forklift Tyne Rotator ¦ qty 1 ¦ rate 0 ¦ to 2026-10-28 ¦ prebill 0 ¦ refs on record ['T0005']
Baseplan 9992300 line 13 | 2026-10-19 | Pending ¦ TRANSPORT ¦ Transport Charge 60' Straight ¦ qty 2 ¦ rate 500 ¦ to None ¦ prebill 1000 ¦ refs on record []
Baseplan 9992300 line 4 | 2026-10-19 | Delivered ¦ 1220903 ¦ Scissor Lift With Operator Protection 43ft (13.0M) - Diesel ¦ qty 1900-01-01T00:00:00 ¦ rate 209.08 ¦ to 2026-10-26 ¦ prebill 1672.64 ¦ refs on record ['EQ0001']
Docket 26133817 (9992300) | 2026-10-19 | Out ¦ 1220903 ¦ Scissor Lift With Operator Protection 43ft (13.0M) - Diesel ¦ charged 0
Schedule 13 · Event Week | 2026-10-19 | access ¦ Scissor Lift ¦ 1 ¦ 43' Diesle Scissor ¦ Broadcast ¦ 1220903 ¦ 26133817 ¦ 800 ¦ irwins
Docket 26142467 (9961976) | 2026-10-20 | Out ¦ 1247787 ¦ COATES-Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD ¦ charged 0
Docket 26142971 (9961976) | 2026-10-20 | Out ¦ 1302007 ¦ COATES-Forklift Tyne Rotator ¦ charged 0
Schedule 13 · Event Week | 2026-10-20 | access ¦ forklift 2.5t RT ¦ 1 ¦ forklift 2.5t RT ¦ Broadcast ¦ Swap over ¦ del 26142467 & Ret
Baseplan 9961976 line 27 | 2026-10-21 | Pending ¦ 1210921 ¦ SUPPLY-Forklift 3.5t Diesel ¦ qty 1 ¦ rate 0 ¦ to 2026-10-26 ¦ prebill 0 ¦ refs on record ['EQ0004']
Baseplan 9992300 line 12 | 2026-10-21 | Delivered ¦ 1286482 ¦ Straight Boom Lift 60ft - Diesel ¦ qty 1 ¦ rate 310.95 ¦ to 2026-10-27 ¦ prebill 2176.65 ¦ refs on record ['EQ0003']
Baseplan 9992300 line 5 | 2026-10-21 | Delivered ¦ 1300290 ¦ Knuckle Boom 61ft (18.6M) - Diesel ¦ qty 1900-01-01T00:00:00 ¦ rate 310.95 ¦ to 2026-10-26 ¦ prebill 1865.7 ¦ refs on record ['EQ0002']
Docket 26141428 (9992300) | 2026-10-21 | Out ¦ 1300290 ¦ Knuckle Boom 61ft (18.6M) - Diesel ¦ charged 0
Docket 26141448 (9992300) | 2026-10-21 | Out ¦ 1286482 ¦ Straight Boom Lift 60ft - Diesel ¦ charged 0
Schedule 13 · Event Week | 2026-10-21 | access ¦ Knuckle Boom ¦ 1 ¦ 60' Knuckle ¦ Broadcast ¦ 1300290 ¦ 26141428 ¦ 730 ¦ mark
Schedule 13 · Event Week | 2026-10-21 | access ¦ Straight Boom ¦ 1 ¦ 60' Straight ¦ Broadcast ¦ 1286482 ¦ 26141448 ¦ 830 ¦ sfl
Schedule 13 · Demob Week 3 | 2026-11-13 | Access ¦ Forklift 5T ¦ 1 ¦ Phillip Park ¦ Long Tines ¦ Coates
Schedule 13 · Demob Week 3 | 2026-11-13 | Access ¦ Forklift 2.5T ¦ 1 ¦ Phillip Park ¦ Coates
Schedule 13 · Demob Week 3 | 2026-11-13 | Access ¦ Forklift 2.5T RT ¦ 2 ¦ Macintosh ¦ Coates

## New lines since 16 Oct
Contract | Line | Status | Item | Description | Qty | Price | Rate 1 | Prebill | Start | Expected term
9973977 | 2 | Delivered | LABOUR | Install & Demob | 1 | 603.78 |  | 603.78 | 2026-10-19 | None
9973977 | 3 | Delivered | TRANSPORT | Transport Charge | 2 | 500 |  | 1000 | 2026-10-19 | None
9968955 | 141 | Pending | PUMPOUT | Pumpout Service FWF & Accessable | 678 | 72.87 |  | 49405.86 | 2026-10-18 | None
9968955 | 142 | Pending | PUMPOUT | Pumpout Service Tank Mounts | 24 | 624.6 |  | 14990.4 | 2026-10-18 | None
9968955 | 143 | Pending | CLEAN | Cleaning & Restock Sewer Connect | 24 | 260.25 |  | 6246 | 2026-10-18 | None
9968955 | 144 | Pending | LABOUR | Install Demob Toilet Blocks | 16 | 603.78 |  | 9660.48 | 2026-10-18 | None
9968955 | 145 | Pending | LABOUR | Labour Charge Accessable Install & Demob | 8 | 88.49 |  | 707.92 | 2026-10-18 | None
9968955 | 146 | Pending | LABOUR | Labour Charge FWF Install & Demob | 444 | 36.44 |  | 16179.36 | 2026-10-18 | None
9968955 | 147 | Pending | TRANSPORT | Transport Charge Blocks & 16 Pan | 32 | 500 |  | 16000 | 2026-10-18 | None
9968955 | 148 | Pending | TRANSPORT | Transport Charge Accessable Toilets | 8 | 500 |  | 4000 | 2026-10-18 | None
9968955 | 149 | Pending | TRANSPORT | Transport Charge FWF | 444 | 47.5 |  | 21090 | 2026-10-18 | None
9968955 | 150 | Delivered | MISC | Pallets Toilet Consumables Paper | 4 | 0 |  | 0 | 2026-10-19 | None
9968929 | 8 | Pending | 1328965 | Spare Air Conditioner - 1hp - 2hp | 1 | 0 | 0 | 0 | 2026-10-21 | 2026-10-22
9968929 | 9 | Pending | 1327125 | Spare Air Conditioner - 1hp - 2hp | 1 | 0 | 0 | 0 | 2026-10-21 | 2026-10-22
9968929 | 10 | Pending | 1326268 | Spare Air Conditioner - 1hp - 2hp | 1 | 0 | 0 | 0 | 2026-10-21 | 2026-10-22
9968929 | 11 | Pending | 1284004 | Spare Refrigerator - Medium | 1 | 0 | 0 | 0 | 2026-10-21 | 2026-10-22
9968929 | 12 | Pending | 1254847 | Spare Refrigerator - Medium | 1 | 0 | 0 | 0 | 2026-10-21 | 2026-10-22
9968862 | 136 | Delivered | MISC | Site Shift for Supply | 1 | 500 |  | 500 | 2026-10-19 | None
9968862 | 137 | Del Req | MISCITEM | Stillage Fire Extinguishers | 1 | 0 | 0 | 0 | 2026-09-14 | 2026-11-13
9968862 | 138 | Quoted | Delivery | Delivery for Line Item(s) * 20 Oct 2026 | 1 | 107.43 |  | 107.43 | 2026-10-20 | None
9974042 | None | [6 empty] | 9974042 | None | None
9961976 | 51 | Pending | LABOUR | Labour Charge | 11 | 291.48 |  | 3206.28 | 2026-10-19 | None
9961976 | 52 | Pending | LABOUR | Labour Charge | 4 | 333.12 |  | 1332.48 | 2026-10-19 | None
9961976 | 53 | Pending | TRANSPORT | Transport Charge | 10 | 300 |  | 3000 | 2026-10-19 | None
9961976 | 54 | Pending | TRANSPORT | Transport Charge | 14 | 450 |  | 6300 | 2026-10-19 | None
9961976 | 55 | Pending | TRANSPORT | Transport Charge | 6 | 600 |  | 3600 | 2026-10-19 | None
9961265 | 40 | Pending | LABOUR | Labour Charge | 24 | 176.97 |  | 4247.28 | 2026-10-19 | None
9961265 | 41 | Pending | TRANSPORT | Transport Charge | 48 | 150 |  | 7200 | 2026-10-19 | None
9961265 | 42 | Pending | TRANSPORT | Transport Charge Site Shifts | 8 | 150 |  | 1200 | 2026-10-19 | None
9961265 | 43 | Delivered | 1211356 | VMS05a Variable Message Board Senior | 1 | 0 | 53.61 | 107.22 | 2026-10-20 | 2026-10-21
9961265 | 44 | Applied | Delivery | Delivery for HA Line Item(s) 43 20 Oct 2026 | 1 | 289.52 |  | 289.52 | 2026-10-20 | None
9973079 | 3 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 20 | 0 | 5.05 | 707 | 2026-10-16 | 2026-10-17
9973079 | 4 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 25 | 0 | 5.05 | 883.75 | 2026-10-19 | 2026-10-20
9973079 | 5 | Delivered | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 12 | 0 | 5.05 | 424.2 | 2026-10-19 | 2026-10-20
9973079 | 6 | Pending | TRANSPORT | Transport Charge | 1 | 150 |  | 150 | 2026-10-19 | None
9973079 | 7 | Pending | TRANSPORT | Transport Charge | 1 | 275 |  | 275 | 2026-10-19 | None
9973079 | 8 | Pending | TRANSPORT | Transport Charge | 1 | 275 |  | 275 | 2026-10-19 | None
9992300 | 13 | Pending | TRANSPORT | Transport Charge 60' Straight | 2 | 500 |  | 1000 | 2026-10-19 | None
9994248 | 1 | Pending |  | Temporary Fence 1.8m (per Meter) | 35 | 0 | 17.5 | 612.5 | 2026-10-20 | 2026-10-26
9994248 | 2 | Pending |  | Barrier - Crowd Control (per Meter) | 45 | 0 | 14 | 630 | 2026-10-20 | 2026-10-26
9994248 | 3 | Del Req | CHAIRSSTACKING | Chairs Stacking | 24 | 0 | 2.2 | 52.8 | 2026-10-20 | 2026-10-26
9994248 | 4 | Quoted | DELIVERY | Delivery for Line Item(s) 3,4 19 Oct 2026 | 1 | 250 |  | 250 | 2026-10-20 | None
9994248 | 5 | Quoted | PICKUP CHARGE | Pickup | 1 | 250 |  | 250 | 2026-10-20 | None
9994996 | 1 | Pending | LABOUR | Labour Charge WFB Install & Removal | 1 | 7700 |  | 7700 | 2026-10-23 | 2026-11-06
9994996 | 2 | Pending | TRANSPORT | Transport Charge WFB Delivery & Removal | 1 | 17900 |  | 17900 | 2026-10-23 | 2026-11-06
9994954 | 1 | Pending |  | Portable Building Shell 6.0M x 3.0M | 1 | 0 | 17.78 | 53.34 | 2026-10-23 | 2026-10-26
9994954 | 2 | Pending | CLEAN7 | Cleaning Fee | 1 | 214.3 |  | 214.3 | 2026-10-23 | None
9994954 | 3 | Pending |  | Portable Building Shell 6.0M x 3.0M | 1 | 0 | 17.78 | 53.34 | 2026-10-23 | 2026-10-26
9994954 | 4 | Pending |  | Portable Building Shell 6.0M x 3.0M | 1 | 0 | 17.78 | 53.34 | 2026-10-23 | 2026-10-26
9994954 | 5 | Pending | LABOUR | Install & Demob | 3 | 655.83 |  | 1967.49 | 2026-10-23 | None
9994954 | 6 | Pending | TRANSPORT | Transport Charge | 6 | 500 |  | 3000 | 2026-10-23 | None
9994954 | 7 | Pending |  | Refrigerator - Large | 1 | 0 | 2.33 | 97.86 | 2026-10-23 | 2026-10-26
9994954 | 8 | Pending |  | Refrigerator - Large | 1 | 0 | 2.33 | 97.86 | 2026-10-23 | 2026-10-26
9994954 | 9 | Pending |  | Refrigerator - Large | 1 | 0 | 2.33 | 97.86 | 2026-10-23 | 2026-10-26
9994954 | 10 | Pending |  | Generator - 200kVA (Diesel) | 1 | 0 | 489.85 | 1469.55 | 2026-10-23 | 2026-10-26
9994954 | 11 | Pending |  | Generator - 200kVA (Diesel) | 1 | 0 | 489.85 | 1469.55 | 2026-10-23 | 2026-10-26

## Changed lines since 16 Oct
Contract | Line | Description | What changed
9987005 | 3 | Transport Charge | Quantity: 2 -> 4
9968862 | 123 | P26 Refrigerator - Large | Delivery Number: None -> 26141713; Serial Number: None -> 2402200050; Item: None -> 1311992; Status: Pending -> Delivered
9968862 | 124 | P28 Refrigerator - Large | Delivery Number: None -> 26141713; Serial Number: None -> 1130128; Item: None -> 1283996; Status: Pending -> Delivered
9968862 | 125 | P34 Chair Padded | Delivery Number: None -> 26141713; Status: Pending -> Delivered
9968862 | 132 | P46 Refrigerator | Delivery Number: None -> 26141713; Status: Pending -> Delivered
9968862 | 133 | Install & Demob | Item: INSTDISMEXTNL -> LABOUR; Description: Installation & Dismantling Charge -> Install & Demob
9961976 | 6 | GN20-S01-Generator 365kVA Diesel | Expected Offrental Time: None -> 08:00:00
9961976 | 7 | GN19-Generator - Diesel - 80kVA DEL AS 60KVA | Status: Del Req -> Delivered; Expected Offrental Time: None -> 08:00:00
9961976 | 9 | GN23-Generator - Sync - Hardwire Only 150kVA Diesel | Expected Offrental Time: None -> 08:00:00
9961976 | 11 | GN18-Generator - 60kVA (Diesel) | Expected Offrental Time: None -> 08:00:00
9961976 | 14 | GN04-Generator - 30kVA (Diesel) | Return Docket Number: None -> 26146441; Status: Del Req -> Off Rent; Expected Offrental Time: None -> 08:00:00; Term Date: None -> 2026-10-26T00:00:00; Term Time: None -> 09:00:00; Term Number: None -> 21961977
9961976 | 15 | G10- Generator - 60kVA (Diesel) | Delivery Number: None -> 26138802; Status: Pending -> Delivered; Expected Offrental Time: None -> 08:00:00
9961976 | 16 | GN01-Generator - 60kVA (Diesel) | Expected Offrental Time: None -> 08:00:00
9961976 | 18 | GN25-Generator - 20kVA (Diesel) | Status: Del Req -> Delivered; Expected Offrental Time: None -> 08:00:00
9961976 | 19 | LT05/06-Lighting Tower POD Metro | Delivery Number: None -> 26139060; Status: Pending -> Delivered; Expected Offrental Time: None -> 08:00:00
9961976 | 20 | LT05/06-Lighting Tower POD Metro | Delivery Number: None -> 26139060; Status: Pending -> Delivered; Expected Offrental Time: None -> 08:00:00
9961976 | 35 | COATES-Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD | Delivery Number: None -> 26142467; Status: Pending -> Delivered; Expected Offrental Time: None -> 08:00:00; Booked Delivery Date: 2026-10-19T00:00:00 -> 2026-10-20T00:00:00
9961976 | 37 | COATES-Forklift Tyne Rotator | Delivery Number: None -> 26142971; Status: Pending -> Delivered; Booked Delivery Date: 2026-10-19T00:00:00 -> 2026-10-20T00:00:00
9961976 | 38 | GN21-Generator - 60kVA (Diesel) | Expected Offrental Time: None -> 08:00:00
9961976 | 42 | GN26 CONCERT Generator - 200kVA (Diesel) | Expected Offrental Time: None -> 08:00:00
9961976 | 43 | GN27 CONCERT-Generator - 200kVA (Diesel) | Expected Offrental Time: None -> 08:00:00
9961976 | 44 | GN13 Generator - 60kVA (Diesel) DEL AS 45KVA | Expected Offrental Time: None -> 08:00:00
9961976 | 46 | Cable - Set of 5 to suit 200KVA | Expected Offrental Time: None -> 08:00:00
9961976 | 47 | Cable - 120mm2 Single Double Insulated | Expected Offrental Time: None -> 08:00:00
9961976 | 48 | GN06 Generator - 60kVA (Diesel) | Expected Offrental Time: None -> 08:00:00
9961976 | 49 | GN24-Generator - 60kVA (Diesel) - Trailer Mounted | Return Docket Number: None -> 26146567; Status: Del Req -> Off Rent; Expected Offrental Time: None -> 08:00:00; Term Date: None -> 2026-10-26T00:00:00; Term Time: None -> 09:00:00; Term Number: None -> 21962074
9961976 | 50 | Delivery for HA Line Item(s) 7,14,50 19 Oct 2026 | Status: Quoted -> Applied; Description: Delivery for Line Item(s) 7,14 15 Oct 2026 -> Delivery for HA Line Item(s) 7,14,50 19 Oct 2026
9972648 | 1 | WB01 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Return Docket Number: None -> 26142360; Status: Delivered -> Off Rent; Term Date: None -> 2026-10-29T00:00:00; Term Time: None -> 18:00:00; Term Number: None -> 21958966; Booked Pickup Date: 2026-10-27T00:00:00 -> 2026-10-29T00:00:00
9972648 | 2 | WB03 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Return Docket Number: None -> 26142331; Status: Delivered -> Off Rent; Term Date: None -> 2026-10-29T00:00:00; Term Time: None -> 18:00:00; Term Number: None -> 21958949
9972648 | 4 | WB05 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Return Docket Number: None -> 26141344; Status: Delivered -> Off Rent; Term Date: None -> 2026-10-27T00:00:00; Term Time: None -> 18:00:00; Term Number: None -> 21958159
9972648 | 6 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Return Docket Number: None -> 26141201; Status: Delivered -> Off Rent; Term Date: None -> 2026-10-27T00:00:00; Term Time: None -> 18:00:00; Term Number: None -> 21958023
9972648 | 9 | WB14 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Delivery Number: None -> 26141397; Status: Pending -> Delivered
9972648 | 10 | WB15 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Delivery Number: None -> 26141397; Status: Pending -> Delivered
9972648 | 11 | WB16 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Delivery Number: None -> 26141411; Status: Pending -> Delivered
9972648 | 12 | WB17 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Delivery Number: None -> 26141598; Status: Pending -> Del Req
9972648 | 13 | WB18 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Delivery Number: None -> 26141598; Status: Pending -> Del Req
9972648 | 16 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Return Docket Number: None -> 26141217; Status: Delivered -> Off Rent; Term Date: None -> 2026-10-27T00:00:00; Term Time: None -> 18:00:00; Term Number: None -> 21958037
9972648 | 17 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Return Docket Number: None -> 26141235; Status: Delivered -> Off Rent; Term Date: None -> 2026-10-27T00:00:00; Term Time: None -> 18:00:00; Term Number: None -> 21958057
9961265 | 13 | VMS10 120T Variable Message Board Senior Premiair | Description: VMS10 Variable Message Board Senior Premiair -> VMS10 120T Variable Message Board Senior Premiair
9961265 | 15 | VMS11 467T Variable Message Board - Premiair | Status: Del Req -> Delivered; Description: VMS11 Variable Message Board - Premiair -> VMS11 467T Variable Message Board - Premiair
9961265 | 16 | VMS12 Variable Message Board Junior | Status: Del Req -> Delivered; Expected Offrental Time: 07:00:00 -> None; Rate ID: 128709 -> 128767
9961265 | 24 | VMS18 472T Variable Message Board Senior Premiair | Status: Del Req -> Delivered; Description: VMS18 Variable Message Board Senior Premiair -> VMS18 472T Variable Message Board Senior Premiair
9961265 | 25 | VMS19 487T Variable Message Board Senior Premiair | Status: Del Req -> Delivered; Description: VMS19 Variable Message Board Senior Premiair -> VMS19 487T Variable Message Board Senior Premiair
9961265 | 26 | VMS20 475T Variable Message Board Senior Premiair | Status: Del Req -> Delivered; Description: VMS20 Variable Message Board Senior Premiair -> VMS20 475T Variable Message Board Senior Premiair
9961265 | 28 | VMS21 Variable Message Board Senior Premiair | Delivery Number: None -> 26143911; Status: Pending -> Delivered
9961265 | 29 | VMS22 445T Variable Message Board Senior Premiair | Delivery Number: None -> 26143911; Status: Pending -> Delivered; Description: VMS22 Variable Message Board Senior Premiair -> VMS22 445T Variable Message Board Senior Premiair; Booked Delivery Date: 2026-10-21T00:00:00 -> 2026-10-22T00:00:00
9961265 | 30 | VMS23 453T Variable Message Board Senior Premiair | Status: Del Req -> Delivered; Description: VMS23 Variable Message Board Senior Premiair -> VMS23 453T Variable Message Board Senior Premiair
9961265 | 31 | VMS24 450T Variable Message Board Senior | Delivery Number: None -> 26143911; Status: Pending -> Delivered; Description: VMS24 Variable Message Board Senior -> VMS24 450T Variable Message Board Senior; Booked Delivery Date: 2026-10-19T00:00:00 -> 2026-10-22T00:00:00
9961265 | 32 | VMS13 Variable Message Board Senior | Status: Del Req -> Delivered; Booked Delivery Date: 2026-10-19T00:00:00 -> 2026-10-16T00:00:00
9961265 | 34 | VMS14 Variable Message Board Junior | Status: Del Req -> Delivered; Booked Delivery Date: 2026-10-19T00:00:00 -> 2026-10-16T00:00:00
9961265 | 35 | VMS15 Variable Message Board Senior | Status: Del Req -> Delivered; Booked Delivery Date: 2026-10-19T00:00:00 -> 2026-10-16T00:00:00
9961265 | 37 | VMS16 Variable Message Board Senior | Status: Del Req -> Delivered; Booked Delivery Date: 2026-10-19T00:00:00 -> 2026-10-16T00:00:00
9961265 | 39 | VMS17 Variable Message Board Senior | Status: Del Req -> Delivered; Booked Delivery Date: 2026-10-19T00:00:00 -> 2026-10-16T00:00:00
9992300 | 1 | Forklift Rough Terrain 5.0t 4WD Diesel | Quantity: 1 -> 1900-01-01T00:00:00
9992300 | 2 | Forklift Rough Terrain 2.5t 4WD Diesel | Quantity: 1 -> 1900-01-01T00:00:00
9992300 | 3 | Fork Extensions 2.4m | Quantity: 1 -> 1900-01-01T00:00:00
9992300 | 4 | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | Status: Del Req -> Delivered; Quantity: 1 -> 1900-01-01T00:00:00
9992300 | 5 | Knuckle Boom 61ft (18.6M) - Diesel | Delivery Number: None -> 26141428; Status: Pending -> Delivered; Quantity: 1 -> 1900-01-01T00:00:00
9992300 | 6 | Trakmat | Quantity: 10 -> 1900-01-10T00:00:00
9992300 | 7 | Transport Charge 5T Forklift | Delivery Number: None -> 26140202; Status: Pending -> Delivered
9992300 | 8 | Transport Charge 2.5T Forklift | Delivery Number: None -> 26140202; Status: Pending -> Delivered
9992300 | 9 | Transport Charge 43' Scissorlift | Delivery Number: None -> 26140202; Status: Pending -> Delivered
9992300 | 11 | Transport Charge Trakmat | Delivery Number: None -> 26140202; Status: Pending -> Delivered
9992300 | 12 | Straight Boom Lift 60ft - Diesel | Delivery Number: None -> 26141448; Status: Pending -> Delivered; Rate 1: 459.55 -> 310.95; Rate 2: 345.42 -> 0
9990776 | 1 | WB13 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | Delivery Number: None -> 26138423; Status: Pending -> Delivered
9990776 | 10 | Shade Cloth | Price: 2775 -> 9.37; Quantity: 9.37 -> 2775
9968955 | 138 | Steps Toilet Block | LINE REMOVED
9968955 | 139 | Steps Toilet Block | LINE REMOVED
9961976 | 17 | GN-24 Generator - Diesel - 80kVA | LINE REMOVED
9973079 | 2 | Delivery for HA Line Item(s) 1,2 15 Sep 2026 | LINE REMOVED

## Dockets since 16 Oct
Contract | Docket | Date | Direction | Fleet item | Description | Charged | Suburb
9961265 | 26115373 | 2026-10-08 | Out | sub-17093 | VMS10 120T Variable Message Board Senior Premiair | 0 | MAIN BEACH
9961265 | 26129008 | 2026-10-16 | Out | SUB-17093 | VMS11 467T Variable Message Board - Premiair | 0 | MAIN BEACH
9961265 | 26129024 | 2026-10-19 | Out | 1211646 | VMS12 Variable Message Board Junior | 0 | MAIN BEACH
9961265 | 26133749 | 2026-10-19 | Out | SUB-2631 | VMS18 472T Variable Message Board Senior Premiair | 0 | MAIN BEACH
9961265 | 26133749 | 2026-10-19 | Out | SUB-2631 | VMS19 487T Variable Message Board Senior Premiair | 0 | MAIN BEACH
9961265 | 26133759 | 2026-10-19 | Out | SUB-2631 | VMS20 475T Variable Message Board Senior Premiair | 0 | MAIN BEACH
9961265 | 26133759 | 2026-10-19 | Out | SUB-2631 | VMS23 453T Variable Message Board Senior Premiair | 0 | MAIN BEACH
9961265 | 26134263 | 2026-10-16 | Out | 1191957 | VMS13 Variable Message Board Senior | 0 | MAIN BEACH
9961265 | 26134263 | 2026-10-16 | Out | 1201864 | VMS14 Variable Message Board Junior | 0 | MAIN BEACH
9961265 | 26134263 | 2026-10-16 | Out | 1211348 | VMS15 Variable Message Board Senior | 0 | MAIN BEACH
9961265 | 26134314 | 2026-10-19 | Out | 1211376 | VMS16 Variable Message Board Senior | 0 | MAIN BEACH
9961265 | 26134314 | 2026-10-19 | Out | 1211364 | VMS17 Variable Message Board Senior | 0 | MAIN BEACH
9961265 | 26141143 | 2026-10-20 | Out | 1211356 | VMS05a Variable Message Board Senior | 289.52 | MAIN BEACH
9961265 | 26143911 | 2026-10-22 | Out | SUB-2631 | VMS21 Variable Message Board Senior Premiair | 0 | MAIN BEACH
9961265 | 26143911 | 2026-10-22 | Out | SUB-2631 | VMS22 445T Variable Message Board Senior Premiair | 0 | MAIN BEACH
9961265 | 26143911 | 2026-10-22 | Out | SUB-1101 | VMS24 450T Variable Message Board Senior | 0 | MAIN BEACH
9961265 | 26143911 | 2026-10-22 | Out | SUB-2631 | VMS21 Variable Message Board Senior Premiair | 0 | MAIN BEACH
9961265 | 26143911 | 2026-10-22 | Out | SUB-2631 | VMS22 445T Variable Message Board Senior Premiair | 0 | MAIN BEACH
9961265 | 26143911 | 2026-10-22 | Out | SUB-1101 | VMS24 450T Variable Message Board Senior | 0 | MAIN BEACH
9961976 | 26130091 | 2026-10-16 | Out | 1320828 | GN06 Generator - 60kVA (Diesel) | 0 | SURFERS PARADISE
9961976 | 26133589 | 2026-10-19 | Out | 1276416 | GN19-Generator - Diesel - 80kVA DEL AS 60KVA | 359.8 | MAIN BEACH
9961976 | 26133589 | 2026-10-19 | Out | 1277400 | GN04-Generator - 30kVA (Diesel) | 359.8 | MAIN BEACH
9961976 | 26134440 | 2026-10-19 | Out | 1277089 | GN24-Generator - 60kVA (Diesel) - Trailer Mounted | 0 | SURFERS PARADISE
9961976 | 26134523 | 2026-10-19 | Out | 1244536 | GN25-Generator - 20kVA (Diesel) | 0 | SOUTHPORT
9961976 | 26138802 | 2026-10-19 | Out | 1283681 | G10- Generator - 60kVA (Diesel) | 0 | MAIN BEACH
9961976 | 26139060 | 2026-10-20 | Out | 1224783 | LT05/06-Lighting Tower POD Metro | 0 | SOUTHPORT
9961976 | 26139060 | 2026-10-20 | Out | 1224791 | LT05/06-Lighting Tower POD Metro | 0 | SOUTHPORT
9961976 | 26142467 | 2026-10-20 | Out | 1247787 | COATES-Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD | 0 | MAIN BEACH
9961976 | 26142971 | 2026-10-20 | Out | 1302007 | COATES-Forklift Tyne Rotator | 0 | SURFERS PARADISE
9968862 | 26141713 | 2026-10-20 | Out | 1311992 | P26 Refrigerator - Large | 0 | MAIN BEACH
9968862 | 26141713 | 2026-10-20 | Out | 1283996 | P28 Refrigerator - Large | 0 | MAIN BEACH
9968862 | 26141713 | 2026-10-20 | Out | CHAIRPADDED | P34 Chair Padded | 0 | MAIN BEACH
9968862 | 26141713 | 2026-10-20 | Out | 1272751 | P46 Refrigerator | 0 | MAIN BEACH
9968955 | 26106375 | 2026-10-12 | Out | 1328980 | WC60 Sewage Holding Tank 6.0M x 2.4M | 0 | MAIN BEACH
9968955 | 26106388 | 2026-10-12 | Out | 1328981 | WC60 Sewage Holding Tank 6.0M x 2.4M | 0 | MAIN BEACH
9972648 | 26129840 | 2026-10-16 | Out | ARMORZONMASHTL2 | WB05 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 0 | MAIN BEACH
9972648 | 26129861 | 2026-10-16 | Out | ARMORZONMASHTL2 | WB04 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 0 | MAIN BEACH
9972648 | 26141397 | 2026-10-21 | Out | ARMORZONMASHTL2 | WB14 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 0 | MAIN BEACH
9972648 | 26141397 | 2026-10-21 | Out | ARMORZONMASHTL2 | WB15 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 0 | MAIN BEACH
9972648 | 26141411 | 2026-10-21 | Out | ARMORZONMASHTL2 | WB16 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 0 | MAIN BEACH
9972648 | 26141598 | 2026-10-22 | Out | ARMORZONMASHTL2 | WB17 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 0 | MAIN BEACH
9972648 | 26141598 | 2026-10-22 | Out | ARMORZONMASHTL2 | WB18 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 0 | MAIN BEACH
9973079 | 26136797 | 2026-10-19 | Out | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 0 | MAIN BEACH
9973079 | 26139242 | 2026-10-19 | Out | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 0 | MAIN BEACH
9973079 | 26139258 | 2026-10-19 | Out | TRAKMAT2.4X1.1 | Trakmat - 2.4M x 1.1M - TM4496 | 0 | MAIN BEACH
9987005 | 26135873 | 2026-10-16 | Out | 1065384 | Laserplane | 0 | MAIN BEACH
9990776 | 26138423 | 2026-10-19 | Out | ARMORZONMASHTL2 | WB13 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 0 | MAIN BEACH
9992300 | 26133345 | 2026-10-16 | Out | 1321364 | Forklift Rough Terrain 5.0t 4WD Diesel | 0 | MAIN BEACH
9992300 | 26133361 | 2026-10-16 | Out | MISCITEM | Fork Extensions 2.4m | 0 | MAIN BEACH
9992300 | 26133373 | 2026-10-16 | Out | 1298390 | Forklift Rough Terrain 2.5t 4WD Diesel | 0 | MAIN BEACH
9992300 | 26133383 | 2026-10-16 | Out | MISCITEM | Trakmat | 0 | MAIN BEACH
9992300 | 26133817 | 2026-10-19 | Out | 1220903 | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | 0 | MAIN BEACH
9992300 | 26141428 | 2026-10-21 | Out | 1300290 | Knuckle Boom 61ft (18.6M) - Diesel | 0 | MAIN BEACH
9992300 | 26141448 | 2026-10-21 | Out | 1286482 | Straight Boom Lift 60ft - Diesel | 0 | MAIN BEACH