## 9961265 by board
Line | Board | Baseplan item | Baseplan fleet | Our fleet | Our rego | Baseplan start | Docket out | Our on-site day | Our basis | Baseplan expected term | Days to 22 Oct (ours) | Hire to 22 Oct | Race days 23-25 Oct | Hire to 25 Oct (min 7 days) | Baseplan prebill | Baseplan days billed | Install (done) | Demob (at demob) | Delivery leg (done) | Pickup leg (at demob) | Fix needed on Baseplan / question
1 | Senior (returned) | 1211404 |  |  |  | 2026-09-07 | 2026-09-07 |  | returned 2026-09-22 | 2026-11-13 |  |  |  |  | 857.76 | 16 |  |  |  |  | returned: Baseplan term 2026-09-22 (16 days billed), but the return docket 26126700 is dated 2026-10-12, the same morning 1211404 went out again as VMS09 (line 12). Was the board off site from 2026-09-22, or on site all along? If on site, 20 days (23 Sep - 12 Oct) are unbilled
3 | Variable Message Board Senio | 1211370 |  |  | ES3206 | 2026-09-07 | 2026-09-07 | 2026-09-07 | the eight boards of 7 Sep (docket 26053081 and following; Timeline load T0001) | 2026-11-13 | 46 | 2466.13 | 3 | 2626.96 | 3591.87 | 67 | 88.485 | 88.485 | 150 | 150
4 | Variable Message Board Senio | 1211354 |  |  | EX0017 | 2026-09-07 | 2026-09-07 | 2026-09-07 | the eight boards of 7 Sep (docket 26053081 and following; Timeline load T0001) | 2026-11-13 | 46 | 2466.13 | 3 | 2626.96 | 3591.87 | 67 | 88.485 | 88.485 | 150 | 150
5 | Variable Message Board Senio | 1182999 |  |  | 410UFQ | 2026-09-07 | 2026-09-07 | 2026-09-07 | the eight boards of 7 Sep (docket 26053081 and following; Timeline load T0001) | 2026-11-13 | 46 | 2466.13 | 3 | 2626.96 | 3591.87 | 67 | 88.485 | 88.485 | 150 | 150
6 | Variable Message Board Senio | 1191877 |  |  | EM6306 | 2026-09-07 | 2026-09-07 | 2026-09-07 | the eight boards of 7 Sep (docket 26053081 and following; Timeline load T0001) | 2026-11-13 | 46 | 2466.13 | 3 | 2626.96 | 3591.87 | 67 | 88.485 | 88.485 | 150 | 150
7 | Variable Message Board Senio | 1211359 |  |  | ER9247 | 2026-09-07 | 2026-09-07, 2026-09-07 | 2026-09-07 | the eight boards of 7 Sep (docket 26053081 and following; Timeline load T0001) | 2026-11-13 | 46 | 2466.13 | 3 | 2626.96 | 3591.87 | 67 | 88.485 | 88.485 | 150 | 150
8 | Variable Message Board Senio | 1211383 |  |  | ER9381 | 2026-09-07 | 2026-09-07, 2026-09-07 | 2026-09-07 | the eight boards of 7 Sep (docket 26053081 and following; Timeline load T0001) | 2026-11-13 | 46 | 2466.13 | 3 | 2626.96 | 3591.87 | 67 | 88.485 | 88.485 | 150 | 150
9 | Variable Message Board - Col | 1271129 |  |  | 536UOO | 2026-09-07 | 2026-09-07, 2026-09-07 | 2026-09-07 | the eight boards of 7 Sep (docket 26053081 and following; Timeline load T0001) | 2026-11-13 | 46 | 2466.13 | 3 | 2626.96 | 3591.87 | 67 | 88.485 | 88.485 | 150 | 150
12 | VMS09 | 1211404 |  |  | TF15JR | 2026-10-08 | 2026-10-12 | 2026-10-08 | Andrew's word on the page: on site 2026-10-08 | 2026-10-27 | 15 | 804.17 | 3 | 965.01 | 1018.59 | 19 | 88.485 | 88.485 | 150 | 150 | docket out 2026-10-12 differs from our day 2026-10-08
13 | VMS10 | SUB-17093 | 120T | 120T | V14221 | 2026-10-08 | 2026-10-08 | 2026-10-08 | Andrew's word on the page: on site 2026-10-08 | 2026-10-27 | 15 | 804.17 | 3 | 965.01 | 1018.59 | 19 | 88.485 | 88.485 | 150 | 150
15 | VMS11 | SUB-17093 | 467T | 467T | TE97G | 2026-10-16 | 2026-10-16 | 2026-10-16 | recorded on site 2026-10-16 by Andrew Fisher (on Timeline load T0128, 2026-10-16) | 2026-10-26 | 7 | 375.28 | 3 | 536.12 | 536.1 | 10 | 88.485 | 88.485 | 150 | 150
16 | VMS12 | 1211646 |  |  | TF59LR | 2026-10-16 | 2026-10-19 | 2026-10-16 | recorded on site 2026-10-16 by Andrew Fisher (on Timeline load T0128, 2026-10-16) | 2026-10-26 | 7 | 375.28 | 3 | 536.12 | 589.71 | 11 | 88.485 | 88.485 | 150 | 150 | docket out 2026-10-19 differs from our day 2026-10-16
24 | VMS18 | SUB-2631 | 472T | 472T | TE58GZ | 2026-10-19 | 2026-10-19 | 2026-10-19 | recorded on site 2026-10-19 by Andrew Fisher (on Timeline load T0158, 2026-10-19) | 2026-10-26 | 4 | 214.45 | 3 | 375.28 | 375.27 | 7 | 88.485 | 88.485 | 150 | 150
25 | VMS19 | SUB-2631 | 487T | 487T | TE02H0 | 2026-10-19 | 2026-10-19 | 2026-10-19 | recorded on site 2026-10-19 by Andrew Fisher (on Timeline load T0158, 2026-10-19) | 2026-10-26 | 4 | 214.45 | 3 | 375.28 | 375.27 | 7 | 88.485 | 88.485 | 150 | 150
26 | VMS20 | SUB-2631 | 475T | 475T | TE88HN | 2026-10-19 | 2026-10-19 | 2026-10-19 | recorded on site 2026-10-19 by Andrew Fisher (on Timeline load T0158, 2026-10-19) | 2026-10-26 | 4 | 214.45 | 3 | 375.28 | 375.27 | 7 | 88.485 | 88.485 | 150 | 150
28 | VMS21 | SUB-2631 |  | 97T | T16922 | 2026-10-22 | 2026-10-22, 2026-10-22 | 2026-10-22 | arrival on the record | 2026-10-26 | 1 | 53.61 | 3 | 375.28 | 214.44 | 4 | 88.485 | 88.485 | 150 | 150 | add fleet 97T (rego T16922) to the line; billed 4 days (22-25 Oct) with no 7-day minimum, while VMS18-20 and 23 are billed the 7-day minimum - one rule or the other
29 | VMS22 | SUB-2631 | 445T | 445T | TE99CL | 2026-10-21 | 2026-10-22, 2026-10-22 | 2026-10-22 | Andrew, 22 Oct: today's delivery (docket 26143911); our record said 21 Oct and is to be corrected | 2026-10-28 | 1 | 53.61 | 3 | 375.28 | 375.27 | 7 | 88.485 | 88.485 | 150 | 150 | start 2026-10-21 -> 2026-10-22 (Baseplan 1 day(s) over)
30 | VMS23 | SUB-2631 | 453T | 453T | TF54CQ | 2026-10-19 | 2026-10-19 | 2026-10-19 | recorded on site 2026-10-19 by Andrew Fisher (on Timeline load T0158, 2026-10-19) | 2026-10-26 | 4 | 214.45 | 3 | 375.28 | 375.27 | 7 | 88.485 | 88.485 | 150 | 150
31 | VMS24 | SUB-1101 | 450T | 450T | TE94CL | 2026-10-19 | 2026-10-22, 2026-10-22 | 2026-10-22 | Andrew, 22 Oct: today's delivery (docket 26143911); our record said 21 Oct and is to be corrected | 2026-10-26 | 1 | 53.61 | 3 | 375.28 | 428.88 | 8 | 88.485 | 88.485 | 150 | 150 | start 2026-10-19 -> 2026-10-22 (Baseplan 3 day(s) over)
32 | VMS13 | 1191957 |  |  | EN3803 | 2026-10-19 | 2026-10-16 | 2026-10-19 | recorded on site 2026-10-19 by Andrew Fisher (on Timeline load T0158, 2026-10-19) | 2026-10-27 | 4 | 214.45 | 3 | 375.28 | 482.49 | 9 | 88.485 | 88.485 | 150 | 150 | docket out 2026-10-16 differs from our day 2026-10-19; VMS14 and VMS15 on the same docket (26134263, 16 Oct) were recorded on site 16 Oct; VMS13 was recorded 19 Oct - confirm 16 Oct with Andrew, then start 16 Oct
34 | VMS14 | 1201864 |  |  | TD98VJ | 2026-10-19 | 2026-10-16 | 2026-10-16 | recorded on site 2026-10-16 by Andrew Fisher (on Timeline load T0158, 2026-10-19) | 2026-10-27 | 7 | 375.28 | 3 | 536.12 | 482.49 | 9 | 88.485 | 88.485 | 150 | 150 | start 2026-10-19 -> 2026-10-16 (Baseplan 3 day(s) short)
35 | VMS15 | 1211348 |  |  | ER9217 | 2026-10-19 | 2026-10-16 | 2026-10-16 | recorded on site 2026-10-16 by Andrew Fisher (on Timeline load T0158, 2026-10-19) | 2026-10-27 | 7 | 375.28 | 3 | 536.12 | 482.49 | 9 | 88.485 | 88.485 | 150 | 150 | start 2026-10-19 -> 2026-10-16 (Baseplan 3 day(s) short)
37 | VMS16 | 1211376 |  |  | ES3211 | 2026-10-19 | 2026-10-19 | 2026-10-16 | recorded on site 2026-10-16 by Andrew Fisher (on Timeline load T0158, 2026-10-19) | 2026-10-27 | 7 | 375.28 | 3 | 536.12 | 482.49 | 9 | 88.485 | 88.485 | 150 | 150 | start 2026-10-19 -> 2026-10-16 (Baseplan 3 day(s) short); docket out 2026-10-19 differs from our day 2026-10-16; recorded on site 16 Oct 12:09 AEST by Andrew; the docket is 19 Oct - confirm with Andrew before the branch moves the start
39 | VMS17 | 1211364 |  |  | ER9410 | 2026-10-19 | 2026-10-19 | 2026-10-16 | recorded on site 2026-10-16 by Andrew Fisher (on Timeline load T0158, 2026-10-19) | 2026-10-27 | 7 | 375.28 | 3 | 536.12 | 482.49 | 9 | 88.485 | 88.485 | 150 | 150 | start 2026-10-19 -> 2026-10-16 (Baseplan 3 day(s) short); docket out 2026-10-19 differs from our day 2026-10-16; recorded on site 16 Oct 12:09 AEST by Andrew; the docket is 19 Oct - confirm with Andrew before the branch moves the start
43 | VMS05a | 1211356 |  |  | ER9244 | 2026-10-20 | 2026-10-20 | 2026-10-20 | recorded on site 2026-10-20 by Andrew Fisher (on Timeline load T0001, 2026-09-07) | 2026-10-21 | 3 | 160.83 | 3 | 375.28 | 107.22 | 2 | 88.485 | 88.485 | 150 | 150 | our register has 1211356 (rego ER9244) as the board at position 05a, pinned by Andrew 20 Oct 10:08 AEST, docket 26141143 the same morning, still on site: the line stays on hire to demob, so the 21 Oct term is wrong. The $289.52 delivery differs from the $150 a leg on line 41 - one rate or the other
TOTAL | 24 boards | [9 empty] | 420 | 22516.84 |  | 26912.98 | 33345.42 |  | 2123.64 | 2123.64 | 3600 | 3600

## 9961265 charge lines
Line | Baseplan line | Baseplan qty | Rate | Baseplan $ | Correct qty | Correct $ | Billable now $ | Later $ | Basis
40 | Labour Charge | 24 | 176.97 | 4247.28 | 24 | 4247.28 | 2123.64 | 2123.64 | 24 boards x $176.97 (the card's one VMS labour figure, read as $88.49 install + $88.49 demob). Install done on every board on site; demob at demob. Baseplan charges the whole $176.97 before demob
41 | Transport Charge | 48 | 150 | 7200 | 48 | 7200 | 3600 | 3600 | 24 boards x 2 legs at Baseplan's $150 (the card says POA for VMS transport - the $150 is Baseplan's figure, to be confirmed). Delivery legs done; pickup legs at demob
42 | Transport Charge Site Shifts | 8 | 150 | 1200 | 2 | 300 | 300 | 0 | site shifts at $150: our record shows two relocations pinned on site (VMS05 -> 05a and VMS07 -> 07a, 20 Oct). 02a and 03a are not yet pinned. Baseplan's 8 shifts are not evidenced on our record - confirm the count with Andrew
44 | Delivery for HA Line Item(s) 43 20 Oct 2026 | 1 | 289.52 | 289.52 | 0 | 0 | 0 | 0 | delivery for line 43 (VMS05a) at $289.52: every other VMS leg is $150 on this contract; if 1211356 is the relocated VMS05 this is a site shift (line 42), not a delivery
TOTAL |  |  |  | 12936.8 |  | 11747.28 | 6023.64 | 5723.64

## Notes
Author: Andrew Fisher. 22 Oct 2026. Our on-site day is the record: the board's own arrival event where it has one, else the day Andrew recorded the board on site (AEST), with the Timeline load it is recorded on beside it. Andrew's word today puts VMS22 and VMS24 on 22 Oct (docket 26143911).
Rates: 2026 street card, ex GST. VMS Board $53.6115 a day from the day it goes in (the project manager's rule: VMS is charged from delivery), minimum 7 days on the card's traffic-management block. Labour $176.97 a board (the card's 2024 figure, read as $88.49 install + $88.49 demob). Transport: POA on the card; $150 a leg is Baseplan's figure.
Hire to 22 Oct is what has run; race days 23-25 Oct are shown but not yet run; boards stay on hire to demob, so the hire to 25 Oct is not the final figure. Baseplan prebills to each line's expected term (13 Nov for the 7 Sep boards), which is why its prebill is higher on those.
Rows shaded red need a Baseplan fix (last column); amber rows are questions for Andrew or our own record.