## 9968955 by reference
Ref | Servicing area | Baseplan lines | FWF on site | FWF Baseplan | Accessible on site | Accessible Baseplan | Blocks on site (sewer + tank-mounted) | Blocks Baseplan | Tanks on site | Tanks Baseplan | 16-pan on site | 16-pan Baseplan | Coates numbers on site not on Baseplan | Baseplan numbers not on site | Fix needed on Baseplan
BJR01 | 1 Pit Lane, Paddock & Teams |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 1
PG01 | 1 Pit Lane, Paddock & Teams |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 1
PG03 | 1 Pit Lane, Paddock & Teams |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 1
PG05 | 1 Pit Lane, Paddock & Teams |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 1
PG29 | 1 Pit Lane, Paddock & Teams |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 1
SPASHDOWN | 9 Main Beach Seaside — Mid-South |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SVP01 | 1 Pit Lane, Paddock & Teams |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 1
T0024 | 3 Island West — EVL, Race Admin & Merch |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1211968 |  | FWF 0 -> 2
T0162 | 1 Pit Lane, Paddock & Teams |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 1
T0176 | 1 Pit Lane, Paddock & Teams |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 2
WC01 | 4 Commodore Park & The Hill entry | 46, 57, 69, 140 | 2 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 172824 | FWF 3 -> 2; number(s) not on site: 172824
WC02 | 4 Commodore Park & The Hill entry | 45 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC04 | 3 Island West — EVL, Race Admin & Merch | 44 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC05 | 3 Island West — EVL, Race Admin & Merch | 1, 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
WC06 | 3 Island West — EVL, Race Admin & Merch | 15, 58 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC07 | 3 Island West — EVL, Race Admin & Merch | 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40, 41, 42, 43 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317743 | 1317643 | number(s) not on site: 1317643; number(s) missing: 1317743
WC09 | 5 Median Strip — FOAM | 102, 103, 105 | 10 | 10 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
WC10 | 5 Median Strip — FOAM | 114 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC11 | 3 Island West — EVL, Race Admin & Merch | 6, 23 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC12 | 1 Pit Lane, Paddock & Teams | 4, 5, 17 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1211963 |  | FWF 3 -> 4; number(s) missing: 1211963
WC13 | 9 Main Beach Seaside — Mid-South | 122 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC15 | 1 Pit Lane, Paddock & Teams | 55, 56 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
WC16 | 1 Pit Lane, Paddock & Teams | 10, 11 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
WC17 | 1 Pit Lane, Paddock & Teams | 20, 21 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
WC19 | 2 Island North / Freight | 117 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC20 | 2 Island North / Freight | 47, 48, 49, 50 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0
WC21 | 2 Island North / Freight | 7, 8, 9, 14, 16, 18, 19 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1083399 | FWF 7 -> 6; number(s) not on site: 1083399
WC23 | 7 Main Beach Seaside — Supply / North | 119 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC24 | 9 Main Beach Seaside — Mid-South | 121 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC25 | 8 Main Beach Seaside — Mid | 118 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC26 | 7 Main Beach Seaside — Supply / North | 120 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC27 | 6 Main Beach Parade / Seaside North | 52, 54 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
WC28 | 5 Median Strip — FOAM | 123 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC29 | 5 Median Strip — FOAM | 124 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC30 | 11 Surfers Paradise / Cypress (north) | 125 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC31 | 4 Commodore Park & The Hill entry | 97, 98 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2
WC33 | 6 Main Beach Parade / Seaside North | 101 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC34 | 4 Commodore Park & The Hill entry | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC35 | 11 Surfers Paradise / Cypress (north) | 126 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC38 | 4 Commodore Park & The Hill entry | 88 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC39 | 4 Commodore Park & The Hill entry | 89 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC40 | 4 Commodore Park & The Hill entry | 90 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC41 | 3 Island West — EVL, Race Admin & Merch | 59 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC42 | 4 Commodore Park & The Hill entry |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 1
WC43 | 1 Pit Lane, Paddock & Teams | 70 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC44 | 2 Island North / Freight | 80, 81 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC45 | 8 Main Beach Seaside — Mid | 115 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC46 | 10 Main Beach Seaside — South | 127 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC47 | 8 Main Beach Seaside — Mid | 116 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC48 | 10 Main Beach Seaside — South | 109 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC49 | 10 Main Beach Seaside — South | 108 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC50 | 7 Main Beach Seaside — Supply / North | 22 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC51 | 10 Main Beach Seaside — South | 110, 111 | 6 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
WC53 | 10 Main Beach Seaside — South |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 3
WC54 | 9 Main Beach Seaside — Mid-South | 112 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC55 | 9 Main Beach Seaside — Mid-South | 128 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC56 | 7 Main Beach Seaside — Supply / North | 113 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC57 | 7 Main Beach Seaside — Supply / North | 107 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC59 | 7 Main Beach Seaside — Supply / North | 106 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC60 | 6 Main Beach Parade / Seaside North | 91, 93, 94, 95 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0
WC61 | 6 Main Beach Parade / Seaside North | 96 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC62 | 11 Surfers Paradise / Cypress (north) | 129 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC65 | 4 Commodore Park & The Hill entry | 130 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC67 | 12 Helen Park | 84 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172824 |  | FWF 2 -> 4
WC68 | 12 Helen Park | 131 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC69 | 12 Helen Park | 87 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC70 | 12 Helen Park | 85 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC71 | 12 Helen Park | 86 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC72 | 12 Helen Park | 132 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC73 | 1 Pit Lane, Paddock & Teams | 133 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC81 | 13 Cypress / Surfers Paradise Blvd |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FWF 0 -> 1
WC85 | 14 Coates Compound (Seaway) | 134 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC86 | 2 Island North / Freight | 51 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
WC100 | 0 No location yet | 12, 13 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 238 | 221 | 4 | 4 | 14 | 14 | 6 | 6 | 2 | 2 |  |  | 17 references to fix

## Labour & transport breakdown
Unit type | Units on site | Install | Steps | Levelling | Cleaning | Demob | Labour done now (install+steps+levelling+cleaning) x units | Demob at demob x units | Transport each way | Delivery legs (done) | Pickup legs (at demob)
FWF | 238 | 36.44 |  |  |  | 36.44 | 8672.72 | 8672.72 | 47.5 | 11305 | 11305
Accessible toilet | 4 | 88.49 |  |  |  | 88.49 | 353.96 | 353.96 | 500 | 2000 | 2000
Toilet block 6 m (8 sewer-connected, 6 tank-mounted) | 14 | 145.74 | 156.15 | 104.1 | 156.15 | 145.74 | 7869.96 | 2040.36 | 500 | 7000 | 7000
16-pan block | 2 | 145.74 |  | 104.1 | 156.15 | 145.74 | 811.98 | 291.48 | 500 | 1000 | 1000
Waste tank 6 m | 6 | 145.74 |  | 104.1 | 156.15 | 145.74 | 2435.94 | 874.44 | no card line | 0 | 0
Pee panel (WC09) | 6 | 145.74 |  | 104.1 | 156.15 | 145.74 | 2435.94 | 874.44 | no card line | 0 | 0
TOTAL | [6 empty] | 22580.5 | 13107.4 |  | 21305 | 21305
Rates are the 2026 card per unit, ex GST. Baseplan line 144 charges blocks at $603.78 (install, steps, cleaning, demob) and leaves out levelling $104.10; the card has levelling on every block line. Waste tanks and pee panels have no transport line on the card; Baseplan charges none. No steps on the 16-pan blocks (Andrew, 22 Oct). Pee panel labour is the street card row 22, as authorised 9 Oct.

## Servicing breakdown
Area | Ref | FWF | Accessible | 16-pan | Waste tanks | Sewer blocks | Tank-mounted blocks | Pump-outs a night (FWF + accessible) | Tank pump-outs a night (tanks + 16-pan) | Sewer cleans a night | Pump-outs x 3 nights $ | Tank pump-outs x 3 $ | Sewer cleans x 3 $ | Total 3 nights $
1 Pit Lane, Paddock & Teams | BJR01 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
1 Pit Lane, Paddock & Teams | PG01 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
1 Pit Lane, Paddock & Teams | PG03 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
1 Pit Lane, Paddock & Teams | PG05 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
1 Pit Lane, Paddock & Teams | PG29 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
1 Pit Lane, Paddock & Teams | SVP01 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
1 Pit Lane, Paddock & Teams | T0162 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
1 Pit Lane, Paddock & Teams | T0176 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
1 Pit Lane, Paddock & Teams | WC12 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 874.44 | 0 | 0 | 874.44
1 Pit Lane, Paddock & Teams | WC15 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1561.5 | 1561.5
1 Pit Lane, Paddock & Teams | WC16 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1561.5 | 1561.5
1 Pit Lane, Paddock & Teams | WC17 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1561.5 | 1561.5
1 Pit Lane, Paddock & Teams | WC43 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 2186.1 | 0 | 0 | 2186.1
1 Pit Lane, Paddock & Teams | WC73 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
1 Pit Lane, Paddock & Teams subtotal |  | 25 | 0 | 0 | 0 | 6 | 0 | 25 | 0 | 6 | 5465.25 | 0 | 4684.5 | 10149.75
2 Island North / Freight | WC19 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
2 Island North / Freight | WC20 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 3747.6 | 0 | 3747.6
2 Island North / Freight | WC21 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1311.66 | 0 | 0 | 1311.66
2 Island North / Freight | WC44 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
2 Island North / Freight | WC86 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
2 Island North / Freight subtotal |  | 9 | 1 | 0 | 2 | 0 | 2 | 10 | 2 | 0 | 2186.1 | 3747.6 | 0 | 5933.7
3 Island West — EVL, Race Admin & Merch | T0024 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
3 Island West — EVL, Race Admin & Merch | WC04 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
3 Island West — EVL, Race Admin & Merch | WC05 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1873.8 | 0 | 1873.8
3 Island West — EVL, Race Admin & Merch | WC06 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
3 Island West — EVL, Race Admin & Merch | WC07 | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 4372.2 | 0 | 0 | 4372.2
3 Island West — EVL, Race Admin & Merch | WC11 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
3 Island West — EVL, Race Admin & Merch | WC41 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 2186.1 | 0 | 0 | 2186.1
3 Island West — EVL, Race Admin & Merch subtotal |  | 37 | 0 | 0 | 1 | 0 | 1 | 37 | 1 | 0 | 8088.57 | 1873.8 | 0 | 9962.37
4 Commodore Park & The Hill entry | WC01 | 2 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 655.83 | 0 | 0 | 655.83
4 Commodore Park & The Hill entry | WC02 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
4 Commodore Park & The Hill entry | WC31 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 2 | 0 | 218.61 | 3747.6 | 0 | 3966.21
4 Commodore Park & The Hill entry | WC34 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
4 Commodore Park & The Hill entry | WC38 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
4 Commodore Park & The Hill entry | WC39 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
4 Commodore Park & The Hill entry | WC40 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1093.05 | 0 | 0 | 1093.05
4 Commodore Park & The Hill entry | WC42 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
4 Commodore Park & The Hill entry | WC65 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
4 Commodore Park & The Hill entry subtotal |  | 14 | 2 | 2 | 0 | 0 | 0 | 16 | 2 | 0 | 3497.76 | 3747.6 | 0 | 7245.36
5 Median Strip — FOAM | WC09 | 10 | 0 | 0 | 0 | 2 | 0 | 10 | 0 | 2 | 2186.1 | 0 | 1561.5 | 3747.6
5 Median Strip — FOAM | WC10 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 655.83 | 0 | 0 | 655.83
5 Median Strip — FOAM | WC28 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
5 Median Strip — FOAM | WC29 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1530.27 | 0 | 0 | 1530.27
5 Median Strip — FOAM subtotal |  | 21 | 0 | 0 | 0 | 2 | 0 | 21 | 0 | 2 | 4590.81 | 0 | 1561.5 | 6152.31
6 Main Beach Parade / Seaside North | WC27 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1873.8 | 0 | 1873.8
6 Main Beach Parade / Seaside North | WC33 | 17 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 3716.37 | 0 | 0 | 3716.37
6 Main Beach Parade / Seaside North | WC60 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 3747.6 | 0 | 3747.6
6 Main Beach Parade / Seaside North | WC61 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1748.88 | 0 | 0 | 1748.88
6 Main Beach Parade / Seaside North subtotal |  | 25 | 0 | 0 | 3 | 0 | 3 | 25 | 3 | 0 | 5465.25 | 5621.4 | 0 | 11086.65
7 Main Beach Seaside — Supply / North | WC23 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1093.05 | 0 | 0 | 1093.05
7 Main Beach Seaside — Supply / North | WC26 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
7 Main Beach Seaside — Supply / North | WC50 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
7 Main Beach Seaside — Supply / North | WC56 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 2623.32 | 0 | 0 | 2623.32
7 Main Beach Seaside — Supply / North | WC57 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
7 Main Beach Seaside — Supply / North | WC59 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1530.27 | 0 | 0 | 1530.27
7 Main Beach Seaside — Supply / North subtotal |  | 28 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 6121.08 | 0 | 0 | 6121.08
8 Main Beach Seaside — Mid | WC25 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
8 Main Beach Seaside — Mid | WC45 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1748.88 | 0 | 0 | 1748.88
8 Main Beach Seaside — Mid | WC47 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
8 Main Beach Seaside — Mid subtotal |  | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 2186.1 | 0 | 0 | 2186.1
9 Main Beach Seaside — Mid-South | SPASHDOWN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 Main Beach Seaside — Mid-South | WC13 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
9 Main Beach Seaside — Mid-South | WC24 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
9 Main Beach Seaside — Mid-South | WC54 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1311.66 | 0 | 0 | 1311.66
9 Main Beach Seaside — Mid-South | WC55 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
9 Main Beach Seaside — Mid-South subtotal |  | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 2186.1 | 0 | 0 | 2186.1
10 Main Beach Seaside — South | WC46 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
10 Main Beach Seaside — South | WC48 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 874.44 | 0 | 0 | 874.44
10 Main Beach Seaside — South | WC49 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 655.83 | 0 | 0 | 655.83
10 Main Beach Seaside — South | WC51 | 6 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1530.27 | 0 | 0 | 1530.27
10 Main Beach Seaside — South | WC53 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 655.83 | 0 | 0 | 655.83
10 Main Beach Seaside — South subtotal |  | 17 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 3934.98 | 0 | 0 | 3934.98
11 Surfers Paradise / Cypress (north) | WC30 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1748.88 | 0 | 0 | 1748.88
11 Surfers Paradise / Cypress (north) | WC35 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
11 Surfers Paradise / Cypress (north) | WC62 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
11 Surfers Paradise / Cypress (north) subtotal |  | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 2404.71 | 0 | 0 | 2404.71
12 Helen Park | WC67 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 874.44 | 0 | 0 | 874.44
12 Helen Park | WC68 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
12 Helen Park | WC69 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 2623.32 | 0 | 0 | 2623.32
12 Helen Park | WC70 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
12 Helen Park | WC71 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1748.88 | 0 | 0 | 1748.88
12 Helen Park | WC72 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
12 Helen Park subtotal |  | 27 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 5902.47 | 0 | 0 | 5902.47
13 Cypress / Surfers Paradise Blvd | WC81 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
13 Cypress / Surfers Paradise Blvd subtotal |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
14 Coates Compound (Seaway) | WC85 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
14 Coates Compound (Seaway) subtotal |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218.61 | 0 | 0 | 218.61
0 No location yet | WC100 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
0 No location yet subtotal |  | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 437.22 | 0 | 0 | 437.22
TOTAL |  | 238 | 4 | 2 | 6 | 8 | 6 | 242 | 8 | 8 | 52903.62 | 14990.4 | 6246 | 74140.02
Rates: pump-out FWF or accessible $72.87 a service, tank pump-out and clean $624.6, sewer-connect clean and restock $260.25. Three services a unit: Fri 23, Sat 24, Sun 25 Oct nights. The 16-pan blocks are pumped as tanks and cleaned with the pump-out. Tank-mounted blocks are cleaned under the tank pump-out. Invoice from the tracker ticks after each night.

## 9968955 charge lines
Line | Baseplan line | Baseplan qty | Rate | Baseplan $ | Correct qty | Correct $ | Billable now $ | Later $ | Basis
141 | Pumpout Service FWF & Accessable | 678 | 72.87 | 49405.86 | 726 | 52903.62 | 0 | 52903.62 | 238 FWF + 4 accessible on site = 242 units x 3 race nights (Fri, Sat, Sun). Nothing done yet; invoice from the tracker ticks after each night
142 | Pumpout Service Tank Mounts | 24 | 624.6 | 14990.4 | 24 | 14990.4 | 0 | 14990.4 | 6 waste tanks + 2 sixteen-pan blocks = 8 x 3 nights; agrees with Baseplan
143 | Cleaning & Restock Sewer Connect | 24 | 260.25 | 6246 | 24 | 6246 | 0 | 6246 | 8 sewer-connected blocks x 3 nights (the 6 tank-mounted blocks are cleaned under line 142); agrees with Baseplan
144 | Install Demob Toilet Blocks | 16 | 603.78 | 9660.48 | 16 | 9660.48 | 7328.64 | 2331.84 | 14 blocks + 2 sixteen-pan = 16; $603.78 is install + steps + cleaning + demob. Install, steps and cleaning done ($458.04 each); demob ($145.74) at demob
145 | Labour Charge Accessable Install & Demob | 8 | 88.49 | 707.92 | 8 | 707.92 | 353.96 | 353.96 | 4 accessible x 2 (install $88.49 done, demob $88.49 at demob)
146 | Labour Charge FWF Install & Demob | 444 | 36.44 | 16179.36 | 476 | 17345.44 | 8672.72 | 8672.72 | 238 FWF x 2 (install $36.44 done, demob $36.44 at demob)
147 | Transport Charge Blocks & 16 Pan | 32 | 500 | 16000 | 32 | 16000 | 8000 | 8000 | 16 blocks x 2 legs at $500; delivery done, return at demob
148 | Transport Charge Accessable Toilets | 8 | 500 | 4000 | 8 | 4000 | 2000 | 2000 | 4 accessible x 2 legs at $500; delivery done, return at demob
149 | Transport Charge FWF | 444 | 47.5 | 21090 | 476 | 22610 | 11305 | 11305 | 238 FWF x 2 legs at $47.50; delivery done, return at demob. Baseplan already charges the Event Portables units this way
TOTAL |  |  |  | 138280.02 |  | 144463.86 | 37660.32 | 106803.54

## Notes
Author: Andrew Fisher. 22 Oct 2026. Units on site are the servicing tracker (Andrew's 13 areas, read 19-20 Oct from the site), one row a reference.
Rates: 2026 card, ex GST. Pump-out FWF/accessible $72.87 a service; tank pump-out $624.60; sewer-connect clean & restock $260.25; block install & demob $603.78; accessible $88.49 a leg; FWF $36.44 a leg; transport $500 (blocks, accessible) and $47.50 (FWF) each way.
Services are the three race nights (Fri 23, Sat 24, Sun 25 Oct). None has happened yet: invoice them from the tracker ticks after each night, never in advance.
Rows shaded red need a Baseplan fix (named in the last column).