## TV order
Order item | Qty | Location | Delivery (order) | Pickup (order) | Baseplan | Finding | Proposed action
FORKLIFT with side shift (ALL TERRAIN) 2.5T | 1 | TV Compound | Sat 17 Oct 2026 08:00 | Tue 27 Oct 2026 14:00 | 9992300 line 2 · Del Req · 1298390 · booked 17 Oct · term 27 Oct · DD 26133373 | Matches. Note 9968726 line 1 (Pending, 19 Oct) names the same unit 1298390 — looks superseded; cancel one or it double-counts. | Confirm with Mead which contract stands; page has no TV compound forklift reference yet.
FORKLIFT with side shift (ALL TERRAIN) 5T | 1 | TV Compound | Sat 17 Oct 2026 08:00 | Tue 27 Oct 2026 14:00 | 9992300 line 1 · Del Req · 1321364 · booked 17 Oct · term 27 Oct · DD 26133345 | Matches. 9968726 line 7 (Pending, 19 Oct) names the same unit — superseded? | As above.
2.5m Tine Extenders | 1 | TV Compound | Sat 17 Oct 2026 08:00 | Tue 27 Oct 2026 14:00 | 9992300 line 3 · Del Req · MISCITEM Fork Extensions 2.4m · booked 17 Oct · DD 26133361 | Matches (2.4 m on the contract vs 2.5 m on the order). 9968726 line 9 SUB-2527 extension also pending. | Confirm length; one line only.
SCISSOR LIFT 13M | 1 | TV Compound | Mon 19 Oct 2026 08:00 | Mon 26 Oct 2026 14:00 | 9992300 line 4 · Del Req · 1220903 43ft · booked 17 Oct · term 26 Oct · DD 26133817 | Date differs: the order says Mon 19 Oct, the contract books Sat 17 Oct. | Move the booking to 19 Oct or confirm 17 Oct suits TV.
KNUCKLE - Camera 1 60FT | 1 | DL - End of Pit Lane | Wed 21 Oct 2026 08:00 | Mon 26 Oct 2026 08:00 | 9992300 line 5 · Pending · 1300290 61ft · booked 17 Oct · term 26 Oct (no DD yet) | Date differs: order Wed 21 Oct, contract 17 Oct; 9968726 line 3 had 21 Oct. Location on the order is end of pit lane, not TV compound. | Set the booking to 21 Oct, end of pit lane; raise the DD.
TRACK MATS | 10 | TV Compound | Sat 17 Oct 2026 08:00 | Tue 27 Oct 2026 14:00 | 9992300 line 6 · Del Req · MISCITEM Trakmat ×10 · booked 17 Oct · DD 26133383 | Matches. The existing 9973079 Trakmat ×20 (TM4496, delivered 15 Sep) is separate. | —
Large Fridge / Freezer | 2 | Garage | Tue 20 Oct 2026 11:00 | Tue 27 Oct 2026 14:00 | No contract line found in any Baseplan sheet | GAP: nothing on Baseplan and no page reference for two TV fridges in the garage. | Raise the lines (or confirm who supplies) and add a reference on the page.
Fencing Full Size | 144 | TV Compound | Mon 19 Oct 2026 09:00 | Mon 26 Oct 2026 09:00 | 9990776-STPS (new, all Pending, booked 19 Oct) carries the event fencing lines incl. Shade Cloth; no TV-specific quantity | Page fencing docket F012 (Advanced Temporary Fencing, 36512) already records S04 Corporate Facility / TV compound: 69 mesh panels. 144 panels on 19 Oct is a further fence. | Confirm with the fencing crew whether the 144 + shade cloth is the 19 Oct event fence or extra.
Shade Cloth Full Size | 144 | TV Compound | Mon 19 Oct 2026 09:00 | Mon 26 Oct 2026 09:00 | 9990776 line 10 · Pending · SHADECLOTH · booked 19 Oct | Quantity on the contract not TV-specific. | As above.
Toilet Sewer Combo 6x3 | 1 | TV Compound | Sat 17 Oct 2026 12:00 | Tue 27 Oct 2026 14:00 | 9973977-KINP line 1 · Delivered · 1311144 WCTV Toilet Block M/F 6m · booked 23 Sep · DD 26091446 · term 13 Nov | Baseplan says delivered 23 Sep; the page reference is T0243 "Toilet Block 6m · WC-TV (sewer connect)" — see record light in the README. | Check on site: if it is already in the TV compound the order line is satisfied; the order pickup 27 Oct vs contract term 13 Nov.

## Baseplan added
Contract | Line | Status | Item | Description | Qty | Booked delivery | Expected term | Delivery no | Record light
9987005 | 7 | Delivered | 1281615 | Forklift Rough Terrain 2.5t 4WD Diesel | 1 | 2026-10-13 | 2026-10-27 | 26127228
9968862 | 131 | Delivered | 107135 | P45 Portable Building Shell 6.0M x 3.0M | 1 | 2026-10-12 | 2026-11-13 | 26122823 | on site · complete
9968862 | 132 | Pending | 1272751 | P46 Refrigerator | 1 | 2026-09-14 | 2026-11-13 |  | on site · complete
9961976 | 44 | Delivered | 1276503 | GN13 Generator - 60kVA (Diesel) DEL AS 45KVA | 1 | 2026-10-12 | 2026-11-12 | 26123259 | on site · complete
9961976 | 45 | Pending | 1261271 | SPARE-Generator - 60kVA (Diesel) | 1 | 2026-10-15 | 2026-10-26
9961976 | 46 | Delivered |  | Cable - Set of 5 to suit 200KVA | 2 | 2026-10-12 | 2026-10-13 | 26127046
9961976 | 47 | Delivered | CABLESSDI120MM | Cable - 120mm2 Single Double Insulated | 10 | 2026-10-12 | 2026-10-13 | 26127046
9961976 | 48 | Del Req | 1320828 | GN06 Generator - 60kVA (Diesel) | 1 | 2026-10-19 | 2026-10-26 | 26130091 | on site · complete
9961976 | 49 | Del Req | 1277089 | GN24-Generator - 60kVA (Diesel) - Trailer Mounted | 1 | 2026-10-19 | 2026-10-26 | 26134440 | not on site
9961976 | 50 | Quoted | Delivery | Delivery for Line Item(s) 7,14 15 Oct 2026 | 1 |  |  | 26133589
9972648 | 16 | Delivered | ARMORZONMASHTL2 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 60 | 2026-10-15 | 2026-10-27 | 26126597 | not on site
9972648 | 17 | Delivered | ARMORZONMASHTL2 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 34 | 2026-10-15 | 2026-10-27 | 26126606 | not on site
9961265 | 31 | Pending | SUB-1101 | VMS24 Variable Message Board Senior | 1 | 2026-10-19 | 2026-10-26 |  | no record
9961265 | 32 | Del Req | 1191957 | VMS13 Variable Message Board Senior | 1 | 2026-10-19 | 2026-10-27 | 26134263 | no record
9961265 | 34 | Del Req | 1201864 | VMS14 Variable Message Board Junior | 1 | 2026-10-19 | 2026-10-27 | 26134263 | no record
9961265 | 35 | Del Req | 1211348 | VMS15 Variable Message Board Senior | 1 | 2026-10-19 | 2026-10-27 | 26134263 | no record
9961265 | 37 | Del Req | 1211376 | VMS16 Variable Message Board Senior | 1 | 2026-10-19 | 2026-10-27 | 26134314 | no record
9961265 | 39 | Del Req | 1211364 | VMS17 Variable Message Board Senior | 1 | 2026-10-19 | 2026-10-27 | 26134314 | no record
9992300 | 1 | Del Req | 1321364 | Forklift Rough Terrain 5.0t 4WD Diesel | 1 | 2026-10-17 | 2026-10-27 | 26133345
9992300 | 2 | Del Req | 1298390 | Forklift Rough Terrain 2.5t 4WD Diesel | 1 | 2026-10-17 | 2026-10-27 | 26133373
9992300 | 3 | Del Req | MISCITEM | Fork Extensions 2.4m | 1 | 2026-10-17 | 2026-10-27 | 26133361
9992300 | 4 | Del Req | 1220903 | Scissor Lift With Operator Protection 43ft (13.0M) - Diesel | 1 | 2026-10-17 | 2026-10-26 | 26133817
9992300 | 5 | Pending | 1300290 | Knuckle Boom 61ft (18.6M) - Diesel | 1 | 2026-10-17 | 2026-10-26
9992300 | 6 | Del Req | MISCITEM | Trakmat | 10 | 2026-10-17 | 2026-10-27 | 26133383
9992300 | 7 | Pending | TRANSPORT | Transport Charge 5T Forklift | 2
9992300 | 8 | Pending | TRANSPORT | Transport Charge 2.5T Forklift | 2
9992300 | 9 | Pending | TRANSPORT | Transport Charge 43' Scissorlift | 2
9992300 | 10 | Pending | TRANSPORT | Transport Charge 60' Boom | 2
9992300 | 11 | Pending | TRANSPORT | Transport Charge Trakmat | 2
9990776 | 1 | Pending | ARMORZONMASHTL2 | WB13 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | 10 | 2026-10-19 | 2026-10-26 |  | not on site
9990776 | 2 | Pending | TEMPFENCEFEETRH | Ped Gates | 32 | 2026-10-19 | 2026-10-26
9990776 | 3 | Pending | TEMPFENCEFEETRH | 1.8m Security Fence | 8778 | 2026-10-19 | 2026-10-26
9990776 | 4 | Pending | TEMPFENCEFEETRH | Fence Relocation | 1520 | 2026-10-19 | 2026-10-26
9990776 | 5 | Pending | TEMPFENCEFEETRH | 1.8m Security Fence w/ Hoarding | 110 | 2026-10-19 | 2026-10-26
9990776 | 6 | Pending | TEMPFENCEFEETRH | 1.8m Fence w/Scrim | 2775 | 2026-10-19 | 2026-10-26
9990776 | 7 | Pending | MISCITEM | Barrier - Crowd Control | 2350 | 2026-10-19 | 2026-10-26
9990776 | 8 | Pending | MISCITEM | Barrier - Crowd Control Flat Feet | 220 | 2026-10-19 | 2026-10-26
9990776 | 9 | Pending | MISCITEM | Demarcation CCB | 4603 | 2026-10-19 | 2026-10-26
9990776 | 10 | Pending | SHADECLOTH | Shade Cloth | 9.37 | 2026-10-19

## Baseplan changed
Contract | Line | Description (new) | Field | Page had | Export now
9987005 | 2 | Supply Telehandler Fork Extension 1800mm | status | Del Req | Delivered
9987005 | 2 | Supply Telehandler Fork Extension 1800mm | booked_delivery | 2026-10-05 | 2026-10-12
9968955 | 4 | WC12 Toilet Portable - Fresh Water Flush | desc | WC21 Toilet Portable - Fresh Water Flush | WC12 Toilet Portable - Fresh Water Flush
9968955 | 5 | WC12 Toilet Portable - Fresh Water Flush | desc | WC21 Toilet Portable - Fresh Water Flush | WC12 Toilet Portable - Fresh Water Flush
9968955 | 6 | WC11 Toilet Portable - Fresh Water Flush | desc | WC21 Toilet Portable - Fresh Water Flush | WC11 Toilet Portable - Fresh Water Flush
9968955 | 7 | WC21 Toilet Portable - Fresh Water Flush | item | 1211963 | 1211977
9968955 | 7 | WC21 Toilet Portable - Fresh Water Flush | delivery_no | 26064136 | 26126905
9968955 | 14 | WC21 Toilet Portable - Fresh Water Flush | desc | WC12 Toilet Portable - Fresh Water Flush | WC21 Toilet Portable - Fresh Water Flush
9968955 | 15 | WC06 Toilet Portable - Fresh Water Flush | desc | WC12 Toilet Portable - Fresh Water Flush | WC06 Toilet Portable - Fresh Water Flush
9968955 | 16 | WC21 Toilet Portable - Fresh Water Flush | desc | WC12 Toilet Portable - Fresh Water Flush | WC21 Toilet Portable - Fresh Water Flush
9968955 | 18 | WC21 Toilet Portable - Fresh Water Flush | desc | WC11 Toilet Portable - Fresh Water Flush | WC21 Toilet Portable - Fresh Water Flush
9968955 | 19 | WC21 Toilet Portable - Fresh Water Flush | desc | WC11 Toilet Portable - Fresh Water Flush | WC21 Toilet Portable - Fresh Water Flush
9968955 | 22 | WC50 Toilet Portable - Fresh Water Flush | desc | Toilet Portable - Fresh Water Flush | WC50 Toilet Portable - Fresh Water Flush
9968955 | 23 | WC11 Toilet Portable - Fresh Water Flush | desc | WC04 Toilet Portable - Fresh Water Flush | WC11 Toilet Portable - Fresh Water Flush
9968955 | 24 | WC07 Toilet Portable - Fresh Water Flush | desc | Toilet Portable - Fresh Water Flush | WC07 Toilet Portable - Fresh Water Flush
9968955 | 39 | WC07 Toilet Portable - Fresh Water Flush | desc | Toilet Portable - Fresh Water Flush | WC07 Toilet Portable - Fresh Water Flush
9968955 | 44 | WC04 Toilet Portable - Fresh Water Flush | desc | WC06 Toilet Portable - Fresh Water Flush | WC04 Toilet Portable - Fresh Water Flush
9968955 | 45 | WC02 Toilet Portable - Fresh Water Flush | desc | WC06 Toilet Portable - Fresh Water Flush | WC02 Toilet Portable - Fresh Water Flush
9968955 | 46 | WC01 Toilet Portable - Fresh Water Flush | desc | WC50 Toilet Portable - Fresh Water Flush | WC01 Toilet Portable - Fresh Water Flush
9968955 | 47 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3m | status | Del Req | Delivered
9968955 | 47 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3m | booked_delivery | 2026-09-14 | 2026-10-07
9968955 | 48 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3m | status | Del Req | Delivered
9968955 | 48 | WC20 Toilet Block Male Female Cyclone Rated 6m x 3m | booked_delivery | 2026-09-14 | 2026-10-07
9968955 | 49 | WC20 Sewage Holding Tank 6.0M x 2.4M | status | Del Req | Delivered
9968955 | 49 | WC20 Sewage Holding Tank 6.0M x 2.4M | item |  | 1311341
9968955 | 49 | WC20 Sewage Holding Tank 6.0M x 2.4M | booked_delivery | 2026-09-14 | 2026-10-07
9968955 | 50 | WC20 Sewage Holding Tank 6.0M x 2.4M | status | Del Req | Delivered
9968955 | 50 | WC20 Sewage Holding Tank 6.0M x 2.4M | item |  | 1328982
9968955 | 50 | WC20 Sewage Holding Tank 6.0M x 2.4M | booked_delivery | 2026-09-14 | 2026-10-07
9968955 | 51 | Wc86 Toilet - Disabled Access | status | Del Req | Delivered
9968955 | 51 | Wc86 Toilet - Disabled Access | item |  | 1296899
9968955 | 51 | Wc86 Toilet - Disabled Access | booked_delivery | 2026-09-14 | 2026-10-07
9968955 | 58 | WC06 Toilet Portable - Fresh Water Flush | desc | WC01 Toilet Portable - Fresh Water Flush | WC06 Toilet Portable - Fresh Water Flush
9968955 | 59 | WC41 Toilet Portable - Fresh Water Flush | status | Del Req | Delivered
9968955 | 59 | WC41 Toilet Portable - Fresh Water Flush | item |  | miscitems
9968955 | 59 | WC41 Toilet Portable - Fresh Water Flush | qty | 1 | 10
9968955 | 59 | WC41 Toilet Portable - Fresh Water Flush | booked_delivery | 2026-09-14 | 2026-09-28
9968955 | 69 | WC01 Toilet Portable - Fresh Water Flush | desc | WC 42 Toilet Portable - Fresh Water Flush | WC01 Toilet Portable - Fresh Water Flush
9968955 | 70 | WC43 Toilet Portable - Fresh Water Flush | status | Del Req | Delivered
9968955 | 70 | WC43 Toilet Portable - Fresh Water Flush | item |  | miscitem
9968955 | 70 | WC43 Toilet Portable - Fresh Water Flush | qty | 1 | 10
9968955 | 70 | WC43 Toilet Portable - Fresh Water Flush | booked_delivery | 2026-09-14 | 2026-09-28
9968955 | 80 | WC44 Toilet Portable - Fresh Water Flush | status | Pending | Delivered
9968955 | 80 | WC44 Toilet Portable - Fresh Water Flush | item |  | miscitem
9968955 | 80 | WC44 Toilet Portable - Fresh Water Flush | delivery_no |  | 26127125
9968955 | 81 | WC44 Toilet Portable - Fresh Water Flush | status | Pending | Delivered
9968955 | 81 | WC44 Toilet Portable - Fresh Water Flush | item |  | miscitem
9968955 | 81 | WC44 Toilet Portable - Fresh Water Flush | delivery_no |  | 26127125
9968955 | 84 | WC67 Toilet Portable - Fresh Water Flush | status | Pending | Delivered
9968955 | 84 | WC67 Toilet Portable - Fresh Water Flush | item |  | miscitems
9968955 | 84 | WC67 Toilet Portable - Fresh Water Flush | delivery_no |  | 26127302
9968955 | 86 | WC71 Toilet Portable - Fresh Water Flush | status | Pending | Delivered
9968955 | 86 | WC71 Toilet Portable - Fresh Water Flush | item |  | miscitems
9968955 | 86 | WC71 Toilet Portable - Fresh Water Flush | delivery_no |  | 26127302
9968955 | 93 | WC60 Toilet Block 6.0M x 3.0M | status | Del Req | Delivered
9968955 | 93 | WC60 Toilet Block 6.0M x 3.0M | item |  | 1119489
9968955 | 93 | WC60 Toilet Block 6.0M x 3.0M | booked_delivery | 2026-09-14 | 2026-10-01
9968955 | 94 | WC60 Sewage Holding Tank 6.0M x 2.4M | status | Del Req | Delivered
9968955 | 94 | WC60 Sewage Holding Tank 6.0M x 2.4M | item |  | 1328980
9968955 | 94 | WC60 Sewage Holding Tank 6.0M x 2.4M | booked_delivery | 2026-09-14 | 2026-10-01
9968955 | 95 | WC60 Sewage Holding Tank 6.0M x 2.4M | status | Del Req | Delivered
9968955 | 95 | WC60 Sewage Holding Tank 6.0M x 2.4M | item |  | 1328981
9968955 | 95 | WC60 Sewage Holding Tank 6.0M x 2.4M | booked_delivery | 2026-09-14 | 2026-10-01
9968955 | 97 | WC31 Toilet - Accessible | status | Del Req | Delivered
9968955 | 97 | WC31 Toilet - Accessible | item |  | 1317645
9968955 | 97 | WC31 Toilet - Accessible | booked_delivery | 2026-09-14 | 2026-10-08
9968955 | 98 | WC31 16 Pan Block | status | Pending | Delivered
9968955 | 98 | WC31 16 Pan Block | delivery_no |  | 26126963
9968955 | 101 | WC33 Toilet Portable - Fresh Water Flush | status | Pending | Delivered
9968955 | 101 | WC33 Toilet Portable - Fresh Water Flush | delivery_no |  | 26127109
9968955 | 103 | WC09 Toilet Block 6.0M x 3.0M | status | Del Req | Delivered
9968955 | 103 | WC09 Toilet Block 6.0M x 3.0M | item |  | 1268858
9968955 | 103 | WC09 Toilet Block 6.0M x 3.0M | booked_delivery | 2026-09-14 | 2026-10-08
9968955 | 105 | WC09 Toilet Block 6.0M x 3.0M | status | Del Req | Delivered
9968955 | 105 | WC09 Toilet Block 6.0M x 3.0M | item |  | 1311146
9968955 | 105 | WC09 Toilet Block 6.0M x 3.0M | booked_delivery | 2026-09-14 | 2026-10-08
9968955 | 106 | WC59 FWF Toilet | status | Pending | Delivered
9968955 | 106 | WC59 FWF Toilet | delivery_no |  | 26127293
9968955 | 111 | WC51 Toilet - Accessible | status | Pending | Del Req
9968955 | 111 | WC51 Toilet - Accessible | delivery_no |  | 26129341
9968955 | 113 | WC56 FWF Toilet | status | Pending | Delivered
9968955 | 113 | WC56 FWF Toilet | delivery_no |  | 26127284
9968955 | 138 | Steps Toilet Block | status | Del Req | Delivered
9968955 | 138 | Steps Toilet Block | booked_delivery | 2026-09-14 | 2026-10-01
9968955 | 139 | Steps Toilet Block | status | Del Req | Delivered
9968955 | 139 | Steps Toilet Block | booked_delivery | 2026-09-14 | 2026-10-01
9968929 | 5 | Shop Front - Shut Down | item |  | 1257261
9968929 | 5 | Shop Front - Shut Down | desc | Container 6.0M x 2.4M | Shop Front - Shut Down
9968862 | 4 | P03 Portable Building Shell 12.0M x 3.0M - Cyclonic Ra | item | 1322579 | 1327212
9968862 | 4 | P03 Portable Building Shell 12.0M x 3.0M - Cyclonic Ra | desc | P03 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | P03 Portable Building Shell 12.0M x 3.0M - Cyclonic Ra
9968862 | 4 | P03 Portable Building Shell 12.0M x 3.0M - Cyclonic Ra | delivery_no | 26064081 | 26126231
9968862 | 61 | P44 Portable Building Shell 6.0M x 3.0M | desc | P58 Portable Building Shell 6.0M x 3.0M | P44 Portable Building Shell 6.0M x 3.0M
9968862 | 79 | P52 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | status | Del Req | Delivered
9968862 | 79 | P52 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | booked_delivery | 2026-09-14 | 2026-10-07
9968862 | 81 | P52 Refrigerator - Large | status | Del Req | Delivered
9968862 | 81 | P52 Refrigerator - Large | item |  | 1328953
9968862 | 81 | P52 Refrigerator - Large | booked_delivery | 2026-09-14 | 2026-10-07
9968862 | 85 | P54 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | status | Del Req | Delivered
9968862 | 85 | P54 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | booked_delivery | 2026-09-14 | 2026-10-07
9968862 | 87 | P55 Ticket Office 6.0Mx3.0M | status | Del Req | Delivered
9968862 | 87 | P55 Ticket Office 6.0Mx3.0M | booked_delivery | 2026-09-14 | 2026-10-07
9968862 | 89 | P56 Portable Building Shell Cyclone Rated 3.6m x 2.4m | desc | Portable Building Shell Cyclone Rated 3.6m x 2.4m | P56 Portable Building Shell Cyclone Rated 3.6m x 2.4m
9968862 | 90 | P57 Portable Building Shell Cyclone Rated 9.6m x 3m | status | Del Req | Delivered
9968862 | 90 | P57 Portable Building Shell Cyclone Rated 9.6m x 3m | booked_delivery | 2026-09-14 | 2026-10-07
9968862 | 91 | P57 Refrigerator - Large | status | Del Req | Delivered
9968862 | 91 | P57 Refrigerator - Large | item |  | 1280688
9968862 | 91 | P57 Refrigerator - Large | booked_delivery | 2026-09-14 | 2026-10-07
9968862 | 94 | P51 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | status | Del Req | Delivered
9968862 | 94 | P51 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | item | 1327213 | 1322579
9968862 | 94 | P51 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | desc | P46 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | P51 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated
9968862 | 94 | P51 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | booked_delivery | 2026-09-14 | 2026-10-06
9968862 | 96 | P46 Refrigerator - Large | status | Pending | Delivered
9968862 | 96 | P46 Refrigerator - Large | item |  | 1328959
9968862 | 96 | P46 Refrigerator - Large | delivery_no |  | 26126190
9968862 | 100 | P46 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | desc | P51 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated | P46 Portable Building Shell 12.0M x 3.0M - Cyclonic Rated
9968862 | 102 | P51 Refrigerator - Large | status | Pending | Delivered
9968862 | 102 | P51 Refrigerator - Large | item |  | 1328957
9968862 | 102 | P51 Refrigerator - Large | delivery_no |  | 26126190
9968862 | 103 | P69 Portable Building Shell 6.0M x 3.0M | status | Pending | Delivered
9968862 | 103 | P69 Portable Building Shell 6.0M x 3.0M | item |  | 107247
9968862 | 103 | P69 Portable Building Shell 6.0M x 3.0M | booked_delivery | 2026-09-14 | 2026-10-12
9968862 | 103 | P69 Portable Building Shell 6.0M x 3.0M | delivery_no |  | 26120550
9968862 | 105 | P25 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | status | Pending | Delivered
9968862 | 105 | P25 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | booked_delivery | 2026-09-14 | 2026-10-14
9968862 | 105 | P25 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | delivery_no |  | 26125993
9968862 | 107 | P25 Refrigerator - Large | status | Pending | Delivered
9968862 | 107 | P25 Refrigerator - Large | item |  | 1260174
9968862 | 107 | P25 Refrigerator - Large | booked_delivery | 2026-09-14 | 2026-10-14
9968862 | 107 | P25 Refrigerator - Large | delivery_no |  | 26125993
9968862 | 108 | P67 Commentary Booth 6.0M x 3.0M | status | Pending | Delivered
9968862 | 108 | P67 Commentary Booth 6.0M x 3.0M | item | 1189410 | 421107
9968862 | 108 | P67 Commentary Booth 6.0M x 3.0M | booked_delivery | 2026-09-14 | 2026-10-14
9968862 | 108 | P67 Commentary Booth 6.0M x 3.0M | delivery_no |  | 26126016
9968862 | 110 | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | status | Pending | Delivered
9968862 | 110 | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | item | 1189412 | 1327217
9968862 | 110 | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | desc | P65 Commentary Booth 6.0M x 3.0M | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated
9968862 | 110 | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | booked_delivery | 2026-09-14 | 2026-10-14
9968862 | 110 | P65 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated | delivery_no |  | 26126006
9968862 | 112 | P65 Refrigerator - Large | status | Pending | Delivered
9968862 | 112 | P65 Refrigerator - Large | item |  | 1283982
9968862 | 112 | P65 Refrigerator - Large | booked_delivery | 2026-09-14 | 2026-10-14
9968862 | 112 | P65 Refrigerator - Large | delivery_no |  | 26126006
9968862 | 113 | P66 Portable Building Shell 6.0M x 3.0M | status | Pending | Delivered
9968862 | 113 | P66 Portable Building Shell 6.0M x 3.0M | item |  | 1327222
9968862 | 113 | P66 Portable Building Shell 6.0M x 3.0M | booked_delivery | 2026-09-14 | 2026-10-14
9968862 | 113 | P66 Portable Building Shell 6.0M x 3.0M | delivery_no |  | 26126001
9968862 | 115 | P66 Refrigerator - Large | status | Pending | Delivered
9968862 | 115 | P66 Refrigerator - Large | item |  | 1311990
9968862 | 115 | P66 Refrigerator - Large | booked_delivery | 2026-09-14 | 2026-10-14
9968862 | 115 | P66 Refrigerator - Large | delivery_no |  | 26126001
9968862 | 116 | P60 Ticket Office 4.8Mx2.4M | status | Pending | Delivered
9968862 | 116 | P60 Ticket Office 4.8Mx2.4M | booked_delivery | 2026-09-14 | 2026-10-15
9968862 | 116 | P60 Ticket Office 4.8Mx2.4M | delivery_no |  | 26129333
9968862 | 118 | P62 Commentary Booth 6.0M x 3.0M | status | Pending | Delivered
9968862 | 118 | P62 Commentary Booth 6.0M x 3.0M | booked_delivery | 2026-09-14 | 2026-10-15
9968862 | 118 | P62 Commentary Booth 6.0M x 3.0M | delivery_no |  | 26129321
9968862 | 120 | P62 Refrigerator - Large | status | Pending | Delivered
9968862 | 120 | P62 Refrigerator - Large | item |  | 1254221
9968862 | 120 | P62 Refrigerator - Large | booked_delivery | 2026-09-14 | 2026-10-15
9968862 | 120 | P62 Refrigerator - Large | delivery_no |  | 26129321
9968862 | 121 | P63 Portable Building Shell 6.0M x 3.0M | status | Pending | Delivered
9968862 | 121 | P63 Portable Building Shell 6.0M x 3.0M | item | 1282487 | 960719
9968862 | 121 | P63 Portable Building Shell 6.0M x 3.0M | booked_delivery | 2026-09-14 | 2026-10-15
9968862 | 121 | P63 Portable Building Shell 6.0M x 3.0M | delivery_no |  | 26129310
9968862 | 126 | P08 Portable Building Shell 6.0M x 3.0M | status | Del Req | Delivered
9968862 | 126 | P08 Portable Building Shell 6.0M x 3.0M | item |  | 421138
9968862 | 126 | P08 Portable Building Shell 6.0M x 3.0M | booked_delivery | 2026-09-14 | 2026-10-06
9968862 | 128 | P08 Refrigerator - Large | status | Del Req | Delivered
9968862 | 128 | P08 Refrigerator - Large | item |  | 1114312
9968862 | 128 | P08 Refrigerator - Large | booked_delivery | 2026-09-14 | 2026-10-06
9974042 | 1 | Container 3.0M x 2.4M | status | Del Req | Delivered
9974042 | 1 | Container 3.0M x 2.4M | item |  | 1134386
9974042 | 1 | Container 3.0M x 2.4M | desc | Container 3.0M x 2.4M | Container 3.0M x 2.4M
9974042 | 1 | Container 3.0M x 2.4M | booked_delivery | 2026-09-28 | 2026-10-07
9974042 | 2 | Container - Refrigerated 6.0M x 2.4M | delivery_no | 26121442 | 26127706
9961976 | 1 | LT01 MOLENDINAR Lighting Tower LED Metro | desc | MOLENDINAR Lighting Tower LED Metro | LT01 MOLENDINAR Lighting Tower LED Metro
9961976 | 2 | LT02 MOLENDINAR Lighting Tower LED Metro | desc | MOLENDINAR Lighting Tower LED Metro | LT02 MOLENDINAR Lighting Tower LED Metro
9961976 | 3 | LT03 MOLENDINAR Lighting Tower LED 76500lm Hybrid | desc | MOLENDINAR Lighting Tower LED 76500lm Hybrid | LT03 MOLENDINAR Lighting Tower LED 76500lm Hybrid
9961976 | 4 | LT04 MOLENDINAR Lighting Tower LED Metro | desc | MOLENDINAR Lighting Tower LED Metro | LT04 MOLENDINAR Lighting Tower LED Metro
9961976 | 7 | GN19-Generator - Diesel - 80kVA DEL AS 60KVA | status | Pending | Del Req
9961976 | 7 | GN19-Generator - Diesel - 80kVA DEL AS 60KVA | delivery_no |  | 26133589
9961976 | 11 | GN18-Generator - 60kVA (Diesel) | status | Del Req | Delivered
9961976 | 13 | SPARE-Generator - 60kVA | desc | GN06-Generator - 60kVA DEL AS 50KVA | SPARE-Generator - 60kVA
9961976 | 14 | GN04-Generator - 30kVA (Diesel) | status | Pending | Del Req
9961976 | 14 | GN04-Generator - 30kVA (Diesel) | delivery_no |  | 26133589
9961976 | 15 | GN10-Generator - 45kVA (Diesel) | item | 1197355
9961976 | 15 | GN10-Generator - 45kVA (Diesel) | desc | GN10-Generator - 20kVA (Diesel) | GN10-Generator - 45kVA (Diesel)
9961976 | 18 | GN25-Generator - 20kVA (Diesel) | status | Pending | Del Req
9961976 | 18 | GN25-Generator - 20kVA (Diesel) | delivery_no |  | 26134523
9961976 | 27 | SUPPLY-Forklift 3.5t Diesel | booked_delivery | 2026-10-05 | 2026-10-19
9961976 | 35 | COATES-Forklift Rough Terrain 2.5t With Switchable 2WD to 4WD | booked_delivery | 2026-10-09 | 2026-10-19
9961976 | 37 | COATES-Forklift Tyne Rotator | booked_delivery | 2026-10-09 | 2026-10-19
9961976 | 42 | GN26 CONCERT Generator - 200kVA (Diesel) | status | Del Req | Delivered
9961976 | 42 | GN26 CONCERT Generator - 200kVA (Diesel) | desc | GN CONCERT Generator - 200kVA (Diesel) | GN26 CONCERT Generator - 200kVA (Diesel)
9961976 | 43 | GN27 CONCERT-Generator - 200kVA (Diesel) | status | Del Req | Delivered
9961976 | 43 | GN27 CONCERT-Generator - 200kVA (Diesel) | desc | GN CONCERT-Generator - 200kVA (Diesel) | GN27 CONCERT-Generator - 200kVA (Diesel)
9972648 | 4 | WB04 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | status | Pending | Del Req
9972648 | 4 | WB04 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | qty | 14 | 12
9972648 | 4 | WB04 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | delivery_no |  | 26129840
9972648 | 5 | WB05 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | status | Pending | Del Req
9972648 | 5 | WB05 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | delivery_no |  | 26129861
9972648 | 6 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | status | Pending | Delivered
9972648 | 6 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | qty | 154 | 60
9972648 | 6 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | booked_delivery | 2026-10-16 | 2026-10-15
9972648 | 6 | WB06 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | delivery_no |  | 26126575
9972648 | 8 | WB13 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | status | Pending | Del Req
9972648 | 8 | WB13 Barrier - Crash Rated Water filled - Armorzone MASH TL2 | delivery_no |  | 26133803
9961265 | 1 | Variable Message Board Senior | status | Delivered | Returned
9961265 | 12 | VMS09 Variable Message Board Senior | status | Pending | Delivered
9961265 | 12 | VMS09 Variable Message Board Senior | booked_delivery | 2026-10-08 | 2026-09-07
9961265 | 12 | VMS09 Variable Message Board Senior | delivery_no |  | 26126728
9961265 | 15 | VMS11 Variable Message Board - Premiair | status | Pending | Del Req
9961265 | 15 | VMS11 Variable Message Board - Premiair | delivery_no |  | 26129008
9961265 | 16 | VMS12 Variable Message Board Junior | status | Pending | Del Req
9961265 | 16 | VMS12 Variable Message Board Junior | delivery_no |  | 26129024
9961265 | 24 | VMS18 Variable Message Board Senior Premiair | status | Pending | Del Req
9961265 | 24 | VMS18 Variable Message Board Senior Premiair | delivery_no |  | 26133749
9961265 | 25 | VMS19 Variable Message Board Senior Premiair | status | Pending | Del Req
9961265 | 25 | VMS19 Variable Message Board Senior Premiair | delivery_no |  | 26133749
9961265 | 26 | VMS20 Variable Message Board Senior Premiair | status | Pending | Del Req
9961265 | 26 | VMS20 Variable Message Board Senior Premiair | delivery_no |  | 26133759
9961265 | 30 | VMS23 Variable Message Board Senior Premiair | status | Pending | Del Req
9961265 | 30 | VMS23 Variable Message Board Senior Premiair | delivery_no |  | 26133759

## Baseplan absent
Contract | Line | Status (page) | Item (page) | Description (page)
9961265 | 18 | Pending | sub-17093 | VMS13 Variable Message Board Senior RPM
9961265 | 19 | Pending | sub-17093 | VMS14 Variable Message Board Senior RPM
9961265 | 21 | Pending | sub-17093 | VMS15 Variable Message Board Senior RPM
9961265 | 22 | Pending | sub-17093 | VMS16 Variable Message Board Senior RPM
9961265 | 23 | Pending | sub-17093 | VMS17 Variable Message Board RPM
9961976 | 12 | Pending | 1261271 | GN13-Generator - 60kVA (Diesel)DEL AS 45KVA
9961976 | 29 | Pending | 1262224 | SUPPLY- Telehandler Fork Extension 1800mm
9961976 | 30 | Pending | 1214298 | EVENTS-Forklift 2.5t Container Diesel
9961976 | 32 | Pending | 1197488 | SPARE-Generator - 300kVA (Diesel)
9961976 | 36 | Pending | 1197215 | SPARE-Generator - 100kVA (Diesel) - Trailer Mounted
9961976 | 39 | Pending | 1276505 | SPARE-Generator - 60kVA (Diesel)
9968862 | 82 | Pending | 1327222 | P53 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated
9968862 | 84 | Pending |  | P53 Refrigerator - Large
9968862 | 97 | Pending | DESK | P46 Desk
9968862 | 98 | Pending | 1327217 | P47 Portable Building Shell 6.0M x 3.0M - Cyclonic Rated
9968862 | 127 | Pending | CLEAN7 | Cleaning Fee
9968955 | 60 | Del Req |  | WC41 Toilet Portable - Fresh Water Flush
9968955 | 61 | Del Req |  | WC41 Toilet Portable - Fresh Water Flush
9968955 | 62 | Del Req |  | WC41 Toilet Portable - Fresh Water Flush
9968955 | 63 | Del Req |  | WC41 Toilet Portable - Fresh Water Flush
9968955 | 64 | Del Req |  | WC41 Toilet Portable - Fresh Water Flush
9968955 | 65 | Del Req |  | WC41 Toilet Portable - Fresh Water Flush
9968955 | 66 | Del Req |  | WC41 Toilet Portable - Fresh Water Flush
9968955 | 67 | Del Req |  | WC41 Toilet Portable - Fresh Water Flush
9968955 | 68 | Del Req |  | WC41 Toilet Portable - Fresh Water Flush
9968955 | 71 | Del Req |  | WC43 Toilet Portable - Fresh Water Flush
9968955 | 72 | Del Req |  | WC43 Toilet Portable - Fresh Water Flush
9968955 | 73 | Del Req |  | WC43 Toilet Portable - Fresh Water Flush
9968955 | 74 | Del Req |  | WC43 Toilet Portable - Fresh Water Flush
9968955 | 75 | Del Req |  | WC43 Toilet Portable - Fresh Water Flush
9968955 | 76 | Del Req |  | WC43 Toilet Portable - Fresh Water Flush
9968955 | 77 | Del Req |  | WC43 Toilet Portable - Fresh Water Flush
9968955 | 78 | Del Req |  | WC43 Toilet Portable - Fresh Water Flush
9968955 | 79 | Del Req |  | WC43 Toilet Portable - Fresh Water Flush
9968955 | 82 | Pending |  | WC66 Toilet Portable - Fresh Water Flush
9968955 | 83 | Pending |  | WC66 Toilet Portable - Fresh Water Flush
9968955 | 99 | Pending | MISCITEM | WC32 Toilet Portable - Fresh Water Flush
9968955 | 135 | Applied | Delivery | Delivery for HA Line Item(s) 22,* 23 Sep 2026
9968955 | 136 | Applied | Delivery | Delivery for HA Line Item(s) 23,* 23 Sep 2026
9968955 | 137 | Applied | Delivery | Delivery for HA Line Item(s) 45,* 23 Sep 2026
9987005 | 6 | Del Req | 1274555 | Events Forklift 2.5t Dual Fuel

## Status conflicts
Conflict | Reference | Item | Description | Contract | Line | Record light
bp Pending, record complete | WC70 |  | WC70 Toilet Portable - Fresh Water Flush | 9968955 | 85 | on site · complete
bp Pending, record complete | WC69 |  | WC69 Toilet Portable - Fresh Water Flush | 9968955 | 87 | on site · complete
bp Pending, record complete | WC38 | MISCITEM | WC38 Toilet Portable - Fresh Water Flush | 9968955 | 88 | on site · complete
bp Pending, record complete | WC39 | MISCITEM | WC39 Toilet Portable - Fresh Water Flush | 9968955 | 89 | on site · complete
bp Pending, record complete | WC40 | MISCITEM | WC40 Toilet Portable - Fresh Water Flush | 9968955 | 90 | on site · complete
bp Pending, record complete | WC61 | MISCITEM | WC61 Toilet Portable - Fresh Water Flush | 9968955 | 96 | on site · complete
bp Pending, record complete | WC34 | MISCITEM | WC34 Toilet Portable - Fresh Water Flush | 9968955 | 100 | on site · complete
bp Pending, record complete | WC09 | MISCITEM | WC09 Toilet Portable - Fresh Water Flush | 9968955 | 102 | on site · complete
bp Pending, record complete | WC57 | MISCITEM | WC57 FWF Toilet | 9968955 | 107 | on site · complete
bp Pending, record complete | WC49 | MISCITEM | WC49 FWF Toilet | 9968955 | 108 | on site · complete
bp Pending, record complete | WC48 | MISCITEM | WC48 FWF Toilet | 9968955 | 109 | on site · complete
bp Pending, record complete | WC51 | MISCITEM | WC51 FWF Toilet | 9968955 | 110 | on site · complete
bp Del Req, record complete | WC51 |  | WC51 Toilet - Accessible | 9968955 | 111 | on site · complete
bp Pending, record complete | WC54 | MISCITEM | WC54 FWF Toilet | 9968955 | 112 | on site · complete
bp Pending, record complete | WC10 | MISCITEM | WC10 Toilet Portable - Fresh Water Flush | 9968955 | 114 | on site · complete
bp Pending, record complete | WC47 | MISCITEM | WC47 Toilet Portable - Fresh Water Flush | 9968955 | 116 | on site · complete
bp Pending, record complete | WC25 | MISCITEM | WC25 Toilet Portable - Fresh Water Flush | 9968955 | 118 | on site · complete
bp Pending, record complete | WC23 | MISCITEM | WC23 Toilet Portable - Fresh Water Flush | 9968955 | 119 | on site · complete
bp Pending, record complete | WC26 | MISCITEM | WC26 Toilet Portable - Fresh Water Flush | 9968955 | 120 | on site · complete
bp Pending, record complete | WC24 | MISCITEM | WC24 Toilet Portable - Fresh Water Flush | 9968955 | 121 | on site · complete
bp Pending, record complete | WC13 | MISCITEM | WC13 Toilet Portable - Fresh Water Flush | 9968955 | 122 | on site · complete
bp Pending, record complete | WC28 | MISCITEM | WC28 Toilet Portable - Fresh Water Flush | 9968955 | 123 | on site · complete
bp Pending, record complete | WC29 | MISCITEM | WC29 Toilet Portable - Fresh Water Flush | 9968955 | 124 | on site · complete
bp Pending, record complete | WC55 | MISCITEM | WC55 Toilet Portable - Fresh Water Flush | 9968955 | 128 | on site · complete
bp Pending, record complete | WC68 | MISCITEM | WC68 Toilet Portable - Fresh Water Flush | 9968955 | 131 | on site · complete
bp Pending, record complete | WC72 | MISCITEM | WC72 Toilet Portable - Fresh Water Flush | 9968955 | 132 | on site · complete
bp Pending, record complete | WC73 | MISCITEM | WC73 Toilet Portable - Fresh Water Flush | 9968955 | 133 | on site · complete
bp Delivered, record None | P10 | 105626 | P10 Portable Building Shell 4.8M x 2.4M | 9968862 | 44 | no record · complete
bp Delivered, record None | P11 | 415576 | P11 Portable Building Shell 4.8M x 2.4M | 9968862 | 46 | no record · complete
bp Delivered, record None | P37 | 1105053 | P37 Portable Building Shell 6.0M x 3.0M | 9968862 | 50 | no record · complete
bp Delivered, record None | P13 | 1097346 | P13 Portable Building Shell 4.8M x 2.4M | 9968862 | 51 | no record · complete
bp Delivered, record None | P14 | 960599 | P14 Portable Building Shell 4.8M x 2.4M | 9968862 | 53 | no record · complete
bp Delivered, record None | P36 | 1189410 | P36 Portable Building Shell 6.0M x 3.0M | 9968862 | 93 | no record · complete
bp Pending, record complete | P46 | 1272751 | P46 Refrigerator | 9968862 | 132 | on site · complete
bp Delivered, record not on site | LT01 | 1264929 | LT01 MOLENDINAR Lighting Tower LED Metro | 9961976 | 1 | not on site
bp Delivered, record not on site | LT02 | 1314284 | LT02 MOLENDINAR Lighting Tower LED Metro | 9961976 | 2 | not on site
bp Delivered, record not on site | LT03 | 1264899 | LT03 MOLENDINAR Lighting Tower LED 76500 | 9961976 | 3 | not on site
bp Delivered, record not on site | LT04 | 1188888 | LT04 MOLENDINAR Lighting Tower LED Metro | 9961976 | 4 | not on site
bp Delivered, record None | GN26 | 1316182 | GN26 CONCERT Generator - 200kVA (Diesel) | 9961976 | 42 | no record
bp Delivered, record None | GN27 | 1316183 | GN27 CONCERT-Generator - 200kVA (Diesel) | 9961976 | 43 | no record
bp Del Req, record complete | GN06 | 1320828 | GN06 Generator - 60kVA (Diesel) | 9961976 | 48 | on site · complete
bp Delivered, record not on site | WB06 | ARMORZONMASHTL2 | WB06 Barrier - Crash Rated Water filled | 9972648 | 6 | not on site
bp Delivered, record not on site | WB06 | ARMORZONMASHTL2 | WB06 Barrier - Crash Rated Water filled | 9972648 | 16 | not on site
bp Delivered, record not on site | WB06 | ARMORZONMASHTL2 | WB06 Barrier - Crash Rated Water filled | 9972648 | 17 | not on site
bp Delivered, record None | VMS09 | 1211404 | VMS09 Variable Message Board Senior | 9961265 | 12 | no record
bp Delivered, record None | VMS10 | sub-17093 | VMS10 Variable Message Board Senior Prem | 9961265 | 13 | no record

## Numbers to fill
Reference | Number | Schedule 9 sheet | Row | Item | Schedule date | Asset cell | DD | Corroboration | Baseplan status (export) | Record light | On the record elsewhere | Proposed
P01 | 1322583 | Week 5 | 2 | Building 12m | 2026-09-14 | 1322583 | D2P. DD#26064071 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P03 | 1327212 | Week 5 | 3 | Building 12m | 2026-09-14 | 1327212 | D2P. DD#26064081 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P05 | 1189422 | Week 5 | 4 | Building 6m | 2026-09-14 | 1189422 | D2P DD#26064095 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
CP1 | 1105057 | Week 5 | 5 | Building 6m | 2026-09-14 | 1105057 | D2D. DD#26064099 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P04 | 1327213 | Week 5 | 7 | Building 12m | 2026-09-14 | 1327213 | D2D. DD#26064087 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
WC05 | 1097377 | Week 5 | 8 | Toilet Block 6m | 2026-09-14 | 1097377 | D2D. DD#26067317 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P33 | 453375 | Week 5 | 9 | Building 9.6m | 2026-09-14 | 453375 | D2D. DD#26064103 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
WC16 | 1322587 | Week 5 | 14 | Toilet Block 6m | 2026-09-14 | 1322587 - 1322588 | Both D2P. DD#26064128 & | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
WC16 | 1322588 | Week 5 | 14 | Toilet Block 6m | 2026-09-14 | 1322587 - 1322588 | Both D2P. DD#26064128 & | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
WC17 | 1327224 | Week 5 | 24 | Toilet Block 6m | 2026-09-15 | 1327224 - 1327223 | D2Dx1 D2Px1. DD#26064268 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
WC17 | 1327223 | Week 5 | 24 | Toilet Block 6m | 2026-09-15 | 1327224 - 1327223 | D2Dx1 D2Px1. DD#26064268 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P09 | 1268824 | Week 5 | 26 | Building 6m | 2026-09-16 | 1268824 | D2P | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P17 | 1268887 | Week 5 | 27 | Building 9.6m | 2026-09-16 | 1268887 | D2P After P19-P21 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P18 | 1097343 | Week 5 | 28 | Building 4.8m | 2026-09-16 | 1097343 | D2D | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P19 | 1110619 | Week 5 | 29 | Building 4.8m | 2026-09-16 | 1110619 | D2D | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P20 | 1097339 | Week 5 | 30 | Building 4.8m | 2026-09-16 | 1097339 | D2P | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P27 | 1097343 | Week 5 | 33 | Building 4.8m | 2026-09-16 | 1097343 | D2P Last | page-schedule |  | no record |  | review
P36 | 1327222 | Week 5 | 35 | Building 6m | 2026-09-17 | 1327222 | D2P | page-schedule |  | no record | P66 | review
P10 | 105626 | Week 5 | 37 | Building 4.8m | 2026-09-17 | 105626 | D2D | baseplan-new | Delivered | no record |  | review
P11 | 415576 | Week 5 | 38 | Building 4.8m | 2026-09-17 | 415576 | D2D | baseplan-new | Delivered | no record |  | review
P12 | 418665 | Week 5 | 39 | Building 4.8m | 2026-09-17 | 418665 | D2D | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P37 | 1105053 | Week 5 | 40 | Building 6m | 2026-09-17 | 1105053 | D2P | baseplan-new | Delivered | no record |  | review
P13 | 1097345 | Week 4 | 2 | Building 4.8m | 2026-09-21 | 1097345 + TOILET | 26081372 | schedule only |  | no record | P15 | review
P14 | 960599 | Week 4 | 3 | Building 4.8m | 2026-09-21 | 960599 + 1 TOILET | 26081383 | baseplan-new | Delivered | no record |  | review
P15 | 127579 | Week 4 | 4 | Building 4.8m | 2026-09-21 | 127579 + TOILET | 26081392 | page-schedule |  | on site |  | review
P16 | 415575 | Week 4 | 5 | Building 4.8m | 2026-09-21 | 415575 + TOILET | 26081396 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P44 | 1273656 | Week 4 | 12 | Building 6m | 2026-09-23 | 1273656 | not torren dd#26088630 | baseplan-new | Delivered | on site | P58 | review
P58 | 198481 | Week 4 | 13 | Building 6m | 2026-09-23 | 198481 | not torren DD#26088639 | baseplan-page |  | on site | P44 | review
WC27 | 1119484 | Week 4 | 19 | Toilet Block 6m | 2026-09-25 | 1119484 | 26091469 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
WC15 | 1327226 | Week 4 | 21 | Toilet Block 6m | 2026-09-25 | 1327226 - 1303835 | not torren dd#26091474 & | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
WC15 | 1303835 | Week 4 | 21 | Toilet Block 6m | 2026-09-25 | 1327226 - 1303835 | not torren dd#26091474 & | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P06 | 1097453 | Week 3 | 3 | Building 6m | 2026-09-28 | 1097453 | not torren dd#26094121 | page-schedule |  | on site |  | review
P38 | 1327218 | Week 3 | 10 | Building 6m | 2026-09-28 | 1327218 | not torren dd#26094129 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P39 | 1327216 | Week 3 | 11 | Building 6m | 2026-09-28 | 1327216 | not torren DD#26094136 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P42 | 1327221 | Week 3 | 12 | Building 6m | 2026-09-28 | 1327221 | not torren dd#26094139 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P53 | 1327222 | Week 3 | 14 | Building 6m | 2026-09-29 | 1327222 | Crane onsite | baseplan-page |  | no record | P66 | review
GN20 | 1276701 | Week 3 | 15 | 350kva | 2026-09-30 | 1276701 | 26102821 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
GN21 | 1261284 | Week 3 | 16 | 60kva | 2026-09-30 | 1261284 | 26102852 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
GN23 | 1297157 | Week 3 | 17 | 150kva | 2026-09-30 | 1297157 | 26103394 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
GN03 | 1320829 | Week 3 | 19 | 30kva | 2026-10-01 | 1320829 EX ROCL | 26102891 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P46 | 1322579 | Week 2 | 6 | Building 12m | 2026-10-06 | 1322579 | 26106162 | schedule only |  | on site | P51 | review
P47 | 1327217 | Week 2 | 7 | Building 6m | 2026-10-06 | 1327217 | no trailer if torrens | baseplan-page |  | not on site | P65 | review
P51 | 1327215 | Week 2 | 8 | Building 12m | 2026-10-06 | 1327215 | 26106178 | baseplan-page |  | on site | P46 | review
GN18 | 1261273 | Week 2 | 13 | 50kva | 2026-10-07 | 1261273 ex REED | 26112495 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P54 | 1327219 | Week 2 | 18 | Building 6m | 2026-10-07 | 1327219 | 3rd 26112733 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P55 | 172114 | Week 2 | 19 | Ticket Box 6m | 2026-10-07 | 172114 | 1st 26112709 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P56 | 1268865 | Week 2 | 20 | Building 3.6m | 2026-10-07 | 1268865 | 2nd 26112730 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P57 | 1268888 | Week 2 | 21 | Building 9.6m | 2026-10-07 | 1268888 | 5th 26112756 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P25 | 1189408 | Week 1 | 14 | Building 6m | 2026-10-14 | 1189408 | traffic control dd261259 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P67 | 1189410 | Week 1 | 15 | Building 6m | 2026-10-14 | 1189410 | traffic control dd261260 | baseplan-page |  | on site |  | review
P60 | 1015699 | Week 1 | 24 | Ticket Box 4.8m | 2026-10-15 | 1015699 | Not Torrens 26129333 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P62 | 1189409 | Week 1 | 25 | Building 6m | 2026-10-15 | 1189409 | Not Torrens 26129321 | baseplan-new | Delivered | on site |  | put on by the drawer rule once Andrew says so
P63 | 1282487 | Week 1 | 26 | Building 6m | 2026-10-15 | 1282487 | Not Torrens 26129310 | baseplan-page |  | on site |  | review
GN04 | 1277400 | Event Week | 3 | 30kva | 2026-10-19 | 1277400 EX EAGS | 26133589 | baseplan-new | Del Req | not on site |  | review
GN10 | 1283681 | Event Week | 4 | 45kva | 2026-10-19 | 1283681-1261271 | TRYING TO GET 1 GOING | schedule only |  | not on site |  | review
GN10 | 1261271 | Event Week | 4 | 45kva | 2026-10-19 | 1283681-1261271 | TRYING TO GET 1 GOING | schedule only |  | not on site |  | review
GN19 | 1276416 | Event Week | 5 | 60kva | 2026-10-19 | 1276416 80KVA EAGS | 26133589 | baseplan-new | Del Req | not on site |  | review
GN24 | 1276412 | Event Week | 6 | 80kva | 2026-10-19 | 1276412 EX GYMP TRYING TO GET MEAD |  | schedule only |  | not on site |  | review
GN25 | 1244536 | Event Week | 7 | 20kva | 2026-10-19 | 1244536 EX NVAC | 26134523 | baseplan-new | Del Req | not on site |  | review
GN24 | 1277089 | Event Week | 8 | 60KVA TRAILER | 2026-10-19 | 1277089 IPSW | 26134440 | baseplan-new | Del Req | not on site |  | review
LT05 | 1224783 | Event Week | 37 | Light Tower | 2026-10-20 | 1224783-1224791 ex reed |  | baseplan-new | Pending | not on site |  | review
LT05 | 1224791 | Event Week | 37 | Light Tower | 2026-10-20 | 1224783-1224791 ex reed |  | baseplan-new | Pending | not on site |  | review

## Schedule 9 new rows
Sheet | Row | Date | Reference | Item | Qty | Local | Notes | Asset | DD
Week 1 | 19 | 2026-10-14 | P46 | fridge | 1 | P46 fridge |  |  | inside Wednesday building
Week 1 | 27 | 2026-10-15 | P53 | fridge | 1 | P53 Fridge |  |  | inside Thursday building
Demob Week 1 | 8 | 2026-10-26 | VMS11 | VMS | 12 | VMS11-23
Demob Week 1 | 21 | 2026-10-27 | VMS9 | VMS | 2 | VMS9-10
Demob Week 1 | 30 | 2026-10-28 | VMS22 | VMS | 1 | VMS22
Demob Week 3 | 13 | 2026-11-13 | VMS1 | VMS | 8 | VMS1-8

## Schedule 9 date changes
Sheet | Reference | Item | Page date | Schedule 9 date | Record light
Week 3 | WC01 | Accessible Toilet | 2026-09-28 | 2026-09-30 | on site · complete
Week 3 | WC50 | FWF | 2026-09-28 | 2026-09-30 | on site · complete
Week 2 | WC38 | FWF | 2026-10-09 | 2026-10-07 | on site · complete
Week 2 | WC39 | FWF | 2026-10-09 | 2026-10-07 | on site · complete
Week 2 | WC40 | FWF | 2026-10-09 | 2026-10-07 | on site · complete
Week 2 | WC61 | FWF | 2026-10-09 | 2026-10-07 | on site · complete
Week 2 | WC34 | FWF | 2026-10-09 | 2026-10-08 | on site · complete
Week 2 | WC09 | FWF | 2026-10-09 | 2026-10-08 | on site · complete
Week 2 | WC09 | Pee Panel | 2026-10-09 | 2026-10-08 | on site · complete
Week 2 | WC09 | Toilet Block 6m | 2026-10-09 | 2026-10-08 | on site · complete
Week 1 | WC57 | FWF | 2026-10-09 | 2026-10-12 | on site · complete
Week 1 | P26 | Fridge Lge | 2026-10-16 | 2026-10-14 | not on site
Week 1 | P28 | Fridge Lge | 2026-10-16 | 2026-10-14 | not on site
Week 1 | P34 | Pad Chair | 2026-10-16 | 2026-10-14 | not on site
Week 1 | WB06 | TL2 | 2026-10-16 | 2026-10-15 | not on site
Event Week | WC29 | FWF | 2026-10-13 | 2026-10-19 | on site · complete
Event Week | WC46 | FWF | 2026-10-15 | 2026-10-19 | not on site
Event Week | WC55 | FWF | 2026-10-15 | 2026-10-19 | on site · complete
Event Week | WC68 | FWF | 2026-10-13 | 2026-10-19 | on site · complete
Event Week | WC72 | FWF | 2026-10-13 | 2026-10-19 | on site · complete
Event Week | WC85 | FWF | 2026-10-19 | 2026-10-20 | not on site
Event Week | WB14 | TL2 | 2026-10-21 | 2026-10-25 | not on site
Demob Week 1 | WB20 | TL2 | 2026-10-26 | 2026-10-29 | not on site
Demob Week 2 | WB19 | TL2 | 2026-11-02 | 2026-11-06 | not on site

## Schedule 9 qty changes
Sheet | Reference | Item | Page qty | Schedule 9 qty | Record light
Week 5 | WC05 | Waste tank |  | 1 | on site · complete
Week 5 | WC05 | Toilet Block 6m |  | T | on site · complete
Week 5 | P09 | Building 6m |  | 1097377 | on site · complete
Week 3 | WC01 | FWF | 1 | 2 | on site · complete
Week 3 | WC60 | Toilet Block 6m | 2 | 1 | on site · complete
Week 3 | WC60 |  | 2 | 1 | on site · complete
Week 2 | WC31 | 16Pan Block | 1 | 2 | on site · complete
Week 2 | WC09 | Pee Panel | 4 | 6 | on site · complete
Week 2 | WC09 | Toilet Block 6m | 4 | 2 | on site · complete
Week 1 | WC67 | FWF | 2 | 4 | on site · complete
Week 1 | WC51 | FWF | 1 | 6 | on site · complete
Week 1 | WB04 | TL2 | 14 | 12 | not on site
Event Week | LT05 | Light Tower | 1 | 2 | not on site

## Schedule 9 note changes
Sheet | Reference | Page note | Schedule 9 note
Week 5 | WC05 | Combo - Tanked | waste tank for WC05
Week 5 | WC16 | 1x Sewer - Female 1x Sewer - Male | 1x Sewer - Female 1x Sewer - Male
Week 5 | WC17 | 1x Sewer - Female 1x Sewer - Male | 1x Sewer - Female 1x Sewer - Male
Week 4 | P14 |  | RET FRIDAY
Week 1 | WC67 |  | up from 2
Week 1 | WC51 |  | load with p60
Week 1 | WB06 | 7.00pm | 10.00am
Week 1 | WB05 | 7.00pm | 8.00am
Event Week | GN10 |  | was a 20kva
Event Week | GN24 |  | Back Up
Event Week | WB14 | 7.00am | 7.00pm
Demob Week 2 | WB19 | 7.00am | 5.00pm

## Page events not in Sched 9
Sheet | Reference | Items (page) | Record light
Week 5 | AA | Building 6m | on site · complete
Week 1 | GN? | 200kva & cables | no record
Week 5 | HRP | Building 6m | no record · complete
Event Week | LT06 | Light Tower | not on site
Event Week | PG01 | FWF | not on site
Event Week | PG03 | FWF | not on site
Event Week | PG05 | FWF | not on site
Event Week | PG29 | FWF | not on site
Event Week | WC10 | FWF | on site · complete
Week 5 | WC100 | FWF Trailer | on site · complete