## Summary
Baseplan SuperCars (5), 16 Oct 2026 - charges checked against the site record (record 8077)
New charges on 9968862, dated 16 Oct | Baseplan | Site record supports now | Not done yet (legit once done) | Charged but not recorded on site
Installation & Dismantling, 45 x $655.83 | 29512.35 | 19987.2 | 6558.3 | 2966.85
Transport up to 6 m, 72 x $500 | 36000 | 18000 | 18000 | 0
Transport 9.6 m & 12 m, 18 x $800 | 14400 | 7200 | 7200 | 0
TOTAL | 79912.35 | 45187.2 | 31758.3 | 2966.85
$655.83 is the whole card labour package for one building: Install 145.74 + Steps 156.15 + Levelling 52.05 + Cleaning 104.10 + Fire extinguisher 52.05 + Demob 145.74. It is charged on all 45 buildings whether or not each piece was done.
On site: install, levelling, cleaning on all 45; steps on 41 (none on P06, P38, P39, P42); fire extinguisher on none; demob still to come.
Transport rates and counts match the card and the buildings on site; half of it is the return trip, not done until demob.

## Install & dismantle
Baseplan line | Ref (site record) | Baseplan label if different | Asset no | Site record item | On site? | Baseplan charges | Work done (ticked on site) | Demob - to come | Charged, not recorded on site | Not done on site
1 | P01 |  | 1322583 | Building 12m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
4 | P03 |  | 1327212 | Building 12m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
7 | P04 |  | 1327213 | Building 12m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
10 | P05 |  | 1189422 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
17 | CP1 |  | 1105057 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
24 | P33 |  | 453375 | Building 9.6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
28 | P09 |  | 1268824 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
33 | P17 |  | 1268887 | Building 9.6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
34 | P19 |  | 1110619 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
36 | P18 |  | 1097343 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
38 | P20 |  | 1097339 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
44 | P10 |  | 105626 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
46 | P11 |  | 415576 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
48 | P12 |  | 418665 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
50 | P37 |  | 1105053 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
51 | P13 |  | 1097346 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
53 | P14 |  | 960599 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
55 | P15 |  | 1097345 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
57 | P16 |  | 415575 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
59 | P58 | P44 | 1273656 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
61 | P44 |  | 198481 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
63 | P41 |  | 1189412 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
64 | P06 |  | 1087453 | Building 6m | on site | 655.83 | 301.89 | 145.74 | 208.2 | Steps, Fire extinguisher
70 | P38 |  | 1327218 | Building 6m | on site | 655.83 | 301.89 | 145.74 | 208.2 | Steps, Fire extinguisher
73 | P39 |  | 1327216 | Building 6m | on site | 655.83 | 301.89 | 145.74 | 208.2 | Steps, Fire extinguisher
76 | P42 |  | 1327221 | Building 6m | on site | 655.83 | 301.89 | 145.74 | 208.2 | Steps, Fire extinguisher
79 | P52 |  | 1327211 | Building 12m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
85 | P54 |  | 1327219 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
87 | P55 |  | 172114 | Ticket Box 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
89 | P56 |  | 1268865 | Building 3.6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
90 | P57 |  | 1268888 | Building 9.6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
92 | P21 |  | 1327220 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
93 | P36 |  | 1189410 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
94 | P51 |  | 1322579 | Building 12m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
100 | P46 |  | 1327215 | Building 12m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
103 | P69 |  | 107247 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
105 | P25 |  | 1189408 | Building 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
108 | P67 |  | 421107 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
110 | P65 |  | 1327217 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
113 | P66 |  | 1327222 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
116 | P60 |  | 1015699 | Ticket Box 4.8m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
118 | P62 |  | 1189409 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
121 | P63 |  | 960719 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
126 | P08 |  | 421138 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
131 | P45 |  | 107135 | Building 6m | on site | 655.83 | 458.04 | 145.74 | 52.05 | Fire extinguisher
| TOTAL |  |  |  |  | 29512.35 | 19987.2 | 6558.3 | 2966.85

## Transport
Line | Baseplan qty | Rate | Baseplan charges | Buildings on site | Delivery leg - done | Return leg - not done yet | Check
Up to 6 m buildings (line 134) | 72 | 500 | 36000 | 36 | 18000 | 18000 | Rate matches the card ($500 each way). Count matches: 36 buildings on site x 2 trips.
9.6 m and 12 m buildings (line 135) | 18 | 800 | 14400 | 9 | 7200 | 7200 | Rate matches the card ($800 each way). Count matches: 9 buildings x 2 trips.

## Other changes vs (4)
Where | Baseplan (5) says | Our site record says | What to do
9961976 line 15 (GN10) | NEW: a 60 kVA generator, asset 1283681, $1,142.96/wk, from 19 Oct (was "GN10 45kVA", no unit) | GN10 is a 20 kVA, asset 1197355, not on site yet, due 19 Oct. 1283681 is the spare we took off GN06. | WRONG UNIT AND SIZE - would charge 60 kVA for a 20 kVA job. Ask the branch.
9961976 line 48 (GN06) | Delivered 15 Oct, asset 1320828, described 60 kVA, $1,184.82/wk | GN06 on site 15 Oct, asset 1320828 (same unit), recorded as 50 kVA | Size differs - check the plate. If it is 50 kVA it should be on the 50 kVA rate.
9992300 line 12 | NEW: Straight Boom Lift 60 ft, asset 1286482, $459.55/wk from 21 Oct, prebill $2,417.94 (TV compound) | Not on our record. Our TV compound references are FL03, FL04 and TM01 only; the knuckle boom (line 5) and scissor lift (line 4) are not on our record either. | Was a second boom asked for, or does it replace the knuckle boom? There is only one boom transport line (line 10).
9972648 line 18 (WB22) | NEW: 4 Armorzone barriers from 18 Oct | No WB22 on our schedule | Not ours unless a request came in. Ask.
9972648 lines 7 and 8 (WB07, WB13) | REMOVED (17 and 10 barriers) | WB07 17 due 18 Oct, WB13 10 due 19 Oct, both still on our schedule | If they go out they will not be billed. Cancelled, or dropped by mistake?
9972648 lines 4 and 5 (WB04, WB05) | Labels swapped since (4); quantities 13 (WB04) and 12 (WB05), delivered 16 Oct | WB04 14 (Helen Park) and WB05 13 (Main Beach) on site 16 Oct | Two fewer barriers billed than are on site.
9968862 lines 34, 92, 105 (P19, P21, P25) | Described 6.0 m x 3.0 m | Recorded as 4.8 m buildings | Description only - billed at the 4.8 m rate ($1,125.84). No money difference.
9968862 line 59 ("P44") | Asset 1273656 labelled P44 (P44 also on line 61, asset 198481) | 1273656 is P58 (1300 Medics); P44 is 198481 | Label only - one building each, nothing double charged.
9968955 line 111 (WC51) | Now Delivered 15 Oct, asset 1197174 | WC51 on site 15 Oct, no number recorded | Agrees. 1197174 can go on the record once you have seen the plate.
9968726 (whole contract) | REMOVED (old TV compound order) | Already held out as superseded by 9992300 | Agrees.
9961976 lines 13 and 45 | REMOVED (spare 60 kVA generators 1283681 and 1261271) | 1283681 was taken off GN06 | Agrees.
9968862 line 63 (P41) | Rate $1,426.17 -> $1,426.07 |  | 10 cents a week. Nothing to do.
9992300 lines 1-6 | Forklifts 5 t and 2.5 t, fork extensions, 10 Trakmats delivered 16 Oct; scissor lift moved to 19 Oct, knuckle boom to 21 Oct | FL03, FL04, TM01 on site | Agrees for the forklifts and Trakmats.