## Day by day
Board | Asset / fleet | Rego | Owner | Position now | On site | Map | [46 empty] | RACE | RACE | RACE | Days to 22 Oct | Hire to 22 Oct | Race days | Hire 23-25 Oct | Hire to 25 Oct (min 7) | Install (done) | Demob (later) | Delivery leg (done) | Pickup leg (later) | Billable now | Later | Board total to 25 Oct | Baseplan line | Baseplan start | Baseplan prebill | Basis / note
[7 empty] | Mon 07 Sep | Tue 08 Sep | Wed 09 Sep | Thu 10 Sep | Fri 11 Sep | Sat 12 Sep | Sun 13 Sep | Mon 14 Sep | Tue 15 Sep | Wed 16 Sep | Thu 17 Sep | Fri 18 Sep | Sat 19 Sep | Sun 20 Sep | Mon 21 Sep | Tue 22 Sep | Wed 23 Sep | Thu 24 Sep | Fri 25 Sep | Sat 26 Sep | Sun 27 Sep | Mon 28 Sep | Tue 29 Sep | Wed 30 Sep | Thu 01 Oct | Fri 02 Oct | Sat 03 Oct | Sun 04 Oct | Mon 05 Oct | Tue 06 Oct | Wed 07 Oct | Thu 08 Oct | Fri 09 Oct | Sat 10 Oct | Sun 11 Oct | Mon 12 Oct | Tue 13 Oct | Wed 14 Oct | Thu 15 Oct | Fri 16 Oct | Sat 17 Oct | Sun 18 Oct | Mon 19 Oct | Tue 20 Oct | Wed 21 Oct | Thu 22 Oct | Fri 23 Oct | Sat 24 Oct | Sun 25 Oct
VMS01 | 1211354 | EX0017 | Coates | VMS 01 · Gold Coast Highway (median strip), south of Queen St interse | 07 Sep | Map | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 46 | 2466.13 | 3 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | 4 | 2026-09-07 | 3591.87 | contract line and docket, 7 Sep (Timeline load T0001)
VMS02 | 1211370 | ES3206 | Coates | VMS 02 · Waterways Drive northbound | 07 Sep | Map | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 46 | 2466.13 | 3 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | 3 | 2026-09-07 | 3591.87 | contract line and docket, 7 Sep (Timeline load T0001)
VMS03 | 1271129 | 536UOO | Coates | VMS 03 · Gold Coast Highway (southbound), north of Breaker St interse | 07 Sep | Map | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 46 | 2466.13 | 3 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | 9 | 2026-09-07 | 3591.87 | contract line and docket, 7 Sep (Timeline load T0001)
VMS04 | 1191877 | EM6306 | Coates | VMS 04 · Admiralty Drive eastbound, Gold Coast Highway intersection | 07 Sep | Map | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 46 | 2466.13 | 3 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | 6 | 2026-09-07 | 3591.87 | contract line and docket, 7 Sep (Timeline load T0001)
VMS05 | 1211356 | ER9244 | Coates | VMS 05a · Relocate VMS05 to Gold Coast Highway (southbound), PB3 | 20 Oct | Map | [43 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 3 | 160.83 | 3 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 399.32 | 238.49 | 852.25 | 43 | 2026-10-20 | 107.22 | pinned at 05a by Andrew Fisher 20 Oct 10:08 AEST; docket 26141143 the same morning
VMS06 | 1211359 | ER9247 | Coates | VMS 06 · Gold Coast Highway northbound at Birt Ave, median strip, 'Th | 07 Sep | Map | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 46 | 2466.13 | 3 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | 7 | 2026-09-07 | 3591.87 | contract line and docket, 7 Sep (Timeline load T0001)
VMS07 | 1182999 | 410UFQ | Coates | VMS 07a · Relocate VMS07 to the eastern end of Macintosh Island Park b | 07 Sep | Map | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 46 | 2466.13 | 3 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | 5 | 2026-09-07 | 3591.87 | contract line and docket, 7 Sep (Timeline load T0001)
VMS08 | 1211383 | ER9381 | Coates | VMS 08 · Gold Coast Highway northbound, south of Staghorn intersectio | 07 Sep | Map | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 46 | 2466.13 | 3 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | 8 | 2026-09-07 | 3591.87 | contract line and docket, 7 Sep (Timeline load T0001)
VMS09 | 1211404 | TF15JR | Coates | VMS 09 · Gold Coast Highway (northbound), north of T E Peters Dr inte | 08 Oct | Map | [31 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 15 | 804.17 | 3 | 160.83 | 965.01 | 88.485 | 88.485 | 150 | 150 | 1042.66 | 238.49 | 1441.98 | 12 | 2026-10-08 | 1018.59 | Andrew's word on the page: 8 Oct 2026
VMS10 | 120T | V14221 | Premiair Hire | VMS 10 · Old Burleigh Rd (northbound), south of Queensland Ave inters | 08 Oct | Map | [31 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 15 | 804.17 | 3 | 160.83 | 965.01 | 88.485 | 88.485 | 150 | 150 | 1042.66 | 238.49 | 1441.98 | 13 | 2026-10-08 | 1018.59 | Andrew's word on the page: 8 Oct 2026
VMS11 | 467T | TE97G | Premiair Hire | VMS 11 · Macintosh Island Park, western end of Macintosh Island Park | 16 Oct | Map | [39 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 7 | 375.28 | 3 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | 15 | 2026-10-16 | 536.1 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0128, 2026-10-16)
VMS12 | 1211646 | TF59LR | Coates | VMS 12 · Macintosh Island Park, co-located with WC16 | 16 Oct | Map | [39 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 7 | 375.28 | 3 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | 16 | 2026-10-16 | 589.71 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0128, 2026-10-16)
VMS13 | 1191957 | EN3803 | Coates | VMS 13 · T14 DL — installed at the conclusion of track activity (Fri/ | 19 Oct | Map | [42 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 4 | 214.45 | 3 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | 32 | 2026-10-19 | 482.49 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS14 | 1201864 | TD98VJ | Coates | VMS 14 · Gold Coast Highway southbound — installed at the conclusion | 16 Oct | Map | [39 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 7 | 375.28 | 3 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | 34 | 2026-10-19 | 482.49 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0158, 2026-10-19); Baseplan starts it 2026-10-19
VMS15 | 1211348 | ER9217 | Coates | VMS 15 · T4 runoff — installed at the conclusion of track activity (F | 16 Oct | Map | [39 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 7 | 375.28 | 3 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | 35 | 2026-10-19 | 482.49 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0158, 2026-10-19); Baseplan starts it 2026-10-19
VMS16 | 1211376 | ES3211 | Coates | VMS 16 · T11 — installed at the conclusion of track activity (Fri/Sat | 16 Oct | Map | [39 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 7 | 375.28 | 3 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | 37 | 2026-10-19 | 482.49 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0158, 2026-10-19); Baseplan starts it 2026-10-19
VMS17 | 1211364 | ER9410 | Coates | VMS 17 · T12 runoff — installed at the conclusion of track activity ( | 16 Oct | Map | [39 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 7 | 375.28 | 3 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | 39 | 2026-10-19 | 482.49 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0158, 2026-10-19); Baseplan starts it 2026-10-19
VMS18 | 472T | TE58GZ | Premiair Hire | VMS 18 · Ocean Ave (westbound), Surfers Paradise Blvd intersection — | 19 Oct | Map | [42 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 4 | 214.45 | 3 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | 24 | 2026-10-19 | 375.27 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS19 | 487T | TE02H0 | Premiair Hire | VMS 19 · Concert egress, within the Palm Bar BOH compound | 19 Oct | Map | [42 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 4 | 214.45 | 3 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | 25 | 2026-10-19 | 375.27 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS20 | 475T | TE88HN | Premiair Hire | VMS 20 · The Esplanade (southbound), next to P60 | 19 Oct | Map | [42 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 4 | 214.45 | 3 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | 26 | 2026-10-19 | 375.27 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS21 | 97T | T16922 | Premiair Hire | VMS 21 · Staghorn Ave / Surfers Paradise Boulevard intersection (east | 22 Oct | Map | [45 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 1 | 53.61 | 3 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 292.1 | 238.49 | 852.25 | 28 | 2026-10-22 | 214.44 | arrival recorded on the page by Andrew Fisher
VMS22 | 445T | TE99CL | Premiair Hire | VMS 22 · South of Sundale Bridge (northbound traffic), in the traffic | 22 Oct | Map | [45 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 1 | 53.61 | 3 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 292.1 | 238.49 | 852.25 | 29 | 2026-10-21 | 375.27 | Andrew, 22 Oct: today's delivery (docket 26143911); the record's 21 Oct is to be corrected; Baseplan starts it 2026-10-21
VMS23 | 453T | TF54CQ | Premiair Hire | VMS 23 · Gold Coast Highway (north of Sundale Bridge), eastern side o | 19 Oct | Map | [42 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 53.61 | 4 | 214.45 | 3 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | 30 | 2026-10-19 | 375.27 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS24 | 450T | TE94CL | Premiair Hire | VMS 24 · The Esplanade before Staghorn Ave intersection (northbound) | 22 Oct | Map | [45 empty] | 53.61 | 53.61 | 53.61 | 53.61 | 1 | 53.61 | 3 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 292.1 | 238.49 | 852.25 | 31 | 2026-10-19 | 428.88 | Andrew, 22 Oct: today's delivery (docket 26143911); the record's 21 Oct is to be corrected; Baseplan starts it 2026-10-19
TOTAL | 24 boards | [5 empty] | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 375.28 | 482.5 | 482.5 | 482.5 | 482.5 | 482.5 | 482.5 | 482.5 | 482.5 | 804.17 | 804.17 | 804.17 | 1072.23 | 1125.84 | 1125.84 | 1286.68 | 1286.68 | 1286.68 | 1286.68 | 420 | 22516.83 | 72 | 3860.03 | 26912.97 | 2123.64 | 2123.64 | 3600 | 3600 | 28240.47 | 5723.64 | 38360.25 |  |  | 33345.42 | Baseplan prebills each line to its expected term (13 Nov for the 7 Sep boards)

## Charges & map
Board | Asset / fleet | Rego | Owner | Position now | Where | Lat | Lon | Map link | On site | Days to 22 Oct | Hire to 22 Oct | Hire 23-25 Oct | Hire to 25 Oct (min 7) | Install (done) | Demob (later) | Delivery leg (done) | Pickup leg (later) | Billable now | Later | Board total to 25 Oct | Basis / note
VMS01 | 1211354 | EX0017 | Coates | VMS 01 | Gold Coast Highway (median strip), south of Queen St intersection | -27.9737 | 153.4203 | https://www.google.com/maps?q=-27.973700,153.420280 | 07 Sep | 46 | 2466.13 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | contract line and docket, 7 Sep (Timeline load T0001) · position is the plan, not a pin taken on site
VMS02 | 1211370 | ES3206 | Coates | VMS 02 | Waterways Drive northbound | -27.979 | 153.4228 | https://www.google.com/maps?q=-27.979000,153.422800 | 07 Sep | 46 | 2466.13 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | contract line and docket, 7 Sep (Timeline load T0001) · position is the plan, not a pin taken on site
VMS03 | 1271129 | 536UOO | Coates | VMS 03 | Gold Coast Highway (southbound), north of Breaker St intersection | -27.9804 | 153.4222 | https://www.google.com/maps?q=-27.980400,153.422250 | 07 Sep | 46 | 2466.13 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | contract line and docket, 7 Sep (Timeline load T0001) · position is the plan, not a pin taken on site
VMS04 | 1191877 | EM6306 | Coates | VMS 04 | Admiralty Drive eastbound, Gold Coast Highway intersection | -27.9867 | 153.427 | https://www.google.com/maps?q=-27.986720,153.427000 | 07 Sep | 46 | 2466.13 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | contract line and docket, 7 Sep (Timeline load T0001) · position is the plan, not a pin taken on site
VMS05 | 1211356 | ER9244 | Coates | VMS 05a | Relocate VMS05 to Gold Coast Highway (southbound), PB3 | -27.9826 | 153.4246 | https://www.google.com/maps?q=-27.982639,153.424639 | 20 Oct | 3 | 160.83 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 399.32 | 238.49 | 852.25 | pinned at 05a by Andrew Fisher 20 Oct 10:08 AEST; docket 26141143 the same morning
VMS06 | 1211359 | ER9247 | Coates | VMS 06 | Gold Coast Highway northbound at Birt Ave, median strip, 'The Marriott' | -27.9927 | 153.428 | https://www.google.com/maps?q=-27.992700,153.428000 | 07 Sep | 46 | 2466.13 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | contract line and docket, 7 Sep (Timeline load T0001) · position is the plan, not a pin taken on site
VMS07 | 1182999 | 410UFQ | Coates | VMS 07a | Relocate VMS07 to the eastern end of Macintosh Island Park bridge | -27.9856 | 153.4297 | https://www.google.com/maps?q=-27.985575,153.429741 | 07 Sep | 46 | 2466.13 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | contract line and docket, 7 Sep (Timeline load T0001)
VMS08 | 1211383 | ER9381 | Coates | VMS 08 | Gold Coast Highway northbound, south of Staghorn intersection | -27.9955 | 153.4277 | https://www.google.com/maps?q=-27.995500,153.427700 | 07 Sep | 46 | 2466.13 | 160.83 | 2626.96 | 88.485 | 88.485 | 150 | 150 | 2704.61 | 238.49 | 3103.93 | contract line and docket, 7 Sep (Timeline load T0001) · position is the plan, not a pin taken on site
VMS09 | 1211404 | TF15JR | Coates | VMS 09 | Gold Coast Highway (northbound), north of T E Peters Dr intersection (southern end of the Convention Centre) | -28.0288 | 153.43 | https://www.google.com/maps?q=-28.028800,153.430050 | 08 Oct | 15 | 804.17 | 160.83 | 965.01 | 88.485 | 88.485 | 150 | 150 | 1042.66 | 238.49 | 1441.98 | Andrew's word on the page: 8 Oct 2026 · position is the plan, not a pin taken on site
VMS10 | 120T | V14221 | Premiair Hire | VMS 10 | Old Burleigh Rd (northbound), south of Queensland Ave intersection | -28.0297 | 153.4341 | https://www.google.com/maps?q=-28.029750,153.434100 | 08 Oct | 15 | 804.17 | 160.83 | 965.01 | 88.485 | 88.485 | 150 | 150 | 1042.66 | 238.49 | 1441.98 | Andrew's word on the page: 8 Oct 2026 · position is the plan, not a pin taken on site
VMS11 | 467T | TE97G | Premiair Hire | VMS 11 | Macintosh Island Park, western end of Macintosh Island Park bridge | -27.9861 | 153.4285 | https://www.google.com/maps?q=-27.986125,153.428467 | 16 Oct | 7 | 375.28 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0128, 2026-10-16)
VMS12 | 1211646 | TF59LR | Coates | VMS 12 | Macintosh Island Park, co-located with WC16 | -27.9859 | 153.4277 | https://www.google.com/maps?q=-27.985938,153.427692 | 16 Oct | 7 | 375.28 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0128, 2026-10-16) · position is the plan, not a pin taken on site
VMS13 | 1191957 | EN3803 | Coates | VMS 13 | T14 DL — installed at the conclusion of track activity (Fri/Sat/Sun); stored in the Altus compound, Cypress Ave | -27.9818 | 153.4245 | https://www.google.com/maps?q=-27.981783,153.424452 | 19 Oct | 4 | 214.45 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS14 | 1201864 | TD98VJ | Coates | VMS 14 | Gold Coast Highway southbound — installed at the conclusion of track activity (Fri/Sat/Sun); stored in the Altus compound, Cypress Ave | -27.9826 | 153.4244 | https://www.google.com/maps?q=-27.982576,153.424393 | 16 Oct | 7 | 375.28 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS15 | 1211348 | ER9217 | Coates | VMS 15 | T4 runoff — installed at the conclusion of track activity (Fri/Sat/Sun); stored in the T2 runoff | -27.9919 | 153.4294 | https://www.google.com/maps?q=-27.991937,153.429354 | 16 Oct | 7 | 375.28 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS16 | 1211376 | ES3211 | Coates | VMS 16 | T11 — installed at the conclusion of track activity (Fri/Sat/Sun); stored in the T11 runoff | -27.9818 | 153.4291 | https://www.google.com/maps?q=-27.981782,153.429140 | 16 Oct | 7 | 375.28 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS17 | 1211364 | ER9410 | Coates | VMS 17 | T12 runoff — installed at the conclusion of track activity (Fri/Sat/Sun); stored in the T10 runoff | -27.9816 | 153.427 | https://www.google.com/maps?q=-27.981594,153.427038 | 16 Oct | 7 | 375.28 | 160.83 | 536.12 | 88.485 | 88.485 | 150 | 150 | 613.77 | 238.49 | 1013.09 | recorded on site 2026-10-16 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS18 | 472T | TE58GZ | Premiair Hire | VMS 18 | Ocean Ave (westbound), Surfers Paradise Blvd intersection — Roadtek to remove/install Fri/Sat/Sun | -27.9931 | 153.4282 | https://www.google.com/maps?q=-27.993096,153.428198 | 19 Oct | 4 | 214.45 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS19 | 487T | TE02H0 | Premiair Hire | VMS 19 | Concert egress, within the Palm Bar BOH compound | -27.9851 | 153.4273 | https://www.google.com/maps?q=-27.985078,153.427267 | 19 Oct | 4 | 214.45 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS20 | 475T | TE88HN | Premiair Hire | VMS 20 | The Esplanade (southbound), next to P60 | -27.9935 | 153.4305 | https://www.google.com/maps?q=-27.993520,153.430527 | 19 Oct | 4 | 214.45 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19)
VMS21 | 97T | T16922 | Premiair Hire | VMS 21 | Staghorn Ave / Surfers Paradise Boulevard intersection (eastbound) | -27.9951 | 153.4293 | https://www.google.com/maps?q=-27.995098,153.429306 | 22 Oct | 1 | 53.61 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 292.1 | 238.49 | 852.25 | arrival recorded on the page by Andrew Fisher
VMS22 | 445T | TE99CL | Premiair Hire | VMS 22 | South of Sundale Bridge (northbound traffic), in the traffic switch lane at Tedder Ave intersection | -27.9975 | 153.4306 | https://www.google.com/maps?q=-27.997545,153.430588 | 22 Oct | 1 | 53.61 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 292.1 | 238.49 | 852.25 | Andrew, 22 Oct: today's delivery (docket 26143911); the record's 21 Oct is to be corrected
VMS23 | 453T | TF54CQ | Premiair Hire | VMS 23 | Gold Coast Highway (north of Sundale Bridge), eastern side of the road, for southbound traffic | -27.9748 | 153.4207 | https://www.google.com/maps?q=-27.974800,153.420700 | 19 Oct | 4 | 214.45 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 452.93 | 238.49 | 852.25 | recorded on site 2026-10-19 by Andrew Fisher (Timeline load T0158, 2026-10-19) · position is the plan, not a pin taken on site
VMS24 | 450T | TE94CL | Premiair Hire | VMS 24 | The Esplanade before Staghorn Ave intersection (northbound) | -27.9927 | 153.4282 | https://www.google.com/maps?q=-27.992674,153.428205 | 22 Oct | 1 | 53.61 | 160.83 | 375.28 | 88.485 | 88.485 | 150 | 150 | 292.1 | 238.49 | 852.25 | Andrew, 22 Oct: today's delivery (docket 26143911); the record's 21 Oct is to be corrected
TOTAL | 24 boards | [8 empty] | 420 | 22516.83 | 3860.03 | 26912.97 | 2123.64 | 2123.64 | 3600 | 3600 | 28240.47 | 5723.64 | 38360.25

## Rates & basis
Author: Andrew Fisher. 22 Oct 2026. Positions, identities and arrivals are the page's own VMS model, read read-only: the pin taken on site where Andrew took one (20-22 Oct), else the plan position; the map link opens that spot.
Rate: 2026 street card, VMS Board, Daily Rate 2026 $53.6115, ex GST, on the traffic-management block that carries a 7-day minimum. VMS is charged from the day the board goes in (the project manager's rule of 17 Sep 2026) until it comes off at demob.
Labour: the card's one VMS figure $176.97 (headed 2024), read as $88.49 install + $88.49 demob; install is done on every board on site, demob is at demob. Transport: the card says POA; $150 a leg is Baseplan's figure on this contract, pending Andrew's word.
Hire to 22 Oct is what has run. 23-25 Oct are the race days (shaded), shown but not yet run. Boards stay on hire until demob, so "to 25 Oct" is not the final hire.
On-site day: the record's arrival event (VMS21); Andrew's word of 22 Oct for VMS22 and VMS24 (today's delivery, docket 26143911; the record says 21 Oct and is to be corrected); the date Andrew said (VMS09, VMS10: 8 Oct); the day he recorded the board on site (VMS11-20, 23); the contract and docket for the seven 7 Sep boards; VMS05 the pin taken at 05a on 20 Oct.