## Summary by type
Type | Unit | Qty - Advanced bill us | Advanced rate | WE PAY ADVANCED | Qty - we charge V8s | Our rate | WE CHARGE V8s | Margin
Clean fence | m | 9068 | $10.00 | 90680 | 9068 | $16.16 | 146545.2 | 55865.2
Scrim fence | m | 3682.5 | $24.40 | 89853 | 3682.5 | $25.53 | 94014.35 | 4161.35
CCB | m | 7460.5 | $5.40 | 40286.7 | 7460.5 | $7.51, $9.65, $13.08 | 84575.44 | 44288.74
Vehicle gates | each | 219 | $50.00 | 10950 | 219 | $40.40 | 8847.6 | -2102.4
Pedestrian gates | each | 22 | $61.00 | 1342 | 22 | $36.18 | 796.04 | -545.96
Bases | each | 300 | $1.00 | 300 | 300 | $3.02 | 906 | 606
Labour | hr | 10.5 | $100.00 | 1050 | 10.5 | $142.00 | 1491 | 441
Dockets, line total |  |  |  | 234461.7 |  |  | 337175.63 | 102713.93
DOCKETS TOTAL (170) |  |  |  | 234461.7 |  |  | 337175.63 | 102713.93
labour notes — 108.5 h they bill on 42 notes, at the labour rate $142.00 an hour | [6 empty] | 15407
team leader — 46 day at what they cost ($200.00 a day) | [6 empty] | 9200
weed mat — 40 rolls at what they cost ($64.50 a roll) | [6 empty] | 2580
shade cloth — 4 rolls at what they cost ($196.00 a roll) | [6 empty] | 784
partial collection, order 4658850 (receipt 4922343) — at what it cost | [6 empty] | 195
Supplier extras at cost (team leader, weed mat, shade cloth, order 4658850) - what we pay |  |  |  | 10231.5
FENCING ON THE PAGE |  |  |  | 244693.2 |  |  | 365341.63 | 120648.43
Fence event labour, race days (event scope) 213 h | [6 empty] | 19412.82
Advanced race crew (forecast cost) |  |  |  | 29891
Scrim rolls (12) · 10000484/1 | [6 empty] | 984.12
Scrim rolls (10) · 10000484/2 | [6 empty] | 950
Scrim rolls (28) · 10000475/1 | [6 empty] | 2296.28
1.8 m fence, 144 m · 9997710/1 | [6 empty] | 190.08
Shade cloth, 144 m · 9997710/2 | [6 empty] | 1349.28
EVERYTHING INCLUDED |  |  |  | 274584.2 |  |  | 390524.21 | 115940.01

## By week
Week | Dockets | Invoiced | Not invoiced yet | Sheet | Advanced order(s) | We pay Advanced | We charge V8s | Margin
Week 1 | 27 | 27 | 0 | CON WK1 | 4647520 | 59658 | 89261.99 | 29603.99
Week 2 | 23 | 23 | 0 | CON WK2 | 4647519 | 25396.5 | 32890.24 | 7493.74
Week 3 | 14 | 14 | 0 | CON WK3 | 4647515 | 47504 | 62866.35 | 15362.35
Week 4 | 23 | 23 | 0 | CON WK4 | 4647517 | 24570 | 44266.84 | 19696.84
Week 5 | 29 | 28 | 1 | CON WK5 | 4647509 | 32620.5 | 44115.06 | 11494.56
Week 6 | 6 | 1 | 5 | CON WK6 |  | 10144 | 15097.64 | 4953.64
Event Week | 48 | 0 | 48 | EVENT WEEK |  | 34568.7 | 48677.51 | 14108.81
TOTAL | 170 | 116 | 54 |  |  | 234461.7 | 337175.63 | 102713.93

## Every docket line by line
Week | Date | Docket | Invoiced? | Type | Qty Advanced bill | Advanced rate | We pay Advanced | Qty we charge | Our rate | We charge V8s | Unit | Our line(s)
Week 1 | 2026-10-12 | 36596 | Invoiced 4647520 | Clean fence | 355 | 10 | 3550 | 355 | 16.1607 | 5737.05 | m | Clean
Week 1 | 2026-10-12 | 36596 | Invoiced 4647520 | CCB | 287.5 | 5.4 | 1552.5 | 287.5 | 13.08 | 3760.5 | m | CCB Demarc
Week 1 | 2026-10-12 | 36596 | Invoiced 4647520 | Vehicle gates | 12 | 50 | 600 | 12 | 40.4 | 484.8 | each | V Gates
Week 1 | 2026-10-12 | 36596 | Invoiced 4647520 | Pedestrian gates | 5 | 61 | 305 | 5 | 36.1839 | 180.92 | each | Ped Gates
Week 1 | 2026-10-12 | 36596 | docket total |  |  |  | 6007.5 |  |  | 10163.27
Week 1 | 2026-10-12 | 36597 | Invoiced 4647520 | Clean fence | -17.5 | 10 | -175 | -17.5 | 16.1607 | -282.81 | m | Clean — the fence under the scrim, charged once in the scrim
Week 1 | 2026-10-12 | 36597 | Invoiced 4647520 | Scrim fence | 17.5 | 24.4 | 427 | 17.5 | 25.53 | 446.78 | m | Scrim
Week 1 | 2026-10-12 | 36597 | docket total |  |  |  | 252 |  |  | 163.97
Week 1 | 2026-10-12 | 36598 | Invoiced 4647520 | Scrim fence | 7.5 | 24.4 | 183 | 7.5 | 25.53 | 191.48 | m | Scrim
Week 1 | 2026-10-12 | 36598 | docket total |  |  |  | 183 |  |  | 191.48
Week 1 | 2026-10-12 | 36599 | Invoiced 4647520 | Scrim fence | 147.5 | 24.4 | 3599 | 147.5 | 25.53 | 3765.68 | m | Scrim
Week 1 | 2026-10-12 | 36599 | docket total |  |  |  | 3599 |  |  | 3765.68
Week 1 | 2026-10-12 | 36600 | Invoiced 4647520 | Bases | 200 | 1 | 200 | 200 | 3.02 | 604 | each | Bases
Week 1 | 2026-10-12 | 36600 | docket total |  |  |  | 200 |  |  | 604
Week 1 | 2026-10-12 | 36601 | Invoiced 4647520 | Scrim fence | 25 | 24.4 | 610 | 25 | 25.53 | 638.25 | m | Scrim
Week 1 | 2026-10-12 | 36601 | docket total |  |  |  | 610 |  |  | 638.25
Week 1 | 2026-10-12 | 36602 | Invoiced 4647520 | Scrim fence | 45 | 24.4 | 1098 | 45 | 25.53 | 1148.85 | m | Scrim
Week 1 | 2026-10-12 | 36602 | docket total |  |  |  | 1098 |  |  | 1148.85
Week 1 | 2026-10-13 | 36603 | Invoiced 4647520 | Clean fence | 450 | 10 | 4500 | 450 | 16.1607 | 7272.32 | m | Clean
Week 1 | 2026-10-13 | 36603 | Invoiced 4647520 | Scrim fence | 52.5 | 24.4 | 1281 | 52.5 | 25.53 | 1340.33 | m | Scrim
Week 1 | 2026-10-13 | 36603 | Invoiced 4647520 | CCB | 672.5 | 5.4 | 3631.5 | 672.5 | 13.08 | 8796.3 | m | CCB Demarc
Week 1 | 2026-10-13 | 36603 | Invoiced 4647520 | Vehicle gates | 14 | 50 | 700 | 14 | 40.4 | 565.6 | each | V Gates
Week 1 | 2026-10-13 | 36603 | Invoiced 4647520 | Pedestrian gates | 4 | 61 | 244 | 4 | 36.1839 | 144.74 | each | Ped Gates
Week 1 | 2026-10-13 | 36603 | docket total |  |  |  | 10356.5 |  |  | 18119.29
Week 1 | 2026-10-13 | 36604 | Invoiced 4647520 | CCB | 105 | 5.4 | 567 | 105 | 9.6511 | 1013.37 | m | CCB flat feet
Week 1 | 2026-10-13 | 36604 | docket total |  |  |  | 567 |  |  | 1013.37
Week 1 | 2026-10-13 | 36605 | Invoiced 4647520 | Clean fence | 95 | 10 | 950 | 95 | 16.1607 | 1535.27 | m | Clean
Week 1 | 2026-10-13 | 36605 | docket total |  |  |  | 950 |  |  | 1535.27
Week 1 | 2026-10-13 | 36606 | Invoiced 4647520 | Clean fence | 10 | 10 | 100 | 10 | 16.1607 | 161.61 | m | Clean
Week 1 | 2026-10-13 | 36606 | docket total |  |  |  | 100 |  |  | 161.61
Week 1 | 2026-10-14 | 36607 | Invoiced 4647520 | Clean fence | 47.5 | 10 | 475 | 47.5 | 16.1607 | 767.63 | m | Clean
Week 1 | 2026-10-14 | 36607 | docket total |  |  |  | 475 |  |  | 767.63
Week 1 | 2026-10-14 | 36608 | Invoiced 4647520 | Clean fence | 97.5 | 10 | 975 | 97.5 | 16.1607 | 1575.67 | m | Clean
Week 1 | 2026-10-14 | 36608 | Invoiced 4647520 | CCB | 192.5 | 5.4 | 1039.5 | 192.5 | 13.08 | 2517.9 | m | CCB Demarc
Week 1 | 2026-10-14 | 36608 | Invoiced 4647520 | Vehicle gates | 8 | 50 | 400 | 8 | 40.4 | 323.2 | each | V Gates
Week 1 | 2026-10-14 | 36608 | docket total |  |  |  | 2414.5 |  |  | 4416.77
Week 1 | 2026-10-14 | 36609 | Invoiced 4647520 | Clean fence | 285 | 10 | 2850 | 285 | 16.1607 | 4605.8 | m | Clean
Week 1 | 2026-10-14 | 36609 | Invoiced 4647520 | Scrim fence | 125 | 24.4 | 3050 | 125 | 25.53 | 3191.25 | m | Scrim
Week 1 | 2026-10-14 | 36609 | Invoiced 4647520 | Vehicle gates | 4 | 50 | 200 | 4 | 40.4 | 161.6 | each | V Gates
Week 1 | 2026-10-14 | 36609 | docket total |  |  |  | 6100 |  |  | 7958.65
Week 1 | 2026-10-14 | 36610 | Invoiced 4647520 | Clean fence | 347.5 | 10 | 3475 | 347.5 | 16.1607 | 5615.84 | m | Clean
Week 1 | 2026-10-14 | 36610 | Invoiced 4647520 | CCB | 200 | 5.4 | 1080 | 200 | 13.08 | 2616 | m | CCB Demarc
Week 1 | 2026-10-14 | 36610 | Invoiced 4647520 | Vehicle gates | 8 | 50 | 400 | 8 | 40.4 | 323.2 | each | V Gates
Week 1 | 2026-10-14 | 36610 | Invoiced 4647520 | Pedestrian gates | 2 | 61 | 122 | 2 | 36.1839 | 72.37 | each | Ped Gates
Week 1 | 2026-10-14 | 36610 | docket total |  |  |  | 5077 |  |  | 8627.41
Week 1 | 2026-10-15 | 36611 | Invoiced 4647520 | Clean fence | 125 | 10 | 1250 | 125 | 16.1607 | 2020.09 | m | Clean
Week 1 | 2026-10-15 | 36611 | Invoiced 4647520 | Scrim fence | 30 | 24.4 | 732 | 30 | 25.53 | 765.9 | m | Scrim
Week 1 | 2026-10-15 | 36611 | Invoiced 4647520 | CCB | 130 | 5.4 | 702 | 130 | 7.51 | 976.3 | m | CCB Event
Week 1 | 2026-10-15 | 36611 | Invoiced 4647520 | Vehicle gates | 4 | 50 | 200 | 4 | 40.4 | 161.6 | each | V Gates
Week 1 | 2026-10-15 | 36611 | docket total |  |  |  | 2884 |  |  | 3923.89
Week 1 | 2026-10-15 | 36612 | Invoiced 4647520 | Clean fence | 275 | 10 | 2750 | 275 | 16.1607 | 4444.19 | m | Clean
Week 1 | 2026-10-15 | 36612 | Invoiced 4647520 | Vehicle gates | 16 | 50 | 800 | 16 | 40.4 | 646.4 | each | V Gates
Week 1 | 2026-10-15 | 36612 | Invoiced 4647520 | Pedestrian gates | 3 | 61 | 183 | 3 | 36.1839 | 108.55 | each | Ped Gates
Week 1 | 2026-10-15 | 36612 | docket total |  |  |  | 3733 |  |  | 5199.14
Week 1 | 2026-10-15 | 36613 | Invoiced 4647520 | CCB | 70 | 5.4 | 378 | 70 | 7.51 | 525.7 | m | CCB Event
Week 1 | 2026-10-15 | 36613 | docket total |  |  |  | 378 |  |  | 525.7
Week 1 | 2026-10-15 | 36614 | Invoiced 4647520 | Clean fence | -50 | 10 | -500 | -50 | 16.1607 | -808.03 | m | Clean
Week 1 | 2026-10-15 | 36614 | Invoiced 4647520 | Scrim fence | 85 | 24.4 | 2074 | 85 | 25.53 | 2170.05 | m | Scrim
Week 1 | 2026-10-15 | 36614 | Invoiced 4647520 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 1 | 2026-10-15 | 36614 | docket total |  |  |  | 1674 |  |  | 1442.82
Week 1 | 2026-10-15 | 36615 | Invoiced 4647520 | Clean fence | 70 | 10 | 700 | 70 | 16.1607 | 1131.25 | m | Clean
Week 1 | 2026-10-15 | 36615 | Invoiced 4647520 | Scrim fence | 40 | 24.4 | 976 | 40 | 25.53 | 1021.2 | m | Scrim
Week 1 | 2026-10-15 | 36615 | docket total |  |  |  | 1676 |  |  | 2152.45
Week 1 | 2026-10-15 | 36616 | Invoiced 4647520 | Clean fence | 142.5 | 10 | 1425 | 142.5 | 16.1607 | 2302.9 | m | Clean
Week 1 | 2026-10-15 | 36616 | Invoiced 4647520 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 1 | 2026-10-15 | 36616 | docket total |  |  |  | 1525 |  |  | 2383.7
Week 1 | 2026-10-16 | 36617 | Invoiced 4647520 | Clean fence | 117.5 | 10 | 1175 | 117.5 | 16.1607 | 1898.88 | m | Clean
Week 1 | 2026-10-16 | 36617 | Invoiced 4647520 | Scrim fence | 37.5 | 24.4 | 915 | 37.5 | 25.53 | 957.38 | m | Scrim
Week 1 | 2026-10-16 | 36617 | docket total |  |  |  | 2090 |  |  | 2856.26
Week 1 | 2026-10-16 | 36618 | Invoiced 4647520 | Clean fence | 147.5 | 10 | 1475 | 147.5 | 16.1607 | 2383.7 | m | Clean
Week 1 | 2026-10-16 | 36618 | Invoiced 4647520 | Vehicle gates | 4 | 50 | 200 | 4 | 40.4 | 161.6 | each | V Gates
Week 1 | 2026-10-16 | 36618 | docket total |  |  |  | 1675 |  |  | 2545.3
Week 1 | 2026-10-16 | 36619 | Invoiced 4647520 | Clean fence | 242.5 | 10 | 2425 | 242.5 | 16.1607 | 3918.97 | m | Clean
Week 1 | 2026-10-16 | 36619 | Invoiced 4647520 | CCB | 302.5 | 5.4 | 1633.5 | 302.5 | 7.51 | 2271.78 | m | CCB Event
Week 1 | 2026-10-16 | 36619 | Invoiced 4647520 | Vehicle gates | 8 | 50 | 400 | 8 | 40.4 | 323.2 | each | V Gates
Week 1 | 2026-10-16 | 36619 | docket total |  |  |  | 4458.5 |  |  | 6513.95
Week 1 | 2026-10-16 | 36620 | Invoiced 4647520 | Bases | 100 | 1 | 100 | 100 | 3.02 | 302 | each | Bases
Week 1 | 2026-10-16 | 36620 | docket total |  |  |  | 100 |  |  | 302
Week 1 | 2026-10-16 | 36621 | Invoiced 4647520 | Clean fence | 2.5 | 10 | 25 | 2.5 | 16.1607 | 40.4 | m | Clean
Week 1 | 2026-10-16 | 36621 | docket total |  |  |  | 25 |  |  | 40.4
Week 1 | 2026-10-16 | 36622 | Invoiced 4647520 | Clean fence | 115 | 10 | 1150 | 115 | 16.1607 | 1858.48 | m | Clean
Week 1 | 2026-10-16 | 36622 | Invoiced 4647520 | Vehicle gates | 6 | 50 | 300 | 6 | 40.4 | 242.4 | each | V Gates
Week 1 | 2026-10-16 | 36622 | docket total |  |  |  | 1450 |  |  | 2100.88
Week 2 | 2026-10-06 | 36573 | Invoiced 4647519 | Clean fence | 97.5 | 10 | 975 | 97.5 | 16.1607 | 1575.67 | m | Clean
Week 2 | 2026-10-06 | 36573 | docket total |  |  |  | 975 |  |  | 1575.67
Week 2 | 2026-10-06 | 36574 | Invoiced 4647519 | Clean fence | 162.5 | 10 | 1625 | 162.5 | 16.1607 | 2626.11 | m | Clean
Week 2 | 2026-10-06 | 36574 | Invoiced 4647519 | Scrim fence | 10 | 24.4 | 244 | 10 | 25.53 | 255.3 | m | Scrim
Week 2 | 2026-10-06 | 36574 | Invoiced 4647519 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 2 | 2026-10-06 | 36574 | docket total |  |  |  | 1969 |  |  | 2962.21
Week 2 | 2026-10-06 | 36575 | Invoiced 4647519 | Clean fence | 120 | 10 | 1200 | 120 | 16.1607 | 1939.28 | m | Clean
Week 2 | 2026-10-06 | 36575 | Invoiced 4647519 | Vehicle gates | 6 | 50 | 300 | 6 | 40.4 | 242.4 | each | V Gates
Week 2 | 2026-10-06 | 36575 | docket total |  |  |  | 1500 |  |  | 2181.68
Week 2 | 2026-10-06 | 36576 | Invoiced 4647519 | Scrim fence | 2.5 | 24.4 | 61 | 2.5 | 25.53 | 63.83 | m | Scrim
Week 2 | 2026-10-06 | 36576 | docket total |  |  |  | 61 |  |  | 63.83
Week 2 | 2026-10-06 | 36577 | Invoiced 4647519 | Scrim fence | 25 | 24.4 | 610 | 25 | 25.53 | 638.25 | m | Scrim
Week 2 | 2026-10-06 | 36577 | Invoiced 4647519 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 2 | 2026-10-06 | 36577 | docket total |  |  |  | 710 |  |  | 719.05
Week 2 | 2026-10-06 | 36578 | Invoiced 4647519 | Clean fence | 75 | 10 | 750 | 75 | 16.1607 | 1212.05 | m | Clean
Week 2 | 2026-10-06 | 36578 | docket total |  |  |  | 750 |  |  | 1212.05
Week 2 | 2026-10-07 | 36579 | Invoiced 4647519 | Clean fence | 35 | 10 | 350 | 35 | 16.1607 | 565.62 | m | Clean
Week 2 | 2026-10-07 | 36579 | Invoiced 4647519 | Scrim fence | 122.5 | 24.4 | 2989 | 122.5 | 25.53 | 3127.43 | m | Scrim
Week 2 | 2026-10-07 | 36579 | Invoiced 4647519 | Vehicle gates | 8 | 50 | 400 | 8 | 40.4 | 323.2 | each | V Gates
Week 2 | 2026-10-07 | 36579 | Invoiced 4647519 | Pedestrian gates | 2 | 61 | 122 | 2 | 36.1839 | 72.37 | each | Ped Gates
Week 2 | 2026-10-07 | 36579 | docket total |  |  |  | 3861 |  |  | 4088.62
Week 2 | 2026-10-07 | 36580 | Invoiced 4647519 | Clean fence | 150 | 10 | 1500 | 150 | 16.1607 | 2424.1 | m | Clean
Week 2 | 2026-10-07 | 36580 | docket total |  |  |  | 1500 |  |  | 2424.1
Week 2 | 2026-10-07 | 36581 | Invoiced 4647519 | Clean fence | -72.5 | 10 | -725 | -72.5 | 16.1607 | -1171.65 | m | Clean — the fence under the scrim, charged once in the scrim
Week 2 | 2026-10-07 | 36581 | Invoiced 4647519 | Scrim fence | 72.5 | 24.4 | 1769 | 72.5 | 25.53 | 1850.93 | m | Scrim
Week 2 | 2026-10-07 | 36581 | docket total |  |  |  | 1044 |  |  | 679.28
Week 2 | 2026-10-07 | 36582 | Invoiced 4647519 | Clean fence | 77.5 | 10 | 775 | 77.5 | 16.1607 | 1252.45 | m | Clean
Week 2 | 2026-10-07 | 36582 | Invoiced 4647519 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 2 | 2026-10-07 | 36582 | docket total |  |  |  | 875 |  |  | 1333.25
Week 2 | 2026-10-08 | 36583 | Invoiced 4647519 | Clean fence | 145 | 10 | 1450 | 145 | 16.1607 | 2343.3 | m | Clean
Week 2 | 2026-10-08 | 36583 | Invoiced 4647519 | Scrim fence | 55 | 24.4 | 1342 | 55 | 25.53 | 1404.15 | m | Scrim
Week 2 | 2026-10-08 | 36583 | Invoiced 4647519 | Vehicle gates | 6 | 50 | 300 | 6 | 40.4 | 242.4 | each | V Gates
Week 2 | 2026-10-08 | 36583 | docket total |  |  |  | 3092 |  |  | 3989.85
Week 2 | 2026-10-08 | 36584 | Invoiced 4647519 | Scrim fence | 7.5 | 24.4 | 183 | 7.5 | 25.53 | 191.48 | m | Scrim
Week 2 | 2026-10-08 | 36584 | docket total |  |  |  | 183 |  |  | 191.48
Week 2 | 2026-10-08 | 36585 | Invoiced 4647519 | Scrim fence | 45 | 24.4 | 1098 | 45 | 25.53 | 1148.85 | m | Scrim
Week 2 | 2026-10-08 | 36585 | Invoiced 4647519 | Pedestrian gates | 1 | 61 | 61 | 1 | 36.1839 | 36.18 | each | Ped Gates
Week 2 | 2026-10-08 | 36585 | docket total |  |  |  | 1159 |  |  | 1185.03
Week 2 | 2026-10-08 | 36586 | Invoiced 4647519 | Scrim fence | 25 | 24.4 | 610 | 25 | 25.53 | 638.25 | m | Scrim
Week 2 | 2026-10-08 | 36586 | docket total |  |  |  | 610 |  |  | 638.25
Week 2 | 2026-10-09 | 36587 | Invoiced 4647519 | Scrim fence | 22.5 | 24.4 | 549 | 22.5 | 25.53 | 574.43 | m | Scrim
Week 2 | 2026-10-09 | 36587 | Invoiced 4647519 | Vehicle gates | 3 | 50 | 150 | 3 | 40.4 | 121.2 | each | V Gates
Week 2 | 2026-10-09 | 36587 | docket total |  |  |  | 699 |  |  | 695.63
Week 2 | 2026-10-09 | 36588 | Invoiced 4647519 | Clean fence | 32.5 | 10 | 325 | 32.5 | 16.1607 | 525.22 | m | Clean
Week 2 | 2026-10-09 | 36588 | Invoiced 4647519 | Scrim fence | 62.5 | 24.4 | 1525 | 62.5 | 25.53 | 1595.63 | m | Scrim
Week 2 | 2026-10-09 | 36588 | docket total |  |  |  | 1850 |  |  | 2120.85
Week 2 | 2026-10-09 | 36589 | Invoiced 4647519 | Scrim fence | 15 | 24.4 | 366 | 15 | 25.53 | 382.95 | m | Scrim
Week 2 | 2026-10-09 | 36589 | docket total |  |  |  | 366 |  |  | 382.95
Week 2 | 2026-10-09 | 36590 | Invoiced 4647519 | Clean fence | 97.5 | 10 | 975 | 97.5 | 16.1607 | 1575.67 | m | Clean
Week 2 | 2026-10-09 | 36590 | Invoiced 4647519 | Vehicle gates | 4 | 50 | 200 | 4 | 40.4 | 161.6 | each | V Gates
Week 2 | 2026-10-09 | 36590 | docket total |  |  |  | 1175 |  |  | 1737.27
Week 2 | 2026-10-09 | 36591 | Invoiced 4647519 | CCB | 105 | 5.4 | 567 | 105 | 7.51 | 788.55 | m | CCB Event
Week 2 | 2026-10-09 | 36591 | docket total |  |  |  | 567 |  |  | 788.55
Week 2 | 2026-10-09 | 36592 | Invoiced 4647519 | Clean fence | 137.5 | 10 | 1375 | 137.5 | 16.1607 | 2222.1 | m | Clean
Week 2 | 2026-10-09 | 36592 | docket total |  |  |  | 1375 |  |  | 2222.1
Week 2 | 2026-10-09 | 36593 | Invoiced 4647519 | Clean fence | 90 | 10 | 900 | 90 | 16.1607 | 1454.46 | m | Clean
Week 2 | 2026-10-09 | 36593 | docket total |  |  |  | 900 |  |  | 1454.46
Week 2 | 2026-10-09 | 36594 | Invoiced 4647519 | CCB | 22.5 | 5.4 | 121.5 | 22.5 | 7.51 | 168.98 | m | CCB Event
Week 2 | 2026-10-09 | 36594 | docket total |  |  |  | 121.5 |  |  | 168.98
Week 2 | 2026-10-09 | 36595 | Invoiced 4647519 | CCB | 10 | 5.4 | 54 | 10 | 7.51 | 75.1 | m | CCB Event
Week 2 | 2026-10-09 | 36595 | docket total |  |  |  | 54 |  |  | 75.1
Week 3 | 2026-09-28 | 36559 | Invoiced 4647515 | Clean fence | 105 | 10 | 1050 | 105 | 16.1607 | 1696.87 | m | Clean
Week 3 | 2026-09-28 | 36559 | Invoiced 4647515 | CCB | 202.5 | 5.4 | 1093.5 | 202.5 | 13.08 | 2648.7 | m | CCB Demarc
Week 3 | 2026-09-28 | 36559 | Invoiced 4647515 | Vehicle gates | 10 | 50 | 500 | 10 | 40.4 | 404 | each | V Gates
Week 3 | 2026-09-28 | 36559 | docket total |  |  |  | 2643.5 |  |  | 4749.57
Week 3 | 2026-09-28 | 36560 | Invoiced 4647515 | Clean fence | 65 | 10 | 650 | 65 | 16.1607 | 1050.45 | m | Clean
Week 3 | 2026-09-28 | 36560 | Invoiced 4647515 | Scrim fence | 427.5 | 24.4 | 10431 | 427.5 | 25.53 | 10914.08 | m | Scrim
Week 3 | 2026-09-28 | 36560 | Invoiced 4647515 | CCB | 447.5 | 5.4 | 2416.5 | 447.5 | 13.08 | 5853.3 | m | CCB Demarc
Week 3 | 2026-09-28 | 36560 | Invoiced 4647515 | Vehicle gates | 6 | 50 | 300 | 6 | 40.4 | 242.4 | each | V Gates
Week 3 | 2026-09-28 | 36560 | Invoiced 4647515 | Pedestrian gates | 1 | 61 | 61 | 1 | 36.1839 | 36.18 | each | Ped Gates
Week 3 | 2026-09-28 | 36560 | docket total |  |  |  | 13858.5 |  |  | 18096.41
Week 3 | 2026-09-28 | 36561 | Invoiced 4647515 | Clean fence | 127.5 | 10 | 1275 | 127.5 | 16.1607 | 2060.49 | m | Clean
Week 3 | 2026-09-28 | 36561 | Invoiced 4647515 | Vehicle gates | 6 | 50 | 300 | 6 | 40.4 | 242.4 | each | V Gates
Week 3 | 2026-09-28 | 36561 | docket total |  |  |  | 1575 |  |  | 2302.89
Week 3 | 2026-09-29 | 36562 | Invoiced 4647515 | Clean fence | 327.5 | 10 | 3275 | 327.5 | 16.1607 | 5292.63 | m | Clean
Week 3 | 2026-09-29 | 36562 | docket total |  |  |  | 3275 |  |  | 5292.63
Week 3 | 2026-09-29 | 36563 | Invoiced 4647515 | CCB | 150 | 5.4 | 810 | 150 | 13.08 | 1962 | m | CCB Demarc
Week 3 | 2026-09-29 | 36563 | docket total |  |  |  | 810 |  |  | 1962
Week 3 | 2026-09-29 | 36564 | Invoiced 4647515 | Scrim fence | 40 | 24.4 | 976 | 40 | 25.53 | 1021.2 | m | Scrim
Week 3 | 2026-09-29 | 36564 | docket total |  |  |  | 976 |  |  | 1021.2
Week 3 | 2026-09-29 | 36565 | Invoiced 4647515 | Clean fence | 25 | 10 | 250 | 25 | 16.1607 | 404.02 | m | Clean
Week 3 | 2026-09-29 | 36565 | docket total |  |  |  | 250 |  |  | 404.02
Week 3 | 2026-09-30 | 36566 | Invoiced 4647515 | Clean fence | -270 | 10 | -2700 | -270 | 16.1607 | -4363.39 | m | Clean — the fence under the scrim, charged once in the scrim
Week 3 | 2026-09-30 | 36566 | Invoiced 4647515 | Scrim fence | 270 | 24.4 | 6588 | 270 | 25.53 | 6893.1 | m | Scrim
Week 3 | 2026-09-30 | 36566 | docket total |  |  |  | 3888 |  |  | 2529.71
Week 3 | 2026-09-30 | 36567 | Invoiced 4647515 | CCB | 215 | 5.4 | 1161 | 215 | 7.51 | 1614.65 | m | CCB Event
Week 3 | 2026-09-30 | 36567 | docket total |  |  |  | 1161 |  |  | 1614.65
Week 3 | 2026-10-01 | 36568 | Invoiced 4647515 | Scrim fence | 447.5 | 24.4 | 10919 | 447.5 | 25.53 | 11424.68 | m | Scrim
Week 3 | 2026-10-01 | 36568 | Invoiced 4647515 | CCB | 420 | 5.4 | 2268 | 420 | 13.08 | 5493.6 | m | CCB Demarc
Week 3 | 2026-10-01 | 36568 | Invoiced 4647515 | Vehicle gates | 6 | 50 | 300 | 6 | 40.4 | 242.4 | each | V Gates
Week 3 | 2026-10-01 | 36568 | docket total |  |  |  | 13487 |  |  | 17160.68
Week 3 | 2026-10-02 | 36569 | Invoiced 4647515 | Clean fence | 12.5 | 10 | 125 | 12.5 | 16.1607 | 202.01 | m | Clean
Week 3 | 2026-10-02 | 36569 | Invoiced 4647515 | Scrim fence | 65 | 24.4 | 1586 | 65 | 25.53 | 1659.45 | m | Scrim
Week 3 | 2026-10-02 | 36569 | Invoiced 4647515 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 3 | 2026-10-02 | 36569 | docket total |  |  |  | 1811 |  |  | 1942.26
Week 3 | 2026-10-02 | 36570 | Invoiced 4647515 | Clean fence | -10 | 10 | -100 | -10 | 16.1607 | -161.61 | m | Clean — the fence under the scrim, charged once in the scrim
Week 3 | 2026-10-02 | 36570 | Invoiced 4647515 | Scrim fence | 10 | 24.4 | 244 | 10 | 25.53 | 255.3 | m | Scrim
Week 3 | 2026-10-02 | 36570 | docket total |  |  |  | 144 |  |  | 93.69
Week 3 | 2026-10-02 | 36571 | Invoiced 4647515 | Clean fence | 332.5 | 10 | 3325 | 332.5 | 16.1607 | 5373.43 | m | Clean
Week 3 | 2026-10-02 | 36571 | Invoiced 4647515 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 3 | 2026-10-02 | 36571 | docket total |  |  |  | 3425 |  |  | 5454.23
Week 3 | 2026-10-02 | 36572 | Invoiced 4647515 | Clean fence | 10 | 10 | 100 | 10 | 16.1607 | 161.61 | m | Clean
Week 3 | 2026-10-02 | 36572 | Invoiced 4647515 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 3 | 2026-10-02 | 36572 | docket total |  |  |  | 200 |  |  | 242.41
Week 4 | 2026-09-21 | 36536 | Invoiced 4647517 | Clean fence | 167.5 | 10 | 1675 | 167.5 | 16.1607 | 2706.92 | m | Clean
Week 4 | 2026-09-21 | 36536 | Invoiced 4647517 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 4 | 2026-09-21 | 36536 | docket total |  |  |  | 1775 |  |  | 2787.72
Week 4 | 2026-09-21 | 36537 | Invoiced 4647517 | Clean fence | 167.5 | 10 | 1675 | 167.5 | 16.1607 | 2706.92 | m | Clean
Week 4 | 2026-09-21 | 36537 | Invoiced 4647517 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 4 | 2026-09-21 | 36537 | docket total |  |  |  | 1775 |  |  | 2787.72
Week 4 | 2026-09-21 | 36538 | Invoiced 4647517 | Clean fence | 32.5 | 10 | 325 | 32.5 | 16.1607 | 525.22 | m | Clean
Week 4 | 2026-09-21 | 36538 | docket total |  |  |  | 325 |  |  | 525.22
Week 4 | 2026-09-22 | 36539 | Invoiced 4647517 | Clean fence | -40 | 10 | -400 | -40 | 16.1607 | -646.43 | m | Clean — the fence under the scrim, charged once in the scrim
Week 4 | 2026-09-22 | 36539 | Invoiced 4647517 | Scrim fence | 40 | 24.4 | 976 | 40 | 25.53 | 1021.2 | m | Scrim
Week 4 | 2026-09-22 | 36539 | docket total |  |  |  | 576 |  |  | 374.77
Week 4 | 2026-09-22 | 36540 | Invoiced 4647517 | CCB | 370 | 5.4 | 1998 | 370 | 13.08 | 4839.6 | m | CCB Demarc
Week 4 | 2026-09-22 | 36540 | docket total |  |  |  | 1998 |  |  | 4839.6
Week 4 | 2026-09-22 | 36541 | Invoiced 4647517 | CCB | 25 | 5.4 | 135 | 25 | 7.51 | 187.75 | m | CCB Event
Week 4 | 2026-09-22 | 36541 | docket total |  |  |  | 135 |  |  | 187.75
Week 4 | 2026-09-22 | 36542 | Invoiced 4647517 | CCB | 60 | 5.4 | 324 | 60 | 13.08 | 784.8 | m | CCB Demarc
Week 4 | 2026-09-22 | 36542 | docket total |  |  |  | 324 |  |  | 784.8
Week 4 | 2026-09-23 | 36543 | Invoiced 4647517 | Clean fence | 20 | 10 | 200 | 20 | 16.1607 | 323.21 | m | Clean
Week 4 | 2026-09-23 | 36543 | docket total |  |  |  | 200 |  |  | 323.21
Week 4 | 2026-09-23 | 36544 | Invoiced 4647517 | Scrim fence | 52.5 | 24.4 | 1281 | 52.5 | 25.53 | 1340.33 | m | Scrim
Week 4 | 2026-09-23 | 36544 | Invoiced 4647517 | Pedestrian gates | 1 | 61 | 61 | 1 | 36.1839 | 36.18 | each | Ped Gates
Week 4 | 2026-09-23 | 36544 | docket total |  |  |  | 1342 |  |  | 1376.51
Week 4 | 2026-09-23 | 36545 | Invoiced 4647517 | Clean fence | 10 | 10 | 100 | 10 | 16.1607 | 161.61 | m | Clean
Week 4 | 2026-09-23 | 36545 | docket total |  |  |  | 100 |  |  | 161.61
Week 4 | 2026-09-23 | 36546 | Invoiced 4647517 | Clean fence | 22.5 | 10 | 225 | 22.5 | 16.1607 | 363.62 | m | Clean
Week 4 | 2026-09-23 | 36546 | docket total |  |  |  | 225 |  |  | 363.62
Week 4 | 2026-09-23 | 36547 | Invoiced 4647517 | Scrim fence | 72.5 | 24.4 | 1769 | 72.5 | 25.53 | 1850.93 | m | Scrim
Week 4 | 2026-09-23 | 36547 | docket total |  |  |  | 1769 |  |  | 1850.93
Week 4 | 2026-09-23 | 36548 | Invoiced 4647517 | Clean fence | 475 | 10 | 4750 | 475 | 16.1607 | 7676.33 | m | Clean
Week 4 | 2026-09-23 | 36548 | docket total |  |  |  | 4750 |  |  | 7676.33
Week 4 | 2026-09-23 | 36549 | Invoiced 4647517 | Clean fence | 13 | 10 | 130 | 13 | 16.1607 | 210.09 | m | Clean
Week 4 | 2026-09-23 | 36549 | docket total |  |  |  | 130 |  |  | 210.09
Week 4 | 2026-09-24 | 36550 | Invoiced 4647517 | Clean fence | 52.5 | 10 | 525 | 52.5 | 16.1607 | 848.44 | m | Clean
Week 4 | 2026-09-24 | 36550 | Invoiced 4647517 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 4 | 2026-09-24 | 36550 | docket total |  |  |  | 625 |  |  | 929.24
Week 4 | 2026-09-24 | 36551 | Invoiced 4647517 | CCB | 510 | 5.4 | 2754 | 510 | 13.08 | 6670.8 | m | CCB Demarc
Week 4 | 2026-09-24 | 36551 | docket total |  |  |  | 2754 |  |  | 6670.8
Week 4 | 2026-09-24 | 36552 | Invoiced 4647517 | Clean fence | 20 | 10 | 200 | 20 | 16.1607 | 323.21 | m | Clean
Week 4 | 2026-09-24 | 36552 | Invoiced 4647517 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 4 | 2026-09-24 | 36552 | docket total |  |  |  | 300 |  |  | 404.01
Week 4 | 2026-09-24 | 36553 | Invoiced 4647517 | Clean fence | 12.5 | 10 | 125 | 12.5 | 16.1607 | 202.01 | m | Clean
Week 4 | 2026-09-24 | 36553 | docket total |  |  |  | 125 |  |  | 202.01
Week 4 | 2026-09-24 | 36554 | Invoiced 4647517 | CCB | 352.5 | 5.4 | 1903.5 | 352.5 | 13.08 | 4610.7 | m | CCB Demarc
Week 4 | 2026-09-24 | 36554 | docket total |  |  |  | 1903.5 |  |  | 4610.7
Week 4 | 2026-09-24 | 36555 | Invoiced 4647517 | Clean fence | 30 | 10 | 300 | 30 | 16.1607 | 484.82 | m | Clean
Week 4 | 2026-09-24 | 36555 | docket total |  |  |  | 300 |  |  | 484.82
Week 4 | 2026-09-25 | 36556 | Invoiced 4647517 | CCB | 377.5 | 5.4 | 2038.5 | 377.5 | 13.08 | 4937.7 | m | CCB Demarc
Week 4 | 2026-09-25 | 36556 | docket total |  |  |  | 2038.5 |  |  | 4937.7
Week 4 | 2026-09-25 | 36557 | Invoiced 4647517 | Clean fence | 100 | 10 | 1000 | 100 | 16.1607 | 1616.07 | m | Clean
Week 4 | 2026-09-25 | 36557 | docket total |  |  |  | 1000 |  |  | 1616.07
Week 4 | 2026-09-25 | 36558 | Invoiced 4647517 | Clean fence | 10 | 10 | 100 | 10 | 16.1607 | 161.61 | m | Clean
Week 4 | 2026-09-25 | 36558 | docket total |  |  |  | 100 |  |  | 161.61
Week 5 | 2026-09-14 | 36505 | Invoiced 4647509 | Clean fence | 87.5 | 10 | 875 | 87.5 | 16.1607 | 1414.06 | m | Clean
Week 5 | 2026-09-14 | 36505 | Invoiced 4647509 | Vehicle gates | 4 | 50 | 200 | 4 | 40.4 | 161.6 | each | V Gates
Week 5 | 2026-09-14 | 36505 | docket total |  |  |  | 1075 |  |  | 1575.66
Week 5 | 2026-09-14 | 36506 | Invoiced 4647509 | Clean fence | 122.5 | 10 | 1225 | 122.5 | 16.1607 | 1979.69 | m | Clean
Week 5 | 2026-09-14 | 36506 | Invoiced 4647509 | Scrim fence | 10 | 24.4 | 244 | 10 | 25.53 | 255.3 | m | Scrim
Week 5 | 2026-09-14 | 36506 | docket total |  |  |  | 1469 |  |  | 2234.99
Week 5 | 2026-09-14 | 36507 | Invoiced 4647509 | Clean fence | 7.5 | 10 | 75 | 7.5 | 16.1607 | 121.21 | m | Clean
Week 5 | 2026-09-14 | 36507 | docket total |  |  |  | 75 |  |  | 121.21
Week 5 | 2026-09-14 | 36508 | Invoiced 4647509 | Clean fence | 20 | 10 | 200 | 20 | 16.1607 | 323.21 | m | Clean
Week 5 | 2026-09-14 | 36508 | docket total |  |  |  | 200 |  |  | 323.21
Week 5 | 2026-09-14 | 36509 | Invoiced 4647509 | Clean fence | 537.5 | 10 | 5375 | 537.5 | 16.1607 | 8686.38 | m | Clean
Week 5 | 2026-09-14 | 36509 | Invoiced 4647509 | Vehicle gates | 16 | 50 | 800 | 16 | 40.4 | 646.4 | each | V Gates
Week 5 | 2026-09-14 | 36509 | Invoiced 4647509 | Pedestrian gates | 2 | 61 | 122 | 2 | 36.1839 | 72.37 | each | Ped Gates
Week 5 | 2026-09-14 | 36509 | docket total |  |  |  | 6297 |  |  | 9405.15
Week 5 | 2026-09-14 | 36510 | Invoiced 4647509 | Labour | 0.5 | 100 | 50 | 0.5 | 142 | 71 | h | Relocation labour
Week 5 | 2026-09-14 | 36510 | docket total |  |  |  | 50 |  |  | 71
Week 5 | 2026-09-14 | 36512 | Invoiced 4647509 | Clean fence | 157.5 | 10 | 1575 | 157.5 | 16.1607 | 2545.31 | m | Clean
Week 5 | 2026-09-14 | 36512 | Invoiced 4647509 | Vehicle gates | 6 | 50 | 300 | 6 | 40.4 | 242.4 | each | V Gates
Week 5 | 2026-09-14 | 36512 | docket total |  |  |  | 1875 |  |  | 2787.71
Week 5 | 2026-09-15 | 36513 | Invoiced 4647509 | Clean fence | 105 | 10 | 1050 | 105 | 16.1607 | 1696.87 | m | Clean
Week 5 | 2026-09-15 | 36513 | Invoiced 4647509 | Scrim fence | 12.5 | 24.4 | 305 | 12.5 | 25.53 | 319.13 | m | Scrim
Week 5 | 2026-09-15 | 36513 | Invoiced 4647509 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 5 | 2026-09-15 | 36513 | docket total |  |  |  | 1455 |  |  | 2096.8
Week 5 | 2026-09-15 | 36514 | Invoiced 4647509 | Clean fence | 62.5 | 10 | 625 | 62.5 | 16.1607 | 1010.04 | m | Clean
Week 5 | 2026-09-15 | 36514 | Invoiced 4647509 | Scrim fence | 70 | 24.4 | 1708 | 70 | 25.53 | 1787.1 | m | Scrim
Week 5 | 2026-09-15 | 36514 | Invoiced 4647509 | Vehicle gates | 6 | 50 | 300 | 6 | 40.4 | 242.4 | each | V Gates
Week 5 | 2026-09-15 | 36514 | Invoiced 4647509 | Pedestrian gates | 1 | 61 | 61 | 1 | 36.1839 | 36.18 | each | Ped Gates
Week 5 | 2026-09-15 | 36514 | docket total |  |  |  | 2694 |  |  | 3075.72
Week 5 | 2026-09-15 | 36515 | Invoiced 4647509 | CCB | 60 | 5.4 | 324 | 60 | 7.51 | 450.6 | m | CCB Event
Week 5 | 2026-09-15 | 36515 | docket total |  |  |  | 324 |  |  | 450.6
Week 5 | 2026-09-15 | 36516 | Invoiced 4647509 | Clean fence | 82.5 | 10 | 825 | 82.5 | 16.1607 | 1333.26 | m | Clean
Week 5 | 2026-09-15 | 36516 | Invoiced 4647509 | Vehicle gates | 5 | 50 | 250 | 5 | 40.4 | 202 | each | V Gates
Week 5 | 2026-09-15 | 36516 | docket total |  |  |  | 1075 |  |  | 1535.26
Week 5 | 2026-09-16 | 36517 | Invoiced 4647509 | Clean fence | 62.5 | 10 | 625 | 62.5 | 16.1607 | 1010.04 | m | Clean
Week 5 | 2026-09-16 | 36517 | Invoiced 4647509 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 5 | 2026-09-16 | 36517 | docket total |  |  |  | 725 |  |  | 1090.84
Week 5 | 2026-09-16 | 36518 | Invoiced 4647509 | Clean fence | 7.5 | 10 | 75 | 7.5 | 16.1607 | 121.21 | m | Clean
Week 5 | 2026-09-16 | 36518 | Invoiced 4647509 | Scrim fence | 22.5 | 24.4 | 549 | 22.5 | 25.53 | 574.43 | m | Scrim
Week 5 | 2026-09-16 | 36518 | Invoiced 4647509 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 5 | 2026-09-16 | 36518 | docket total |  |  |  | 724 |  |  | 776.44
Week 5 | 2026-09-16 | 36519 | Invoiced 4647509 | Clean fence | -72.5 | 10 | -725 | -72.5 | 16.1607 | -1171.65 | m | Clean — the fence under the scrim, charged once in the scrim
Week 5 | 2026-09-16 | 36519 | Invoiced 4647509 | Scrim fence | 72.5 | 24.4 | 1769 | 72.5 | 25.53 | 1850.93 | m | Scrim
Week 5 | 2026-09-16 | 36519 | docket total |  |  |  | 1044 |  |  | 679.28
Week 5 | 2026-09-16 | 36520 | Invoiced 4647509 | Clean fence | 62.5 | 10 | 625 | 62.5 | 16.1607 | 1010.04 | m | Clean
Week 5 | 2026-09-16 | 36520 | Invoiced 4647509 | Scrim fence | 40 | 24.4 | 976 | 40 | 25.53 | 1021.2 | m | Scrim
Week 5 | 2026-09-16 | 36520 | Invoiced 4647509 | Vehicle gates | 4 | 50 | 200 | 4 | 40.4 | 161.6 | each | V Gates
Week 5 | 2026-09-16 | 36520 | docket total |  |  |  | 1801 |  |  | 2192.84
Week 5 | 2026-09-16 | 36521 | Invoiced 4647509 | Clean fence | 27.5 | 10 | 275 | 27.5 | 16.1607 | 444.42 | m | Clean
Week 5 | 2026-09-16 | 36521 | docket total |  |  |  | 275 |  |  | 444.42
Week 5 | 2026-09-16 | 36522 | Invoiced 4647509 | CCB | 277.5 | 5.4 | 1498.5 | 277.5 | 7.51 | 2084.03 | m | CCB Event
Week 5 | 2026-09-16 | 36522 | docket total |  |  |  | 1498.5 |  |  | 2084.03
Week 5 | 2026-09-17 | 36523 | Invoiced 4647509 | Clean fence | -22.5 | 10 | -225 | -22.5 | 16.1607 | -363.62 | m | Clean — the fence under the scrim, charged once in the scrim
Week 5 | 2026-09-17 | 36523 | Invoiced 4647509 | Scrim fence | 22.5 | 24.4 | 549 | 22.5 | 25.53 | 574.43 | m | Scrim
Week 5 | 2026-09-17 | 36523 | docket total |  |  |  | 324 |  |  | 210.81
Week 5 | 2026-09-17 | 36524 | Not invoiced yet | Clean fence | 137.5 | 10 | 1375 | 137.5 | 16.1607 | 2222.1 | m | Clean
Week 5 | 2026-09-17 | 36524 | docket total |  |  |  | 1375 |  |  | 2222.1
Week 5 | 2026-09-17 | 36525 | Invoiced 4647509 | Labour | 1 | 100 | 100 | 1 | 142 | 142 | h | Relocation labour
Week 5 | 2026-09-17 | 36525 | docket total |  |  |  | 100 |  |  | 142
Week 5 | 2026-09-17 | 36526 | Invoiced 4647509 | Clean fence | 10 | 10 | 100 | 10 | 16.1607 | 161.61 | m | Clean
Week 5 | 2026-09-17 | 36526 | docket total |  |  |  | 100 |  |  | 161.61
Week 5 | 2026-09-17 | 36528 | Invoiced 4647509 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 5 | 2026-09-17 | 36528 | Invoiced 4647509 | Labour | 0.5 | 100 | 50 | 0.5 | 142 | 71 | h | Relocation labour
Week 5 | 2026-09-17 | 36528 | docket total |  |  |  | 150 |  |  | 151.8
Week 5 | 2026-09-17 | 36529 | Invoiced 4647509 | Clean fence | 35 | 10 | 350 | 35 | 16.1607 | 565.62 | m | Clean
Week 5 | 2026-09-17 | 36529 | Invoiced 4647509 | Scrim fence | 10 | 24.4 | 244 | 10 | 25.53 | 255.3 | m | Scrim
Week 5 | 2026-09-17 | 36529 | docket total |  |  |  | 594 |  |  | 820.92
Week 5 | 2026-09-17 | 36530 | Invoiced 4647509 | Clean fence | 15 | 10 | 150 | 15 | 16.1607 | 242.41 | m | Clean
Week 5 | 2026-09-17 | 36530 | Invoiced 4647509 | CCB | 50 | 5.4 | 270 | 50 | 7.51 | 375.5 | m | CCB Event
Week 5 | 2026-09-17 | 36530 | docket total |  |  |  | 420 |  |  | 617.91
Week 5 | 2026-09-17 | 36531 | Invoiced 4647509 | Clean fence | -105 | 10 | -1050 | -105 | 16.1607 | -1696.87 | m | Clean — the fence under the scrim, charged once in the scrim
Week 5 | 2026-09-17 | 36531 | Invoiced 4647509 | Scrim fence | 105 | 24.4 | 2562 | 105 | 25.53 | 2680.65 | m | Scrim
Week 5 | 2026-09-17 | 36531 | docket total |  |  |  | 1512 |  |  | 983.78
Week 5 | 2026-09-18 | 36532 | Invoiced 4647509 | Clean fence | 12.5 | 10 | 125 | 12.5 | 16.1607 | 202.01 | m | Clean
Week 5 | 2026-09-18 | 36532 | Invoiced 4647509 | Scrim fence | 132.5 | 24.4 | 3233 | 132.5 | 25.53 | 3382.73 | m | Scrim
Week 5 | 2026-09-18 | 36532 | Invoiced 4647509 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 5 | 2026-09-18 | 36532 | docket total |  |  |  | 3458 |  |  | 3665.54
Week 5 | 2026-09-18 | 36533 | Invoiced 4647509 | Clean fence | 40 | 10 | 400 | 40 | 16.1607 | 646.43 | m | Clean
Week 5 | 2026-09-18 | 36533 | Invoiced 4647509 | Vehicle gates | 2 | 50 | 100 | 2 | 40.4 | 80.8 | each | V Gates
Week 5 | 2026-09-18 | 36533 | docket total |  |  |  | 500 |  |  | 727.23
Week 5 | 2026-09-18 | 36534 | Invoiced 4647509 | CCB | 235 | 5.4 | 1269 | 235 | 13.08 | 3073.8 | m | CCB Demarc
Week 5 | 2026-09-18 | 36534 | docket total |  |  |  | 1269 |  |  | 3073.8
Week 5 | 2026-09-18 | 36535 | Invoiced 4647509 | CCB | 30 | 5.4 | 162 | 30 | 13.08 | 392.4 | m | CCB Demarc
Week 5 | 2026-09-18 | 36535 | docket total |  |  |  | 162 |  |  | 392.4
Week 6 |  | workbook:Week 6:row3 | Invoiced | Clean fence | 232.5 | 10 | 2325 | 232.5 | 16.1607 | 3757.36 | m | Clean
Week 6 |  | workbook:Week 6:row3 | Invoiced | Vehicle gates | 3 | 50 | 150 | 3 | 40.4 | 121.2 | each | V Gates
Week 6 |  | workbook:Week 6:row3 | docket total |  |  |  | 2475 |  |  | 3878.56
Week 6 | 2026-09-09 | 36501 | Not invoiced yet | Clean fence | 247.5 | 10 | 2475 | 247.5 | 16.1607 | 3999.77 | m | Clean
Week 6 | 2026-09-09 | 36501 | docket total |  |  |  | 2475 |  |  | 3999.77
Week 6 | 2026-09-11 | 36502 | Not invoiced yet | Clean fence | 257.5 | 10 | 2575 | 257.5 | 16.1607 | 4161.38 | m | Clean
Week 6 | 2026-09-11 | 36502 | docket total |  |  |  | 2575 |  |  | 4161.38
Week 6 | 2026-09-11 | 36503 | docket total |  |  |  | 0 |  |  | 0
Week 6 | 2026-09-11 | 36504 | Not invoiced yet | Clean fence | 0 | 10 | 0 | 0 | 16.1607 | 0 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Week 6 | 2026-09-11 | 36504 | Not invoiced yet | Scrim fence | 72.5 | 24.4 | 1769 | 72.5 | 25.53 | 1850.93 | m | Scrim
Week 6 | 2026-09-11 | 36504 | docket total |  |  |  | 1769 |  |  | 1850.93
Week 6 | 2026-09-12 | 36511 | Not invoiced yet | Labour | 8.5 | 100 | 850 | 8.5 | 142 | 1207 | hr | Labour
Week 6 | 2026-09-12 | 36511 | docket total |  |  |  | 850 |  |  | 1207
Event Week | 2026-10-19 | 36623 | Not invoiced yet | Clean fence | 97.5 | 10 | 975 | 97.5 | 16.1607 | 1575.67 | m | Clean
Event Week | 2026-10-19 | 36623 | Not invoiced yet | CCB | 100 | 5.4 | 540 | 100 | 13.08 | 1308 | m | CCB Demarc
Event Week | 2026-10-19 | 36623 | docket total |  |  |  | 1515 |  |  | 2883.67
Event Week | 2026-10-19 | 36624 | Not invoiced yet | Clean fence | 32.5 | 10 | 325 | 32.5 | 16.1607 | 525.22 | m | Clean
Event Week | 2026-10-19 | 36624 | docket total |  |  |  | 325 |  |  | 525.22
Event Week | 2026-10-19 | 36625 | Not invoiced yet | Clean fence | 0 | 10 | 0 | 0 | 16.1607 | 0 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-19 | 36625 | Not invoiced yet | Scrim fence | 285 | 24.4 | 6954 | 285 | 25.53 | 7276.05 | m | Scrim
Event Week | 2026-10-19 | 36625 | docket total |  |  |  | 6954 |  |  | 7276.05
Event Week | 2026-10-19 | 36626 | Not invoiced yet | Clean fence | 492.5 | 10 | 4925 | 492.5 | 16.1607 | 7959.14 | m | Clean
Event Week | 2026-10-19 | 36626 | docket total |  |  |  | 4925 |  |  | 7959.14
Event Week | 2026-10-20 | 36627 | Not invoiced yet | CCB | 132.5 | 5.4 | 715.5 | 132.5 | mixed | 1036.85 | m | CCB Demarc; CCB Event
Event Week | 2026-10-20 | 36627 | docket total |  |  |  | 715.5 |  |  | 1036.85
Event Week | 2026-10-20 | 36628 | Not invoiced yet | Clean fence | 0 | 10 | 0 | 0 | 16.1607 | 0 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-20 | 36628 | Not invoiced yet | Scrim fence | 25 | 24.4 | 610 | 25 | 25.53 | 638.25 | m | Scrim
Event Week | 2026-10-20 | 36628 | docket total |  |  |  | 610 |  |  | 638.25
Event Week | 2026-10-20 | 36629 | Not invoiced yet | Clean fence | -80 | 10 | -800 | -80 | 16.1607 | -1292.86 | m | Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-20 | 36629 | Not invoiced yet | Scrim fence | 80 | 24.4 | 1952 | 80 | 25.53 | 2042.4 | m | Scrim
Event Week | 2026-10-20 | 36629 | Not invoiced yet | CCB | 420 | 5.4 | 2268 | 420 | mixed | 4170.73 | m | CCB Demarc; CCB Event
Event Week | 2026-10-20 | 36629 | docket total |  |  |  | 3420 |  |  | 4920.27
Event Week | 2026-10-20 | 36630 | Not invoiced yet | Clean fence | 30 | 10 | 300 | 30 | 16.1607 | 484.82 | m | Clean
Event Week | 2026-10-20 | 36630 | docket total |  |  |  | 300 |  |  | 484.82
Event Week | 2026-10-20 | 36631 | Not invoiced yet | Clean fence | 0 | 10 | 0 | 0 | 16.1607 | 0 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-20 | 36631 | Not invoiced yet | Scrim fence | 5 | 24.4 | 122 | 5 | 25.53 | 127.65 | m | Scrim
Event Week | 2026-10-20 | 36631 | docket total |  |  |  | 122 |  |  | 127.65
Event Week | 2026-10-20 | 36632 | docket total |  |  |  | 0 |  |  | 0
Event Week | 2026-10-20 | 36633 | Not invoiced yet | Clean fence | 17.5 | 10 | 175 | 17.5 | 16.1607 | 282.81 | m | Clean
Event Week | 2026-10-20 | 36633 | docket total |  |  |  | 175 |  |  | 282.81
Event Week | 2026-10-20 | 36634 | Not invoiced yet | CCB | 12.5 | 5.4 | 67.5 | 12.5 | 13.08 | 163.5 | m | CCB Demarc
Event Week | 2026-10-20 | 36634 | docket total |  |  |  | 67.5 |  |  | 163.5
Event Week | 2026-10-20 | 36635 | Not invoiced yet | CCB | 72.5 | 5.4 | 391.5 | 72.5 | mixed | 619.42 | m | CCB Event; CCB flat feet
Event Week | 2026-10-20 | 36635 | docket total |  |  |  | 391.5 |  |  | 619.42
Event Week | 2026-10-20 | 36636 | Not invoiced yet | CCB | 205 | 5.4 | 1107 | 205 | 13.08 | 2681.4 | m | CCB Demarc
Event Week | 2026-10-20 | 36636 | docket total |  |  |  | 1107 |  |  | 2681.4
Event Week | 2026-10-20 | 36637 | Not invoiced yet | CCB | 25 | 5.4 | 135 | 25 | 7.51 | 187.75 | m | CCB Event
Event Week | 2026-10-20 | 36637 | docket total |  |  |  | 135 |  |  | 187.75
Event Week | 2026-10-20 | 36638 | Not invoiced yet | CCB | 88 | 5.4 | 475.2 | 88 | 9.6511 | 849.3 | m | CCB flat feet
Event Week | 2026-10-20 | 36638 | docket total |  |  |  | 475.2 |  |  | 849.3
Event Week | 2026-10-21 | 36639 | Not invoiced yet | Clean fence | 0 | 10 | 0 | 0 | 16.1607 | 0 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-21 | 36639 | Not invoiced yet | Scrim fence | 15 | 24.4 | 366 | 15 | 25.53 | 382.95 | m | Scrim
Event Week | 2026-10-21 | 36639 | docket total |  |  |  | 366 |  |  | 382.95
Event Week | 2026-10-21 | 36640 | Not invoiced yet | Clean fence | 47.5 | 10 | 475 | 47.5 | 16.1607 | 767.63 | m | Clean
Event Week | 2026-10-21 | 36640 | docket total |  |  |  | 475 |  |  | 767.63
Event Week | 2026-10-21 | 36642 | Not invoiced yet | Clean fence | 0 | 10 | 0 | 0 | 16.1607 | 0 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-21 | 36642 | Not invoiced yet | Scrim fence | 7.5 | 24.4 | 183 | 7.5 | 25.53 | 191.48 | m | Scrim
Event Week | 2026-10-21 | 36642 | docket total |  |  |  | 183 |  |  | 191.48
Event Week | 2026-10-21 | 36643 | Not invoiced yet | Clean fence | -15 | 10 | -150 | -15 | 16.1607 | -242.41 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-21 | 36643 | Not invoiced yet | Scrim fence | 47.5 | 24.4 | 1159 | 47.5 | 25.53 | 1212.68 | m | Scrim
Event Week | 2026-10-21 | 36643 | Not invoiced yet | CCB | 20 | 5.4 | 108 | 20 | 7.51 | 150.2 | m | CCB Event
Event Week | 2026-10-21 | 36643 | docket total |  |  |  | 1117 |  |  | 1120.47
Event Week | 2026-10-21 | 36644 | docket total |  |  |  | 0 |  |  | 0
Event Week | 2026-10-21 | 36645 | Not invoiced yet | CCB | 12.5 | 5.4 | 67.5 | 12.5 | 13.08 | 163.5 | m | CCB Demarc
Event Week | 2026-10-21 | 36645 | docket total |  |  |  | 67.5 |  |  | 163.5
Event Week | 2026-10-21 | 36646 | Not invoiced yet | Clean fence | 15 | 10 | 150 | 15 | 16.1607 | 242.41 | m | Clean
Event Week | 2026-10-21 | 36646 | docket total |  |  |  | 150 |  |  | 242.41
Event Week | 2026-10-21 | 36647 | Not invoiced yet | CCB | 47.5 | 5.4 | 256.5 | 47.5 | 7.51 | 356.73 | m | CCB Event
Event Week | 2026-10-21 | 36647 | docket total |  |  |  | 256.5 |  |  | 356.73
Event Week | 2026-10-21 | 36756 | Not invoiced yet | Clean fence | 10 | 10 | 100 | 10 | 16.1607 | 161.61 | m | Clean
Event Week | 2026-10-21 | 36756 | docket total |  |  |  | 100 |  |  | 161.61
Event Week | 2026-10-21 | 36757 | Not invoiced yet | Clean fence | 70 | 10 | 700 | 70 | 16.1607 | 1131.25 | m | Clean
Event Week | 2026-10-21 | 36757 | docket total |  |  |  | 700 |  |  | 1131.25
Event Week | 2026-10-22 | 36648 | Not invoiced yet | Clean fence | 37.5 | 10 | 375 | 37.5 | 16.1607 | 606.03 | m | Clean
Event Week | 2026-10-22 | 36648 | docket total |  |  |  | 375 |  |  | 606.03
Event Week | 2026-10-22 | 36649 | Not invoiced yet | Clean fence | 0 | 10 | 0 | 0 | 16.1607 | 0 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-22 | 36649 | Not invoiced yet | Scrim fence | 40 | 24.4 | 976 | 40 | 25.53 | 1021.2 | m | Scrim
Event Week | 2026-10-22 | 36649 | docket total |  |  |  | 976 |  |  | 1021.2
Event Week | 2026-10-22 | 36650 | Not invoiced yet | Clean fence | 5 | 10 | 50 | 5 | 16.1607 | 80.8 | m | Clean
Event Week | 2026-10-22 | 36650 | docket total |  |  |  | 50 |  |  | 80.8
Event Week | 2026-10-22 | 36751 | Not invoiced yet | Clean fence | 147.5 | 10 | 1475 | 147.5 | 16.1607 | 2383.7 | m | Clean
Event Week | 2026-10-22 | 36751 | Not invoiced yet | CCB | 315 | 5.4 | 1701 | 315 | 7.51 | 2365.65 | m | CCB Event
Event Week | 2026-10-22 | 36751 | docket total |  |  |  | 3176 |  |  | 4749.35
Event Week | 2026-10-22 | 36752 | Not invoiced yet | Clean fence | 20 | 10 | 200 | 20 | 16.1607 | 323.21 | m | Clean
Event Week | 2026-10-22 | 36752 | docket total |  |  |  | 200 |  |  | 323.21
Event Week | 2026-10-22 | 36753 | Not invoiced yet | Clean fence | 17.5 | 10 | 175 | 17.5 | 16.1607 | 282.81 | m | Clean
Event Week | 2026-10-22 | 36753 | docket total |  |  |  | 175 |  |  | 282.81
Event Week | 2026-10-22 | 36754 | Not invoiced yet | Clean fence | 37.5 | 10 | 375 | 37.5 | 16.1607 | 606.03 | m | Clean
Event Week | 2026-10-22 | 36754 | docket total |  |  |  | 375 |  |  | 606.03
Event Week | 2026-10-22 | 36755 | Not invoiced yet | Clean fence | 35 | 10 | 350 | 35 | 16.1607 | 565.62 | m | Clean
Event Week | 2026-10-22 | 36755 | Not invoiced yet | CCB | 45 | 5.4 | 243 | 45 | 7.51 | 337.95 | m | CCB Event
Event Week | 2026-10-22 | 36755 | docket total |  |  |  | 593 |  |  | 903.57
Event Week | 2026-10-22 | 36758 | Not invoiced yet | Clean fence | 30 | 10 | 300 | 30 | 16.1607 | 484.82 | m | Clean
Event Week | 2026-10-22 | 36758 | docket total |  |  |  | 300 |  |  | 484.82
Event Week | 2026-10-22 | 36759 | Not invoiced yet | Clean fence | 0 | 10 | 0 | 0 | 16.1607 | 0 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-22 | 36759 | Not invoiced yet | Scrim fence | 72.5 | 24.4 | 1769 | 72.5 | 25.53 | 1850.93 | m | Scrim
Event Week | 2026-10-22 | 36759 | docket total |  |  |  | 1769 |  |  | 1850.93
Event Week | 2026-10-22 | 36760 | Not invoiced yet | CCB | 10 | 5.4 | 54 | 10 | 13.08 | 130.8 | m | CCB Demarc
Event Week | 2026-10-22 | 36760 | docket total |  |  |  | 54 |  |  | 130.8
Event Week | 2026-10-22 | 36761 | Not invoiced yet | Clean fence | 2.5 | 10 | 25 | 2.5 | 16.1607 | 40.4 | m | Clean; Clean — the fence under the scrim, charged once in the scrim
Event Week | 2026-10-22 | 36761 | Not invoiced yet | Scrim fence | 32.5 | 24.4 | 793 | 32.5 | 25.53 | 829.73 | m | Scrim
Event Week | 2026-10-22 | 36761 | docket total |  |  |  | 818 |  |  | 870.13
Event Week | 2026-10-22 | 36762 | Not invoiced yet | Clean fence | 20 | 10 | 200 | 20 | 16.1607 | 323.21 | m | Clean
Event Week | 2026-10-22 | 36762 | docket total |  |  |  | 200 |  |  | 323.21
Event Week | 2026-10-22 | 36763 | docket total |  |  |  | 0 |  |  | 0
Event Week | 2026-10-22 | 36764 | Not invoiced yet | CCB | 15 | 5.4 | 81 | 15 | 7.51 | 112.65 | m | CCB Event
Event Week | 2026-10-22 | 36764 | docket total |  |  |  | 81 |  |  | 112.65
Event Week | 2026-10-23 | 36765 | Not invoiced yet | Clean fence | 5 | 10 | 50 | 5 | 16.1607 | 80.8 | m | Clean
Event Week | 2026-10-23 | 36765 | docket total |  |  |  | 50 |  |  | 80.8
Event Week | 2026-10-23 | 36766 | Not invoiced yet | CCB | 10 | 5.4 | 54 | 10 | 7.51 | 75.1 | m | CCB Event
Event Week | 2026-10-23 | 36766 | docket total |  |  |  | 54 |  |  | 75.1
Event Week | 2026-10-23 | 36767 | Not invoiced yet | Clean fence | 7.5 | 10 | 75 | 7.5 | 16.1607 | 121.21 | m | Clean
Event Week | 2026-10-23 | 36767 | docket total |  |  |  | 75 |  |  | 121.21
Event Week | 2026-10-23 | 36768 | Not invoiced yet | CCB | 50 | 5.4 | 270 | 50 | 7.51 | 375.5 | m | CCB Event
Event Week | 2026-10-23 | 36768 | docket total |  |  |  | 270 |  |  | 375.5
Event Week | 2026-10-25 | 36769 | Not invoiced yet | Clean fence | 10 | 10 | 100 | 10 | 16.1607 | 161.61 | m | Clean
Event Week | 2026-10-25 | 36769 | docket total |  |  |  | 100 |  |  | 161.61
Event Week | 2026-10-25 | 36770 | Not invoiced yet | Clean fence | 22.5 | 10 | 225 | 22.5 | 16.1607 | 363.62 | m | Clean
Event Week | 2026-10-25 | 36770 | docket total |  |  |  | 225 |  |  | 363.62
Event Week | 2026-10-25 | 36771 | docket total |  |  |  | 0 |  |  | 0