## Summary
GC500 fencing (9990776): what we charge the V8s and what we pay Advanced - signed dockets 9 Sep to 23 Oct 2026, ex GST
From the live record on 25 Oct 2026 (page v12.15), priced by the page itself: 167 signed red-book dockets. Our rates are the 2026 street card or your named rates. Advanced's costs are their approved pricing on the purchase orders for weeks 1-5 (115 dockets), and their rate sheet for week 6 and the event week (52 dockets) until their invoices land.
1. What we charge - how the $405,150.96 is built
Item | Qty (our dockets) | Unit | We charge / unit | Our rate comes from | We charge | We pay / unit | Advanced's rate comes from
Clean fence 1.8 m | 13270 | m | 16.1607 | 2026 street card: Temporary Fencing 1.8m x 2.5m (per mtr) | 214452.46 | 10 | Advanced's rate sheet
Scrim fence (braced, shade cloth on) | 3977.5 | m | 25.53 | your rate, 2026-09-24 | 101545.7 | 24.4 | Advanced's rate sheet (braced for scrim)
CCB demarcation | 5062.5 | m | 13.08 | 2026 street card: CCB Demarcation Fencing (per mtr) (confirmed 2026-09-24) | 66217.5 | 5.4 | Advanced's rate sheet
CCB event | 2195 | m | 7.51 | 2026 street card: Crowd Control Barrier (per mtr) (confirmed 2026-09-24) | 16484.48 | 5.4 | Advanced's rate sheet
CCB flat feet | 270 | m | 9.6511 | 2026 street card: CCB Flat feet | 2605.81 | 5.4 | typed on our record 15 Oct (no flat-feet line on their sheet)
Labour (docket 36511) | 8.5 | hr | 142 | your rate, 2026-09-22 | 1207 | 100 | Advanced's rate sheet
Relocation | 137.5 | m | 8.652 | 2026 street card: Relocation of Fencing (per mtr) | 1189.65 |  | they bill relocation by the hour, $100
Pedestrian gates | 22 | each | 36.1839 | 2026 street card: Pedestrian Gate | 796.04 | 61 | typed on our record 15 Oct; their invoices say $61 incl one wheel
Fence blocks | 216 | each | 3.02 | 2026 street card: Fence Blocks( per block) (confirmed 2026-10-02) | 652.32 |  | no per-block line on their sheet: the cost is on their invoice
Vehicle gates | 3 | each | 0 | included in the metre rate (the project manager, 1 Oct 2026) | 0 | 50 | Advanced's rate sheet
Total we charge |  |  |  |  | 405150.96
Each docket line is rounded to the cent, as the page and the build price it. Multiplying the totals above straight through gives 13 cents less ($405,150.83).
2. What we pay Advanced for the same work
Item | Qty Advanced bill | Unit | Their rate | Note | We pay
Clean fence 1.8 m | 9718 | m | 10 | their clean metres leave out the scrimmed fence and the gate openings (see 5) | 97180
Scrim fence (braced, shade cloth on) | 3682.5 | m | 24.4 |  | 89853
CCB demarcation | 6410 | m | 5.4 | on weeks 1-5 Advanced bill all CCB on this one line, same $5.40 | 34614
CCB event | 927.5 | m | 5.4 |  | 5008.5
CCB flat feet | 123 | m | 5.4 |  | 664.2
Labour (docket 36511) | 8.5 | hr | 100 |  | 850
Relocation | 2 | h | 100 | relocation billed as labour hours | 200
Pedestrian gates | 22 | each | 61 |  | 1342
Vehicle gates | 219 | each | 50 | billed by Advanced; not charged to the V8s (inside the metre rate) | 10950
Bases | 300 | each | 1 | on their week 3 invoice | 300
Fence, barriers and gates on the 167 dockets |  |  |  |  | 240961.7
Team leader | 46 | days | 200 | on the purchase orders, weeks 1-5 | 9200
Weed mat supply — 40 rolls | 40 | rolls | 64.5 | on purchase order 4647520 | 2580
Shade cloth supply — 4 rolls | 4 | rolls | 196 | on purchase order 4647520 | 784
Invoice under the sheet rates: 4647508 (Week 6) |  |  |  | receipt 4918492 $8,992.00 against $10,869.00 at the sheet rates; the invoice stands (the project manager, 23 Oct) | -1877
Invoice under the sheet rates: 4647509 (Week 5) |  |  |  | receipt 4922398 $33,670.00 against $35,045.50 at the sheet rates; the invoice stands (the project manager, 23 Oct) | -1375.5
Fencing cost on the page |  |  |  |  | 250273.2
Labour notes (green book) | 108.5 | h | 100 | 42 service notes: Advanced's labour, a cost only (inside our metre rates) | 10850
We pay for the work on the 167 dockets |  |  |  |  | 261123.2
Other Advanced invoice: order 4658850 |  |  |  | INV 93920 - partial Collection (receipt 4922343); not in the page's fencing cost | 195
Total we pay Advanced, everything to date |  |  |  |  | 261318.2
3. What Advanced have billed, order by order - and whether it matches our record
Week | Order | Advanced's sheet | Order amount | Receipt | How it matches | We carry
Week 6 | 4647508 |  | 8992 | 4918492 | invoiced; no sheet to check line by line; the order stands; our 6 dockets at their rates come to $10,869.00, so the invoice is $1,877.00 less | 8992
Week 5 | 4647509 | 33670.5 | 33670 | 4922398 | sheet $33,670.50, 50 cents over the order; the order stands; not on their sheet: docket 36524 ($1,375.00 at their rates) | 33670
Week 4 | 4647517 | 26695 | 26695 | 4926209 | Advanced's approved sheet = the order, to the cent | 26695
Week 3 | 4647515 | 50154 | 50154 |  | Advanced's approved sheet = the order, to the cent; their sheet prints the order as 464517 | 50154
Week 2 | 4647519 | 28246.5 | 28246.5 |  | Advanced's approved sheet = the order, to the cent | 28246.5
Week 1 | 4647520 | 66272 | 66272 |  | Advanced's approved sheet = the order, to the cent; not on their sheet: labour note 24479 ($50.00) | 66322
Event Week | 4647522 |  |  |  | nothing billed yet; 45 dockets and 11 labour notes on our record, at their rates | 47043.7
Demob | 4647523 |  |  |  | nothing billed yet; no papers yet
Other | 4658850 |  | 195 | 4922343 | INV 93920 - partial Collection; tied to no docket (the collection forms carry counts, no money); not in the page's fencing cost | 195
Total | [5 empty] | 261318.2
4. The difference
We charge the V8s |  |  |  |  | 405150.96
We pay Advanced |  |  |  |  | 261318.2
Margin |  |  |  | 35.5% of what we charge | 143832.76
5. Needs your call - scrim fence charged twice?
The scrim rate ($25.53 a metre, set 24 Sep) is the fence with shade cloth on it: card fence $16.16 + card shade cloth $9.37. Advanced bill braced-for-scrim the same way, all in ($24.40, not $10 + $24.40).
The crews' papers write the whole fence run as clean, scrimmed sections included. On 109 of the 115 dockets Advanced have invoiced, their clean metres are exactly the paper's clean less the scrim and 2.5 m for each vehicle gate. Docket 36532: paper 150 m clean and 132.5 m scrim; Advanced bill 12.5 m clean, 132.5 m scrim and 2 vehicle gates.
Our record charges the paper's clean metres at $16.16 and the scrim metres again at $25.53, so the fence under the scrim is charged twice: 3,977.5 m x $16.1607 = $64,279.18.
Baseplan keys them as separate metres (line 3 clean, line 6 fence with scrim + line 10 shade cloth), as the 2026 programme does, and 2025 billed "1.8 m fence with scrim" as its own all-in metre ($26.75, mesh $17.65).
If that is right: we charge $340,871.78, not $405,150.96; Baseplan is short $31,764.95, not $96,044.13; the margin is $79,553.58 (23.3%).
Nothing on the record or the page has been changed: it is your rate ruling.
6. Also worth knowing
Pedestrian gates: we pay $61.00 each and charge the card's $36.18, so each one loses $24.82 (22 gates, $546.04 under).
Vehicle gates: Advanced bill $50 each (219, $10,950.00); we charge none on their own, as the project manager settled (inside the metre rate).
The event week (19-23 Oct, 45 dockets) is costed at Advanced's rate sheet until their invoice comes in (order 4647522 has no amount yet), so the paid side can still move.
Not in these figures: the demob (removal is inside the metre rate; its papers are still to come) and the fence team's event labour under the C004 scope (3.15 Security & Demarcation Fencing, 213 h at $91.14 = $19,412.82), which is a separate charge.

## By week
Week | Dockets dated | Dockets | On Advanced's invoice pricing | We charge | We pay: dockets | We pay: team leader + materials | We pay: labour notes | Invoice adjustment | We pay: all in | Purchase order | Order amount | Receipt
Week 6 | 2026-09-09 to 2026-09-12 | 6 | 0 | 16148.09 | 10869 | 0 | 0 | -1877 | 8992 | 4647508 | 8992 | 4918492
Week 5 | 2026-09-14 to 2026-09-18 | 29 | 28 | 52939.53 | 32620.5 | 2000 | 425 | -1375.5 | 33670 | 4647509 | 33670 | 4922398
Week 4 | 2026-09-21 to 2026-09-25 | 23 | 23 | 47656.3 | 24570 | 1600 | 525 | 0 | 26695 | 4647517 | 26695 | 4926209
Week 3 | 2026-09-28 to 2026-10-02 | 14 | 14 | 83881.22 | 47504 | 2000 | 650 | 0 | 50154 | 4647515 | 50154
Week 2 | 2026-10-06 to 2026-10-09 | 23 | 23 | 40810.39 | 25396.5 | 1600 | 1250 | 0 | 28246.5 | 4647519 | 28246.5
Week 1 | 2026-10-12 to 2026-10-16 | 27 | 27 | 105705.12 | 59658 | 5364 | 1300 | 0 | 66322 | 4647520 | 66272
Event Week | 2026-10-19 to 2026-10-23 | 45 | 0 | 58010.31 | 40343.7 | 0 | 6700 | 0 | 47043.7 | 4647522
Total |  | 167 | 115 | 405150.96 | 240961.7 | 12564 | 10850 | -3252.5 | 261123.2
Other | order 4658850 | [7 empty] | 195 | 4658850 | 195 | 4922343
Total, everything |  |  |  | 405150.96 |  |  |  |  | 261318.2
Week 6 includes one undated row from the fencing cost tracker (232.5 m clean, 3 vehicle gates). Labour notes go to the week of their date; extras and invoice adjustments to their order's week.

## Dockets
Docket | Date | Week | Location | Clean m | Scrim m | CCB demarc m | CCB event m | Flat feet m | Ped gates | V gates | Relocation m | Blocks | Labour h | We charge | We pay | Paid at | Advanced clean m | Advanced scrim m | Advanced V gates | Scrim also in clean (m) | On an Advanced sheet
tracker row |  | Week 6 |  | 232.5 | [5 empty] | 3 |  |  |  | 3757.36 | 2475 | Advanced's rate sheet |  |  |  |  | week 6: no sheet
36501 | 2026-09-09 | Week 6 | Sea World Drive, Main Beach | 247.5 | [9 empty] | 3999.77 | 2475 | Advanced's rate sheet |  |  |  |  | week 6: no sheet
36502 | 2026-09-11 | Week 6 | Phillip Park (Advanced compound) | 257.5 | [9 empty] | 4161.38 | 2575 | Advanced's rate sheet |  |  |  |  | week 6: no sheet
36503 | 2026-09-11 | Week 6 | Sea World Drive, Main Beach | [10 empty] | 0 | 0 | Advanced's rate sheet |  |  |  |  | week 6: no sheet
36504 | 2026-09-11 | Week 6 | Helen Park, BSF compound | 72.5 | 72.5 | [8 empty] | 3022.58 | 2494 | Advanced's rate sheet |  |  |  | 72.5 | week 6: no sheet
36511 | 2026-09-12 | Week 6 | Yatala — Morayfield (Phillip Island / Morayfield), region Yatala | [9 empty] | 8.5 | 1207 | 850 | Advanced's rate sheet |  |  |  |  | week 6: no sheet
36505 | 2026-09-14 | Week 5 | Cypress Carpark | 97.5 | [9 empty] | 1575.67 | 1075 | Advanced's invoice pricing, order 4647509 | 87.5 | 0 | 4 |  | yes
36506 | 2026-09-14 | Week 5 | S18 C.2 construction zone | 132.5 | 10 | [8 empty] | 2396.59 | 1469 | Advanced's invoice pricing, order 4647509 | 122.5 | 10 | 0 | 10 | yes
36507 | 2026-09-14 | Week 5 | Admiralty Drive — crossing closure | 7.5 | [9 empty] | 121.21 | 75 | Advanced's invoice pricing, order 4647509 | 7.5 | 0 | 0 |  | yes
36508 | 2026-09-14 | Week 5 | P.B03 C.2 | 20 | [9 empty] | 323.21 | 200 | Advanced's invoice pricing, order 4647509 | 20 | 0 | 0 |  | yes
36509 | 2026-09-14 | Week 5 | Pit Building / Paddock C.2 — perimeter fencing | 577.5 |  |  |  |  | 2 |  |  |  |  | 9405.17 | 6297 | Advanced's invoice pricing, order 4647509 | 537.5 | 0 | 16 |  | yes
36510 | 2026-09-14 | Week 5 | Sea World Drive, Main Beach | [7 empty] | 50 |  |  | 432.6 | 50 | Advanced's invoice pricing, order 4647509 | 0 | 0 | 0 |  | yes
36512 | 2026-09-14 | Week 5 | S04 Corporate Facility / TV compound | 172.5 | [9 empty] | 2787.72 | 1875 | Advanced's invoice pricing, order 4647509 | 157.5 | 0 | 6 |  | yes
36513 | 2026-09-15 | Week 5 | S07 C-Zone | 127.5 | 12.5 | [8 empty] | 2379.62 | 1455 | Advanced's invoice pricing, order 4647509 | 105 | 12.5 | 2 | 12.5 | yes
36514 | 2026-09-15 | Week 5 | Event Operations — iEDM compound | 147.5 | 70 |  |  |  | 1 |  |  |  |  | 4206.98 | 2694 | Advanced's invoice pricing, order 4647509 | 62.5 | 70 | 6 | 70 | yes
36515 | 2026-09-15 | Week 5 | S07 — hill protection |  |  |  | 60 | [6 empty] | 450.6 | 324 | Advanced's invoice pricing, order 4647509 | 0 | 0 | 0 |  | yes
36516 | 2026-09-15 | Week 5 | Track storage | 87.5 | [9 empty] | 1414.06 | 1075 | Advanced's invoice pricing, order 4647509 | 82.5 | 0 | 5 |  | yes
36517 | 2026-09-16 | Week 5 | S.O.5 C.2 | 67.5 | [9 empty] | 1090.85 | 725 | Advanced's invoice pricing, order 4647509 | 62.5 | 0 | 2 |  | yes
36518 | 2026-09-16 | Week 5 | S.O.5 — grandstand, back of house | 35 | 22.5 | [8 empty] | 1140.05 | 724 | Advanced's invoice pricing, order 4647509 | 7.5 | 22.5 | 2 | 22.5 | yes
36519 | 2026-09-16 | Week 5 | Event operations — iEDM compound |  | 72.5 | [8 empty] | 1850.93 | 1044 | Advanced's invoice pricing, order 4647509 | -72.5 | 72.5 | 0 | 72.5 | yes
36520 | 2026-09-16 | Week 5 | Coates compound / ABD compound | 112.5 | 40 | [8 empty] | 2839.28 | 1801 | Advanced's invoice pricing, order 4647509 | 62.5 | 40 | 4 | 40 | yes
36521 | 2026-09-16 | Week 5 | S.O.8 exclusion zone | 27.5 | [9 empty] | 444.42 | 275 | Advanced's invoice pricing, order 4647509 | 27.5 | 0 | 0 |  | yes
36522 | 2026-09-16 | Week 5 | Triangles mound, green bays — Macintosh Island Park |  |  |  | 277.5 | [6 empty] | 2084.03 | 1498.5 | Advanced's invoice pricing, order 4647509 | 0 | 0 | 0 |  | yes
36523 | 2026-09-17 | Week 5 | Helen Park — BSF compound |  | 22.5 | [8 empty] | 574.43 | 324 | Advanced's invoice pricing, order 4647509 | -22.5 | 22.5 | 0 | 22.5 | yes
36524 | 2026-09-17 | Week 5 | Race admin | 137.5 | [9 empty] | 2222.1 | 1375 | Advanced's rate sheet |  |  |  |  | NO
36525 | 2026-09-17 | Week 5 | S.O.5 C.2 | [7 empty] | 60 |  |  | 519.12 | 100 | Advanced's invoice pricing, order 4647509 | 0 | 0 | 0 |  | yes
36526 | 2026-09-17 | Week 5 | S.O.5 — retaining wall | 10 | [9 empty] | 161.61 | 100 | Advanced's invoice pricing, order 4647509 | 10 | 0 | 0 |  | yes
36528 | 2026-09-17 | Week 5 | S.O.8 exclusion zone | [7 empty] | 27.5 |  |  | 237.93 | 150 | Advanced's invoice pricing, order 4647509 | 0 | 0 | 2 |  | yes
36529 | 2026-09-17 | Week 5 | P.B.03 | 45 | 10 | [8 empty] | 982.53 | 594 | Advanced's invoice pricing, order 4647509 | 35 | 10 | 0 | 10 | yes
36530 | 2026-09-17 | Week 5 | PB01 works area | 15 |  |  | 50 | [6 empty] | 617.91 | 420 | Advanced's invoice pricing, order 4647509 | 15 | 0 | 0 |  | yes
36531 | 2026-09-17 | Week 5 | Pit building paddock |  | 105 | [8 empty] | 2680.65 | 1512 | Advanced's invoice pricing, order 4647509 | -105 | 105 | 0 | 105 | yes
36532 | 2026-09-18 | Week 5 | S10 compound | 150 | 132.5 | [8 empty] | 5806.83 | 3458 | Advanced's invoice pricing, order 4647509 | 12.5 | 132.5 | 2 | 132.5 | yes
36533 | 2026-09-18 | Week 5 | S10 C.2 | 45 | [9 empty] | 727.23 | 500 | Advanced's invoice pricing, order 4647509 | 40 | 0 | 2 |  | yes
36534 | 2026-09-18 | Week 5 | S10 to pit entry |  |  | 235 | [7 empty] | 3073.8 | 1269 | Advanced's invoice pricing, order 4647509 | 0 | 0 | 0 |  | yes
36535 | 2026-09-18 | Week 5 | S10 to pedestrian bridge |  |  | 30 | [7 empty] | 392.4 | 162 | Advanced's invoice pricing, order 4647509 | 0 | 0 | 0 |  | yes
36536 | 2026-09-21 | Week 4 | S08 C.Z. — construction zone | 172.5 | [9 empty] | 2787.72 | 1775 | Advanced's invoice pricing, order 4647517 | 167.5 | 0 | 2 |  | yes
36537 | 2026-09-21 | Week 4 | S04 C.Z. — construction zone | 172.5 | [9 empty] | 2787.72 | 1775 | Advanced's invoice pricing, order 4647517 | 167.5 | 0 | 2 |  | yes
36538 | 2026-09-21 | Week 4 | S.O.5 grandstand walkway | 32.5 | [9 empty] | 525.22 | 325 | Advanced's invoice pricing, order 4647517 | 32.5 | 0 | 0 |  | yes
36539 | 2026-09-22 | Week 4 | Cypress Carpark |  | 40 | [8 empty] | 1021.2 | 576 | Advanced's invoice pricing, order 4647517 | -40 | 40 | 0 | 40 | yes
36540 | 2026-09-22 | Week 4 | The Hill |  |  | 370 | [7 empty] | 4839.6 | 1998 | Advanced's invoice pricing, order 4647517 | 0 | 0 | 0 |  | yes
36541 | 2026-09-22 | Week 4 | The Hill — green bays |  |  |  | 25 | [6 empty] | 187.75 | 135 | Advanced's invoice pricing, order 4647517 | 0 | 0 | 0 |  | yes
36542 | 2026-09-22 | Week 4 | Viewing mound |  |  | 60 | [7 empty] | 784.8 | 324 | Advanced's invoice pricing, order 4647517 | 0 | 0 | 0 |  | yes
36543 | 2026-09-23 | Week 4 | PB02 stair protection | 20 | [9 empty] | 323.21 | 200 | Advanced's invoice pricing, order 4647517 | 20 | 0 | 0 |  | yes
36544 | 2026-09-23 | Week 4 | K01 kitchen compound fencing | 52.5 | 52.5 |  |  |  | 1 |  |  |  |  | 2224.95 | 1342 | Advanced's invoice pricing, order 4647517 | 0 | 52.5 | 0 | 52.5 | yes
36545 | 2026-09-23 | Week 4 | Race admin | 10 | [9 empty] | 161.61 | 100 | Advanced's invoice pricing, order 4647517 | 10 | 0 | 0 |  | yes
36546 | 2026-09-23 | Week 4 | S.O.4 C.Z. — construction zone | 22.5 | [9 empty] | 363.62 | 225 | Advanced's invoice pricing, order 4647517 | 22.5 | 0 | 0 |  | yes
36547 | 2026-09-23 | Week 4 | PB01 footings | 72.5 | 72.5 | [8 empty] | 3022.58 | 1769 | Advanced's invoice pricing, order 4647517 | 0 | 72.5 | 0 | 72.5 | yes
36548 | 2026-09-23 | Week 4 | PB01 to Kapalua | 475 | [9 empty] | 7676.33 | 4750 | Advanced's invoice pricing, order 4647517 | 475 | 0 | 0 |  | yes
36549 | 2026-09-23 | Week 4 | PB02 footings — north side | 32.5 | [9 empty] | 525.22 | 130 | Advanced's invoice pricing, order 4647517 | 13 | 0 | 0 |  | yes
36550 | 2026-09-24 | Week 4 | Axis — Hill Prd | 62.5 | [9 empty] | 1010.04 | 625 | Advanced's invoice pricing, order 4647517 | 52.5 | 0 | 2 |  | yes
36551 | 2026-09-24 | Week 4 | Breaker St / Serisier Ave — T12 to T14 |  |  | 510 | [7 empty] | 6670.8 | 2754 | Advanced's invoice pricing, order 4647517 | 0 | 0 | 0 |  | yes
36552 | 2026-09-24 | Week 4 | Telstra C.O.W. | 25 | [9 empty] | 404.02 | 300 | Advanced's invoice pricing, order 4647517 | 20 | 0 | 2 |  | yes
36553 | 2026-09-24 | Week 4 | PB01 to Kapalua | 12.5 | [9 empty] | 202.01 | 125 | Advanced's invoice pricing, order 4647517 | 12.5 | 0 | 0 |  | yes
36554 | 2026-09-24 | Week 4 | Main Beach Rd — supply compound to S22 |  |  | 352.5 | [7 empty] | 4610.7 | 1903.5 | Advanced's invoice pricing, order 4647517 | 0 | 0 | 0 |  | yes
36555 | 2026-09-24 | Week 4 | P.B.02 footings (south) | 30 | [9 empty] | 484.82 | 300 | Advanced's invoice pricing, order 4647517 | 30 | 0 | 0 |  | yes
36556 | 2026-09-25 | Week 4 | Narrow Neck to S.O.8 grandstand |  |  | 402.5 | [7 empty] | 5264.7 | 2038.5 | Advanced's invoice pricing, order 4647517 | 0 | 0 | 0 |  | yes
36557 | 2026-09-25 | Week 4 | S.O.8 pedestrian walkway | 100 | [9 empty] | 1616.07 | 1000 | Advanced's invoice pricing, order 4647517 | 100 | 0 | 0 |  | yes
36558 | 2026-09-25 | Week 4 | Oceanway C.Z. — concrete barrier infill | 10 | [9 empty] | 161.61 | 100 | Advanced's invoice pricing, order 4647517 | 10 | 0 | 0 |  | yes
36559 | 2026-09-28 | Week 3 | S.08 to Midwater, Castle St | 130 |  | 202.5 | [7 empty] | 4749.59 | 2643.5 | Advanced's invoice pricing, order 4647515 | 105 | 0 | 10 |  | yes
36560 | 2026-09-28 | Week 3 | GC Hwy median strip (north) | 507.5 | 427.5 | 447.5 |  |  | 1 |  |  |  |  | 25005.12 | 13858.5 | Advanced's invoice pricing, order 4647515 | 65 | 427.5 | 6 | 427.5 | yes
36561 | 2026-09-28 | Week 3 | Ocean Way carpark and construction zone | 142.5 | [9 empty] | 2302.9 | 1575 | Advanced's invoice pricing, order 4647515 | 127.5 | 0 | 6 |  | yes
36562 | 2026-09-29 | Week 3 | S.01 to Gate 6 (beach run) | 327.5 | [9 empty] | 5292.63 | 3275 | Advanced's invoice pricing, order 4647515 | 327.5 | 0 | 0 |  | yes
36563 | 2026-09-29 | Week 3 | S18 grandstand to Meriton |  |  | 150 | [7 empty] | 1962 | 810 | Advanced's invoice pricing, order 4647515 | 0 | 0 | 0 |  | yes
36564 | 2026-09-29 | Week 3 | WC15 - rear fencing (toilets) | 40 | 40 | [8 empty] | 1667.63 | 976 | Advanced's invoice pricing, order 4647515 | 0 | 40 | 0 | 40 | yes
36565 | 2026-09-29 | Week 3 | S04 to S05 pedestrian bridge | 25 | [9 empty] | 404.02 | 250 | Advanced's invoice pricing, order 4647515 | 25 | 0 | 0 |  | yes
36566 | 2026-09-30 | Week 3 | Rear of pit building / rear of Puppet Theatre |  | 270 | [6 empty] | 216 |  | 7545.42 | 3888 | Advanced's invoice pricing, order 4647515 | -270 | 270 | 0 | 270 | yes
36567 | 2026-09-30 | Week 3 | Smoking zones - trackwide |  |  |  | 215 | [6 empty] | 1614.65 | 1161 | Advanced's invoice pricing, order 4647515 | 0 | 0 | 0 |  | yes
36568 | 2026-10-01 | Week 3 | GC Hwy median strip (south) | 462.5 | 447.5 | 420 | [7 empty] | 24392.6 | 13487 | Advanced's invoice pricing, order 4647515 | 0 | 447.5 | 6 | 447.5 | yes
36569 | 2026-10-02 | Week 3 | Event - ELEC | 82.5 | 65 | [8 empty] | 2992.71 | 1811 | Advanced's invoice pricing, order 4647515 | 12.5 | 65 | 2 | 65 | yes
36570 | 2026-10-02 | Week 3 | Telstra COW |  | 10 | [8 empty] | 255.3 | 144 | Advanced's invoice pricing, order 4647515 | -10 | 10 | 0 | 10 | yes
36571 | 2026-10-02 | Week 3 | Triangle to Gate 6 beach run | 337.5 | [9 empty] | 5454.24 | 3425 | Advanced's invoice pricing, order 4647515 | 332.5 | 0 | 2 |  | yes
36572 | 2026-10-02 | Week 3 | S14 construction zone | 15 | [9 empty] | 242.41 | 200 | Advanced's invoice pricing, order 4647515 | 10 | 0 | 2 |  | yes
36573 | 2026-10-06 | Week 2 | Paradise Waters — Gate 2 entry | 97.5 | [9 empty] | 1575.67 | 975 | Advanced's invoice pricing, order 4647519 | 97.5 | 0 | 0 |  | yes
36574 | 2026-10-06 | Week 2 | TV parking | 177.5 | 10 | [8 empty] | 3123.82 | 1969 | Advanced's invoice pricing, order 4647519 | 162.5 | 10 | 2 | 10 | yes
36575 | 2026-10-06 | Week 2 | S01–S02 — stairs | 135 | [9 empty] | 2181.69 | 1500 | Advanced's invoice pricing, order 4647519 | 120 | 0 | 6 |  | yes
36576 | 2026-10-06 | Week 2 | S01 — toilet infill | 2.5 | 2.5 | [8 empty] | 104.23 | 61 | Advanced's invoice pricing, order 4647519 | 0 | 2.5 | 0 | 2.5 | yes
36577 | 2026-10-06 | Week 2 | Club 500 storage — perimeter fence | 30 | 25 | [8 empty] | 1123.07 | 710 | Advanced's invoice pricing, order 4647519 | 0 | 25 | 2 | 25 | yes
36578 | 2026-10-06 | Week 2 | TV compound perimeter fence | 75 | [9 empty] | 1212.05 | 750 | Advanced's invoice pricing, order 4647519 | 75 | 0 | 0 |  | yes
36579 | 2026-10-07 | Week 2 | Commodore Park | 177.5 | 122.5 |  |  |  | 2 |  |  |  |  | 6068.32 | 3861 | Advanced's invoice pricing, order 4647519 | 35 | 122.5 | 8 | 122.5 | yes
36580 | 2026-10-07 | Week 2 | S17–S20 — walk through (grandstands) | 150 | [9 empty] | 2424.1 | 1500 | Advanced's invoice pricing, order 4647519 | 150 | 0 | 0 |  | yes
36581 | 2026-10-07 | Week 2 | S04 — Corporate |  | 72.5 | [8 empty] | 1850.93 | 1044 | Advanced's invoice pricing, order 4647519 | -72.5 | 72.5 | 0 | 72.5 | yes
36582 | 2026-10-07 | Week 2 | Race Admin — double stack — C.2 | 82.5 | [9 empty] | 1333.26 | 875 | Advanced's invoice pricing, order 4647519 | 77.5 | 0 | 2 |  | yes
36583 | 2026-10-08 | Week 2 | Helen Park C.2 + perimeter fence | 215 | 55 | [8 empty] | 4878.7 | 3092 | Advanced's invoice pricing, order 4647519 | 145 | 55 | 6 | 55 | yes
36584 | 2026-10-08 | Week 2 | North S01 — Infill | 7.5 | 7.5 | [8 empty] | 312.69 | 183 | Advanced's invoice pricing, order 4647519 | 0 | 7.5 | 0 | 7.5 | yes
36585 | 2026-10-08 | Week 2 | Podium | 45 | 45 |  |  |  | 1 |  |  |  |  | 1912.26 | 1159 | Advanced's invoice pricing, order 4647519 | 0 | 45 | 0 | 45 | yes
36586 | 2026-10-08 | Week 2 | Teams Area | 25 | 25 | [8 empty] | 1042.27 | 610 | Advanced's invoice pricing, order 4647519 | 0 | 25 | 0 | 25 | yes
36587 | 2026-10-09 | Week 2 | Event Operations — perimeter fence | 30 | 22.5 | [8 empty] | 1059.25 | 699 | Advanced's invoice pricing, order 4647519 | 0 | 22.5 | 3 | 22.5 | yes
36588 | 2026-10-09 | Week 2 | Club 500 Toilets | 95 | 62.5 | [8 empty] | 3130.9 | 1850 | Advanced's invoice pricing, order 4647519 | 32.5 | 62.5 | 0 | 62.5 | yes
36589 | 2026-10-09 | Week 2 | S04 Corporate Toilets | 15 | 15 | [8 empty] | 625.36 | 366 | Advanced's invoice pricing, order 4647519 | 0 | 15 | 0 | 15 | yes
36590 | 2026-10-09 | Week 2 | Club 500 exclusion zone CZ | 107.5 | [9 empty] | 1737.28 | 1175 | Advanced's invoice pricing, order 4647519 | 97.5 | 0 | 4 |  | yes
36591 | 2026-10-09 | Week 2 | Club 500 Creek Protection |  |  |  | 105 | 42 | [5 empty] | 1193.9 | 567 | Advanced's invoice pricing, order 4647519 | 0 | 0 | 0 |  | yes
36592 | 2026-10-09 | Week 2 | The Hill — Monster CZ | 137.5 | [9 empty] | 2222.1 | 1375 | Advanced's invoice pricing, order 4647519 | 137.5 | 0 | 0 |  | yes
36593 | 2026-10-09 | Week 2 | S21 Grandstand — Walk through | 90 | [9 empty] | 1454.46 | 900 | Advanced's invoice pricing, order 4647519 | 90 | 0 | 0 |  | yes
36594 | 2026-10-09 | Week 2 | Smoking Zones — The Hill / Club 500 |  |  |  | 22.5 | [6 empty] | 168.98 | 121.5 | Advanced's invoice pricing, order 4647519 | 0 | 0 | 0 |  | yes
36595 | 2026-10-09 | Week 2 | Rear of S20 — Shower |  |  |  | 10 | [6 empty] | 75.1 | 54 | Advanced's invoice pricing, order 4647519 | 0 | 0 | 0 |  | yes
36596 | 2026-10-12 | Week 1 | Main Beach Pde - Madison Point to Ferny Ave, Higman St to Equinox, Ferny Ave southern side, Seacrest to Pacific Point | 385 |  | 287.5 |  |  | 5 |  |  |  |  | 10163.29 | 6007.5 | Advanced's invoice pricing, order 4647520 | 355 | 0 | 12 |  | yes
36597 | 2026-10-12 | Week 1 | The Spit - McMahon's/HTH Compound |  | 17.5 | [8 empty] | 446.78 | 252 | Advanced's invoice pricing, order 4647520 | -17.5 | 17.5 | 0 | 17.5 | yes
36598 | 2026-10-12 | Week 1 | Main Beach Pde - Rhapsody | 7.5 | 7.5 | [8 empty] | 312.69 | 183 | Advanced's invoice pricing, order 4647520 | 0 | 7.5 | 0 | 7.5 | yes
36599 | 2026-10-12 | Week 1 | Supply Compound | 147.5 | 147.5 | [8 empty] | 6149.38 | 3599 | Advanced's invoice pricing, order 4647520 | 0 | 147.5 | 0 | 147.5 | yes
36600 | 2026-10-12 | Week 1 | I.E.D.M - Compound | [10 empty] | 0 | 200 | Advanced's invoice pricing, order 4647520 | 0 | 0 | 0 |  | yes
36601 | 2026-10-12 | Week 1 | Commodore Park - Ticket Entry | 25 | 25 | [8 empty] | 1042.27 | 610 | Advanced's invoice pricing, order 4647520 | 0 | 25 | 0 | 25 | yes
36602 | 2026-10-12 | Week 1 | COW - OPTUS | 45 | 45 | [8 empty] | 1876.08 | 1098 | Advanced's invoice pricing, order 4647520 | 0 | 45 | 0 | 45 | yes
36603 | 2026-10-13 | Week 1 | Eastern Residents & Demarc - Cable St to Gate 8A - DL & DR | 537.5 | 52.5 | 672.5 |  |  | 4 |  |  |  |  | 18967.75 | 10356.5 | Advanced's invoice pricing, order 4647520 | 450 | 52.5 | 14 | 52.5 | yes
36604 | 2026-10-13 | Week 1 | Breaker St - T11 - DL |  |  |  |  | 105 | [5 empty] | 1013.37 | 567 | Advanced's invoice pricing, order 4647520 | 0 | 0 | 0 |  | yes
36605 | 2026-10-13 | Week 1 | Aloha Lane to Cronin St (Crest) | 95 | [9 empty] | 1535.27 | 950 | Advanced's invoice pricing, order 4647520 | 95 | 0 | 0 |  | yes
36606 | 2026-10-13 | Week 1 | Fishermans Walk | 10 | [9 empty] | 161.61 | 100 | Advanced's invoice pricing, order 4647520 | 10 | 0 | 0 |  | yes
36607 | 2026-10-14 | Week 1 | Main Beach Tower | 47.5 | [9 empty] | 767.63 | 475 | Advanced's invoice pricing, order 4647520 | 47.5 | 0 | 0 |  | yes
36608 | 2026-10-14 | Week 1 | Ferny Ave to Narrow Neck Court | 117.5 |  | 192.5 | [7 empty] | 4416.78 | 2414.5 | Advanced's invoice pricing, order 4647520 | 97.5 | 0 | 8 |  | yes
36609 | 2026-10-14 | Week 1 | Esplanade south of Meriton - Porsche Lounge CZ | 420 | 420 | [8 empty] | 17510.09 | 6100 | Advanced's invoice pricing, order 4647520 | 285 | 125 | 4 | 420 | yes
36610 | 2026-10-14 | Week 1 | G8 & surround | 367.5 |  | 200 |  |  | 2 |  |  |  |  | 8627.43 | 5077 | Advanced's invoice pricing, order 4647520 | 347.5 | 0 | 8 |  | yes
36611 | 2026-10-15 | Week 1 | Surfers Paradise Light Rail | 165 | 30 |  | 130 | [6 empty] | 4408.72 | 2884 | Advanced's invoice pricing, order 4647520 | 125 | 30 | 4 | 30 | yes
36612 | 2026-10-15 | Week 1 | Pacific Ave to Cable St | 315 |  |  |  |  | 3 |  |  |  |  | 5199.17 | 3733 | Advanced's invoice pricing, order 4647520 | 275 | 0 | 16 |  | yes
36613 | 2026-10-15 | Week 1 | Porsche CZ |  |  |  | 70 | [6 empty] | 525.7 | 378 | Advanced's invoice pricing, order 4647520 | 0 | 0 | 0 |  | yes
36614 | 2026-10-15 | Week 1 | S.0.8 B.O.H. | 40 | 85 | [8 empty] | 2816.48 | 1674 | Advanced's invoice pricing, order 4647520 | -50 | 85 | 2 | 85 | yes
36615 | 2026-10-15 | Week 1 | Gate 5 Compound | 110 | 40 | [8 empty] | 2798.88 | 1676 | Advanced's invoice pricing, order 4647520 | 70 | 40 | 0 | 40 | yes
36616 | 2026-10-15 | Week 1 | Triangle CZ | 147.5 | [9 empty] | 2383.7 | 1525 | Advanced's invoice pricing, order 4647520 | 142.5 | 0 | 2 |  | yes
36617 | 2026-10-16 | Week 1 | Main Beach Light Rail | 155 | 37.5 | [8 empty] | 3462.29 | 2090 | Advanced's invoice pricing, order 4647520 | 117.5 | 37.5 | 0 | 37.5 | yes
36618 | 2026-10-16 | Week 1 | Cypress Carpark | 152.5 | [9 empty] | 2464.51 | 1675 | Advanced's invoice pricing, order 4647520 | 147.5 | 0 | 4 |  | yes
36619 | 2026-10-16 | Week 1 | Focus to Meriton - The Esplanade | 262.5 |  |  | 302.5 | [6 empty] | 6513.96 | 4458.5 | Advanced's invoice pricing, order 4647520 | 242.5 | 0 | 8 |  | yes
36620 | 2026-10-16 | Week 1 | I.E.D.M - Compound | [10 empty] | 0 | 100 | Advanced's invoice pricing, order 4647520 | 0 | 0 | 0 |  | yes
36621 | 2026-10-16 | Week 1 | Monster C.Z. - The Hill | 2.5 | [9 empty] | 40.4 | 25 | Advanced's invoice pricing, order 4647520 | 2.5 | 0 | 0 |  | yes
36622 | 2026-10-16 | Week 1 | Golden Gate | 130 | [9 empty] | 2100.89 | 1450 | Advanced's invoice pricing, order 4647520 | 115 | 0 | 6 |  | yes
36623 | 2026-10-19 | Event Week | S15 C2 - hoarding fence and demarcation | 97.5 |  | 100 | [7 empty] | 2883.67 | 1515 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36624 | 2026-10-19 | Event Week | Admiralty Drive Intersection | 32.5 | [9 empty] | 525.22 | 325 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36625 | 2026-10-19 | Event Week | Gate 1 - S23 Compound | 285 | 285 | [8 empty] | 11881.85 | 9804 | Advanced's rate sheet |  |  |  | 285 | event week: not billed yet
36626 | 2026-10-19 | Event Week | Seaway Carpark - The Spit and fuel compound | 492.5 | [9 empty] | 7959.14 | 4925 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36627 | 2026-10-20 | Event Week | Track wide (four spots) |  |  | 7.5 | 125 | [6 empty] | 1036.85 | 715.5 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36628 | 2026-10-20 | Event Week | PB03 - footings | 25 | 25 | [8 empty] | 1042.27 | 860 | Advanced's rate sheet |  |  |  | 25 | event week: not billed yet
36629 | 2026-10-20 | Event Week | PB03 - Gate 1 - Helen Park |  | 80 | 182.5 | 237.5 | [6 empty] | 6213.13 | 4220 | Advanced's rate sheet |  |  |  | 80 | event week: not billed yet
36630 | 2026-10-20 | Event Week | Macintosh Island - entry | 30 | [9 empty] | 484.82 | 300 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36631 | 2026-10-20 | Event Week | Podium | 5 | 5 | [8 empty] | 208.45 | 172 | Advanced's rate sheet |  |  |  | 5 | event week: not billed yet
36632 | 2026-10-20 | Event Week | Pit Lane - S01 | [10 empty] | 0 | 0 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36633 | 2026-10-20 | Event Week | Fire hydrant - S01 - toilets | 17.5 | [9 empty] | 282.81 | 175 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36634 | 2026-10-20 | Event Week | S07 viewing mound |  |  | 12.5 | [7 empty] | 163.5 | 67.5 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36635 | 2026-10-20 | Event Week | Esplanade north to the Triangle |  |  |  | 37.5 | 35 | [5 empty] | 619.42 | 391.5 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36636 | 2026-10-20 | Event Week | Higman St and Rhapsody |  |  | 205 | [7 empty] | 2681.4 | 1107 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36637 | 2026-10-20 | Event Week | Macintosh Island foot bridge |  |  |  | 25 | [6 empty] | 187.75 | 135 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36638 | 2026-10-20 | Event Week | Pit Building north |  |  |  |  | 88 | [5 empty] | 849.3 | 475.2 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36639 | 2026-10-21 | Event Week | McIntosh Island storage | 15 | 15 | [8 empty] | 625.36 | 516 | Advanced's rate sheet |  |  |  | 15 | event week: not billed yet
36640 | 2026-10-21 | Event Week | D.S - storage | 47.5 | [9 empty] | 767.63 | 475 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36642 | 2026-10-21 | Event Week | Gate 6 | 7.5 | 7.5 | [8 empty] | 312.69 | 258 | Advanced's rate sheet |  |  |  | 7.5 | event week: not billed yet
36643 | 2026-10-21 | Event Week | Club 500 | 32.5 | 47.5 |  | 20 | [6 empty] | 1888.1 | 1592 | Advanced's rate sheet |  |  |  | 47.5 | event week: not billed yet
36644 | 2026-10-21 | Event Week | Porsche to Staghorn St (Esplanade) | [10 empty] | 0 | 0 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36645 | 2026-10-21 | Event Week | Inlet (Breaker St) |  |  | 12.5 | [7 empty] | 163.5 | 67.5 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36646 | 2026-10-21 | Event Week | S08 - TV | 15 | [9 empty] | 242.41 | 150 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36647 | 2026-10-21 | Event Week | Club 500 - creek protection |  |  |  | 47.5 | [6 empty] | 356.73 | 256.5 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36756 | 2026-10-21 | Event Week | Meriton | 10 | [9 empty] | 161.61 | 100 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36757 | 2026-10-21 | Event Week | The Spit - Transporter Compound | 70 | [9 empty] | 1131.25 | 700 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36648 | 2026-10-22 | Event Week | Gate 7 | 37.5 | [9 empty] | 606.03 | 375 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36649 | 2026-10-22 | Event Week | Gate 10 | 40 | 40 | [8 empty] | 1667.63 | 1376 | Advanced's rate sheet |  |  |  | 40 | event week: not billed yet
36650 | 2026-10-22 | Event Week | Malibu - Breaker St | 5 | [9 empty] | 80.8 | 50 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36751 | 2026-10-22 | Event Week | Ocean Ave | 147.5 |  |  | 315 | [6 empty] | 4749.35 | 3176 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36752 | 2026-10-22 | Event Week | Staghorn St Entry | 20 | [9 empty] | 323.21 | 200 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36753 | 2026-10-22 | Event Week | Gate 9 - Breaker St | 17.5 | [9 empty] | 282.81 | 175 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36754 | 2026-10-22 | Event Week | Aloha Lane - Gate 8 | 37.5 | [9 empty] | 606.03 | 375 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36755 | 2026-10-22 | Event Week | Helipad | 35 |  |  | 45 | [6 empty] | 903.57 | 593 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36758 | 2026-10-22 | Event Week | T.V - Compound | 30 | [9 empty] | 484.82 | 300 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36759 | 2026-10-22 | Event Week | Rhapsody Sales Office - walk through | 72.5 | 72.5 | [8 empty] | 3022.58 | 2494 | Advanced's rate sheet |  |  |  | 72.5 | event week: not billed yet
36760 | 2026-10-22 | Event Week | Macintosh Island - fallen tree |  |  | 10 | [7 empty] | 130.8 | 54 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36761 | 2026-10-22 | Event Week | Rubbish Compactor (Cleanaway) | 35 | 32.5 | [8 empty] | 1395.35 | 1143 | Advanced's rate sheet |  |  |  | 32.5 | event week: not billed yet
36762 | 2026-10-22 | Event Week | Turn 2-3 - Crash Protection | 20 | [9 empty] | 323.21 | 200 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36763 | 2026-10-22 | Event Week | Triangle | [10 empty] | 0 | 0 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36764 | 2026-10-22 | Event Week | Monster (Energy) |  |  |  | 15 | [6 empty] | 112.65 | 81 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36765 | 2026-10-23 | Event Week | Gate 5 - Ocean Ave | 5 | [9 empty] | 80.8 | 50 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36766 | 2026-10-23 | Event Week | Smoking Zone - Breaker St |  |  |  | 10 | [6 empty] | 75.1 | 54 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36767 | 2026-10-23 | Event Week | Gate 7 - security entry | 7.5 | [9 empty] | 121.21 | 75 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
36768 | 2026-10-23 | Event Week | Club 500 - B.O.H. |  |  |  | 50 | [6 empty] | 375.5 | 270 | Advanced's rate sheet |  |  |  |  | event week: not billed yet
Total |  |  |  | 13270 | 3977.5 | 5062.5 | 2195 | 270 | 22 | 3 | 137.5 | 216 | 8.5 | 405150.96 | 240961.7

## Labour notes and extras
Labour notes (green book): Advanced Environmental Services service notes, a cost only
Note | Date | Hours | Rate | On an Advanced sheet |  | We pay
24451 | 2026-09-15 | 0.5 | 100 | yes |  | 50
24452 | 2026-09-15 | 0.5 | 100 | yes |  | 50
24453 | 2026-09-16 | 1.5 | 100 | yes |  | 150
24454 | 2026-09-17 | 1 | 100 | yes |  | 100
24455 | 2026-09-18 | 0.75 | 100 | yes |  | 75
24456 | 2026-09-21 | 0.75 | 100 | yes |  | 75
24457 | 2026-09-21 | 1 | 100 | yes |  | 100
24458 | 2026-09-23 | 1 | 100 | yes |  | 100
24459 | 2026-09-24 | 1.5 | 100 | yes |  | 150
24460 | 2026-09-25 | 1 | 100 | yes |  | 100
24461 | 2026-09-29 | 1 | 100 | yes |  | 100
24462 | 2026-09-29 | 2 | 100 | yes |  | 200
24463 | 2026-09-30 | 0.75 | 100 | yes |  | 75
24464 | 2026-09-30 | 1 | 100 | yes |  | 100
24465 | 2026-10-01 | 1 | 100 | yes |  | 100
24466 | 2026-10-02 | 0.5 | 100 | yes |  | 50
24467 | 2026-10-02 | 0.25 | 100 | yes |  | 25
24468 | 2026-10-06 | 0.25 | 100 | yes |  | 25
24469 | 2026-10-06 | 0.75 | 100 | yes |  | 75
24470 | 2026-10-07 | 1.5 | 100 | yes |  | 150
24471 | 2026-10-07 | 1.5 | 100 | yes |  | 150
24472 | 2026-10-07 | 4 | 100 | yes |  | 400
24473 | 2026-10-08 | 4 | 100 | yes |  | 400
24474 | 2026-10-09 | 0.5 | 100 | yes |  | 50
24475 | 2026-10-12 | 3 | 100 | yes |  | 300
24478 | 2026-10-12 | 0.5 | 100 | yes |  | 50
24476 | 2026-10-13 | 2 | 100 | yes |  | 200
24477 | 2026-10-13 | 1.5 | 100 | yes |  | 150
24479 | 2026-10-13 | 0.5 | 100 | NO |  | 50
24480 | 2026-10-14 | 1.5 | 100 | yes |  | 150
24481 | 2026-10-15 | 4 | 100 | yes |  | 400
24482 | 2026-10-19 | 1.25 | 100 | event week: not billed yet |  | 125
24483 | 2026-10-20 | 1 | 100 | event week: not billed yet |  | 100
24484 | 2026-10-20 | 2 | 100 | event week: not billed yet |  | 200
24485 | 2026-10-20 | 8 | 100 | event week: not billed yet |  | 800
24486 | 2026-10-20 | 0.5 | 100 | event week: not billed yet |  | 50
24489 | 2026-10-21 | 0.5 | 100 | event week: not billed yet |  | 50
24487 | 2026-10-22 | 31.5 | 100 | event week: not billed yet |  | 3150
24488 | 2026-10-22 | 20 | 100 | event week: not billed yet |  | 2000
24490 | 2026-10-22 | 0.75 | 100 | event week: not billed yet |  | 75
24491 | 2026-10-22 | 1 | 100 | event week: not billed yet |  | 100
24492 | 2026-10-22 | 0.5 | 100 | event week: not billed yet |  | 50
Total |  | 108.5 |  |  |  | 10850
Extras on Advanced's purchase orders
Order | Date | What | Qty | Unit | Rate | We pay
4647509 | 2026-09-14 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647509 | 2026-09-15 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647509 | 2026-09-16 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647509 | 2026-09-17 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647509 | 2026-09-18 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647515 | 2026-09-28 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647515 | 2026-09-29 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647515 | 2026-09-30 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647515 | 2026-10-01 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647515 | 2026-10-02 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647517 | 2026-09-21 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647517 | 2026-09-22 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647517 | 2026-09-23 | Team leader — daily supplier charge | 1 | day | 200 | 200
4647517 | 2026-09-24 | Team leader — daily supplier charge | 1 | day | 200 | 200
4647517 | 2026-09-25 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647519 | 2026-10-06 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647519 | 2026-10-07 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647519 | 2026-10-08 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647519 | 2026-10-09 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647520 | 2026-10-12 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647520 | 2026-10-13 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647520 | 2026-10-14 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647520 | 2026-10-14 | Weed mat supply — 40 rolls | 40 | rolls | 64.5 | 2580
4647520 | 2026-10-14 | Shade cloth supply — 4 rolls | 4 | rolls | 196 | 784
4647520 | 2026-10-15 | Team leader — daily supplier charge | 2 | day | 200 | 400
4647520 | 2026-10-16 | Team leader — daily supplier charge | 2 | day | 200 | 400
Total | [5 empty] | 12564