## Summary
GC500 fencing (9990776): what we charge the V8s and what we pay Advanced
Signed dockets 9 Sep to 23 Oct 2026 · AUD ex GST · from the live record, 25 Oct 2026
We charge the V8s | 340871.73 | 167 signed fencing dockets at the 2026 card and your rates
We pay Advanced | 255218.2 | their approved sheets and invoices, and the event week at their rates
Margin | 85653.53 | 25.1% of what we charge
What we pay Advanced, by invoice
Invoice received | 69552 | weeks 4, 5 and 6, and the partial collection
Approved sheet, no invoice yet | 144722.5 | weeks 1, 2 and 3: their sheets match the orders to the cent
Nothing from Advanced yet (our estimate) | 40943.7 | the event week, 19 to 23 Oct
Total we pay Advanced | 255218.2
Good to know
Advanced bill off their own approved weekly sheets, so their quantities don't match ours line for line: all their CCB is one line at $5.40, vehicle gates are billed on their own, and their clean metres leave out the gate openings.
The scrim fence is charged once: the papers' clean metres include the fence under the scrim, so it comes off the clean and is charged in the scrim at $25.53 (fence + shade cloth).
The event week is our estimate at Advanced's rates until their invoice comes in (order 4647522), so it can still move. Nothing is dated Sat 24 or Sun 25 Oct.
Not in these figures: the demob, and the fence team's event labour under the C004 scope (213 h at $91.14 = $19,412.82), which is charged separately.

## We charge the V8s
What we charge the V8s
AUD ex GST · rates from the 2026 street card or your named rates
Item | Qty | Unit | Rate | Total
Clean fence (not scrimmed) | 9292.5 | m | 16.1607 | 150173.23
Scrim fence (fence + shade cloth) | 3977.5 | m | 25.53 | 101545.7
CCB demarcation | 5062.5 | m | 13.08 | 66217.5
CCB event | 2195 | m | 7.51 | 16484.48
CCB flat feet | 270 | m | 9.6511 | 2605.81
Labour | 8.5 | h | 142 | 1207
Relocation | 137.5 | m | 8.652 | 1189.65
Pedestrian gates | 22 | each | 36.1839 | 796.04
Fence blocks | 216 | each | 3.02 | 652.32
Vehicle gates | 3 | each | inside the metre rate | 0
Total |  |  |  | 340871.73
Clean fence is the papers' clean less the fence under the scrim, which is charged once, in the scrim. Each docket's lines are rounded to the cent, as the page prices them.

## We pay Advanced
What we pay Advanced
AUD ex GST · their approved sheets for weeks 1 to 5, their rate sheet for week 6 and the event week
Item | Qty | Unit | Rate | Total
Clean fence | 9035.5 | m | 10 | 90355
Scrim fence (braced for scrim) | 3682.5 | m | 24.4 | 89853
CCB demarcation | 6410 | m | 5.4 | 34614
CCB event | 927.5 | m | 5.4 | 5008.5
CCB flat feet | 123 | m | 5.4 | 664.2
Labour | 8.5 | h | 100 | 850
Relocation (billed by the hour) | 2 | h | 100 | 200
Pedestrian gates | 22 | each | 61 | 1342
Vehicle gates | 219 | each | 50 | 10950
Bases | 300 | each | 1 | 300
Team leader | 46 | days | 200 | 9200
Weed mat, 40 rolls | 40 | rolls | 64.5 | 2580
Shade cloth, 4 rolls | 4 | rolls | 196 | 784
Labour notes | 108.5 | h | 100 | 10850
Partial collection (invoice 93920) |  |  |  | 195
Weeks 5 and 6 invoiced under their rates (the order amounts stand) |  |  |  | -2527.5
Total |  |  |  | 255218.2

## Invoices
What we pay Advanced, by invoice
AUD ex GST · order amounts as on the purchase orders; "we carry" is what our record pays for that week
Status | Week | Order | Order amount | Receipt | We carry | Notes
Invoice received | Week 6 | 4647508 | 8992 | 4918492 | 8992 | no sheet came with the invoice; the order amount stands
Invoice received | Week 5 | 4647509 | 33670 | 4922398 | 33670 | Advanced's sheet says $33,670.50; the order amount stands; docket 36524 is not on their sheet
Invoice received | Week 4 | 4647517 | 26695 | 4926209 | 26695
Invoice received | Partial collection | 4658850 | 195 | 4922343 | 195 | INV 93920 - partial Collection; not tied to a docket
Invoice received — total |  |  |  |  | 69552
Approved sheet, no invoice yet | Week 3 | 4647515 | 50154 |  | 50154 | their sheet prints the order as 464517
Approved sheet, no invoice yet | Week 2 | 4647519 | 28246.5 |  | 28246.5
Approved sheet, no invoice yet | Week 1 | 4647520 | 66272 |  | 66322 | labour note 24479 ($50) is not on their sheet, so it is carried on top
Approved sheet, no invoice yet — total |  |  |  |  | 144722.5
Nothing from Advanced yet (our estimate) | Event Week | 4647522 |  |  | 40943.7 | 45 dockets and 11 labour notes at their rates; their invoice is still to come
Nothing from Advanced yet (our estimate) — total |  |  |  |  | 40943.7
Total we pay Advanced |  |  |  |  | 255218.2

## Event week by day
The event week, day by day
AUD ex GST · every paper handed over on Friday (40) and Saturday (5) is in, under the day the work was done
Day worked | Papers | We pay Advanced | We charge the V8s
Mon 19 Oct | 4 | 13719 | 18644.08
Tue 20 Oct | 12 | 7518.7 | 11992.02
Wed 21 Oct | 10 | 3415 | 4518.03
Thu 22 Oct | 15 | 9142 | 12345.54
Fri 23 Oct | 4 | 449 | 652.61
Labour notes (Mon 19 Oct to Thu 22 Oct) | 11 | 6700 | inside the metre rates
Event week | 56 | 40943.7 | 48152.28
Our estimate at Advanced's rates until their invoice for the event week comes in. Nothing is dated Sat 24 or Sun 25 Oct.

## Dockets
Every signed fencing docket
AUD ex GST · we pay Advanced per docket; team leader, materials, labour notes and the invoice adjustments are on "We pay Advanced"
Docket | Date | Week | Location | We charge the V8s | We pay Advanced | Invoice
tracker row | (week 6, no day) | Week 6 |  | 3757.36 | 2475 | Invoice received
36501 | Wed 9 Sep | Week 6 | Sea World Drive, Main Beach | 3999.77 | 2475 | Invoice received
36502 | Fri 11 Sep | Week 6 | Phillip Park (Advanced compound) | 4161.38 | 2575 | Invoice received
36503 | Fri 11 Sep | Week 6 | Sea World Drive, Main Beach | 0 | 0 | Invoice received
36504 | Fri 11 Sep | Week 6 | Helen Park, BSF compound | 1850.93 | 1769 | Invoice received
36511 | Sat 12 Sep | Week 6 | Yatala — Morayfield (Phillip Island / Morayfield), region Yatala | 1207 | 850 | Invoice received
36505 | Mon 14 Sep | Week 5 | Cypress Carpark | 1575.67 | 1075 | Invoice received
36506 | Mon 14 Sep | Week 5 | S18 C.2 construction zone | 2234.98 | 1469 | Invoice received
36507 | Mon 14 Sep | Week 5 | Admiralty Drive — crossing closure | 121.21 | 75 | Invoice received
36508 | Mon 14 Sep | Week 5 | P.B03 C.2 | 323.21 | 200 | Invoice received
36509 | Mon 14 Sep | Week 5 | Pit Building / Paddock C.2 — perimeter fencing | 9405.17 | 6297 | Invoice received
36510 | Mon 14 Sep | Week 5 | Sea World Drive, Main Beach | 432.6 | 50 | Invoice received
36512 | Mon 14 Sep | Week 5 | S04 Corporate Facility / TV compound | 2787.72 | 1875 | Invoice received
36513 | Tue 15 Sep | Week 5 | S07 C-Zone | 2177.61 | 1455 | Invoice received
36514 | Tue 15 Sep | Week 5 | Event Operations — iEDM compound | 3075.73 | 2694 | Invoice received
36515 | Tue 15 Sep | Week 5 | S07 — hill protection | 450.6 | 324 | Invoice received
36516 | Tue 15 Sep | Week 5 | Track storage | 1414.06 | 1075 | Invoice received
36517 | Wed 16 Sep | Week 5 | S.O.5 C.2 | 1090.85 | 725 | Invoice received
36518 | Wed 16 Sep | Week 5 | S.O.5 — grandstand, back of house | 776.43 | 724 | Invoice received
36519 | Wed 16 Sep | Week 5 | Event operations — iEDM compound | 679.28 | 1044 | Invoice received
36520 | Wed 16 Sep | Week 5 | Coates compound / ABD compound | 2192.85 | 1801 | Invoice received
36521 | Wed 16 Sep | Week 5 | S.O.8 exclusion zone | 444.42 | 275 | Invoice received
36522 | Wed 16 Sep | Week 5 | Triangles mound, green bays — Macintosh Island Park | 2084.03 | 1498.5 | Invoice received
36523 | Thu 17 Sep | Week 5 | Helen Park — BSF compound | 210.81 | 324 | Invoice received
36524 | Thu 17 Sep | Week 5 | Race admin | 2222.1 | 1375 | not on any Advanced sheet
36525 | Thu 17 Sep | Week 5 | S.O.5 C.2 | 519.12 | 100 | Invoice received
36526 | Thu 17 Sep | Week 5 | S.O.5 — retaining wall | 161.61 | 100 | Invoice received
36528 | Thu 17 Sep | Week 5 | S.O.8 exclusion zone | 237.93 | 150 | Invoice received
36529 | Thu 17 Sep | Week 5 | P.B.03 | 820.92 | 594 | Invoice received
36530 | Thu 17 Sep | Week 5 | PB01 works area | 617.91 | 420 | Invoice received
36531 | Thu 17 Sep | Week 5 | Pit building paddock | 983.78 | 1512 | Invoice received
36532 | Fri 18 Sep | Week 5 | S10 compound | 3665.54 | 3458 | Invoice received
36533 | Fri 18 Sep | Week 5 | S10 C.2 | 727.23 | 500 | Invoice received
36534 | Fri 18 Sep | Week 5 | S10 to pit entry | 3073.8 | 1269 | Invoice received
36535 | Fri 18 Sep | Week 5 | S10 to pedestrian bridge | 392.4 | 162 | Invoice received
36536 | Mon 21 Sep | Week 4 | S08 C.Z. — construction zone | 2787.72 | 1775 | Invoice received
36537 | Mon 21 Sep | Week 4 | S04 C.Z. — construction zone | 2787.72 | 1775 | Invoice received
36538 | Mon 21 Sep | Week 4 | S.O.5 grandstand walkway | 525.22 | 325 | Invoice received
36539 | Tue 22 Sep | Week 4 | Cypress Carpark | 374.77 | 576 | Invoice received
36540 | Tue 22 Sep | Week 4 | The Hill | 4839.6 | 1998 | Invoice received
36541 | Tue 22 Sep | Week 4 | The Hill — green bays | 187.75 | 135 | Invoice received
36542 | Tue 22 Sep | Week 4 | Viewing mound | 784.8 | 324 | Invoice received
36543 | Wed 23 Sep | Week 4 | PB02 stair protection | 323.21 | 200 | Invoice received
36544 | Wed 23 Sep | Week 4 | K01 kitchen compound fencing | 1376.51 | 1342 | Invoice received
36545 | Wed 23 Sep | Week 4 | Race admin | 161.61 | 100 | Invoice received
36546 | Wed 23 Sep | Week 4 | S.O.4 C.Z. — construction zone | 363.62 | 225 | Invoice received
36547 | Wed 23 Sep | Week 4 | PB01 footings | 1850.93 | 1769 | Invoice received
36548 | Wed 23 Sep | Week 4 | PB01 to Kapalua | 7676.33 | 4750 | Invoice received
36549 | Wed 23 Sep | Week 4 | PB02 footings — north side | 525.22 | 130 | Invoice received
36550 | Thu 24 Sep | Week 4 | Axis — Hill Prd | 1010.04 | 625 | Invoice received
36551 | Thu 24 Sep | Week 4 | Breaker St / Serisier Ave — T12 to T14 | 6670.8 | 2754 | Invoice received
36552 | Thu 24 Sep | Week 4 | Telstra C.O.W. | 404.02 | 300 | Invoice received
36553 | Thu 24 Sep | Week 4 | PB01 to Kapalua | 202.01 | 125 | Invoice received
36554 | Thu 24 Sep | Week 4 | Main Beach Rd — supply compound to S22 | 4610.7 | 1903.5 | Invoice received
36555 | Thu 24 Sep | Week 4 | P.B.02 footings (south) | 484.82 | 300 | Invoice received
36556 | Fri 25 Sep | Week 4 | Narrow Neck to S.O.8 grandstand | 5264.7 | 2038.5 | Invoice received
36557 | Fri 25 Sep | Week 4 | S.O.8 pedestrian walkway | 1616.07 | 1000 | Invoice received
36558 | Fri 25 Sep | Week 4 | Oceanway C.Z. — concrete barrier infill | 161.61 | 100 | Invoice received
36559 | Mon 28 Sep | Week 3 | S.08 to Midwater, Castle St | 4749.59 | 2643.5 | Approved sheet, no invoice yet
36560 | Mon 28 Sep | Week 3 | GC Hwy median strip (north) | 18096.42 | 13858.5 | Approved sheet, no invoice yet
36561 | Mon 28 Sep | Week 3 | Ocean Way carpark and construction zone | 2302.9 | 1575 | Approved sheet, no invoice yet
36562 | Tue 29 Sep | Week 3 | S.01 to Gate 6 (beach run) | 5292.63 | 3275 | Approved sheet, no invoice yet
36563 | Tue 29 Sep | Week 3 | S18 grandstand to Meriton | 1962 | 810 | Approved sheet, no invoice yet
36564 | Tue 29 Sep | Week 3 | WC15 - rear fencing (toilets) | 1021.2 | 976 | Approved sheet, no invoice yet
36565 | Tue 29 Sep | Week 3 | S04 to S05 pedestrian bridge | 404.02 | 250 | Approved sheet, no invoice yet
36566 | Wed 30 Sep | Week 3 | Rear of pit building / rear of Puppet Theatre | 3182.03 | 3888 | Approved sheet, no invoice yet
36567 | Wed 30 Sep | Week 3 | Smoking zones - trackwide | 1614.65 | 1161 | Approved sheet, no invoice yet
36568 | Thu 1 Oct | Week 3 | GC Hwy median strip (south) | 17160.69 | 13487 | Approved sheet, no invoice yet
36569 | Fri 2 Oct | Week 3 | Event - ELEC | 1942.26 | 1811 | Approved sheet, no invoice yet
36570 | Fri 2 Oct | Week 3 | Telstra COW | 93.69 | 144 | Approved sheet, no invoice yet
36571 | Fri 2 Oct | Week 3 | Triangle to Gate 6 beach run | 5454.24 | 3425 | Approved sheet, no invoice yet
36572 | Fri 2 Oct | Week 3 | S14 construction zone | 242.41 | 200 | Approved sheet, no invoice yet
36573 | Tue 6 Oct | Week 2 | Paradise Waters — Gate 2 entry | 1575.67 | 975 | Approved sheet, no invoice yet
36574 | Tue 6 Oct | Week 2 | TV parking | 2962.21 | 1969 | Approved sheet, no invoice yet
36575 | Tue 6 Oct | Week 2 | S01–S02 — stairs | 2181.69 | 1500 | Approved sheet, no invoice yet
36576 | Tue 6 Oct | Week 2 | S01 — toilet infill | 63.83 | 61 | Approved sheet, no invoice yet
36577 | Tue 6 Oct | Week 2 | Club 500 storage — perimeter fence | 719.05 | 710 | Approved sheet, no invoice yet
36578 | Tue 6 Oct | Week 2 | TV compound perimeter fence | 1212.05 | 750 | Approved sheet, no invoice yet
36579 | Wed 7 Oct | Week 2 | Commodore Park | 4088.63 | 3861 | Approved sheet, no invoice yet
36580 | Wed 7 Oct | Week 2 | S17–S20 — walk through (grandstands) | 2424.1 | 1500 | Approved sheet, no invoice yet
36581 | Wed 7 Oct | Week 2 | S04 — Corporate | 679.28 | 1044 | Approved sheet, no invoice yet
36582 | Wed 7 Oct | Week 2 | Race Admin — double stack — C.2 | 1333.26 | 875 | Approved sheet, no invoice yet
36583 | Thu 8 Oct | Week 2 | Helen Park C.2 + perimeter fence | 3989.86 | 3092 | Approved sheet, no invoice yet
36584 | Thu 8 Oct | Week 2 | North S01 — Infill | 191.48 | 183 | Approved sheet, no invoice yet
36585 | Thu 8 Oct | Week 2 | Podium | 1185.03 | 1159 | Approved sheet, no invoice yet
36586 | Thu 8 Oct | Week 2 | Teams Area | 638.25 | 610 | Approved sheet, no invoice yet
36587 | Fri 9 Oct | Week 2 | Event Operations — perimeter fence | 695.63 | 699 | Approved sheet, no invoice yet
36588 | Fri 9 Oct | Week 2 | Club 500 Toilets | 2120.86 | 1850 | Approved sheet, no invoice yet
36589 | Fri 9 Oct | Week 2 | S04 Corporate Toilets | 382.95 | 366 | Approved sheet, no invoice yet
36590 | Fri 9 Oct | Week 2 | Club 500 exclusion zone CZ | 1737.28 | 1175 | Approved sheet, no invoice yet
36591 | Fri 9 Oct | Week 2 | Club 500 Creek Protection | 1193.9 | 567 | Approved sheet, no invoice yet
36592 | Fri 9 Oct | Week 2 | The Hill — Monster CZ | 2222.1 | 1375 | Approved sheet, no invoice yet
36593 | Fri 9 Oct | Week 2 | S21 Grandstand — Walk through | 1454.46 | 900 | Approved sheet, no invoice yet
36594 | Fri 9 Oct | Week 2 | Smoking Zones — The Hill / Club 500 | 168.98 | 121.5 | Approved sheet, no invoice yet
36595 | Fri 9 Oct | Week 2 | Rear of S20 — Shower | 75.1 | 54 | Approved sheet, no invoice yet
36596 | Mon 12 Oct | Week 1 | Main Beach Pde - Madison Point to Ferny Ave, Higman St to Equinox, Ferny Ave southern side, Seacrest to Pacific Point | 10163.29 | 6007.5 | Approved sheet, no invoice yet
36597 | Mon 12 Oct | Week 1 | The Spit - McMahon's/HTH Compound | 163.97 | 252 | Approved sheet, no invoice yet
36598 | Mon 12 Oct | Week 1 | Main Beach Pde - Rhapsody | 191.48 | 183 | Approved sheet, no invoice yet
36599 | Mon 12 Oct | Week 1 | Supply Compound | 3765.68 | 3599 | Approved sheet, no invoice yet
36600 | Mon 12 Oct | Week 1 | I.E.D.M - Compound | 0 | 200 | Approved sheet, no invoice yet
36601 | Mon 12 Oct | Week 1 | Commodore Park - Ticket Entry | 638.25 | 610 | Approved sheet, no invoice yet
36602 | Mon 12 Oct | Week 1 | COW - OPTUS | 1148.85 | 1098 | Approved sheet, no invoice yet
36603 | Tue 13 Oct | Week 1 | Eastern Residents & Demarc - Cable St to Gate 8A - DL & DR | 18119.31 | 10356.5 | Approved sheet, no invoice yet
36604 | Tue 13 Oct | Week 1 | Breaker St - T11 - DL | 1013.37 | 567 | Approved sheet, no invoice yet
36605 | Tue 13 Oct | Week 1 | Aloha Lane to Cronin St (Crest) | 1535.27 | 950 | Approved sheet, no invoice yet
36606 | Tue 13 Oct | Week 1 | Fishermans Walk | 161.61 | 100 | Approved sheet, no invoice yet
36607 | Wed 14 Oct | Week 1 | Main Beach Tower | 767.63 | 475 | Approved sheet, no invoice yet
36608 | Wed 14 Oct | Week 1 | Ferny Ave to Narrow Neck Court | 4416.78 | 2414.5 | Approved sheet, no invoice yet
36609 | Wed 14 Oct | Week 1 | Esplanade south of Meriton - Porsche Lounge CZ | 10722.6 | 6100 | Approved sheet, no invoice yet
36610 | Wed 14 Oct | Week 1 | G8 & surround | 8627.43 | 5077 | Approved sheet, no invoice yet
36611 | Thu 15 Oct | Week 1 | Surfers Paradise Light Rail | 3923.9 | 2884 | Approved sheet, no invoice yet
36612 | Thu 15 Oct | Week 1 | Pacific Ave to Cable St | 5199.17 | 3733 | Approved sheet, no invoice yet
36613 | Thu 15 Oct | Week 1 | Porsche CZ | 525.7 | 378 | Approved sheet, no invoice yet
36614 | Thu 15 Oct | Week 1 | S.0.8 B.O.H. | 1442.82 | 1674 | Approved sheet, no invoice yet
36615 | Thu 15 Oct | Week 1 | Gate 5 Compound | 2152.45 | 1676 | Approved sheet, no invoice yet
36616 | Thu 15 Oct | Week 1 | Triangle CZ | 2383.7 | 1525 | Approved sheet, no invoice yet
36617 | Fri 16 Oct | Week 1 | Main Beach Light Rail | 2856.26 | 2090 | Approved sheet, no invoice yet
36618 | Fri 16 Oct | Week 1 | Cypress Carpark | 2464.51 | 1675 | Approved sheet, no invoice yet
36619 | Fri 16 Oct | Week 1 | Focus to Meriton - The Esplanade | 6513.96 | 4458.5 | Approved sheet, no invoice yet
36620 | Fri 16 Oct | Week 1 | I.E.D.M - Compound | 0 | 100 | Approved sheet, no invoice yet
36621 | Fri 16 Oct | Week 1 | Monster C.Z. - The Hill | 40.4 | 25 | Approved sheet, no invoice yet
36622 | Fri 16 Oct | Week 1 | Golden Gate | 2100.89 | 1450 | Approved sheet, no invoice yet
36623 | Mon 19 Oct | Event Week | S15 C2 - hoarding fence and demarcation | 2883.67 | 1515 | Nothing from Advanced yet (our estimate)
36624 | Mon 19 Oct | Event Week | Admiralty Drive Intersection | 525.22 | 325 | Nothing from Advanced yet (our estimate)
36625 | Mon 19 Oct | Event Week | Gate 1 - S23 Compound | 7276.05 | 6954 | Nothing from Advanced yet (our estimate)
36626 | Mon 19 Oct | Event Week | Seaway Carpark - The Spit and fuel compound | 7959.14 | 4925 | Nothing from Advanced yet (our estimate)
36627 | Tue 20 Oct | Event Week | Track wide (four spots) | 1036.85 | 715.5 | Nothing from Advanced yet (our estimate)
36628 | Tue 20 Oct | Event Week | PB03 - footings | 638.25 | 610 | Nothing from Advanced yet (our estimate)
36629 | Tue 20 Oct | Event Week | PB03 - Gate 1 - Helen Park | 4920.27 | 3420 | Nothing from Advanced yet (our estimate)
36630 | Tue 20 Oct | Event Week | Macintosh Island - entry | 484.82 | 300 | Nothing from Advanced yet (our estimate)
36631 | Tue 20 Oct | Event Week | Podium | 127.65 | 122 | Nothing from Advanced yet (our estimate)
36632 | Tue 20 Oct | Event Week | Pit Lane - S01 | 0 | 0 | Nothing from Advanced yet (our estimate)
36633 | Tue 20 Oct | Event Week | Fire hydrant - S01 - toilets | 282.81 | 175 | Nothing from Advanced yet (our estimate)
36634 | Tue 20 Oct | Event Week | S07 viewing mound | 163.5 | 67.5 | Nothing from Advanced yet (our estimate)
36635 | Tue 20 Oct | Event Week | Esplanade north to the Triangle | 619.42 | 391.5 | Nothing from Advanced yet (our estimate)
36636 | Tue 20 Oct | Event Week | Higman St and Rhapsody | 2681.4 | 1107 | Nothing from Advanced yet (our estimate)
36637 | Tue 20 Oct | Event Week | Macintosh Island foot bridge | 187.75 | 135 | Nothing from Advanced yet (our estimate)
36638 | Tue 20 Oct | Event Week | Pit Building north | 849.3 | 475.2 | Nothing from Advanced yet (our estimate)
36639 | Wed 21 Oct | Event Week | McIntosh Island storage | 382.95 | 366 | Nothing from Advanced yet (our estimate)
36640 | Wed 21 Oct | Event Week | D.S - storage | 767.63 | 475 | Nothing from Advanced yet (our estimate)
36642 | Wed 21 Oct | Event Week | Gate 6 | 191.48 | 183 | Nothing from Advanced yet (our estimate)
36643 | Wed 21 Oct | Event Week | Club 500 | 1120.47 | 1117 | Nothing from Advanced yet (our estimate)
36644 | Wed 21 Oct | Event Week | Porsche to Staghorn St (Esplanade) | 0 | 0 | Nothing from Advanced yet (our estimate)
36645 | Wed 21 Oct | Event Week | Inlet (Breaker St) | 163.5 | 67.5 | Nothing from Advanced yet (our estimate)
36646 | Wed 21 Oct | Event Week | S08 - TV | 242.41 | 150 | Nothing from Advanced yet (our estimate)
36647 | Wed 21 Oct | Event Week | Club 500 - creek protection | 356.73 | 256.5 | Nothing from Advanced yet (our estimate)
36756 | Wed 21 Oct | Event Week | Meriton | 161.61 | 100 | Nothing from Advanced yet (our estimate)
36757 | Wed 21 Oct | Event Week | The Spit - Transporter Compound | 1131.25 | 700 | Nothing from Advanced yet (our estimate)
36648 | Thu 22 Oct | Event Week | Gate 7 | 606.03 | 375 | Nothing from Advanced yet (our estimate)
36649 | Thu 22 Oct | Event Week | Gate 10 | 1021.2 | 976 | Nothing from Advanced yet (our estimate)
36650 | Thu 22 Oct | Event Week | Malibu - Breaker St | 80.8 | 50 | Nothing from Advanced yet (our estimate)
36751 | Thu 22 Oct | Event Week | Ocean Ave | 4749.35 | 3176 | Nothing from Advanced yet (our estimate)
36752 | Thu 22 Oct | Event Week | Staghorn St Entry | 323.21 | 200 | Nothing from Advanced yet (our estimate)
36753 | Thu 22 Oct | Event Week | Gate 9 - Breaker St | 282.81 | 175 | Nothing from Advanced yet (our estimate)
36754 | Thu 22 Oct | Event Week | Aloha Lane - Gate 8 | 606.03 | 375 | Nothing from Advanced yet (our estimate)
36755 | Thu 22 Oct | Event Week | Helipad | 903.57 | 593 | Nothing from Advanced yet (our estimate)
36758 | Thu 22 Oct | Event Week | T.V - Compound | 484.82 | 300 | Nothing from Advanced yet (our estimate)
36759 | Thu 22 Oct | Event Week | Rhapsody Sales Office - walk through | 1850.93 | 1769 | Nothing from Advanced yet (our estimate)
36760 | Thu 22 Oct | Event Week | Macintosh Island - fallen tree | 130.8 | 54 | Nothing from Advanced yet (our estimate)
36761 | Thu 22 Oct | Event Week | Rubbish Compactor (Cleanaway) | 870.13 | 818 | Nothing from Advanced yet (our estimate)
36762 | Thu 22 Oct | Event Week | Turn 2-3 - Crash Protection | 323.21 | 200 | Nothing from Advanced yet (our estimate)
36763 | Thu 22 Oct | Event Week | Triangle | 0 | 0 | Nothing from Advanced yet (our estimate)
36764 | Thu 22 Oct | Event Week | Monster (Energy) | 112.65 | 81 | Nothing from Advanced yet (our estimate)
36765 | Fri 23 Oct | Event Week | Gate 5 - Ocean Ave | 80.8 | 50 | Nothing from Advanced yet (our estimate)
36766 | Fri 23 Oct | Event Week | Smoking Zone - Breaker St | 75.1 | 54 | Nothing from Advanced yet (our estimate)
36767 | Fri 23 Oct | Event Week | Gate 7 - security entry | 121.21 | 75 | Nothing from Advanced yet (our estimate)
36768 | Fri 23 Oct | Event Week | Club 500 - B.O.H. | 375.5 | 270 | Nothing from Advanced yet (our estimate)
Total |  |  | 167 dockets | 340871.73 | 234136.7

## Labour notes
Labour notes (green book)
AUD ex GST · Advanced's labour at $100 an hour, a cost only: it is inside the metre rates we charge
Note | Date | Hours | We pay | Invoice
24451 | Tue 15 Sep | 0.5 | 50 | Invoice received
24452 | Tue 15 Sep | 0.5 | 50 | Invoice received
24453 | Wed 16 Sep | 1.5 | 150 | Invoice received
24454 | Thu 17 Sep | 1 | 100 | Invoice received
24455 | Fri 18 Sep | 0.75 | 75 | Invoice received
24456 | Mon 21 Sep | 0.75 | 75 | Invoice received
24457 | Mon 21 Sep | 1 | 100 | Invoice received
24458 | Wed 23 Sep | 1 | 100 | Invoice received
24459 | Thu 24 Sep | 1.5 | 150 | Invoice received
24460 | Fri 25 Sep | 1 | 100 | Invoice received
24461 | Tue 29 Sep | 1 | 100 | Approved sheet, no invoice yet
24462 | Tue 29 Sep | 2 | 200 | Approved sheet, no invoice yet
24463 | Wed 30 Sep | 0.75 | 75 | Approved sheet, no invoice yet
24464 | Wed 30 Sep | 1 | 100 | Approved sheet, no invoice yet
24465 | Thu 1 Oct | 1 | 100 | Approved sheet, no invoice yet
24466 | Fri 2 Oct | 0.5 | 50 | Approved sheet, no invoice yet
24467 | Fri 2 Oct | 0.25 | 25 | Approved sheet, no invoice yet
24468 | Tue 6 Oct | 0.25 | 25 | Approved sheet, no invoice yet
24469 | Tue 6 Oct | 0.75 | 75 | Approved sheet, no invoice yet
24470 | Wed 7 Oct | 1.5 | 150 | Approved sheet, no invoice yet
24471 | Wed 7 Oct | 1.5 | 150 | Approved sheet, no invoice yet
24472 | Wed 7 Oct | 4 | 400 | Approved sheet, no invoice yet
24473 | Thu 8 Oct | 4 | 400 | Approved sheet, no invoice yet
24474 | Fri 9 Oct | 0.5 | 50 | Approved sheet, no invoice yet
24475 | Mon 12 Oct | 3 | 300 | Approved sheet, no invoice yet
24478 | Mon 12 Oct | 0.5 | 50 | Approved sheet, no invoice yet
24476 | Tue 13 Oct | 2 | 200 | Approved sheet, no invoice yet
24477 | Tue 13 Oct | 1.5 | 150 | Approved sheet, no invoice yet
24479 | Tue 13 Oct | 0.5 | 50 | not on their sheet
24480 | Wed 14 Oct | 1.5 | 150 | Approved sheet, no invoice yet
24481 | Thu 15 Oct | 4 | 400 | Approved sheet, no invoice yet
24482 | Mon 19 Oct | 1.25 | 125 | Nothing from Advanced yet (our estimate)
24483 | Tue 20 Oct | 1 | 100 | Nothing from Advanced yet (our estimate)
24484 | Tue 20 Oct | 2 | 200 | Nothing from Advanced yet (our estimate)
24485 | Tue 20 Oct | 8 | 800 | Nothing from Advanced yet (our estimate)
24486 | Tue 20 Oct | 0.5 | 50 | Nothing from Advanced yet (our estimate)
24489 | Wed 21 Oct | 0.5 | 50 | Nothing from Advanced yet (our estimate)
24487 | Thu 22 Oct | 31.5 | 3150 | Nothing from Advanced yet (our estimate)
24488 | Thu 22 Oct | 20 | 2000 | Nothing from Advanced yet (our estimate)
24490 | Thu 22 Oct | 0.75 | 75 | Nothing from Advanced yet (our estimate)
24491 | Thu 22 Oct | 1 | 100 | Nothing from Advanced yet (our estimate)
24492 | Thu 22 Oct | 0.5 | 50 | Nothing from Advanced yet (our estimate)
Total |  | 108.5 | 10850